## Sheet
Borehole | Daily Cost | Phase | Borehole Section | Start Time | End Time | Duration(h) | Start Depth(m) | End Depth(m) | Operation Code | Activity Code | Sub Code | Planned | Time Classification | NPT Reason | NPT Vendor | Comments | Translated Comments | Perforation | Additional Code
GZR-401 |  | RIG |  | 2023-05-22 21:00 | 2023-05-22 22:00 | 1:00 | [6 empty] | Productive |  |  | P/U, M/U & RACK BACK 5" 25.6# DP & R/B IN DERRICK.
GZR-401 |  | RIG |  | 2023-05-22 22:00 | 2023-05-22 23:00 | 1:00 | [6 empty] | Productive |  |  | CONDUCTED SAFETY STANDDOWN FOR DROPS WITH CREW #C
GZR-401 |  | RIG |  | 2023-05-22 23:00 | 2023-05-23 | 1:00 | [6 empty] | Productive |  |  | P/U, M/U & RACK BACK 5" 25.6# DP & R/B IN DERRICK. 13
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 09:30 | 9:30 | [6 empty] | Productive |  |  | - CONT.P/U AND RACK BACK5'' 25.6# G3 DP (TOTAL 55 STAND ). MEANWHILE: - CONT, MIXING SPUD MUD
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 10:30 | 1:00 | [6 empty] | Productive |  |  | P/U, M/U & RACK BACK 5 STANDS OF 5" HWDP IN DERRICK
GZR-401 |  | RIG |  | 2023-05-22 10:30 | 2023-05-22 14:00 | 3:30 | [6 empty] | Productive |  |  | - R\D AIR SLIPS - PICK UP LIFTING SUB P/U, M/U & RACK BACK : - 1 STAND OF 8.1/4" DC. - 4 DRILLABLE DCS STANDS ( 2X8.1/4" DCS + XO + 1X 5" HWDP)
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 15:00 | 1:00 | [6 empty] | Productive |  |  | -P/U AND RACK BACK5'' 19.5#G2 DP (TOTAL 5 STAND ).
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 16:00 | 1:00 | [6 empty] | Productive |  |  | CONDUCTED SAFETY STANDDOWN FOR DROPS WITH CREW #C
GZR-401 |  | RIG |  | 2023-05-22 16:00 | 2023-05-22 20:30 | 4:30 | [6 empty] | Productive |  |  | -P/U AND RACK BACK5'' 19.5#G2 DP (TOTAL 20 STAND ).
GZR-401 |  | RIG |  | 2023-05-22 20:30 | 2023-05-22 21:00 | 0:30 | [6 empty] | Productive |  |  | PJSM FOR P\U & M\U 24" BHA AND DRILLING 24" HOLE SECTION
GZR-401 |  | RIG |  | 2023-05-22 21:00 | 2023-05-22 23:15 | 2:15 | [6 empty] | Productive |  |  | - PREPARE FOR BHA HANDLING. - PU 24" KYMERA BIT (SN/ 5284759) - PU BIT BREAKER - M/U 24'' KYMERA BIT WITH BIT SUB & 12'' SHOCK SUB, 9 1/2" DC AND XO - MAKE UP ABOVE WITH DRILLABLE STAND FROM DERRICK. - CONNECT TDS - STAGE UP PUMPS TO 450 GPM - TAG BOTTOM AT 14 M
GZR-401 |  | RIG |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 | [6 empty] | Productive |  |  | *** SPUD IN GZR-401 AT 23/05/2023 23:15 HRS DRILL 24" HOLE FROM 14 M TO 17 M LIMITING ROP TO 5 M/HR WITH FOLLOWING PARAMETERS: WOB: 2-10 KLBS RPM: 60 RPM SPP: 250 PSI FLOW RATE: 450 GPM
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 04:45 | 4:45 | [6 empty] | Productive |  |  | CONT. DRILL 24" HOLE FROM 17 M TO 43 MLIMITING ROP TO 5 M/HR WITH FOLLOWING PARAMETERS: WOB: 2-10 KLBS RPM: 60 RPM SPP: 250-260 PSI FLOW RATE: 450 GPM Page 2 of 120
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 06:15 | 1:30 | [6 empty] | Productive |  |  | POOH AND RACKBACK DC DRILLABLE STAND WITH XO. PU, MU AND RIH WITH : - 23 15/16"STRING STABILIZER - 9.1/2" DC - 23 15/16"STRING STABILIZER
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 18:00 | 11:45 | [6 empty] | Productive |  |  | CONTINUE DRILL 24" HOLE FROM 43 M TO 145 M WITH CONTROLLED PARAMETERS. FR 550-1000 GPM , SPP 500 PSI- 1800 PSI WOB 20- 40 KLBS , RPM 60-90 , TRQ 3-9 KFT.LBS
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | CONTINUE DRILL 24" HOLE FROM 145 M TO 244 M WITH FOLLOWING PARAMETERS. FR 1000 GPM , SPP 1700 - 2180 PSI,WOB 30- 40 KLBS , RPM 100-130 , TRQ 5-10 KFT.LBS AVG ROP: 18 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | CONTINUE DRILL 24" HOLE FROM 244 M TO 320 M WITH FOLLOWING PARAMETERS. FR 1000 GPM , SPP 1700 - 2180 PSI,WOB 35- 40 KLBS , RPM 100-130 , TRQ 5-10 KFT.LBS NOTES: - FROM 310 M, AFTER THE CONNECTION OBSERVED SPP LESS THAN PREVIOUSLY BY 1000 PSI, CHECK THE MUD PUMPS FOUND MP#3 SCREEN PLUGGED. - DRILL WITH 2 PUMPS FROM 310 M TO 318 M TO CLEAN MP#3 SECREEN. - NO SWF OR LOSSES OBSERVED. AVG ROP: 15 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-23 | 18:00 | [6 empty] | Productive |  |  | CONTINUE DRILL 24" HOLE FROM 320 M TO 555 M WITH FOLLOWING PARAMETERS. FR 1100 GPM , SPP 1700 - 3000 PSI,WOB 25- 35 KLBS , RPM 120-130 , TRQ 7-12 KFT.LBS NOTES: - AT 13:20 OBSERVE MUD PUMP # 1 EXPENSION JOINT IS LEAKING. - DRILL WITH 2 PUMPS FROM 396 M TO 440 M. AVG ROP: 16.73 M/HR - DISCONNECT FLOW LINE FROM RAISER - REMOVE MOUSE HOLE - PULL RISER & LAY DOWN SAME. - R/U 20" MASTER BUSHING. Page 3 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 04:15 | 4:15 | [6 empty] | Productive |  |  | CONTINUE DRILL 24" HOLE FROM 555 M TO 618 M (SECTION TD). FR 1100 GPM , SPP 1700 - 3000 PSI,WOB 25- 30 KLBS , RPM 120-140 , TRQ 7-11 KFT.LBS NOTES: - FROM 590 M, OBSERVED SEVERE DROP IN TQ AND ROP INDICATING BIT BALLING, HAD TO PICK UP OFF BOTTOM AND ROTATE WITH 170 RPM SEVERAL TIMES, AT 597 M GOT IMPROVEMENT ON DRILLING TQ FOLLOWED BY GRADUAL IMPROVEMENT ON ROP. - AT 615 M OBSERVE MUD PUMP # 2 CAP SEAL IS LEAKING. - DRILL WITH 2 PUMPS FROM 615 M TO 618 M. - NO DOWN HOLE LOSSES OBSERVED DURING DRILLING THE SECTION - INCREASED MW TO 1.23 SG - AVG ROP: 16.85 M/HR
GZR-401 |  | RIG |  | 2023-05-22 04:15 | 2023-05-22 05:15 | 1:00 | [6 empty] | Productive |  |  | PUMP 100 BBLS HI-VIS SWEEP AND CIRC TELL SHAKERS CLEAN WITH 1100 GPM, 2800 PSI - 19 BBLS DOWN HOLE LOSSES OBSERVED WHILE CIRCULATION. - MUD IN/OUT =1.23 SG
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 05:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WITHOUT RISER MARGIN -- NO FLOW. MEANWHILE: TBT FOR POOH
GZR-401 |  | RIG |  | 2023-05-22 05:30 | 2023-05-22 07:00 | 1:30 | [6 empty] | Productive |  |  | - POOH ON ELEVATORWITH 24" BHA FROM 618 M TO 311 M. - MONITOR WELL THROUGH TRIP TANK. -HAD 5 CONNECTIONES WITH OVERTORQUE CONNECTION AND BRAKE THE SAME USING THE MANUAL TONG.
GZR-401 |  | RIG |  | 2023-05-22 07:00 | 2023-05-22 07:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WITHOUT RISER MARGIN -- OBSERVE LOSSES 20 BB/HR.
GZR-401 |  | RIG |  | 2023-05-22 07:15 | 2023-05-22 08:00 | 0:45 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATORWITH 24" BHA FROM 311 M TO 150 M. - MONITOR WELL THROUGH TRIP TANK, 20 BBLS/HR STATIC LOSSES. NOTE: - NO OVER TORQUE CONNECTION WAS OBSERVED.
GZR-401 |  | RIG |  | 2023-05-22 08:00 | 2023-05-22 08:15 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK WELL WITHOUT THE RISER AT TOP OF FIRST DRILL COLLAR STAND. - OBSERVE LOSSES 20 BBL/HR.
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 09:30 | 1:15 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 24" BHA AND R/B 8.1/4'' DC FROM 150 M TO 54 M. Page 4 of 120
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 12:00 | 2:30 | [6 empty] | Productive |  |  | - CONT. POOH ON ELEVATOR WITH 24" BHA R/B 8.1/4'' DC AND L/D REMAINING BHA ITEMS FROM 54 M TO SURFACE. - TOP STAB & LOWER WERE IN GAUGE, 90% BALLED UP. - LAY DOWN 2X 9 1/2" DC. - LAY DOWN SHOCK SUB - LAY DOWN BIT SUB - LAY DOWN BIT, FULLY BALLED UP NOTE: BIT DULL GRADING: 2-1-SS-A-1-I-BU-TD - MONITOR WELL ON TRIP TANK, STATIC LOSSES 20 BBLS/HR
GZR-401 |  | RIG |  | 2023-05-22 12:00 | 2023-05-22 12:15 | 0:15 | [6 empty] | Productive |  |  | - CLEAN AND CLEAR RIG FLOOR.
GZR-401 |  | RIG |  | 2023-05-22 12:15 | 2023-05-22 12:30 | 0:15 | [6 empty] | Productive |  |  | - TBT FOR REMOVING THE RAISER.
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 14:30 | 2:00 | [6 empty] | Productive |  |  | - DRAINED RISER - DISCONNECT FLOW LINE FROM RAISER - REMOVE MOUSE HOLE - PULL RISER & LAY DOWN SAME. - R/U 20" MASTER BUSHING.
GZR-401 |  | RIG |  | 2023-05-22 14:30 | 2023-05-22 15:00 | 0:30 | [6 empty] | Productive |  |  | - MOVE BOP FROM BOP TROLLEY TO OTHER SIDE BELOW SUB BASE USING BOP WINCH - RIG DOWN BOP TROLLEY.
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 16:00 | 1:00 | [6 empty] | Productive |  |  | R/U FRANKS TRS 18 5/8'' CSG HANDLING EQUIPMENTS - RIG UP SDE - RIG UP BOWL, SLIPS LIFTER, SLIPS AND CONTROL PANEL. - RIG UP POWER TONG
GZR-401 |  | RIG |  | 2023-05-22 16:00 | 2023-05-22 16:15 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 18.5/8" CASING RUNNING.
GZR-401 |  | RIG |  | 2023-05-22 16:15 | 2023-05-23 | 7:45 | [6 empty] | Productive |  |  | RIH WITH 18 5/8" CSG FROM SURFACE TO 500 M. - FUNCTION TEST FLOAT SHOE - BAKER LOCK THE FIRST TWO CONNECTIONS. - USED BACK-UP TONGS FOR FIRST 10 JOINTS. - FILL UP CASING EVERY JOINT WHILE RIH THROUGH TDS. - MONITOR WELL ON TRIP TANK, STATIC LOSSES 8 BBLS/HR NOTE: - AT 20:00 TBT AND CREW SHIFT HANDOVER
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:00 | 1:00 | [6 empty] | Productive |  |  | RIH WITH 18 5/8" CSG FROM 500 M TO 590 M. - FILL UP CASING EVERY JOINT WHILE RIH THROUGH TDS. - MONITOR WELL ON TRIP TANK, STATIC LOSSES 8 BBLS/HR - SMOOTH RIH TO BOTTOM. Page 5 of 120
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 01:30 | 0:30 | [6 empty] | Productive |  |  | - RIG DOWN FRANKS SLIP LIFTER. - REMOVE CASING BUSHING TO ALLOW MODIFIED CENTRALIZER TO PASS THOUGH ROTARY.
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 02:00 | 0:30 | [6 empty] | Productive |  |  | - P/U LAST JOINT CSG WITH MODIFIED CENTRALIIZER - INSTALL CASING BUSHING AND PLACE STRING IN MANUAL SLIPS. - CHANGE OUT ELEVATOR TO 5" DP ELEVATOR.
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 02:30 | 0:30 | [6 empty] | Productive |  |  | MU 18.5/8" WATER BUSHING TO HWDP STAND THEN MU STAND TO LAST CASING JOINT #46.
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 03:30 | 1:00 | [6 empty] | Productive |  |  | - RIH AND WASH DOWN WITH 200 GPM, 50 PSI PRESSURE. - PLACE WATER BUSHING ABOUT 0.5 M ABOVE CELLAR FLOOR - INSTALL ANT TIGHT BASE CLAMP - LANDED OFF CASING ON BASE CLAMP - 18.5/8'' CSG SHOE AT 614.89 M
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 03:45 | 0:15 | [6 empty] | Productive |  |  | FILL UP CASING & BREAK CIRCULATION
GZR-401 |  | RIG |  | 2023-05-22 03:45 | 2023-05-22 04:30 | 0:45 | [6 empty] | Productive |  |  | - B/O WATER BUSHING AND L/D. - RACK BACK HWDP STAND. - INSTALL 26" MASTER BUSHING
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 06:30 | 2:00 | [6 empty] | Productive |  |  | - TBT - M/U STING-IN SUB WITH 5'' DP STD - INSTALLED PIPE CENTERLIZER AND SECURED THE SAME. - RIH INNER STRING TO 613 M - TAG SHOE STING-INAT 613.9 M - M/U SURFACE LINE WITH FOSV+ SES+ FOSV+PUP.
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 07:15 | 0:45 | [6 empty] | Productive |  |  | - CIRCULATED AND CONDITION HOLE WITH 200 GPM, 80 PSI. OFFLINE: CONDUCT PJSM PRIOR TO PERFORM CMT JOB
GZR-401 |  | RIG |  | 2023-05-22 07:15 | 2023-05-22 07:45 | 0:30 | [6 empty] | Productive |  |  | - FLUSHED SURFACE LINES. - PRESSURE TESTED CEMENT LINES 300 PSI LOW AND 2000 PSI HIGH FOR 5/ 5 MIN.
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 10:45 | 3:00 | [6 empty] | Productive |  |  | MIX AND PUMP 18-5/8" CEMENT AS FOLLOW: - PUMPED 424 BBL OF LEAD SLURRY (1.43 SG) WITH FR: 5-6 BBL/MIN, - PUMPED 151 BBL OF TAIL SLURRY (1.67 SG) WITH FR: 4-5 BPM - CEMENT RETURN TO CELLAR AFTER PUMPING 500 BBLS OF LEAD CMT. - DISPLACED WITH 5 BBLS MIX WATER FOLLOWED BY 22 BBLS 1.23 SG MUD. - BLED BACK0 BBLS RETURNED - FLOAT HOLDING. - CEMENT IN PLACE AT 11:00 AM Page 6 of 120
GZR-401 |  | RIG |  | 2023-05-22 10:45 | 2023-05-22 11:00 | 0:15 | [6 empty] | Productive |  |  | - BREAK OUT CEMENT LINES FROM SIDE ENTRY SUB. - UNSTABED CEMENT STRINGER AND LD CEMENT ASSEMBLY - LOADED FOAM BALL INTO DRILL PIPE STRING. POOH UP WITH FULL STAND. - CIRCULATE 120% STRING VOLUME, 850-900 GPM. - POOH AND RACK BACK 2 STANDS MEANWHILE, LEVEL IN CELLAR WAS DROPPING, FILL UP WITH 1.23 SG MUD.
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 12:30 | 1:30 | [6 empty] | Productive |  |  | ** CEMENT TOP FILL JOB #1 *** - IMMEDIATELY SWITCH TO CELLAR FOR TOP FILL - PUMPED 1000 LTR OF ECONOLITE - POOH PVC PIPE FOR ECONOLITE TO SURFACE. - PUMP CEMENT WITH GOOD RETURNS.START SEEN CEMENT AT CELLAR AFTER~ 45 BBL PUMPED , AFTER 55 BBL OBSERVE CEMENT LEVEL DROP CONT PUMP CEMENT TILL TOTAL OF 100 BBL PUMPED. - POOH PVC PIPE FOR CEMENT TO SURFACE. - CLEAN AND CLEAR CEMENT FROM CELLAR. FILL CELLAR AND KEPT WATCHING THE LEVEL - OBSERVE DROP IN CEMENT LEVEL FILL UP WITH 1.23 SG MUD.
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 13:30 | 1:00 | [6 empty] | Productive |  |  | WAIT ON CEMENT. KEPT FILLING CELLAR WITH 1.23 SG MUD,OBSERVE MUDLEVEL IN CELLAR DROP , TOTAL LOSSES 23 BBL MEANWHILE: POOH & RACKBACK REMAINING 5" DP STANDS.
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 15:30 | 2:00 | [6 empty] | Productive |  |  | ** CEMENT TOP FILL JOB #2 ** - RUN 2X CEMENT PVC PIPES TO 8 M BELOW CELLAR. - PUMP CEMENT WITH GOOD RETURNS.START SEEN CEMENT AT CELLAR AFTER 50 BBL PUMPED ,CONT PUMP CEMENT TILL TOTAL OF 80 BBL PUMPED. . - CLEAN AND CLEAR CEMENT FROM CELLAR. FILL CELLAR AND KEPT WATCHING THE LEVEL - OBSERVE DROP IN CEMENT LEVEL FILL UP WITH 1.23 S.G MUD.
GZR-401 |  | RIG |  | 2023-05-22 15:30 | 2023-05-22 16:15 | 0:45 | [6 empty] | Productive |  |  | WAIT ON CEMENT. KEPT FILLING CELLAR WITH 1.23 SG MUD, OBSERVE MUDLEVEL IN CELLAR DROP THEN BECAME STABLE. Page 7 of 120
GZR-401 |  | RIG |  | 2023-05-22 16:15 | 2023-05-22 17:00 | 0:45 | [6 empty] | Productive |  |  | ** CEMENT TOP FILL JOB #3 ** - RUN 2X CEMENT PVC PIPES TO MAX OF 2 M BELOW CELLAR. - PUMP CEMENT WITH GOOD RETURNS.START SEEN CEMENT AT CELLAR AFTER 4 BBL PUMPED ,CONT PUMP CEMENT TILL TOTAL OF 15 BBL PUMPED. . - CLEAN AND CLEAR CEMENT FROM CELLAR. FILL CELLAR AND KEPT WATCHING THE LEVEL - STATIC
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 18:30 | 1:30 | [6 empty] | Productive |  |  | KEEP MONITOR MUD LEVEL AT CELLAR- STATIC. MEANWHILE: - CLEAR RIG FLOOR. - SPOT BOP TROLLY AND MOVE BOP TO V-DOOR SIDE AND LAND ON TEST STUMP ON BOP TROLLY.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 21:15 | 2:45 | [6 empty] | Productive |  |  | TBT. - REMOVE MASTER BUSHING. - R/U 20'' RAISER , ENERGISE SEALS. - CONNECT FLOW LINE, INSTALL KILL LINE, TRIP TANK LINE AND DUMP VALVE - FILL UP RISER AND CHECK FOR LEAK, NO LEAK - RU MOUSE HOLE. ** OFFLINE: - CREW HANDOVER @20:00 - START PREPARING 17.5" BHA AT RIG FLOOR. - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CLEAN MUD PITS AND PREPARED HYDROGAURD MUD 1.28 SG.
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 21:30 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR PU AND RIH 17.5" BHA
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-23 | 2:30 | [6 empty] | Productive |  |  | P/U & M/U AND RIH 17.1/2"BHA TO 116 M : - NOV BIT ,TYPE: TK625 ,SN: E270129 (6 X 13), - BIT SUB (WITH FLOAT VALVE) - 2 X 9 1/2" DC - 17 3/8" STRING STAB + 7.5/8" REG X 6.5/8" REG XO - 9X 8 1/4"DC - 8ﬂPOWER STROKE HYDRAULIC JARS ** OFFLINE: - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CONT. PREPARE TANKSFOR DISPLACEMENT WITH HYDROGAURD MUD 1.28 SG. - CONT. WORKING IN MUD PUMP #1 SUCTION LINE Page 8 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:00 | 1:00 | [6 empty] | Productive |  |  | CONT. P/U & M/U AND RIH 17.1/2"BHA FROM 116 M TO 284 M: - 3 X 8 1/4" DC - 6.5/8" REG X 4.1/2 NC50 XO - 15 X 5" HWDP. WEIGHT BELOW THE JAR IS 50 KLBS TOTAL BHA WEIGHT IS87 KLBS. ** OFFLINE: - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CONT. WORKING IN MUD PUMP #1 SUCTION LINE
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 01:45 | 0:45 | [6 empty] | Productive |  |  | - RIH WITH 17 1/2" BHA ON 5" 25.6# DP STANDS FROM 284 M TO 560 M. ** OFFLINE: - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CONT. WORKING IN MUD PUMP #1 SUCTION LINE
GZR-401 |  | RIG |  | 2023-05-22 01:45 | 2023-05-22 02:15 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS
GZR-401 |  |  |  | 2023-05-22 02:15 | 2023-05-22 02:45 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | OBSERVED BEND IN ODS BAIL HYDRAULIC CYLINDER - REMOVED DEFECT HYDRAULIC CYLINDER - INSTALLED NEW HYDRAULIC CYLINDER AND FUNCTION TEST THE SAME ** OFFLINE: - CONT. WORKING IN MUD PUMP #1 SUCTION LINE
GZR-401 |  | RIG |  | 2023-05-22 02:45 | 2023-05-22 03:45 | 1:00 | [6 empty] | Productive |  |  | - WASH DOWN PRECAUTIONARY FROM 560 M TO 613 M - TAGGED ON CEMENT AT 613 M - COMMENCED DISPLACING WELL TO HYDROGAURD MUD.
GZR-401 |  | RIG |  | 2023-05-22 03:45 | 2023-05-22 04:30 | 0:45 | [6 empty] | Productive |  |  | - DRILL OUT CEMENT, FLOAT SHOE & RAT HOLE FROM 613 M TO 618 M USING BELOW PARAMETERS WOB: 5 -12 K, RPM: 50-80 TQ: 3-6.5 KLBS.FT, GPM: 750-800, SPP: 1700-2300 PSI. - WIPE STRING THROUGH THE SHOE SEVERAL TIMES WITHOUT ISSUE. - PUMP 50 BBLS HI-VIS ON FLY AFTER CREALING RAT HOLE - MW IN \ MW OUT = 1.28 SG Page 9 of 120
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 06:15 | 1:45 | [6 empty] | Productive |  |  | DRILL 17.5'' HOLE SECTION FROM 618 M TO 666 M - WOB: 7-20 KLBS, RPM: 80-140, TQ: 4-12 KLBS.FT, GPM: 1000-1100 SPP: 3600-4000 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HIVIS EVERY CONNECTION - DRILL WITH 3 PUMPS. * TOP OF FIQA SHARGI AT 627 M. AVG ROP : 49 M\HR
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 09:30 | 3:15 | [6 empty] | Productive |  |  | CONT. DRILLING 17.5" SECTION FROM 666 M TO 744 M. - WOB: 7-20 KLBS, RPM: 80-140, TQ: 4-12 KLBS.FT, GPM: 870 SPP: 2600-2800 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HIVIS EVERY CONNECTION - DRILL WITH 2 PUMPS.
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 17:45 | 8:15 | [6 empty] | Productive |  |  | CONT. DRILLING 17.5'' HOLE SECTION FROM 744 M TO 1038 M - WOB: 7-20 KLBS, RPM: 80-140, TQ: 4-12 KLBS.FT, GPM: 1000-1100 SPP: 3600-4000 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HIVIS EVERY CONNECTION - DRILL WITH 3 PUMPS. * TOP OF NATIH AT 1030 M AVG ROP : 49 M\HR
GZR-401 |  | RIG |  | 2023-05-22 17:45 | 2023-05-22 18:15 | 0:30 | [6 empty] | Productive |  |  | DROP INSPECTION
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-22 20:00 | 1:45 | [6 empty] | Productive |  |  | DRILL 17.5'' HOLE SECTION FROM 1038 M TO 1063 M ( SECTION TD 33 M INTO NATIH ) - WOB: 7-20 KLBS, RPM: 120-140, TQ: 5-12 KLBS.FT, GPM: 870-1000 SPP: 2700-2900 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HIVIS EVERY CONNECTION - MW IN = MW OUT = 1.32 SG - DRILL WITH 2 PUMPS. - RAISED MUD WEIGHT TO 1.32 SG 50 M PRIOR REACHING TD. AVG ROP : 22 M\HR NOTES: - AT 1033 M DURING CONNECTION OBSERVED CONNECTION WASH-OUT R\B DP STAND #27 AND M\UP DP STAND #28 - DRILLED WITH 2 MP WITH 870 GPM FROM 1033 M TO 1063 M ( SECTION TD ) Page 10 of 120
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-22 21:30 | 1:30 | [6 empty] | Productive |  |  | - PUMPED 100 HI VIS AND CIRCULATED HOLE CLEAN - FR: 870 GPM, SPP: 2700-3000 PSI, 75 RPM,TRQ1-2 KLBS.FT - NO LOSSES WAS ENCOUNTERED.
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-22 21:45 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED PJSM PRIOR POOH WITH REAM BACK
GZR-401 |  | RIG |  | 2023-05-22 21:45 | 2023-05-23 | 2:15 | [6 empty] | Productive |  |  | - BACK REAMED WITH 17.1/2'' BHA FROM 1063 M TO 857 M. - FR: 870-1000 GPM, SPP: 2900 -3400 PSI, 75 RPM/ 2- 11 KLB.FT NOTES: - PUMPED 50 BBL OF HI-VIS AT 886 M,
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 04:00 | 4:00 | [6 empty] | Productive |  |  | - BACK REAMED WITH 17.1/2'' BHA FROM 857 M TO 610 M.(INSIDE 18 5/8" CSG) - FR: 1000 GPM, SPP: 3200 -3400 PSI, 75 RPM, TQ: 2- 11 KLB.FT
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 04:45 | 0:45 | [6 empty] | Productive |  |  | PUMPED 50 BBL HI-VIS PILL AND CIRCULATE HOLE CLEAN. FR 1000-1100 GPM , SPP 3200-4000 PSI, 75 RPM, TRQ 1-2 KFT.LBS. SHAKER CUTTINGS INCREASED BY ~ 20 % , ~ 10% CAVINGS MAINLY FROM SHARQI
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 06:00 | 1:15 | [6 empty] | Productive |  |  | UNABLED TO PULL ON ELEVATOR INSIDE CASING , CONTINUE WITH PUMP OUT AND BACK REAM. - PUMP OUT AND BACK REAMWITH 17.1/2'' BHA FROM 610 M TO 470 M. FR: 900-1000 GPM, SPP: 3200-3600 PSI, RPM: 75, TQ: 1-3 KLB.FT NOTE: - AT 480 M PUMP AND CIRCULATE 50 BBL OF HI-VIS
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 06:30 | 0:30 | [6 empty] | Productive |  |  | CONT. POH 17.1/2" BHA ON ELEVATOR FROM 470 M TO 285 M.
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 09:00 | 2:30 | [6 empty] | Productive |  |  | POOH 17 1/2" BHA FROM 285 M TO SURFACE. - RACK BACK 5X STANDS 5" HWDP - RACK BACK 1X STANDS 8 1/4" DC - L\D 8" HYDRAULIC JAR - RACK BACK 3X STANDS 8 1/4" DC - L\D 17-3/8"STAB ( 5% BALLED UP) - L\D 2X 9 1/2" DC - L\D BIT SUB - L\D NOV TK 625 BIT ( 10 % BALLED UP) NOTES: - BIT GRADING: 1-1-WT-A-X-I-NO-TD
GZR-401 |  | RIG |  | 2023-05-22 09:00 | 2023-05-22 09:15 | 0:15 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR
GZR-401 |  | RIG |  | 2023-05-22 09:15 | 2023-05-22 10:15 | 1:00 | [6 empty] | Productive |  |  | - DISCONNECT FLOW LINE. - RIG DOWN RISER USING CRANE. OFFLINE: PREPARED FRANKS TRS EQUIPMENT
GZR-401 |  | RIG |  | 2023-05-22 10:15 | 2023-05-22 10:45 | 0:30 | [6 empty] | Productive |  |  | RD MOUSE HOLE AND V-DOOR IN ORDER TO WORK ON BOP TEST OFF LINE WHILE RUNNING CASING. Page 11 of 120
GZR-401 |  | RIG |  | 2023-05-22 10:45 | 2023-05-22 11:00 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR RU FRANKS TRS EQUIPMENTS
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 13:45 | 2:45 | [6 empty] | Productive |  |  | RIG UP FRANKS TRS EQUIPMENT: SERVICE LOOP, FA-1, POWER UNIT OFFLINE: REMOVE LANDING BASE AND FLUSH CUT 18 5/8" CSG. COVER THE HOLE WITH A GRATING.
GZR-401 |  | RIG |  | 2023-05-22 13:45 | 2023-05-22 14:00 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 13.3/8" CASING RUNNING
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 15:00 | 1:00 | [6 empty] | Productive |  |  | - REMOVE MASTER BUSHING - P/U WELLHEAD BY & INSTALL IN ROTARY. - INSTALL BACK MASTER BUSHING AND PUT WELLHEAD PUP JOINT ON CASING SLIPS - P/U 13 3/8", L-80, 72PPF, BTC LANDING JOINT AND MADE UP THE SAME TO WELLHEAD. - L/D WELL HEAD WITH LANDING JOINT.
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 15:30 | 0:30 | [6 empty] | Productive |  |  | CREW CHANGE HANDOVER AND TBT.
GZR-401 |  | RIG |  | 2023-05-22 15:30 | 2023-05-22 16:00 | 0:30 | [6 empty] | Productive |  |  | REMOVE MASTER BUSHING. RU FRANKS FMS SLIPS
GZR-401 |  | RIG |  | 2023-05-22 16:00 | 2023-05-22 16:45 | 0:45 | [6 empty] | Productive |  |  | PU 13.3/8" REAMER SHOE ASSEMBLY - RUN SHOE AND FUNCTION TESTED -OK. - P/U 13 3/8", 72PPF, L-80BTC FLOAT COLLAR ASSEMBLY & M/U TO REAMER SHOE JOINT ( M\UP WITH FA-1 ) - FILLED UP THE SHOE TRACK & FUNCTION TESTED - OK. APPLIED THREAD LOCK ON SHOE TRACK CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 16:45 | 2023-05-23 | 7:15 | [6 empty] | Productive |  |  | P/U 13 3/8", L-80, 72PF BTC CASING JOINTS & RIH TO 777 M. - MONITOR ANNULAR LEVEL & CLEAR CELLAR VOLUME USING CELLAR PUMP. - FILL UP EVERY JOINT WHILE RIH VIA FA-1. - TORQUE UP CONNECTIONS TO THE TRIANGLE MARK (~ 12000 FT.LBS), USING FA-1 - TRIPPING SPEED: 8-10 JNT/HR.
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 02:00 | 2:00 | [6 empty] | Productive |  |  | P/U 13 3/8", L-80, 72PF BTC CASING JOINTS & RIH FROM 777 M TO 1048 - MONITOR ANNULAR LEVEL & CLEAR CELLAR VOLUME USING CELLAR PUMP. - FILL UP EVERY JOINT WHILE RIH VIA FA-1. - TORQUE UP CONNECTIONS TO THE TRIANGLE MARK (~ 12000 FT.LBS), USING FA-1 - TRIPPING SPEED: 8 -10 JNT/HR. Page 12 of 120
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 02:45 | 0:45 | [6 empty] | Productive |  |  | PICK UP EXTRA JOINT AND RIH TO 1056 M, STRING STARTS TAKE WEIGHT. APPLY 60 KLBS DOWN , NO PROGRESS. PICK UP AND CHECK FREE UP, SLACK DOWN 80 KLBS, NO PROGRESS. PICK UP FREE AGAIN AND SLACK DOWN UNTIL 100 KLBS, NO PROGRESS. - WASH DOWN WITH SLOW PROGRESS TO 1058 M. 250 GPM , 320 PSI. - REAM DOWN TO 1063 M. TQ 5-8 KLBS, 40 RPM. 300 GPM , 400-450 PSI
GZR-401 |  | RIG |  | 2023-05-22 02:45 | 2023-05-22 03:45 | 1:00 | [6 empty] | Productive |  |  | CIRCULATE AND RECIPROCATE STRING. FR: 450 GPM, SPP: 460 PSI NO LOSSES OFFLINE: -TBT PRIOR P/U & M/U WELLHEAD
GZR-401 |  | RIG |  | 2023-05-22 03:45 | 2023-05-22 04:30 | 0:45 | [6 empty] | Productive |  |  | LAY DOWN EXTRA JOINTS # 91 & 90.
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 05:45 | 1:15 | [6 empty] | Productive |  |  | - P/U AND MADE UP WELL HEAD ASSEMBLY TO CASING STRING, ORIENTATED STRING FOR SOV - REMOVE FMS SLIPS. - RAN IN, M/U LANDING BASE IN CELLAR AND LANDED OFF STRING CONFIRMING CENTRAL. DN WT 270 KLBS. - INSTALL MASTER BUSHING - 13 3/8" CSG SHOE AT 1058 M, FLOAT COLLAR AT 1045 M. OFFLINE: - LOAD TOP & BOTTOM PLUGS INTO CEMENT HEAD
GZR-401 |  | RIG |  | 2023-05-22 05:45 | 2023-05-22 06:15 | 0:30 | [6 empty] | Productive |  |  | RIG UP CEMENT LINE AND CEMENT HEAD. FLUSH CEMENT LINE. CONNECTED CEMENT LINE TO CEMENT HEAD.
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 07:00 | 0:45 | [6 empty] | Productive |  |  | CIRCULATE THROUGH CEMENT HEAD WITH 400 GPM, SPP 450 PSI MEANWHILE PJSM FOR CEMENT JOB.
GZR-401 |  | RIG |  | 2023-05-22 07:00 | 2023-05-22 07:15 | 0:15 | [6 empty] | Productive |  |  | PRESSURE TEST CEMENT LINE TO 4500 PSI- GOOD TEST
GZR-401 |  | RIG |  | 2023-05-22 07:15 | 2023-05-22 07:45 | 0:30 | [6 empty] | Productive |  |  | - PUMPED 100 BBL OF 1.43SG TUNED SPACER BY RIG PUMP WITH 250 GPM/ 160 PSI. MEANWHILE: CEMENTERS MIXING RETARDER AND THEN START PREPARING LEAD SLURRY.
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 09:45 | 2:00 | [6 empty] | Productive |  |  | DROP BOTTOM PLUG AND VERIFIED THE DROP OF THE PLUG BY FLAG INDICATOR. - MIX AND PUMP 422 BBL OF 1.57SG LEAD SLURRY AT 5-6 BBL/MIN - MIX AND PUMP 103 BBL OF 1.89SG TAIL SLURRY AT 4-5 BBLMIN
GZR-401 |  | RIG |  | 2023-05-22 09:45 | 2023-05-22 10:00 | 0:15 | [6 empty] | Productive |  |  | - DROP TOP PLUG - CMT UNIT PUMPED 10 BBL SPACER BEHIND. Page 13 of 120
GZR-401 |  | RIG |  | 2023-05-22 10:00 | 2023-05-22 11:30 | 1:30 | [6 empty] | Productive |  |  | - SWITCH OVER TO RIG PUMPS AND CONT. CEMENT DISPLACEMENT PUMPING 492 BBLS OF 1.25 SG HYDROGARD MUD. - BUMPED PLUG WITH 630 PSI FINAL CIRCULATING PRESSURE, INCREASE THE PRESSURE TO 3200 PSI. - NO RECORDABLE LOSSES WHILE CMT. - DUMP TOTAL OF 179 BBL AS BELOW : 36 BBL OF CONTAMINATED MUD WITH SPACER. 62 BBL OF NEAT SPACER. 46 BBL OF SPACER WITH CEMENT. 35 BBL NEAT CEMENT
GZR-401 |  | RIG |  | 2023-05-22 11:30 | 2023-05-22 12:15 | 0:45 | [6 empty] | Productive |  |  | ****13.3/8"CASING INTEGRITY TEST TO 3200 PSI**** - LINE UP TO CEMENT UNIT FOR CASING TEST AND CHECK FLOATS. - EQUALIZE PRESSURE AND OPEN LO-TRQ VALVE ON RIG FLOOR, ISOLATE RIG STANDPIPE MANIFOLD. - MONITOR PRESSURE AT 3200 PSI - PRESSURE STABLE. - BLED BACK VOLUME TO CEMENT UNIT - VOLUME RETURN 6.0 BBL. >> FLOATS HOLDING
GZR-401 |  | RIG |  | 2023-05-22 12:15 | 2023-05-22 12:45 | 0:30 | [6 empty] | Productive |  |  | - R/D CEMENT LINES AND CEMENT HEAD.
GZR-401 |  | RIG |  | 2023-05-22 12:45 | 2023-05-22 13:30 | 0:45 | [6 empty] | Productive |  |  | - DISCONNECT WELLHEAD RUNNING TOOL FROM WELL HEAD. - POH AND DISCONNECT LANDING JOINT FROM RUNNING TOOL.
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 15:30 | 2:00 | [6 empty] | Productive |  |  | - RD FRANKS TRS EQUIPMENTS
GZR-401 |  | RIG |  | 2023-05-22 15:30 | 2023-05-22 16:30 | 1:00 | [6 empty] | Productive |  |  | - INSTALL CELLAR FRAMS & GRATING
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 19:30 | 3:00 | [6 empty] | Productive |  |  | - INSTALL SOVS ON WELLHEAD USING RIG WINCH AND TIGHTENED THE SAME - P/T LOWER SOVS TO 5K - P/T UPPER SOVS TO 10K MEANWHILE: - PT AUTO IBOP TO 10 K PSI - GOOD TEST - PT MANUAL IBOP TO 10 K PSI - GOOD TEST
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 19:45 | 0:15 | [6 empty] | Productive |  |  | CREW HANDOVER AND TBT ORIOR NU BOP
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-22 22:30 | 2:45 | [6 empty] | Productive |  |  | - N/U BOP ON WELLHEAD STACK. - TIGHTENED FASTLOCK CONNECTION. - CONNECTED KILL LINE AND CHOKE LINE. - CONNECTED HYDRULIC CONTROL LINES.
GZR-401 |  | RIG |  | 2023-05-22 22:30 | 2023-05-23 | 1:30 | [6 empty] | Productive |  |  | - NU MUD RISER AND FLOW LINE. - INSTALL MOUSE HOLE
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 | [6 empty] | Productive |  |  | TBT PRIOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY - RUN AND INSTALL TEST ASSEMBLY Page 14 of 120
GZR-401 |  | RIG |  | 2023-05-22 00:30 | 2023-05-22 01:45 | 1:15 | [6 empty] | Productive |  |  | - PERFORM BOP CONNECTION PRESSURE TEST TO 300 PSI /10000 PSI FOR 5 MIN EACH AGAINST UPPER PIPE RAM, VALVE 78 IN CHOKE MANIFOLD AND KILL LINE LO-TORK VALVE >> GOOD TEST.
GZR-401 |  | RIG |  | 2023-05-22 01:45 | 2023-05-22 02:00 | 0:15 | [6 empty] | Productive |  |  | DISCONNECTED TEST LINES. RETRIEVED AND LAID DOWN TEST ASSEMBLY.
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 02:15 | 0:15 | [6 empty] | Productive |  |  | INSTALLED WEAR BUSHING AND L/D RUNNING TOOL.
GZR-401 |  | RIG |  | 2023-05-22 02:15 | 2023-05-22 03:15 | 1:00 | [6 empty] | Productive |  |  | - PERFORMED BOP FUNCTION TEST - PERFORMED BOP DRAW DOWN TEST. OK - PERFORMED DEDICATED SHEAR DRAW DOWN TEST. OK
GZR-401 |  | RIG |  | 2023-05-22 03:15 | 2023-05-22 03:30 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR P/U AND RACK BACK DP.
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 08:45 | 5:15 | [6 empty] | Productive |  |  | RIH WITH 69 X G2 5" DP (19.5#) SINGLES POOH AND RACK BACK 23 STANDS OF 19.5# G2 DP
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 09:00 | 0:15 | [6 empty] | Productive |  |  | CREW CHANGE & HANDOVER PJSM PRIOR P/U, M/U AND RIH 12-1/4" BHA.
GZR-401 |  | RIG |  | 2023-05-22 09:00 | 2023-05-22 13:00 | 4:00 | [6 empty] | Productive |  |  | P/U, M/U AND RIH 12-1/4"BHA TO 102.9 M AS FOLLOW: - PICK UP NEW 12-1/4ﬂPDC Bit HDBS GTi75WKHO (10x12/32 NOZZLES) - 12 1/8" RSS I-CRUISE -NO SLEEVE STAB. - 8" MWD TOOL - 12.1/8" STABILIZER - 8" DOWNHOLE SCREEN. - 8 FLOAT SUB. - 8" PBL SUB. - 8 X 8.1/4" DC AT 11:30 SHALLOW TEST THE MWD TOOL AND I-CRUISE AT FR 800GPM; SPP:1030 PSI. NOTES: - USED MANUAL TONGS TO MU MWD ANDICRUISE TOOLS.
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 14:00 | 1:00 | [6 empty] | Productive |  |  | ATTEMPT TO M/U THE DC TO DLR USING THE IRONROUGHNECK SPINNER IN THE MOUSE HOLE BUT UNABLE TO M/U , BREAK OUT AND FOUND DAMAGE IN THE DLR BOX. CHECKED THE DC PIN TO THE BHA STRING , NO ISSUES. P/U THE BACK UP DLR AND M/U THE SAME TO THE BHA. Page 15 of 120
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 16:30 | 2:30 | [6 empty] | Productive |  |  | CONT. RIH 12.1/4" BHA FROM 102.9 M TO 458.23 M AS FOLLOW: - NOV DOG LEG REAMER (DLR). - 4 X 8 1/4" DC - 8 1/4" DRILLING JAR. - 3 X 8 1/4" DC - XO - 5 STANDS HWDP FROM MAST - 5 STANDS (10 JOINTS) HWDP SINGLE IN - FILL UP STRING - WEIGHT BELOW JAR: 60 KLBS. - TOTAL BHA WEIGHT: 100 KLBS.
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 19:15 | 2:45 | [6 empty] | Productive |  |  | CONT. RIH WITH 12-1/4" BHA SINGLE IN WITH G2 DP FROM 458.23 M TO 850 M - MONITOR DISPLACEMENT ON TRIP TANK
GZR-401 |  | RIG |  | 2023-05-22 19:15 | 2023-05-22 19:30 | 0:15 | [6 empty] | Productive |  |  | PJSM , PRIOR TO SLIP AND CUT.
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 21:30 | 2:00 | [6 empty] | Productive |  |  | SLIP AND CUT DRILL LINE - HANG BLOCK AND PARKED TDS. - SLIP 12 M AND CUT 24 OF DRILL LINE. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT. NOTE: - AT 20:00 CREW HANDOVER
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-22 22:30 | 1:00 | [6 empty] | Productive |  |  | CONT. RIH WITH 12-1/4" BHA SINGLE IN WITH G2 DP FROM 850 M TO 1006 M - MONITOR DISPLACEMENT ON TRIP TANK
GZR-401 |  | RIG |  | 2023-05-22 22:30 | 2023-05-22 23:00 | 0:30 | [6 empty] | Productive |  |  | CONDUCTED D1 & D6 DRILL KICK WHILE TRIPPING WITH CREW # C - DRILLER AND ML NOTICE THE INCREASE IN TRIP TANK - GOOD RESPONSE FROM CREW IN SECURING THE WELL IN LESS THAN 1 MINS. - DISCUSS COMPLICATION IF ANNULAR LEAKING.
GZR-401 |  |  |  | 2023-05-22 23:00 | 2023-05-22 23:15 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | - OBSERVED LEAK IN CHOKE VALVE #1 HYDRAULIC HOSE - CHANGE LINE UP TO CHOKE VALVE #2. ( MEANTIME INSTALL NEW HYDRAULIC HOSE FOR CHOKE #1) - PRESSURED UP 13 3/8" CSG TO 400-450 PSI. OBSERVED PRESSURE DROP ( CHOKE #2 NOT HOLDING ) - CHANGE LINE UP TO CHOKE VALVE #1
GZR-401 |  | RIG |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 | [6 empty] | Productive |  |  | PERFORMED D4 WELL KILL DRILL WITH CREW # C - PRESSURED UP 13 3/8" CSG TO 400-450 PSI - GOOD RESPONSE FROM CREW, AD AND DR TRAINED IN CHOKE, HAD AFTER ACTION REVIEW AND DISCUSS THE FINDINGS. Page 16 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:45 | 0:45 | [6 empty] | Productive |  |  | - TOOK SCR - TOOK FLOW BACK BASE LINE WITH 750 GPM , RIG RECORDED 26 BBL, MUD LOGGER RECORDED 24 BBL - TOOK FLOW BACK BASE LINE WITH 900 GPM , RIG RECORDED 38 BBL, MUD LOGGER RECORDED 35 BBL
GZR-401 |  | RIG |  | 2023-05-22 00:45 | 2023-05-22 01:00 | 0:15 | [6 empty] | Productive |  |  | WASH DOWN LAST STAND FROM 1006 M UNTIL TAG CEMENT WIPER PLUGS AT 1043.5 M FR: 380 GPM, SPP: 620 PSI
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 03:30 | 2:30 | [6 empty] | Productive |  |  | DRILL SHOE TRACK DRILL CEMENT PLUGS FROM 1043 M TO 1045 M FR 550-750 GPM, SPP 1200-1950 PSI, WOB 10 - 35 KLBS, RPM 50-80 , TRQ 2 -8 KFT.LBS. TRIED DIFFERENT PARAMETERS. MANAGED TO DRILL IT WITH 35 KLBS WOB
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 05:00 | 1:30 | [6 empty] | Productive |  |  | DRILL OUT SHOE TRACK FROM 1045 M TO 1058 M FR 750-800 GPM, SPP 1900-2400 PSI, WOB 5-12 KLBS, RPM 70 , TRQ 2-7 KFT.LBS. TAG REMER SHOE AT 1058 M. CLEAR RAT HOLE FROM 1058 M TO 1063 M. FR 800 GPM, SPP 2400 PSI , 70 RPM, TRQ 2-7 KFT.LBS WOB
GZR-401 |  | RIG |  | 2023-05-22 05:00 | 2023-05-22 05:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 06:15 | 1:00 | [6 empty] | Productive |  |  | DRILL NEW FORMATION FROM 1063 M TO 1068 M. FR 850 GPM, SPP 2490 PSI, 60-70 RPM, TRQ 3.5 -7.5 KFT.LBS. - SPACE-OUT THE STRING FOR FIT MW IN = MW OUT = 1.25 SG
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 06:30 | 0:15 | [6 empty] | Productive |  |  | - POOH TO INSIDE CASING - LINE UP TO PUMP THROUG KILL LINE AND STRING FOR FIT
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 07:00 | 0:30 | [6 empty] | Productive |  |  | ***** FIT AT 13-3/8 CASING SHOE (NATIH A/B) TO 1.66 SG OVER 1.25 SG MUD IN HOLE USING MUD PUMPS ***** - PJSM. - CLOSED UPPER PIPE RAMS. - STARTED PUMPING WITH RIG PUMPS AT 0.5 BBL/MIN PUMP RATE. - PRESSURED UP WELL TO 620 PSI. - MONITORED PRESSURE FOR 30 MINUTES. - BLED OFF PRESSURE. - FIT PRESSURE REACHED WAS 620 PSI WITH 1.25 SG TEST FLUID, EMW ACHIEVED WAS 1.66 SG. Page 17 of 120
GZR-401 |  | RIG |  | 2023-05-22 07:00 | 2023-05-22 15:45 | 8:45 | [6 empty] | Productive |  |  | DRILL FROM 1068 M TO 1170 M. FR 800-850 GPM, SPP 2200-2500PSI, WOB 10-15 KLBS , RPM 60-80 , TRQ 2-10 KFT.LBS - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - CONTROL DRLG PARAMETERS TILL DLR GET OUT FROM SHOE. AVG ROP: 14.12 M/HR.
GZR-401 |  | RIG |  | 2023-05-22 15:45 | 2023-05-23 | 8:15 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 1170 M TO 1364M. FR 800-900 GPM, SPP 2700-2900 PSI, WOB 10-35 KLBS , RPM 90-130 , TRQ 4-13 KFT.LBS AVG ROP: 29 M/HR NOTES: - AT 1265 M @19:45 DURING CONNECTION FUNCTION TEST CHOKE VALVE #2. GOOD TEST - AT 1293 M @ 20:50GREASE WASHPIPE - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - OBSERVED DOWNHOLE VIBRATION AS PER MWD TOOL ( HIGH TO MODERATE ), DRILL WITH CONTROL PARAMETERS DRILLING SUMMARY ================== FOOTAGE DRILLED: 301 M DAILY BIT HRS: 14.44 HR AVG ROP: 20.84 M/HR MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 10810.44169.76 11390.318.08 12540.0696.90 13400.06109.98 Page 18 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 17:00 | 17:00 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 1364 M TO 1813M. FR 900 GPM, SPP 3200-3480 PSI, WOB 10-35 KLBS , RPM 140 , TRQ 4-11 KFT.LBS AVG ROP: 35.2M/HR NOTES: - AT 1380 M @ 00:30TOOK SCR - AT 1409 M @01:45HAD OVER TRQ CONNECTION TOOK 5 MINS MORE TO B\O THE SAME - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. -NAHR UMR AT 1440 M. - SHUAIBA AT 1525 M. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 14560.09239.35 14840.0092.84 16570.09335.67 18010.00163.94
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 17:30 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS.
GZR-401 |  | RIG |  | 2023-05-22 17:30 | 2023-05-23 | 6:30 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 1813 M TO 1940M. FR 900 GPM, SPP 3500-3700 PSI, WOB 25-35 KLBS , RPM 140 , TRQ 4-15 KFT.LBS DRILLING SUMMARY ================== FOOTAGE DRILLED: 576 M DAILY BIT HRS: 18.64 HR AVG ROP: 31 M/HR NOTES: - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - DOWNHOLE VIBRATION AS PER MWD TOOL ( LOW TO MODERATE ) - HABSHAN AT 1889 M. - AT 1935 M EXPERIENCE LATERAL VIBRATION IN HABSHAN FORMATIONS- MITIGATE IT BY REDUCING WOB AND RPM OR P\U OFF-BOTTOM. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 18300.06163.94 18880.06202.41 19160.09200.41 Page 19 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 17:45 | 17:45 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 1940 M TO 2273M. FR 800- 900 GPM, SPP 3200-3800 PSI, WOB 15-35 KLBS , RPM 120-160 , TRQ 7 -14 KFT.LBS AVG ROP: 23.6 M/HR NOTES: - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. ( 5-10 % INCREASE IN CUTTING ) - FROM 1935 M TO 1946 m EXPERIENCE LATERAL VIBRATION IN HABSHAN FORMATIONS- MITIGATE IT BY REDUCING WOB & RPM OR P\U OFF-BOTTOM. - AT 1985 M TOOK SCR MP #2 &3. - FROM 1940 M TO 1970 M OBSERVED INCREASE IN CAVING PERCENTAGE FROM NAHR UMR BY 20% AND SIZE OF 5 - 7 CM - AT 2043 M GREASE WASHPIPE. - DRILL WITH 870 GPM WITH 2 PUMPS FROM 2132 M TO 2203 M. -AT 2215 M GREASE WASHPIPE. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 19450.14164.25 20030.0673.98 20320.09206.17 21180.0695.46 22050.06243.81
GZR-401 |  | RIG |  | 2023-05-22 17:45 | 2023-05-22 18:00 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D2 WITH CREW # D. GOOD RESPONSE FROM DRILLER AND MUD LOGGER IN DETECTING THE INCREASE IN PVT. DRILLER SPACE OUT STRING FOR FLOW CHECK. - HAD AN AAR .
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-22 18:15 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE. Page 20 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-23 | 5:45 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2273 M TO 2394M. FR 870- 900 GPM, SPP 3500-3900 PSI, WOB 30-40 KLBS , RPM 130-180 , TRQ 8 -15 KFT.LBS DRILLING SUMMARY ================== FOOTAGE DRILLED: 454 M DAILY BIT HRS: 19.18 HR AVG ROP: 23.67 M/HR NOTES: - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. ( 5 % INCREASE IN CUTTING ) - AT 2273 M TOOK SCR MP #1 &2. - MAFRAQ AT 2287 M MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 22910.0621.33 23490.09120.18 23770.0692.19 Page 21 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 17:45 | 17:45 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2394 M TO 2705M. FR 870- 900 GPM, SPP 3700-3950 PSI, WOB 35-45 KLBS , RPM 140-180 , TRQ 8 -15 KFT.LBS AVG ROP : 20.44 M\HR NOTES: - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS FROM 2307 M TO 2435 M, - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. ( 5 % INCREASE IN CUTTING ) - HAD ISSUE WITH MP#3DRILL WITH 870 GPM USING 2 PUMPS FROM 2417 M TO 2434 M. - AT 2475 M GREASE WASHPIPE. -AT 2676 M GREASE WASHPIPE. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 24060.06204.35 24350.06145.21 24630.09137.14 25210.12117.61 26360.1417.85 26650.0930.75
GZR-401 |  | RIG |  | 2023-05-22 17:45 | 2023-05-22 18:15 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS. Page 22 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-22 21:45 | 3:30 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2705M TO 2762M. FR 870 GPM, SPP 3750-4000 PSI, WOB 35-40 KLBS , RPM 140-180 , TRQ 8 -18 KFT.LBS AVG ROP : 20.3 M\HR NOTES: - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS. - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - FROM 2725 M TO 2762 OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 27220.09335.38 27510.06303.93
GZR-401 |  |  |  | 2023-05-22 21:45 | 2023-05-22 22:45 | 1:00 |  |  |  | RREP |  |  | Non-Productive |  |  | HAD HYDRAULIC OIL LEAK IN TDS FIXED THE SAME. Page 23 of 120
GZR-401 |  | RIG |  | 2023-05-22 22:45 | 2023-05-23 | 1:15 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2762 M TO 2781 M. FR 870 GPM, SPP 3750-4000 PSI, WOB 35-40 KLBS , RPM 140-170 , TRQ 8 -18 KFT.LBS AVG ROP : 16 M\HR DRILLING SUMMARY ================== FOOTAGE DRILLED: 387 M DAILY BIT HRS: 19.32 HR AVG ROP: 20.03 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. ( 5% INCREASE IN CUTTING ) - FROM 2762 M TO 2770 OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 27800.00229.43
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2781 M TO 2861 M. FR 870-900 GPM, SPP 3750-4200 PSI, WOB 35-45 KLBS , RPM 140-180 , TRQ 8 -18 KFT.LBS AVG ROP : 16.5 M\HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - HAD AN ISSUE WITH MP#1 DRILL WITH 870 GPM USING 2 PUMPS FROM 2825 M TO 2840 M. - AT 2819 M @ 02:45GREASE WASHPIPE. - OBSERVEDSTICK AND SLIP, MITIGATED WITH DIFF PARAMETERS FROM 2307 M TO 2435 M. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 28090.0696.74 28380.06145.85 Page 24 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 2997 M TO 3080 M. FR 865 GPM, SPP 4100-4250 PSI, WOB 27-42 KLBS , RPM 130-180 , TRQ 9 -16 KFT.LBS AVG ROP : 16 M\HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~865 GPM - EXPERIENCEDSTICK SLIP AND VIBRATION IN MWD TOOLS IN DIFFERENT SPOTS INSIDE KHUFF - HAD TO CONTROL RPM AND WOB. OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 40-42 KLBS MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 30100.0018.04 30390.00315.74 30680.06305.76
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 15:00 | 9:00 |  |  |  | RREP |  |  | Non-Productive |  |  | -CONNECT STAND # 29 G3 AND OBSERVE WASH OUT IN CONNECTION. - TRY TO BREAK OUT FROM SAVER SUB BUT NO SUCESS. - RUN ONE SINGLE FROM STAND #29 IN MOUSE HOLE AND TRY TO BREAK OUT THE FIRST SINGLE , BUT NO SUCESS WITH IRONROUGHNECK. - TRY TO BREAK OUT WITH MANUAL TONG WITH UPTO 60 LB.FT - NO SUCESS. - DECIDED TO BREAK OUT THE JOINT WITH HEAT, APPLY HEAT AND BREAK THE FIRST SIGNLE OF STAND # 29 WITH MANUAL TONG UPTO 45 LB.FT - SUCESS. - POH AND L/D STAND # 28 TO ALLOW TO LOWER THE TDS TO ROTARY LEVEL. - REMOVE GRAPPLE. - REMOVE LOCK WIRE AND SAVER SUB CLAMP. - REMOVE SAVER SUB. - INSTALL NEW SAVER SUB AND CLAMP. - INSTALL GRAPPLE. - P\U AND M\UP STAND #28 FROM GROUND AND RESUME DRILLIGN
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 15:30 | 0:30 | [6 empty] | Productive |  |  | TDS SERVICE. Page 25 of 120
GZR-401 |  | RIG |  | 2023-05-22 15:30 | 2023-05-23 | 8:30 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3080 M TO 3155 M. FR 850 GPM, SPP 4100-4250 PSI, WOB 27-42 KLBS , RPM 120-180 , TRQ 9 -18 KFT.LBS AVG ROP : 10.4 M\HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~865 GPM - FROM 3102 M TO 3137 M, HAD AN ISSUE IN MP #2, CONT. DRILLING WITH 2 MP. - FROM 3117 M TO 3120 M OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. - EXPERIENCEDSTICK SLIP AND VIBRATION IN MWD TOOLS IN DIFFERENT SPOTS INSIDE KHUFF - HAD TO CONTROL RPM AND WOB. OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 40-42 KLBS. DRILLING SUMMARY ================== FOOTAGE DRILLED: 157 M DAILY BIT HRS: 12.14 HR AVG ROP: 12.93 M/HR MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 31260.0672.53 31540.06129.08 Page 26 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 17:15 | 17:15 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3155 M TO 3395 M. FR 810-830 GPM, SPP 4120-4250 PSI, WOB 27-43 KLBS , RPM 150-180 , TRQ 8 -16 KFT.LBS AVG ROP :17.6 M\HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~830 GPM - AT 3165 M TOOK SCR. - FROM 3193 M TO 3207 M, HAD AN ISSUE IN MP #3, CONT. DRILLING WITH 2 MUD PUMPS. - AT 3200 M STARTED INCREASING MW FORM 1.25 SG TO 1.28 SG ~ 50 M PRIOR ENTERING GHARIF - EXPERIENCEDSTICK SLIP AND VIBRATION IN MWD TOOLS IN DIFFERENT SPOTS INSIDE KHUFF - HAD TO CONTROL WOB AND DRILL WITH 180 RPM ACROSS KHUFF. - OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 40 KLBS. - PUMP 50 BBL OF NUT SHELL AT 3308 M. - TOP OF GHARIF AT 3452 M. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 31820.0997.84 33260.06178.51
GZR-401 |  | RIG |  | 2023-05-22 17:15 | 2023-05-22 18:00 | 0:45 | [6 empty] | Productive |  |  | TDS SERVICE AND DROP INSPECTION. Page 27 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3395 M TO 3440 M. FR 800-830 GPM, SPP 4120-4250 PSI, WOB 27-45 KLBS , RPM150-180 , TRQ 8 -13 KFT.LBS AVG ROP : 9.88 M\HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~800 GPM - EXPERIENCEDSTICK SLIP AND VIBRATION IN MWD TOOLS IN DIFFERENT SPOTS INSIDE KHUFF - HAD TO CONTROL WOB AND DRILL WITH 180 RPM ACROSS KHUFF. - OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 40 KLBS. - PUMP 50 BBL OF NUT SHELL AT 3395 M. - DUMP SAND TRAP ON CONNECTION AT 3423 M. - FUNCTION TEST BOP AT 3423 M. - TOP OF HAUSHI L.S AT 3429 M - FROM 3430 M TO 3440 M, HAD AN ISSUE IN MP #3, CONT. DRILLING WITH 2 MUD PUMPS. DRILLING SUMMARY ================== FOOTAGE DRILLED: 286 M DAILY BIT HRS: 18.13 HR AVG ROP: 15.77 M/HR MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 34130.09166.38
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 16:15 | 16:15 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3440 M TO 3497 M. FR 800-810 GPM, SPP 4200-4300 PSI, WOB 25-45 KLBS , RPM120-160 , TRQ 6 -10 KFT.LBS - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4300 DRILL WITH ~800 GPM. - TOP OF BASAL SAND AT 3478 M. AVG ROP : XXX M\HR
GZR-401 |  |  |  | 2023-05-22 16:15 | 2023-05-22 16:45 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | FAILURE IN MUD PUMP 2 AND 3 , MEANWHILE RECIPROCATED THE STRING WITH 350 GPM, SPP 1050 PSI, RPM 30, TRQ 2 KFT.LBS - REPLACED VALVE SET IN MP #2 - CHANGE OUT DISCHARGE MODULE IN MP #3 Page 28 of 120
GZR-401 |  | RIG |  | 2023-05-22 16:45 | 2023-05-23 | 7:15 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3497 M TO 3512 M. FR 800 GPM, SPP 4230-4300 PSI, WOB 25-55 KLBS , RPM120-140 , TRQ 5 -10 KFT.LBS - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~800 GPM. - TOP OF AL KHALATAAT 3508 M - OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 35-40 KLBS. - HAD AN ISSUE IN MP #3, CONT. DRILLING WITH 2 MUD PUMPS. AVG ROP : 2.1 M\HR OFFLINE: - CONTINUES CHANGE OUT DISCHARGE MODULE IN MP #3 DRILLING SUMMARY ================== FOOTAGE DRILLED: 72 M DAILY BIT HRS: 18.84 HR AVG ROP: 3.82 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 09:30 | 9:30 | [6 empty] | Productive |  |  | CONT. DRILLING 12.1/4'' HOLE SECTION FROM 3512 M TO 3525.5 M. FR 800 GPM, SPP 4250-4300 PSI, WOB 25-50 KLBS , RPM120-150 , TRQ 5 -9 KFT.LBS - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE 900 GPM DUE TO HIGH SPP ~ 4270 DRILL WITH ~800 GPM. - OBSERVED STICK SLIP AND VIBRATION INCREASE ONCE WOB APPROACH 35-40 KLBS. - HAD AN ISSUE IN MP #3, CONT. DRILLING WITH 2 MUD PUMPS. - SLOW PROGRESS AVG ROP < 2 M\HR. ATTEMPTED TO OPTIMIZE THE ROP USING DIFFERENT DRILLING PARAMETERS ANDPERFORMED DRILL-OFF TESTS BUT OBSERVE HIGH STICK AND SLIP AND NO PROGRESS IN ROP. - DECISION MADE TO POH DUE TO LOW ROP. AVG ROP : 1.88 M\HR DRILLING SUMMARY ================== FOOTAGE DRILLED: 13 M DAILY BIT HRS: 7.03 HR AVG ROP: 1.88 M/HR Page 29 of 120
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 12:30 | 3:00 | [6 empty] | Productive |  |  | - INCREASE MW FROM 1.28 SG TO 1.30 SG PRIOR POOH. - PREPARED WEIGHTED PILL TO INCREASE MWFROM 1.28 SG TO 1.30 SG PRIOR POOH MEANWHILE RECIPROCATE THE STRING UP \ DOWN. - MW IN \ OUT = 1.30 SG. - NO LOSSES.
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 13:00 | 0:30 | [6 empty] | Productive |  |  | - TOOK SCR. - FLOW CHECK WELL-OK STATIC. - INSTALLED AIR SLIPS
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 19:30 | 6:30 | [6 empty] | Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 3525.5 MTO 1527 M. - SMOOTH POH ON ELEVATOR BUT ENCOUNTERED OVERPULL FROM 2980 M TO 2870 M UPTO 40 KLB. NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 11 X CONNECTION WITH OVERTORQUE.
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 19:45 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D1 DRILL KICK WHILE TRIPPING WITH CREW # A - GOOD RESPONSE FROM CREWIN SECURING THE WELL IN LESS THAN 2 MINS. - AAR
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-22 21:15 | 1:30 | [6 empty] | Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 1527 MTO 1356 M. - SMOOTH POH ON ELEVATOR BUT ENCOUNTERED OVERPULL FROM 1472 M TO 1356 M UPTO 40 KLB. - OBSERVED OVERPULL MORE THAN 60 KLB AT 1356 M, WORK TO PASS THE SPOT NO SUCCESS NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 3 X CONNECTION WITH OVERTORQUE.
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 23:30 | 2:15 | [6 empty] | Productive |  |  | - PUMP OUT FROM 1356 M TO 1170 M, WITH 800 GPM, SPP 2500-2700 PSI - OBSERVED OVERPULL MORE THAN 60 KLB NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 3 X CONNECTION WITH OVERTORQUE.
GZR-401 |  | RIG |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 | [6 empty] | Productive |  |  | - BACKREAM FROM 1170 M TO 1165M WITH, WITH 800 GPM, SPP 2500-2700 PSI, RPM 45, TRQ 1.5 - 4 KFT.LBS NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 1 X CONNECTION WITH OVERTORQUE. Page 30 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 | [6 empty] | Productive |  |  | - BACKREAM FROM 1165 M TO 1035 M WITH, WITH 800 GPM, SPP 2500-2700 PSI, RPM 45, TRQ 1.5 - 4 KFT.LBS. (INSIDE 13 3/8" CSG SHOE) NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 4 X CONNECTION WITH OVERTORQUE.
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 02:00 | 0:30 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN WITH 900 GPM, SPP 3300-3400, RPM 45 - ~ 5 % INCREASED IN CUTTING
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 02:15 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK WELL-OK STATIC.
GZR-401 |  | RIG |  | 2023-05-22 02:15 | 2023-05-22 03:30 | 1:15 | [6 empty] | Productive |  |  | SLIP DRILL LINE - TBT PRIOR SLIP DRILL LINE. - HANG TRAVELING BLOCK - SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 05:30 | 2:00 | [6 empty] | Productive |  |  | - CONT. POOH 12.25" BHA ON ELEVATOR FROM 1007 M TO 471 M.TOP OF BHA. NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 5 X CONNECTION WITH OVERTORQUE. - USED MANUAL TONG- HT65 TO BREAK-OUT ALL CONNECTION WITH 55-60 KLB.FT
GZR-401 |  | RIG |  | 2023-05-22 05:30 | 2023-05-22 05:45 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK AT TOP OF BHA- WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 05:45 | 2023-05-22 06:00 | 0:15 | [6 empty] | Productive |  |  | - CONT. POH 12 1/4" BHA FROM 471 M TO 444 M. - LAY DOWN 5'' HWDP
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 06:15 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D1 DRILL KICK WHILE TRIPPING WITH CREW # D - GOOD RESPONSE FROM CREWIN SECURING THE WELL IN LESS THAN 2 MINS. - AAR.
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 07:30 | 1:15 | [6 empty] | Productive |  |  | - CONT. POH 12 1/4" BHA FROM 444 M TO 318 M. - LAY DOWN TOTAL 5 STDS OF 5'' HWDP.
GZR-401 |  | RIG |  | 2023-05-22 07:30 | 2023-05-22 08:00 | 0:30 | [6 empty] | Productive |  |  | - CONT. POH 12 1/4" BHA FROM 318 M TO 190 M. - RACK BACK 5 STDS OF 5" HWDP.
GZR-401 |  | RIG |  | 2023-05-22 08:00 | 2023-05-22 09:45 | 1:45 | [6 empty] | Productive |  |  | - CONT. POH 12 1/4" BHAFROM 190 M TO 132.77 M AS BELOW - L/D 3 X JTS 8 1/4" DC. - L/D 8" JAR. - L/D 1 X JTS 8 1/4" DC # 12. Page 31 of 120
GZR-401 |  |  |  | 2023-05-22 09:45 | 2023-05-22 11:45 | 2:00 |  |  |  | RREP |  |  | Non-Productive |  |  | - TRIED TO BREAK OUT THE 8.1/4" DC JT# 11 WITH IRON ROUHNECK- NO SUCCESS. - TRIED WITH MANUAL TONG- HT65 WITH UPTO 65 KLB.FT - NO SUCCESS. - TRIED WITH MANUAL TONG BV100 UPTO 90 KLB.FT - NO SUCCESS. - DECIDED TO BREAK OUT THE JOINT WITH HEAT. - TBT ON RIG FLOOR ON THE HEAT OPERATION APPLIED ON THE DC CONNECTION. - APPLY HEAT AND BREAK-OUT WITH MANUAL TONG UP TO 60 KLB.FTAND L/D 8.1/4" DC JT # 11 - SUCCESS. - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 11:45 | 2023-05-22 13:00 | 1:15 | [6 empty] | Productive |  |  | CONT. POH AND LAY DOWN 12.1/4" BHA FROM 123 M TO 103 M. - BREAK AND L/D 2 X JTS 8.1/4" DC # 10 AND 9. - L/D DOG LEG REAMER.
GZR-401 |  |  |  | 2023-05-22 13:00 | 2023-05-22 17:30 | 4:30 |  |  |  | RREP |  |  | Non-Productive |  |  | - TRIED TO BREAK OUT THE 8.1/4" DC JT # 8 WITH MANUAL TONG BV100 UPTO 90 KLB.FT - NO SUCCESS. - DECIDED TO BREAK OUT THE JOINT WITH HEAT. - APPLY HEAT AND BREAKUP AND L/D 8.1/4" DC JT # 8 - NO SUCCESS. - DECIDED TO RACK BACK 8.1/4" STD WITH JTS # 8,7,6. - APPLY HEAT AND R/B 8.1/4"DC STD FROM 103 M TO 74 M. - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 17:30 | 2023-05-22 18:30 | 1:00 | [6 empty] | Productive |  |  | TRIED TO BREAK OUT 8.1/4" DC JT # 5 , OBSERVE OVERTORQUE. -TRIED WITH MANUAL TONG UPTO 90 KLB.FT. - APPLY HEAT AND BREAKUP AND L/D 8.1/4" DC JT # 5. - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 21:45 | 3:15 | [6 empty] | Productive |  |  | CONT. POH AND LAY DOWN 12.1/4" BHA FROM 65 M TOSURFACE - BREAK AND L/D 4 X JTS 8.1/4" DC # 4, 3, 2 AND 1. - BREAK-OUT WITH MANUAL TONG UP TO 80 KLB.FT - L/D PBL SUB. - LAY DOWN FLOAT SUB WITH NON-PORTED FLOAT VALVE. - LAY DOWN STABS - LAY DOWN 8" FILTER SUB AND MWD. - BREAK OUT THE BIT AND LAY DOWN I-CRUISE. ( 40% BALLDUP ON THE BIT) - BIT GRADING: 3-2-WT-C-X-I-CR-PR - ALL COMPONENTS BREAK-OUT WITH MANUAL TONG UP TO 80 KLB.FT. - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 21:45 | 2023-05-22 22:00 | 0:15 | [6 empty] | Productive |  |  | CLEAN & CLEAR RIG FLOOR Page 32 of 120
GZR-401 |  | RIG |  | 2023-05-22 22:00 | 2023-05-22 22:15 | 0:15 | [6 empty] | Productive |  |  | - PU , MU WEAR BUSHING RETRIEVE TOOL. - RETRIEVED WEAR BUSHING
GZR-401 |  | RIG |  | 2023-05-22 22:15 | 2023-05-22 23:00 | 0:45 | [6 empty] | Productive |  |  | - PU, MU JETTING TOOL - JET AND FLUSH BOP AND WELLHEAD
GZR-401 |  | RIG |  | 2023-05-22 23:00 | 2023-05-22 23:15 | 0:15 | [6 empty] | Productive |  |  | - LAY DOWN JETTING TOOL AND WEAR BUSHING RUNING TOOL
GZR-401 |  | RIG |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 | [6 empty] | Productive |  |  | - REMOVE BAILS AND ELEVATOR. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 | [6 empty] | Productive |  |  | - REMOVE SAVER SUB
GZR-401 |  | RIG |  | 2023-05-22 00:30 | 2023-05-22 00:45 | 0:15 | [6 empty] | Productive |  |  | -PJSM WITH ALL CREW PRIOR R/U FRANKS EQUIPMENT.
GZR-401 |  | RIG |  | 2023-05-22 00:45 | 2023-05-22 02:30 | 1:45 | [6 empty] | Productive |  |  | - RIG UP FA-1 SERVICE LOOP. - PICK UP AND RIG UP CRT. - CONDUCT DROP INSPECTION. - R/UP HYDRAULIC ELEVATOR - MU SAFETY VALVE WITH 9.5/8" WATER BUSHING. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 02:45 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 9 5/8" HANGER DUMMY RUN
GZR-401 |  | RIG |  | 2023-05-22 02:45 | 2023-05-22 04:00 | 1:15 | [6 empty] | Productive |  |  | 9-5/8'' CASING HANGER DUMMY RUN: - PU AND RIH 9-5/8'' CASING HANGER ACROSS ROTARY. - PU, MU LANDING JOINT TO 9-5/8'' CASING HANGER. - LAND CASING HANGER IN WELL HEAD PROFILE. HOP 10.56 M BRT, STICK UP 1.09 M. - VERIFY YELLOW MARK THROUGH WH LOWER SOV™S. - POOH AND LD 9-5/8'' CASING HANGER ASSEMBLY.
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 04:30 | 0:30 | [6 empty] | Productive |  |  | - REMOVE MASTER BUSHINGS. - INSTALLED FMS. - VERIFIED INTERLOCKING SYSTEM IS WORKING PROPERLY FOR CRT AND FMS.
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 04:45 | 0:15 | [6 empty] | Productive |  |  | - PJSM WITH ALL CREW PRIOR P/U 9 5/8" SHOE TRACK AND RIH WITH CASING.
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 05:30 | 0:45 | [6 empty] | Productive |  |  | RIH WITH 9-5/8'' SHOE TRACK: - PICK UP 9 5/8" REAMER SHOE,FUNCTION TEST FLOAT. OK - PU, MU AND RIH SHOE TRACK TO 52.25 M. TESTED FLOATS FUNCTIONING OK. - APPLIED BAKERLOCK ON SHOETRACK CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 05:30 | 2023-05-22 05:45 | 0:15 | [6 empty] | Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 52 M TO 77 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS.
GZR-401 |  |  |  | 2023-05-22 05:45 | 2023-05-22 06:00 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | TROUBLESHOOTING PIPE CAT , RE-INSTALL BASKET CHAIN. Page 33 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 08:00 | 2:00 | [6 empty] | Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 77 M TO 276 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED7-10 JNT / HR
GZR-401 |  | RIG |  | 2023-05-22 08:00 | 2023-05-22 08:15 | 0:15 | [6 empty] | Productive |  |  | TBT WITH FRANK AND RIG CREW ON RIG 9.5/8" CASING.
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 08:45 | 0:30 | [6 empty] | Productive |  |  | FOUND THE PIPE CAT BAKET PULL CLIVES BROKEN , REPLACED WITH NEW ONE.
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 12:00 | 3:15 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 276 M TO 582 M - AT 284 MHAD ISSUE WITH JT# 25 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 15 MINS MORE. - FILLED UP EVERY JOINT USING FA-1. - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED8-11 JNT / HR.
GZR-401 |  |  |  | 2023-05-22 12:00 | 2023-05-22 12:30 | 0:30 | [6 empty] | Non-Productive |  |  | - OBSERVE FA-1 SLIPS HYDRAUILC OIL QUICK CONNECTION -DISCONNECTED. - B/O JT # 51 TO LOWER THE FA-1 TO FIX THE HYDRAULIC CONNECTION. - REMAKE JT# 51.
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 18:15 | 5:45 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 582 M TO 1159 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - BREAK CIRCULATION AT 13 3/8" SHOE, 420 GPM, 500 PSI, WT UP 215 KIP, WT DN 205 KIP - AT 17:00 TBT AND CREW SHIFT HANDOVER - RUNNING SPEED10-11 JNT / HR
GZR-401 |  |  |  | 2023-05-22 18:15 | 2023-05-22 18:30 | 0:15 | [6 empty] | Non-Productive |  |  | - OBSERVE FA-1 SLIPS HYDRAUILC OIL QUICK CONNECTION -DISCONNECTED. - FIXED THE SAME
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-23 | 5:30 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1159 M TO 1800 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED11 JNT / HR Page 34 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 14:15 | 14:15 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1800 M TO 3483 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED10-11 JNT / HR NOTE: - REMADE JOINT-234 TOOK 4MIN. - REMADE JOINT-253 TOOK 3 MIN. - REMADE JOINT-261 TOOK 11 MIN.
GZR-401 |  |  |  | 2023-05-22 14:15 | 2023-05-22 14:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - OBSERVED STRING SLACKED OFF MORE THAN 40 KLBS. - ESTABLISHED CIRCULATION GRADUALLY AND STARTED WAHING DOWN TO 3490M. - FLOW RATE 70GPM-400 GPM, PRESSURE 660 PSI TO 1020 PSI. - SUDUNLY PRESSURE SHOOTS UP TO 1500 PSI AND FLOW OUT DISCONTINUED.
GZR-401 |  |  |  | 2023-05-22 14:30 | 2023-05-22 20:30 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - KEPT 1500 PSI BACK PRESSURE AND WORKED ON STRING UP/DN WITH GRADUAL OP INCREMENTS OF 50KLBS TO 300KLBS OVER PULL AND 300 KBLS S/L WEIGHT, NO SUCCESS. - APPLIED 14K FT.LBS TORQUE AND SLACKED OFF THE STRING WITH PRESSURE AND WITHOUT PRESSURE, NO SUCCESS.
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-23 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | WAITING ON WIRELINE CCL, CBL AND GAMMA RAY MEANWHILE : - KEPT 1500-1600 PSI BACK PRESSURE AND WORKED ON STRING UP/DN WITH GRADUAL OP INCREMENTS OF 50KLBS TO 300KLBS OVER PULL AND 300 KBLS S/L WEIGHT, NO SUCCESS. - APPLIED 14K FT.LBS TORQUE AND SLACKED OFF THE STRING WITH PRESSURE AND WITHOUT PRESSURE, NO SUCCESS. NOTES: - MONITOR WELL THROUGH TRIP TANK - LOSSES RATE ~ 2-3 BBLS/HRS Page 35 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 13:30 | 13:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | WAITING ON WIRELINE CCL, CBL AND GAMMA RAY MEANWHILE : - KEPT 1500-1600 PSI BACK PRESSURE AND WORKED ON STRING UP/DN WITH GRADUAL OP INCREMENTS OF 50KLBS TO 300KLBS OVER PULL AND 300 KBLS S/L WEIGHT, NO SUCCESS. - APPLIED 14K FT.LBS TORQUE AND SLACKED OFF THE STRING WITH PRESSURE AND WITHOUT PRESSURE, NO SUCCESS. - MONITOR WELL THROUGH TRIP TANK - LOSSES RATE ~ 2-3 BBLS/HRS
GZR-401 |  |  |  | 2023-05-22 13:30 | 2023-05-22 14:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM WITH ALL CREW PRIOR TO L/D FA-1 TOOL. - DISCUSSED ALL THE RISKS OF HAVING 2.5M 9 5/8' STICKUP AND THE MITIGATIONS TO HAVE A SAFE OPERATION.
GZR-401 |  |  |  | 2023-05-22 14:00 | 2023-05-22 17:30 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/D FRANKS FA-1 AND L/D SAME. - MONITOR WELL ON TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 17:30 | 2023-05-22 20:30 | 3:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - BAKER WIRELINE ARRIVED ON LOCATION AND STARTED PREPARING THEIR TOOLS AND EQUIPMENT. - MEANWHILE RIG CREW INSTALLED BAILS AND 5' DP ELEVATOR. NOTE: - AT 20:00 CREW SHIFT HANDOVER
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 23:00 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | PJSM PRIOR RU WIRELINE TOOLS RIG UP WIRELINE SHEAVES AND CABLE. PICK UP AND MAKE UP TOOL STRING FOR RUN #1: CENTRALIZER- VDL-SBT-CENTRLIZER- ELECTR- GR-CCL NOTE: - AT 21:00 WL CREW SHIFT HANDOVER. - PICK UP AND MAKE UP TOOLS IN MOUSE HOLE CENTRALIZER- VDL-SBT-CENTRLIZER. - PICK UP AND MAKE UP TOOLS IN GROUNDELECTR- GR-CCL - MONITOR WELL THROUGH TRIP TANK - LOSSES RATE ~ 0.8 BBLS/HRS
GZR-401 |  |  |  | 2023-05-22 23:00 | 2023-05-23 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - STARTED RIH AND LOG WITH RUN #1 - RUN TO 200 M, OPEN PADS AND START NORMALIZATION PASS. Page 36 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 05:00 | 5:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. RIH WITH RUN #1: CENTRALIZER- VDL-SBT-CENTRLIZER- ELECTR- GR-CCL TO 3430 M ~ 10 M ABOVE 9-5/8'' FLOAT COLLER. - START RECORD UP REPEAT PASS FROM 3430 M. - RECORD MAIN PASS FROM 3430 M. - POOH TO SURFACE - MONITOR WELL THROUGH TRIP TANK - LOSSES RATE ~ 0.8 BBLS/HRS
GZR-401 |  |  |  | 2023-05-22 05:00 | 2023-05-22 08:30 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/D BAKER WIRELINE TOOLS, CABLE AND SHEAVES.
GZR-401 |  |  |  | 2023-05-22 08:30 | 2023-05-22 22:00 | 13:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - WAIT ON FISHING EQUIPMENT. - MONITOR WELL THROUGH TRIP TANK, LOSSES RATE 0.8 BBLS/HR. MEANWHILE : - RIG DOWN 5'' ELEVATOR - RIG UP SIDE-DOOR ELEVATOR
GZR-401 |  |  |  | 2023-05-22 22:00 | 2023-05-22 22:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RECEIVED THE COLD CUTTER TOOLS ON SITE. - INSPECT AND MOVE TO RIG FLOOR.
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM WITH DRILLING CREW PRIOR 9-5/8'' COLD CUTTING AT RIG FLOOR
GZR-401 |  |  |  | 2023-05-22 23:00 | 2023-05-23 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - LATCH 9-5/8'' SIDE-DOOR ELEVATOR TO 9-5/8'' CASING AND KEEP IT IN TENSION. - RIG UP COLD CUTTER AND INSTALLED AROUND 9-5/8'' CASING IN RIG FLOOR AT 0.46 M FROM FMS. - START CUTTING OPERATION AS PER COLD CUTTER ENGINEER INSTRUCTION - TAKE ~ 15 MIN TO CUT 9-5/8'' CASING - RIG DOWN COLD CUTTER TOOLS. - RIG DOWN 9-5/8'' CUTTING PIECE (2.48M) - MONITOR WELL THROUGH TRIP TANK, LOSSES RATE 0.8 BBLS/HR.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 12:45 | 12:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - WAIT ON FISHING EQUIPMENT. MEANWHILE: - INSTALL RIG SAVER SUB - INSTALL 5'' ELEVATOR. - MONITOR WELL THROUGH TRIP TANK, LOSSES RATE 0.8 BBLS/HR.
GZR-401 |  |  |  | 2023-05-22 12:45 | 2023-05-22 13:30 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - FISHING EQUIPMENT ARRIVED ON LOCATION. - OFF LOADED, CHECKED AND MEASURED THE SAME.
GZR-401 |  |  |  | 2023-05-22 13:30 | 2023-05-22 14:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM WITH ALL CREW PRIOR R/U TO CUT THE CASING. - DISCUSSED THE JOB SEQUENCE AND HIGHLIGHTED THE RISKS AND MITIGATIONS.
GZR-401 |  |  |  | 2023-05-22 14:00 | 2023-05-22 14:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/U 8 3/8" TAPER MILL , 8 1/4" CUTTER AND TWO SINGLES OF 5" DP. - FUNCTION TEST THE CASING CUTTER WITH 100 GPM TO OPEN THE BLADES. Page 37 of 120
GZR-401 |  |  |  | 2023-05-22 14:45 | 2023-05-22 15:30 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH WITH CUTTER ASSY. TO 22M AND CUT 9 5/8" CASING WITH 60 RPM, 110 GPM, AND 1500 PSI PRESSURE. - TOOK 5MIN FOR THE ACTUAL CUT TO BE DONE.
GZR-401 |  |  |  | 2023-05-22 15:30 | 2023-05-22 16:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POH WITH CUTTER ASSY. TO SURFACE. - CHECKED THE CUTTER ASSY. AND L/D SAME.
GZR-401 |  |  |  | 2023-05-22 16:00 | 2023-05-22 18:15 | 2:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - P/U 8 1/4" ITCO SPEAR WITH ONE SINGLE OF 5" DP AND ENGAGED THE SAME TO THE CUT CASING. - PULL THE FIRST JOINT OF CUT CASING THE TO THE COLLAR CONNECTION BELOW. - DISCONNECT THE FIRST CUT JOINT (WITHOUT COLLAR FROM THE LOWER CUT JOINT), USING POWER TONG AND BACKUP TONG. - L/D THE FIRST CUT JOINT USING PIPE CAT. - CHANGED OUT DP ELEVATOR WITH CASING SIDE DOOR ELEVATOR AND CONNECT TO THE LOWER CUT JOINT. - L/D THE LOWER CUT JOINT USING PIPE CAT.
GZR-401 |  |  |  | 2023-05-22 18:15 | 2023-05-22 19:15 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - L/D FRANKS FMS. - INSTALL RIG MASTER BUSHING.
GZR-401 |  |  |  | 2023-05-22 19:15 | 2023-05-22 19:45 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | RELEASE THE SPEAR FROM THE UPPER PART OF THE CUT 9-5/8'' CASING AT GROUND
GZR-401 |  |  |  | 2023-05-22 19:45 | 2023-05-22 20:15 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CREW SHIFT HANDOVER - PJSM WITH ALL CREW PRIOR R/U TO CUT THE CASING. - DISCUSSED THE JOB SEQUENCE AND HIGHLIGHTED THE RISKS AND MITIGATIONS.
GZR-401 |  |  |  | 2023-05-22 20:15 | 2023-05-22 20:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/U 8 3/8" TAPER MILL , 8 1/4" CUTTER AND TWO SINGLES OF 5" DP.
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 21:15 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH WITH CUTTER ASSY. TO 111 M AND CUT 9 5/8" CASING WITH 60 RPM, TRQ 4-5.3 KFT.LB,110-170 GPM, AND 2000-2300 PSI PRESSURE. - TOOK 5MIN FOR THE ACTUAL CUT TO BE DONE.
GZR-401 |  |  |  | 2023-05-22 21:15 | 2023-05-22 22:00 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POH WITH CUTTER ASSY. TO SURFACE. - CHECKED THE CUTTER ASSY. AND L/D SAME. Page 38 of 120
GZR-401 |  |  |  | 2023-05-22 22:00 | 2023-05-23 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - P/U 8 1/4" ITCO SPEAR WITH ONE SINGLE OF 5" DP AND ENGAGED THE SAME TO THE CUT CASING AT ~22 M - PULL THE FIRST JOINT OF CUT CASING THE TO THE COLLAR CONNECTION BELOW. - DISCONNECT THE FIRST CUT JOINT (WITHOUT COLLAR FROM THE LOWER CUT JOINT), USING POWER TONG AND BACKUP TONG. - L/D THE FIRST CUT JOINT USING PIPE CAT. - CHANGED OUT DP ELEVATOR WITH CASING SIDE DOOR ELEVATOR AND CONNECT TO THE LOWER CUT JOINT. - CONT. POOH & L/D1 X CUT 9-5/8'' CASING
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:15 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. POOH & L/D6 X CUT 9-5/8'' CASING - RIG DOWN 9-5/8'' CASING SIDE DOOR ELEVATOR
GZR-401 |  | RIG |  | 2023-05-22 01:15 | 2023-05-22 02:15 | 1:00 | [6 empty] | Productive |  |  | - INSTALL 5''ELEVATOR. - MAKE UP CAMERON JETTING TOOL - JET WASH BOP
GZR-401 |  | RIG |  | 2023-05-22 02:15 | 2023-05-22 03:15 | 1:00 | [6 empty] | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY
GZR-401 |  | RIG |  | 2023-05-22 03:15 | 2023-05-22 08:45 | 5:30 | [6 empty] | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD . - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), LOW 250-350 PSI-LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK.
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 09:15 | 0:30 | [6 empty] | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
GZR-401 |  | RIG |  | 2023-05-22 09:15 | 2023-05-22 10:00 | 0:45 | [6 empty] | Productive |  |  | - SERVICE TDS - CHANGE IRONROUGHNECK DIES. Page 39 of 120
GZR-401 |  |  |  | 2023-05-22 10:00 | 2023-05-22 11:15 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/U 8 3/8" TAPER MILL , 8 1/4" CUTTER AND 1 5'' DP STAND - FUNCTION TEST THE CASING CUTTER WITH 100 GPM TO OPEN THE BLADES. - INSTALL AIR SLIPS - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 11:15 | 2023-05-22 13:15 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH WITH CUTTER ASSY TO 527 M - OBERVED THE WEARBUSHING NOT INSTALLED - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 13:15 | 2023-05-22 14:30 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH 8 3/8" TAPER MILL , 8 1/4" CUTTER TO SURFACE AND LAYDOWN THE SAME
GZR-401 |  |  |  | 2023-05-22 14:30 | 2023-05-22 15:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - INSTALL WEAR BUSHING.
GZR-401 |  |  |  | 2023-05-22 15:00 | 2023-05-22 16:15 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/U 8 3/8" TAPER MILL , 8 1/4" CUTTER AND RIH TO 468 M. - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 16:15 | 2023-05-22 16:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FLOW CHECK AS TRIP SHEET SHOWN INCREASE IN TRIP TANK ~ 2 BBLS - WELL STATIC
GZR-401 |  |  |  | 2023-05-22 16:30 | 2023-05-23 | 7:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. RIH WITH 8 3/8" TAPER MILL , 8 1/4" CUTTER FROM 468 M TO 2623 M. - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. RIH WITH 8 3/8" TAPER MILL , 8 1/4" CUTTER FROM 2623 M TO 3035 M. - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 01:30 | 2023-05-22 02:15 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CUT 9 5/8" CASING WITH 60 RPM, TRQ 4-13 KFT.LB, FLOW RATE 130-200 GPM, SPP 2000-2500 PSI PRESSURE. - TOOK 20 MIN FOR THE ACTUAL CUT TO BE DONE.
GZR-401 |  |  |  | 2023-05-22 02:15 | 2023-05-22 06:00 | 3:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - OBSERVED PIPE INSTALL WHEN THE TORQUE REACH 13 KFT.LB. - TRY TO POH WITH CUTTER ASSY, OBSERVED OVERPULL MORE THAN 50 KLBS - WORKED ON STRING UP/DN WITH GRADUAL OP INCREMENTS OF 50KLBS TO 450 KLBS OVER PULL AND 240 KBLS S/L WEIGHT, NO SUCCESS. - APPLIED 12 K FT.LBS TORQUE AND SLACKED OFF TO 220, NO SUCCESS. Page 40 of 120
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 08:30 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - AFTER SEVERAL ATTEMPTS, MANAGED TO GET FREE ROTATION WITH 50 RPM AND 5-7 KFT.IBF TORQUE. - ATTEMPTED TO P/UP WITHOUT PUMPING, NO SUCCESS. OBSERVE OVERPULL. - P/UP GRADUALLY IN STAGES TO 450 KLBS (200 KLBS OVERPULL), NO SUCCESS - DISCUSS THE ISSUE WITH BP OFFICE AND GULF ENERGY - AGREED TO KEEP WORKING STRING UP/DOWN WITH MAXIMUM WEIGHT
GZR-401 |  |  |  | 2023-05-22 08:30 | 2023-05-22 10:00 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - WORK STRING UP/DOWN BY SLACKING WITH 100 KLBS DOWN AND PULLING MAXIMUM OVERPULL TO 230 KLBS (TOTAL WEIGHT IN MD = 480 KLBS) - CIRCULATE STRING EVERY 15-20 MINUTES OF THE STRING WORKOUT - AFTER SEVERAL ATTEMPTS, MANAGED TO FREE STRING AND RETRACT CUTTERS WITH 230 KLBS OVERPULL. - CONFIRM P/UP WT. = 260 KLBS
GZR-401 |  |  |  | 2023-05-22 10:00 | 2023-05-22 21:30 | 11:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH WITH 8 3/8" TAPER MILL , 8 1/4" CUTTER FROM 3035M TO SURFACE. - AT THE SURFACE OBSERVED THE PISTON NOT BACK TO THE ORIGINAL POSITION AND ALL 3 KNIFE WERE IN STUCK IN OPEN POSITION BY 1'' FROM CUTTER BODY. - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 21:30 | 2023-05-22 21:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CLEAN CLEAR RIG FLOOR
GZR-401 |  |  |  | 2023-05-22 21:45 | 2023-05-22 22:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PU, MU WEAR BUSHING RETRIEVE TOOL. - RETRIEVED WEAR BUSHING
GZR-401 |  |  |  | 2023-05-22 22:00 | 2023-05-23 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | P/U. M/U AND RUN SPEAR BHA TO 15 M AS BELOW: - TBT, PJSM - 8 ¼™™ OD ITCO SPEAR (DRESSED WITH 8.597™™ GRAPPLE) - SPEAR STOP SUB C/W 10 ¾™™ OD STOP RING - X/O 6 5/8™™ R PIN X 4 ½™™ IF B - 6 ¼™™OD SAFETY JOINT - 6 ½™™OD CIRCULATING SUB - 6 ¾™™OD FISHING AGITATOR - 6 ¾™™OD SHOCK TOOL - 6 1/4™™ OD FISHING JAR NOTE: FUNCTION TEST AGITATOR AS PER FISHING ENG INSTRUCTION WITH 100 GPM. - MONITORED WELL ON TRIP TANK WITH TRIP SHEET Page 41 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 00:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. RUN SPEAR BHA WITH 5™™HWDP TO 111 M AND ENGAGE THE SPEAR WITH 9-5/8'' CASING NOTE: - UP WEIGHT = 65 KLBS - DOWN WEIGHT = 70 KLBS - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 00:45 | 2023-05-22 03:00 | 2:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - ENGAGE 9.5/8" CASING WITH SPEAR ASSEMBLY. - P/UP AND ATTEMPT TO PULL CASING WITH THE SPEAR WITH 20 KLBS OVER PULL INCREAMENT REACHING TO MAXIMUM OVER PULL AT 100 KLBS (TOTAL STRING WT. IN MD = 600 KLBS), NO SUCCESS. - KICK ON MUD PUMP'S TO ACTIVATE THE AGITATOR WITH GRADUAL FLOW RATE INCREMENTS FROM 50 TO 300 GPM, SPP 300 PSI, APLLY 50 KLBS OVER PULL FOR~ 45 MINS. - WORK ON STRING UP/DN WITH BY APPLYING MAXIMUM OVER PULL OF 100 KLBS AND 80 KBLS S/L WEIGHT, NO SUCCESS. - ATTEMPTED TOP JAR UP. MADE SEVERAL ATTEMPTS TO JAR UP, ONLY AFTER THE 7TH ATTEMPT, MANAGED TO JAR UP AND FREE THE CASING. - PULL CASING UP AND CONFIRM STRING WT. = 485 KLBS.
GZR-401 |  |  |  | 2023-05-22 03:00 | 2023-05-22 07:00 | 4:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | SLOWLY POOH SPEAR FISHING BHA FROM 111 M TO SURFACE - RACK BACK 4 X 5'' HWDP - RIG UP SINGLE OF 5'' HWDP AND CONNECTED TO FISHING JAR - POOH SPEAR BHA WITH THE FISH TO THE SURFACE. - INSTALL BUSHING AND SET THE 9-5/8'' CASING ON SLIPS AND USED SAFETY CLAMP. - DISCONNECT THE SPEAR FROM THE FISH. - B/O AND L/D1 X CUT 9-5/8'' CASING. NOTE: - POOH SLICK WITH NO INDICATION OF LOSSES - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  |  |  | 2023-05-22 07:00 | 2023-05-22 09:00 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - REMOVE SAVER SUB - REMOVE RIG ELEVATOR AND BAILES NOTE: - CREW CHANGE HANDOVER. - PJSM WITH ALL CREW PRIOR R/U FRANKS EQUIPMENT. Page 42 of 120
GZR-401 |  |  |  | 2023-05-22 09:00 | 2023-05-22 12:00 | 3:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIG UP FA-1. - PICK UP AND RIG UP CRT. - R/UP POWER TONG - CONDUCT DROP INSPECTION AND POST JARRING INSPECTION. - R/UP HYDRAULIC ELEVATOR - MU SAFETY VALVE WITH 9.5/8" WATER BUSHING. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 12:00 | 2023-05-22 13:00 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - REMOVE MASTER BUSHINGS. - INSTALLED FMS. - VERIFIED INTERLOCKING SYSTEM IS WORKING PROPERLY FOR CRT AND FMS.
GZR-401 |  |  |  | 2023-05-22 13:00 | 2023-05-22 13:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM WITH ALL CREW PRIOR TO LAY DOWN 9 5/8" CASING.
GZR-401 |  |  |  | 2023-05-22 13:30 | 2023-05-23 | 10:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PULL OUT AND LAY DOWN 9.5/8" CASING FROM 2918M TO 2112 M - AVG. LAY DOWN SPEED = 5-7 JOINTS/HR - L/D USING FA-1 AND POWER TONG - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 09:30 | 9:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. PULL OUT AND LAY DOWN 9.5/8" CASING TO 1338 M - AVG. LAY DOWN SPEED = 7-8 JNTS/HR - L/D USING FA-1 AND POWER TONG - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 09:30 | 2023-05-22 11:00 | 1:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | WORK ON REPLACING DAMAGED PIN IN THE BELT TONG THAT SUPPORT LIFTING ARM FOR THE BELT TONG.
GZR-401 |  |  |  | 2023-05-22 11:00 | 2023-05-22 20:00 | 9:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. PULL OUT AND LAY DOWN 9.5/8" CASING FROM 1338 M TO 609 M - AVG. LAY DOWN SPEED = 7-8 JNTS/HR - L/D USING FA-1 AND POWER TONG - MONITOR WELL THROUGH TRIP TANK - CONDUCT SAFETY STANDDOWN WITH CREW FOR RED ZONE MANAGMENT ENHANCEMENT
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 23:30 | 3:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. PULL OUT AND LAY DOWN 9.5/8" CASING FROM 609 M TO 417 M - AVG. LAY DOWN SPEED = 7-8 JNTS/HR - OBSERVE OVER TORQUE IN SOME OF THE JOINTS - L/D USING FA-1 AND POWER TONG - MONITOR WELL THROUGH TRIP TANK OFFLINE: - MIXING 75 BBLS OF SPACER
GZR-401 |  |  |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | TROUBLESHOOTING PIPE CAT Page 43 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 05:30 | 5:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. PULL OUT AND LAY DOWN 9.5/8" CASING FROM 417 M TO SURFACE - AVG. LAY DOWN SPEED = 6 JNTS/HR - OBSERVE OVER TORQUE IN SOME OF THE JOINTS - L/D USING FA-1 AND POWER TONG - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 05:30 | 2023-05-22 09:00 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIG DOWN FRANKS EQUIPMENT - R/DN FA-1. - R/DN POWER TONG, HYDRAULIC ELEVATOR, BELT TONGS AND FMS - R/DN SERVICE LOOP - DISCONNECT SAFETY VALVE FROM 9.5/8" WATER BUSHING. OFFLINE: - RIG UP MWD UNIT AND EQUIPMENT
GZR-401 |  |  |  | 2023-05-22 09:00 | 2023-05-22 10:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - R/UP SAFER SUB, 5" ELEVATOR AND BAILS
GZR-401 |  |  |  | 2023-05-22 10:30 | 2023-05-22 11:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - MAKE UP CAMERON JETTING TOOL - JET WASH WELLHEAD ANDBOP WITH 335-500 GPM
GZR-401 |  |  |  | 2023-05-22 11:00 | 2023-05-22 11:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - INSTALL WEAR BUSHING
GZR-401 |  |  |  | 2023-05-22 11:30 | 2023-05-22 12:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM - CLEAN AND CLEAR RIG FLOOR - R/UP 3.5" HANDLING EQUIPMENT
GZR-401 |  |  |  | 2023-05-22 12:00 | 2023-05-22 15:00 | 3:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - P/UP AND RIH 3.5" SINGLES FROM GROUND TO 382 M - PERFORM D1 DRILL WITH CREW - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 15:00 | 2023-05-22 17:30 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CHANGE OUT TO 5" HANDLING EQUIPMENT - CONTINUE RIH WITH 5" DP STANDS FROM DERRICK TO 1440 M OFFLINE: START PREPARING BARITE FOR VISCUS PILL
GZR-401 |  |  |  | 2023-05-22 17:30 | 2023-05-22 18:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE BOTTOMS UP WITH 500 GPM, 40 RPM, 1170 PSI - MEANWHILE, PREPARE AND MIX VISCOUS REACTIVE PILL WEIGHT TO 1.42 SG AS PER PROGRAM - MIXED THE FOLLOWING AS PER PROGRAM: * BENTONITE TO 2280 IBS * BARITE TO 14601.83 IBS - UNABLE TO GET MORE THAN 1.40 SG OF THEVISCOUS REACTIVE PILL Page 44 of 120
GZR-401 |  |  |  | 2023-05-22 18:45 | 2023-05-22 22:15 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE ATTEMPTING TO RAISE THE WEIGHT OF THE PILL BY ADDING BARITE TO 15601.83 IBS - STILL UNABLE TO GET MORE THAN 1.40 SG FOR THE PILL - HALLIBURTON CREW DISCUSSED THE ISSUE WITH TOWN - ENGINEERS IN TOWN PERFORM LAB TEST WITH 1.40 SG VISCOUS REACTIVE PILL - AT 21:30 RE-CHECK THE VISCOUS REACTIVE PILL WEIGHT GET 1.41 SG. - AGREE WITH TEAM TO GO AHEAD WITH 1.41 SG VISCOUS REACTIVE PILL
GZR-401 |  |  |  | 2023-05-22 22:15 | 2023-05-22 23:15 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE MIXING VISCOUS REACTIVE PILL BY ADDING 475 GAL OF ECONOLITE. - CHECK THE RHEOLOGY OF VISCOUS REACTIVE PILL AS FOLLOW: -
GZR-401 |  |  |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | PJSM, TBT BEFORE PUMP VISCOUS REACTIVE PILL AND CEMENT PLUG
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMPING 67 BBLS OF VISCOUS REACTIVE PILL @ 150-250 GPM, SPP 150-400 PSI , 40 RPM - DISPLACE VISCOUS REACTIVE PILL BY 59.74 BBLS + 3 BBLS SURFACE LINE = TOTAL 63 BBLS
GZR-401 |  |  |  | 2023-05-22 00:30 | 2023-05-22 01:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH @ 8M/MIN OF 3.5'' CEMENT STINGER TO 1340 M WITH
GZR-401 |  |  |  | 2023-05-22 01:00 | 2023-05-22 02:15 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE 2 BOTTOM UP @ 620 GPM, SPP 1560 PSI . - NO INDICATION OF VISCOUS REACTIVE PILL AT SURFACE.
GZR-401 |  |  |  | 2023-05-22 02:15 | 2023-05-22 03:00 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | DISCUSS WITH THE TEAM FURTHER PLAN - AGREE TO MIX ANOTHER VISCOUS REACTIVE PILL - MEANWHILE TO RUN 20 M DEEPER AND CIRCUALTE B/U TO CHECK THE TOP OF VISCOUS REACTIVE PILL
GZR-401 |  |  |  | 2023-05-22 03:00 | 2023-05-22 03:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH TO 1360 M AND CIRCULATED BOTTOM UP @ 620 GPM, SPP 1580 PSI, 40 RPM - STILL NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. MEANWHILE: - CONTINUE MIXING ANOTHER VISCOUS REACTIVE PILL
GZR-401 |  |  |  | 2023-05-22 03:45 | 2023-05-22 04:45 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH TO 1382 M AND CIRCULATED BOTTOM UP @ 620 GPM, SPP 1580 PSI, 40 RPM - STILL NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. MEANWHILE: - CONTINUE MIXING ANOTHER VISCOUS REACTIVE PILL Page 45 of 120
GZR-401 |  |  |  | 2023-05-22 04:45 | 2023-05-22 06:00 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH TO 1400 M AND CIRCULATED BOTTOM UP @ 620 GPM, SPP 1580 PSI, 40 RPM - STILL NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. MEANWHILE: - CONTINUE MIXING ANOTHER VISCOUS REACTIVE PILL
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 07:00 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH TO 1420 M AND CIRCULATED BOTTOM UP @ 620 GPM, SPP 1640 PSI, 40 RPM - STILL NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. MEANWHILE: - CONTINUE MIXING ANOTHER VISCOUS REACTIVE PILL
GZR-401 |  |  |  | 2023-05-22 07:00 | 2023-05-22 09:00 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH TO 1440 M AND CIRCULATED BOTTOM UP @ 620 GPM, SPP 1640 PSI, 40 RPM - STILL NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. MEANWHILE: - CONTINUE MIXING ANOTHER VISCOUS REACTIVE PILL - START ADDING ECONOLITE TO THE VISCUS REACTIVE PILL AT 07:40 - CHECK RHEOLOGY OF THE PILL
GZR-401 |  |  |  | 2023-05-22 09:00 | 2023-05-22 09:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMP AND SPOT 67 BBLS OF VISCOUS REACTIVE PILL @ 150-250 GPM, SPP 150-400 PSI , 40 RPM - DISPLACE THE PILL WITH 59.74 BBLS + 3 BBLS SURFACE LINE = TOTAL 63 BBLS (DISPLACEMENT VOLUME INCLUDES 4.98 BBLS UNDER-DISPLACEMENT)
GZR-401 |  |  |  | 2023-05-22 09:45 | 2023-05-22 10:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH WITH OF 3.5'' CEMENT STINGER TO 1340 M@ 8M/MIN
GZR-401 |  |  |  | 2023-05-22 10:00 | 2023-05-22 12:30 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CIRCULATE 2 BOTTOM UP WITH 500 GPM, SPP 1170 PSI , 40 RPM. - NO SIGN OF VISCOUS REACTIVE PILL AT SURFACE. - DISCUSS THE ISSUE AND WAY FORWARD WITH OFFICE TEAM - DECIDED TO MIX A THIRD LIGHTER VISCUS PILL (1.32 SG) Page 46 of 120
GZR-401 |  |  |  | 2023-05-22 12:30 | 2023-05-22 18:30 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PREPARE MIXING TANK AND ARRANGE CHEMICALS - MIX 67 BBLS OF 1.32 SG VISCOUS REACTIVE PILL. MEANWHILE: - RIH TO 1440 M - CIRCULATE B/U AND CHECK FOR ANY INDICATION OF THE 2NDVISCOUS REACTIVE PILL, NO SIGN OF THE PILL AT SURFACE. - PERFORM DROP SURVEY IN AREAS 1 & 2 - START ADDING ECONOLITE TO THE VISCUS REACTIVE PILL AT 17:30 - CHECK RHEOLOGY OF THE PILL
GZR-401 |  |  |  | 2023-05-22 18:30 | 2023-05-22 19:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMP AND SPOT 67 BBLS OF VISCOUS REACTIVE PILL @ 150-250 GPM, SPP 150-400 PSI , 40 RPM - DISPLACE THE PILL WITH 59.74 BBLS + 3 BBLS SURFACE LINE = TOTAL 63 BBLS (DISPLACEMENT VOLUME INCLUDES 4.98 BBLS UNDER-DISPLACEMENT)
GZR-401 |  |  |  | 2023-05-22 19:00 | 2023-05-22 19:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH WITH OF 3.5'' CEMENT STINGER TO 1340 M@ 8M/MIN
GZR-401 |  |  |  | 2023-05-22 19:30 | 2023-05-22 21:30 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE 2 BOTTOM UP @ 500 GPM, SPP 1170 PSI . - OBSERVED VISCOUS REACTIVE PILL AT SURFACE AFTER 5900 STROKES. - DUMP ALL EXCESS VISCIUS PILL TO WASTE PIT. MEANWHILE: - CONDUCTED TBT PRIOR CEMENT JOB - PREFORMED SURFACE LINE PT LOW: 300 PSI , HIGH 4000 PSI. GOOD TEST
GZR-401 |  |  |  | 2023-05-22 21:30 | 2023-05-22 22:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | STARTED MIXING 105 BBL OF 2.04 SG CEMENT SLURRY IN BATCH MIXER MEANWHILE: - PULL TO 1330 M AND R\B ONE STAND OF 5" DP - R\UP AND CONNECT CEMENT LINE TO STRING THOUGH SES. - MONITOR WELL THROUGH TRIP TANK Page 47 of 120
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - SWITCH PUMPING LINE TO CEMENT UNIT. - CEMENT UNIT PUMPED 70 BBL OF 1.4 SG TUNED SPACER AHEAD AT 6 BPM. - CEMENT UNIT PUMPED 105 BBL OF 2.04 SG CEMENT SLURRY FROM BATCH MIXER AT 5-6 BPM. - CEMENT UNIT PUMPED 3.5 BBL OF 1.4 SG TUNED SPACER AHEAD AT 6 BPM. - CEMENT DISPLACEMENT (INCLUDING 7.87 BBLS UNDER DISPLACEMENT): * DISPLACED 35 BBL OF 1.3 SG MUD WITH 7-8 BPM * DISPLACED 10 BBL OF 1.3 SG MUD WITH 2-3 BPM - SHUT-IN CEMENT PUMP NO RETURNS OBSERVED IN CEMENT UNIT. NOTE: - CEMENT IN PLACE AT 23:30 PM. - NO LOSSES DURING CMT JOB.
GZR-401 |  |  |  | 2023-05-22 23:30 | 2023-05-22 23:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | R\D CEMENT LINE
GZR-401 |  |  |  | 2023-05-22 23:45 | 2023-05-23 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH WITH OF 3.5'' CEMENT STINGER FROM 1330 M TO 1220 M@ 9-10M/MIN - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. POOH WITH OF 3.5'' CEMENT STINGER FROM 1220 M TO 1060 M ( 100 M ABOVE THEORETICAL TOC)@ 9-10 M\MIN - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 00:30 | 2023-05-22 01:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | DROP FOAM BALL AND CIRCULATE 2X BOTTOM-UP WITH 600 GPM , SPP: 1560-1470PSI AND 40 RPM. - DUMP TOTAL OF 100 BBL AS BELOW: * 40 BBL OF CONTAMINATED MUD WITH SPACER. * 60 BBL OF CONTAMINATED MUD & SPACER AND TRACES OF CEMENT.
GZR-401 |  |  |  | 2023-05-22 01:45 | 2023-05-22 03:00 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. POOH WITH OF 3.5'' CEMENT STINGER FROM 1060 M TO 400 M - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 03:00 | 2023-05-22 05:45 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | SLIP & CUT DRILL LINE - HANG TRAVELING BLOCK - CUT 24 M AND SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. - CALIBRATED MUD LOGGERS BLOCK HEIGHT. - R\B 1X STAND OF 5" DP
GZR-401 |  |  |  | 2023-05-22 05:45 | 2023-05-22 08:30 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH AND L\D3.5'' DP CEMENT STINGER FROM 380 M TO SURFACE. - AT 05:50 REMOVE 5" DP ELEVATOR AND INSTALL 3.5" DP ELEVATOR - R/DN 3.5" HANDLING EQUIPMENT - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 08:30 | 2023-05-22 09:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CLEAR AND CLEAN RIG FLOOR - JET BOP, KILL LINE AND CHOKE LINE Page 48 of 120
GZR-401 |  |  |  | 2023-05-22 09:00 | 2023-05-22 09:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM PRIOR P/U, M/U AND RIH 12-1/4" BHA. - MWD R/UP TOOLFACE SCREEN TO THE RIG FLOOR.
GZR-401 |  |  |  | 2023-05-22 09:30 | 2023-05-22 20:00 | 10:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | P/U, M/U AND RIH 12-1/4"BHA TO454 M AS FOLLOW: - TRICON BIT W/ NOZZELS 2X20 & 2X18, SN#: RP8201 - 9.5/8" GEOFORCE LOBE 6/7 - 3.5 STG MOTOR (WITH 1.83DEG) - W/ FLOAT VALVE - 11.3/4" STRING STABILIZER - 8" HOC - 8" DOWNHILE SCREEN - 8" PBL SUB - 12 X 8.1/4" DC - SINGLING IN FROM PIPE CAT - 8" JAR - 3X8.1/4" DC - SINGLING IN FROM PIPE CAT - X/OVER SUB - 30 X 5" HWDP - 15 JOINTS FROM PIPE CAT + 5 STANDS FROM MAST - USED MANUAL TONGS TO MU MWD AND MOTOR TOOLS. - SHALLOW TEST THE MWD TOOL AT 138 M WITH FR 650 GPM; SPP 1000 PSI. - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 20:00 | 2023-05-22 21:00 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | P\UP AND RIH WITH 3 STANDS OF 5" G3 25.6# DP ( STANDS WITH WASH-OUT) AND L\D THE SAME.
GZR-401 |  |  |  | 2023-05-22 21:00 | 2023-05-22 21:15 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FUNCTION TEST BOP FORM RIG FLOOR PANEL.
GZR-401 |  |  |  | 2023-05-22 21:15 | 2023-05-22 22:30 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. RIH WITH STANDS OF 5" G2 19.5# DP FROM 454 M TO 1040 M. - MONITOR WELL THROUGH TRIP TANK
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | WAITING ON CEMENT
GZR-401 |  |  |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | COMMENCED WASH DOWN WITH 12.25" GEOFORCE BHA FROM 1040 M TO 1087 M. - FR: 700 GPM, SPP: 2050
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 02:00 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. WASH DOWN WITH 12.25" GEOFORCE BHA FROM 1087 M TO 1167 M. - FR: 670-700 GPM, SPP: 2090-1850 - TAGGED CEMENT TWICE AT 1167.6 M WITH 8-10 KLBS. NOTE: - ADJUST TOOL FACE AT 180 DEG - WHILE WASHING DOWN FROM 1087 TO 1167 M OBSERVED CONTAMINATED CEMENT WITH MUD AT SHAKRES. Page 49 of 120
GZR-401 |  |  |  | 2023-05-22 02:00 | 2023-05-22 03:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - P\UP OFF BOTTOM TO 1145 M - DISPLACED MUD IN THE WELL FROM 1.30 SG TO 1.25 SG. - MW IN / MW OUT = 1.25 SG MEANTIME: - DD UPDATED SIDE TRACK PROGRAM AS PER ACTUAL KOP: 1167.65 M.
GZR-401 |  |  |  | 2023-05-22 03:30 | 2023-05-22 03:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FLOW CHECK WELL, STATIC.
GZR-401 |  |  |  | 2023-05-22 03:45 | 2023-05-22 04:15 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RECORDED FLOW BACK AS BELOW : FR 700 GPM , EX-LOG : 35 BBL , RIG FLOOR :36 BBL FR 850 GPM , EX-LOG : 51 BBL , RIG FLOOR :50 BBL - TOOK SCR WITH MP # 1&2
GZR-401 |  |  |  | 2023-05-22 04:15 | 2023-05-22 04:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - WASH DOWN FROM 1145 M TO 1167 M. - ADJUST TOOL FACE AT 180 DEG Page 50 of 120
GZR-401 |  |  |  | 2023-05-22 04:30 | 2023-05-22 17:00 | 12:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - COMMENCED TIME DRILLING FROM 1167.65 M TO 1171.31 M ( 1" PER 5 MIN ) FR: 700 GPM, SPP: 1750-1820 PSI, DIFF PRESSURE: 15-70 PSI - KICK OFF POINT AT 1167M. - OBSERVE HARD CEMENT ON SURFACE. NOTE: - TOOK CUTTING SAMPLE AT 05:30 @1167.5M. ( 90% CEMENT & 10% FORMATION ). - TOOK CUTTING SAMPLE AT 06:20 @1168.0M. ( 70% CEMENT & 30% FORMATION ). - TOOK CUTTING SAMPLE AT 07:30 @1168.5M. ( 70% CEMENT & 30% FORMATION ). - TOOK CUTTING SAMPLE AT 08:00 @1168.8M. ( 60% CEMENT & 40% FORMATION ). - TOOK CUTTING SAMPLE AT 08:45 @1169.0M. ( 50% CEMENT & 50% FORMATION ). - TOOK CUTTING SAMPLE AT 09:30 @1169.2M. ( 50% CEMENT & 50% FORMATION ). - TOOK CUTTING SAMPLE AT 10:15 @1169.3M. ( 50% CEMENT & 50% FORMATION ). - TOOK CUTTING SAMPLE AT 11:00 @1169.75M. ( 60% CEMENT & 40% FORMATION ). - TOOK CUTTING SAMPLE AT 11:45 @1169.9M. ( 70% CEMENT & 30% FORMATION ). - TOOK CUTTING SAMPLE AT 13:15 @1170.0M. ( 50% CEMENT & 50% FORMATION ). - TOOK CUTTING SAMPLE AT 14:00 @1170.25M. ( 40% CEMENT & 60% FORMATION ). - TOOK CUTTING SAMPLE AT 14:45 @1170.5M. ( 40% CEMENT & 60% FORMATION ). - TOOK CUTTING SAMPLE AT 15:15 @1170.7M. ( 40% CEMENT & 60% FORMATION ). - TOOK CUTTING SAMPLE AT 16:00 @1170.9M. ( 40% CEMENT & 60% FORMATION ). Page 51 of 120
GZR-401 |  |  |  | 2023-05-22 17:00 | 2023-05-22 21:45 | 4:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE TIME DRILLING FROM 1171.31 M TO 1173.6 M ( 1" PER 3 MIN ) FR: 700 GPM, SPP: 1790-1820 PSI, DIFF PRESSURE: 50-100 PSI NOTE: - TOOK CUTTING SAMPLE AT 16:45 @1171.15 M. ( 40 % FORMATION ). - TOOK CUTTING SAMPLE AT 17:30 @1171.45 M. ( 50 % FORMATION ). - TOOK CUTTING SAMPLE AT 18:30 @1171.8 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 19:15 @1172.17 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 20:00 @1172.55 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 20:45 @1172.94 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 21:30 @1173.3 M. ( 40 % FORMATION ). - TOOK CUTTING SAMPLE AT 22:15 @1173.6 M. ( 40 % FORMATION ).
GZR-401 |  |  |  | 2023-05-22 21:45 | 2023-05-23 | 2:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE TIME DRILLING FROM 1173.6 M TO 1174.27 M ( 1" PER 5 MIN ) FR: 700 GPM, SPP: 1790-1800PSI, DIFF PRESSURE: 50-125 PSI NOTE: - TOOK CUTTING SAMPLE AT 23:00 @1173.83 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 23:45 @1174.13 M. ( 60 % FORMATION ). Page 52 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 13:30 | 13:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE TIME DRILLING FROM 1173.6 M TO 1175.98 M ( 1" PER 5-4 MIN ) FR: 700 GPM, SPP: 1720-1860 PSI, DIFF PRESSURE: 20-95 PSI - PUMP 25 BBLS HI VIS @ 1177.27M. NOTE: - TOOK CUTTING SAMPLE AT 00:30 @1174.27 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 01:15 @1174.49 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 02:00 @1174.73 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 02:45 @1174.97 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 03:30 @1175.01 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 04:15 @1175.31 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 05:00 @1175.56 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 05:45 @1175.78 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 06:30 @1176.0 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 07:15 @1176.22 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 08:00 @1176.5 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 08:45 @1176.65 M. ( 60 % FORMATION ). - TOOK CUTTING SAMPLE AT 09:30 @1176.88 M. ( 50 % FORMATION ). - TOOK CUTTING SAMPLE AT 10:15 @1177.11 M. ( 50 % FORMATION ). - TOOK CUTTING SAMPLE AT 11:15 @1177.40 M. ( 50 % FORMATION ). - TOOK CUTTING SAMPLE AT 12:00 @1177.74 M. ( 70 % FORMATION ). - TOOK CUTTING SAMPLE AT 12:45 @1177.74 M. ( 80 % FORMATION ). - TOOK CUTTING SAMPLE AT 13:30 @1178.3 M. ( 80 % FORMATION ).
GZR-401 |  |  |  | 2023-05-22 13:30 | 2023-05-22 14:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE TIME DRILLING FROM 1178.3 M TO 1179.00 M ( 1" PER 3 MIN ) FR: 700 GPM, SPP: 1860-1880 PSI, DIFF PRESSURE: 20-95 PSI NOTE: KICK OFF POINT IS AT 1178M AFTER GETTING 80% FORMATION - TOOK CUTTING SAMPLE AT 14:30 @1178.73 M. ( 80 % FORMATION ). Page 53 of 120
GZR-401 |  |  |  | 2023-05-22 14:45 | 2023-05-22 16:30 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONTINUE TIME DRILLING FROM 1179 M TO 1181.11 M ( 1" PER 1 MIN ) FR: 700 GPM, SPP: 1860-1880 PSI, DIFF PRESSURE: 20-100 PSI NOTE: - TOOK CUTTING SAMPLE AT 15:15 @1179.15 M. ( 80 % FORMATION ). - TOOK CUTTING SAMPLE AT 16:00 @1180.0 M. ( 90 % FORMATION ).
GZR-401 |  |  |  | 2023-05-22 16:30 | 2023-05-22 19:00 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - START DRILLING WITH ROTATION FROM 1181.11 M TO 1192 M. FR: 700 GPM, WOB: 13-30 KLBS, TQ: 2-3 KFT.IBF, RPM: 30, SPP: 1860-1908 PSI, DIF PRESSURE: 50-100 PSI. AVG ROP: 4.56 M\HR. NOTE: - TOOK CUTTING SAMPLE AT 16:45 @1181.34M. ( 100 %FORMATION ). - TOOK CUTTING SAMPLE AT 17:15 @1184.5M. ( 100 %FORMATION ). - TOOK CUTTING SAMPLE AT 17:15 @ 1186.5 M. ( 100 % FORMATION ).
GZR-401 |  |  |  | 2023-05-22 19:00 | 2023-05-22 20:00 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. SLIDING WITH 12.25" GEO FROM 1192 M TO 1196M. FR: 700 GPM, WOB: 25-30 KLBS, SPP: 1950 PSI, DIF PRESSURE: 80-120 PSI.
GZR-401 |  |  |  | 2023-05-22 20:00 | 2023-05-23 | 4:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. DRILLING 12.25" HOLE SECTOIN FROM 1196 M TO 1218 M. FR: 700 GPM, WOB: 22-35 KLBS, TQ: 3-7 KFT.IBF, RPM: 30, SPP: 1950-2130 PSI, DIF PRESSURE: 130-190 PSI. AVG ROP: 8.9 M\HR. DRILLING SUMMARY ================== FOOTAGE DRILLED: 44 M DAILY BIT HRS: 21.38 HR AVG ROP: 2.1 M/HR NOTE: - TOOK SURVEY AT 1203 M ( MWD AT 1185.4 M): INCL: 2.03 DEG, AZM: 184.71 DEG. DOGLEG: 2.504 DEG/30 M - SLIDING WITH 12.25" BHA FROM 1203 M TO 1206 M. - SLIDING WITH 12.25" BHA FROM 1216 M TO 1218 M. Page 54 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. DRILLING 12.25" HOLE SECTION FROM 1218 M TO 1232 M. FR: 700 GPM, WOB: 22-35 KLBS, TQ: 3-8 KFT.IBF, RPM: 30, SPP: 1950 - 2150 PSI, DIF PRESSURE: 130-190 PSI. AVG ROP: 14.4 M\HR. NOTE: - CONT.SLI DING WITH 12.25" BHA FROM 1218 M TO 1225 M. - TOOK SURVEY AT 1232 M ( MWD AT 1214.3 M): INCL: 5.16 DEG, AZM: 185.06 DEG, DOGLEG: 3.2 DEG/30 M DECISION MADE TO POOH WITH 12.25" GEO-FORCE BHA WITH PROJECTION INC. AT BIT 7.5-8 DEG
GZR-401 |  |  |  | 2023-05-22 01:30 | 2023-05-22 02:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMPED 50 HI VIS AND CIRCULATED HOLE CLEAN - FR: 700 GPM, SPP: 1820-2000 PSI - NO LOSSES WAS ENCOUNTERED.
GZR-401 |  |  |  | 2023-05-22 02:45 | 2023-05-22 03:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FLOW CHECK WELL-OK STATIC.
GZR-401 |  |  |  | 2023-05-22 03:00 | 2023-05-22 03:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POOH 12 1/4" GEO-FORCE BHA ON ELEVATOR FROM 1232 MTO 1057 M. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 03:30 | 2023-05-22 03:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FLOW CHECK WELL-OK STATIC. ( INSIDE 13-3/8" CSG SHOE)
GZR-401 |  |  |  | 2023-05-22 03:45 | 2023-05-22 05:00 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POOH 12 1/4" GEO-FORCE BHA ON ELEVATOR FROM 1057 MTO 455 M. ( TOP OF BHA ) NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 05:00 | 2023-05-22 05:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - FLOW CHECK PRIOR BHA ENTER BOP - WELL STATIC - PUMP 20 BBL OF 1.42 SG SLUG - FLOW CHECK WELL POST PUMPING SLUG- STATIC
GZR-401 |  |  |  | 2023-05-22 05:45 | 2023-05-22 09:30 | 3:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. POH 12 1/4" GEO-FORCE BHA FROM 455 M TO SURFACE AS FOLLOW: - RACK BACK 10 STDS OF 5" HWDP. - RACK BACK 5 STDS OF 8.1/4" DC - L/D JAR, PBL SUB AND STRING STAB. - L/D MWD AND MOTOR BIT GRADING: 1-1-NO-A-1-I-NO-TD
GZR-401 |  |  |  | 2023-05-22 09:30 | 2023-05-22 09:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CLEAR AND CLEAN RIG FLOOR.
GZR-401 |  |  |  | 2023-05-22 09:45 | 2023-05-22 10:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | TDS SERVICE Page 55 of 120
GZR-401 |  |  |  | 2023-05-22 10:00 | 2023-05-22 11:45 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | PJSM P/U, M/U AND RIH 12-1/4"BHA#2 TO 102 M AS FOLLOW: - PICK UP NEW 12-1/4ﬂPDC Bit NOV TKC66 (3x12 & 6X13 NOZZLES) - 12 1/8" RSS I-CRUISE - 12.1/8" SLEEVE STAB. - 8" MWD TOOL - 8" DOWNHOLE SCREEN. - 8 FLOAT SUB. - 12.1/8" STABILIZER - 8" PBL SUB. - 10 X 8.1/4" DC NOTES: - USED MANUAL TONGS TO MU MWD ANDICRUISE TOOLS.
GZR-401 |  |  |  | 2023-05-22 11:45 | 2023-05-22 12:30 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | SHALLOW TEST MWD TOOL AND I-CRUISE AT: - FR 750GPM; SPP:1090 PSI. UNABLE TO GET SURVEY - FR 800 GPM, SPP: 1163 PSI. SURVEY SENT TO SURFACE. INC = 0.32 DEG, AZI = 138.5 DEG
GZR-401 |  |  |  | 2023-05-22 12:30 | 2023-05-22 14:15 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONTINUE P/U, M/U AND RIH 12-1/4" BHA#2 TO 448 M AS FOLLOW: - DOGLEG REAMER - 2 X 8.1/4" DC - 8" POWERSTROKE HYDRAULIC JAR - 3 X 8.1/4" DC - CROSSOVER - 30 X 5" HWDP - FILL UP STRING - WEIGHT BELOW JAR: 55 KLBS. - TOTAL BHA WEIGHT: 105 KLBS.
GZR-401 |  |  |  | 2023-05-22 14:15 | 2023-05-22 16:00 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. RIH WITH 12-1/4" BHA SINGLE IN WITH G2 DP FROM 448 M TO 1140 M DOWNLINK ICRUISE - MONITOR DISPLACEMENT ON TRIP TANK
GZR-401 |  |  |  | 2023-05-22 16:00 | 2023-05-22 18:00 | 2:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | TROUBLESHOOT MWD DEPTH SENSOR AS IT CAME OFF AND LOOSE WHILE TRIPPING IN HOLE.
GZR-401 |  |  |  | 2023-05-22 18:00 | 2023-05-22 20:15 | 2:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN TO CLEAR AND SMOOTH SIDETRACK SPOT FROM 1040M TO 1232 M. - OBSERVE HIGH TQ(3-4 KFT-IBF) AT 1176-1181 M. REAM BACK AND CLEAR THE TIGHT SPOT SEVERAL TIMES - FR= 800 GPM, RPM = 60, TQ = 2 KFT.IBF, SPP = 2440 PSI. Page 56 of 120
GZR-401 |  |  |  | 2023-05-22 20:15 | 2023-05-22 21:15 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RECORDED FLOW BACK AS BELOW : FR 900 GPM , EX-LOG : 49 BBL , RIG FLOOR :45 BBL FR 700 GPM , EX-LOG : 41 BBL , RIG FLOOR :44 BBL - TOOK SCR WITH MP # 1&2 - SENT 4 DOWNLINKS TO SETUP I-CRUISE FOR DRILLING
GZR-401 |  |  |  | 2023-05-22 21:15 | 2023-05-23 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | BED IN THE BIT AND RESUME DRILLING 12.25 " HOLE SECTION FROM 1232 TO 1313 M FR 900 GPM, SPP 3000-3120 PSI, WOB 15-30 KLBS , RPM 130-160 , TRQ 6 -12 KFT.LBS NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. DRILLING SUMMARY ================== FOOTAGE DRILLED: 81 M DAILY BIT HRS: 2.02 HR AVG ROP: 40 M/HR MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM.DOGLEG RATE ( DEG/30 M) 12507.45186.06 1.916 12797.43186.06 0.141 13076.81185.97 0.660 Page 57 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 1313 TO 1515 M FR 900 GPM, SPP 3100-3400 PSI, WOB 25-30 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 48 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - AT 1423 M, INC: 0.21 DEG , PRIOR ENTERING NAHR UMR AND SET I-CRUISE TO VERTICAL MODE. MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM.DOGLEG RATE ( DEG/30 M) 13365.65189.08 1.254 13653.76200.82 2.192 13941.57237.54 2.802 14230.21321.10 1.625 14510.07175.13 0.282 14800.04120.16 0.060 15090.003.76 0.042
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 08:45 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 1315 TO 1658 M FR 900 GPM, SPP 3100-3400 PSI, WOB 25-30 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 78 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED.
GZR-401 |  |  |  | 2023-05-22 08:45 | 2023-05-22 09:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | FLOW CHECK WELL, DUE TO NOT GETTING HOLE FILL AS PER CALCULATED VALUE. WELL STATIC. Page 58 of 120
GZR-401 |  |  |  | 2023-05-22 09:00 | 2023-05-22 10:45 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 1658 TO 1730 M FR 900 GPM, SPP 3100-3400 PSI, WOB 25-30 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 70 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - PERFORMED FIRE AND H2S DRILL
GZR-401 |  |  |  | 2023-05-22 10:45 | 2023-05-22 11:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | PERFORM D2 DRILL WITH CREW C.
GZR-401 |  |  |  | 2023-05-22 11:00 | 2023-05-22 18:00 | 7:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 1730 TO 1942 M FR 900 GPM, SPP 3100-3400 PSI, WOB 25-30 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 38.8 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - PERFORMED FIRE AND H2S DRILL - PERFORMED D2 DRILL WITH CREW C MWD SURVEYS: --------------------------------------------------- DEPTH.INCL.AZIM. 15670.07185.52 15960.06230.44 17110.0411.41 17970.08164.77 19120.0851.8 19410.04227.07
GZR-401 |  |  |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 1942 TO 2090 M FR 900 GPM, SPP 3100-3700 PSI, WOB 25-35 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 29 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. DRILLING SUMMARY ================== FOOTAGE DRILLED: 777 M DAILY BIT HRS: 17.64 HR AVG ROP: 44 M/HR Page 59 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2090 TO 2119 M FR 900 GPM, SPP 3100-3700 PSI, WOB 25-35 KLBS , RPM 130-160 , TRQ 7 -13 KFT.LBS AVG ROP: 29 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - AT 2119 M GREASE WASH PIPE
GZR-401 |  |  |  | 2023-05-22 01:30 | 2023-05-22 01:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | DUMP SAND TRAP AND FILL UP THE SAME
GZR-401 |  |  |  | 2023-05-22 01:45 | 2023-05-22 06:00 | 4:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2119 TO 2229 M FR 900 GPM, SPP 3400-3700 PSI, WOB 25-35 KLBS , RPM 130-160 , TRQ 7 -14 KFT.LBS AVG ROP: 32.3 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED.
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 13:45 | 7:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2229 TO 2435 M FR 900 GPM, SPP 3700-3900 PSI, WOB 25-35 KLBS , RPM 140-160 , TRQ 9 -14 KFT.LBS AVG ROP: 27.5 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - AT 2290 M CONNECTION TAKE SCR
GZR-401 |  |  |  | 2023-05-22 13:45 | 2023-05-22 14:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | SERVICE TDS Page 60 of 120
GZR-401 |  |  |  | 2023-05-22 14:00 | 2023-05-23 | 10:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2435 TO 2666 M FR 900 GPM, SPP 3700-4100 PSI, WOB 25-45 KLBS , RPM 140-170 , TRQ 9 -17 KFT.LBS AVG ROP: 30 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - AT 2463 M DAMP SAND TRAP. - AT 2637 M TOOK SCR MP #1 & 2. - FROM 2653 M TO 2666 M OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. DRILLING SUMMARY ================== FOOTAGE DRILLED: 576 M DAILY BIT HRS: 18.46 HR AVG ROP: 31.2 M/HR
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2666 TO 2781 M FR 885-900 GPM, SPP 4000-4100 PSI, WOB 15 - 45 KLBS , RPM 150-170 , TRQ 10 -18 KFT.LBS AVG ROP: 21.9 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 30 BBL OF HI-VIS EVERY 4-5 STANDS DRILLED. - AT 2666 M TOOK SURVEY - FROM 2653 M TO 2780 M OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. - AT 2723 M GREASE WASH PIPE Page 61 of 120
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 20:30 | 14:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2781 TO 3011 M FR 900 GPM, SPP 4000-4150 PSI, WOB 35 - 45 KLBS , RPM 150-160 , TRQ 10 -15 KFT.LBS AVG ROP: 20 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - AT 2838 M GREASE WASH PIPE
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 21:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | SERVICE TDS
GZR-401 |  |  |  | 2023-05-22 21:00 | 2023-05-22 22:00 | 1:00 |  |  |  | RREP |  |  | Non-Productive |  |  | HAD LEAK IN TDS WASH PIPE. - R\B ONE STAND - INSTALLED FOSV - REMOVED OLD WASH PIPE - INSTALLED NEW WASH PIPE.
GZR-401 |  |  |  | 2023-05-22 22:00 | 2023-05-23 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 2982 TO 3040 M FR 860-900 GPM, SPP 4100-4250 PSI, WOB 35 - 45 KLBS , RPM 130-160 , TRQ 10 -16 KFT.LBS AVG ROP: 19.5 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP > 4280 PSI - OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM. DRILLING SUMMARY ================== FOOTAGE DRILLED: 374 M DAILY BIT HRS: 17.8 HR AVG ROP: 21 M/HR Page 62 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3040 TO 3155 M FR 850-860 GPM, SPP 4150-4250 PSI, WOB 35 - 45 KLBS , RPM 120-160 , TRQ 12 -18 KFT.LBS AVG ROP: 22 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP > 4280 PSI - OBSERVED STRING GOT STALLED SEVERAL TIMES DRILLING TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB OR B\U OFF-BOTTOM.
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-23 | 18:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3155 TO 3456 M FR 780-840 GPM, SPP 4150-4300 PSI, WOB 35 - 45 KLBS , RPM 130-160 , TRQ 12 -15 KFT.LBS AVG ROP: 23 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - AT 3172 M START INCREASE MW TO 1.30 SG. - AT 3212 M GREASE WASHPIPE. - AT 3212 TOOKSCR. - AT 3415 M @ 20:45FUNCTION TEST BOP FROM TP PANEL - HAD AN ISSUE IN MP #3 DRILL WITH MP 1&2 FROM 3413 M TO 3448 M WITH 780 GPM - TOP OF GHARIF AT 3254 M. - PUMP 30 BBL OF NUT SHELL AT 3300 M. - PUMP 30 BBL OF NUT SHELL AT 3355 M. - PUMP 30 BBL OF NUT SHELL AT 3413 M. DRILLING SUMMARY ================== FOOTAGE DRILLED: 416 M DAILY BIT HRS: 18.49 HR AVG ROP: 22.5 M/HR Page 63 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:00 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3456 TO 3471 M FR 780-800 GPM, SPP 4150-4300 PSI, WOB 35 - 45 KLBS , RPM 150 , TRQ 12 -15 KFT.LBS AVG ROP: 16 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI
GZR-401 |  |  |  | 2023-05-22 01:00 | 2023-05-22 01:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | SERVICE TDS
GZR-401 |  |  |  | 2023-05-22 01:30 | 2023-05-22 06:00 | 4:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3471 TO 3505 M FR 780 GPM, SPP 4150-4300 PSI, WOB 25 - 50 KLBS , RPM 120-150 , TRQ 9 -18 KFT.LBS AVG ROP: 9.6 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMPED 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - AT 3497 M OBSERVED HIGH STICK SLIP TORQUE INCREASED GRADUALLY TO TRQ. LIMIT OF 18 K FT.LBS. MITIGATED THE SAME BY REDUCING WOB & INCREASE RMP AND B\U OFF-BOTTOM
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 22:30 | 16:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3505 TO 3584 M FR 780 GPM, SPP 4180-4300 PSI, WOB 25 - 55 KLBS , RPM 110-150 , TRQ 9 -12 KFT.LBS AVG ROP: 5 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - HAD AN ISSUE IN MP #1 DRILL WITH 2 MPS FROM 3582 M
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:15 | 0:45 |  |  |  | RREP |  |  | Non-Productive |  |  | HAD AN ISSUE IN SEAT VALVE MP #3 AND MP #1. - P\UP OFF-BOTTOM - FIXED MUD PUMPS 1&3 SEAT VALVE ISSUE Page 64 of 120
GZR-401 |  |  |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3584 TO 3586 M FR 780 GPM, SPP 4180-4300 PSI, WOB 25 - 55 KLBS , RPM 110-150 , TRQ 9 -12 KFT.LBS NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI DRILLING SUMMARY ================== FOOTAGE DRILLED: 130 M DAILY BIT HRS: 20.86 HR AVG ROP: 6.23 M/HR
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 05:45 | 5:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3586 TO 3596 M FR 780 GPM, SPP 4200-4300 PSI, WOB 45 - 55 KLBS , RPM 80-130 , TRQ 7 -9 KFT.LBS AVG ROP: 2.1 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - HAD AN ISSUE IN MP #2 DRILL WITH 2 MPS FROM 3586 M - AT 3587 M GREASE WASH PIPE
GZR-401 |  |  |  | 2023-05-22 05:45 | 2023-05-22 06:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONDUCTED D2 WITH CREW # C. GOOD RESPONSE FROM DRILLER AND MUD LOGGER IN DETECTING THE INCREASE IN PVT. DRILLER SPACE OUT STRING FOR FLOW CHECK. - HAD AN AAR . Page 65 of 120
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 15:45 | 9:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT.DRILLING 12.25 " HOLE SECTION FROM 3596 TO 3615 M FR 780 GPM, SPP 4200-4300 PSI, WOB 45 - 55 KLBS , RPM 80-130 , TRQ 7 -9 KFT.LBS AVG ROP: 1.9 M/HR NOTES: - REAMED 3 M UP/DN EVERY CONNECTION AT 45 RPM. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - AT 3610 M START INCREASED MW TO 1.32 SG - SLOW PROGRESS AVG ROP < 2 M\HR. ATTEMPTED TO OPTIMIZE THE ROP USING DIFFERENT DRILLING PARAMETERS ANDPERFORMED DRILL-OFF TESTS BUT OBSERVE HIGH STICK AND SLIP AND NO PROGRESS IN ROP. - DECISION MADE TO POH DUE TO LOW ROP.
GZR-401 |  |  |  | 2023-05-22 15:45 | 2023-05-22 17:30 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMP 50 BBLS HI-VIS - CIRCULATE HOLE CLEAN WITH 780 GPM, SPP 4200-4250, RPM 45 - 5 % CAVING FROM GHARIF FORMATION 1-2 CM
GZR-401 |  |  |  | 2023-05-22 17:30 | 2023-05-22 18:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - TOOK SCR. - FLOW CHECK WELL-OK STATIC. - INSTALLED AIR SLIPS
GZR-401 |  |  |  | 2023-05-22 18:00 | 2023-05-22 18:45 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | PERFORM DROP INSPECTION FOR AREA #1,2&3
GZR-401 |  |  |  | 2023-05-22 18:45 | 2023-05-22 19:15 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 3615 MTO 3375 M. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 19:15 | 2023-05-22 19:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONDUCTED D1 DRILL KICK WHILE TRIPPING WITH CREW # D - GOOD RESPONSE FROM CREWIN SECURING THE WELL IN LESS THAN 2 MINS. - AAR
GZR-401 |  |  |  | 2023-05-22 19:30 | 2023-05-22 20:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 3375 MTO 3196 M. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 21:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | AT 3196 M OBSERVED OVERPULL > 60 KLBS, UNABLE TO PASS TIGHT SPOT WITH WIPING STRING. - ATTEMPT TO PASS TIGHT SPOT WITH PUMP OUT - NO SUCCESS. - ATTEMPT TO PASS TIGHT SPOT WITH REAM BACK- NO SUCCESS, TRQ REACHED TO 18KFT.LBS AND STRING GOT STALLED. FR: 780 GPM, SPP: 3950 PSI - FIRED HYDRAULIC JAR 3 TIMES, STRING GOT FREE. Page 66 of 120
GZR-401 |  |  |  | 2023-05-22 21:30 | 2023-05-23 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | HARD BACK REAM WITH 12.25" BHA FROM 3196 M TO 3136 M. FR: 780 GPM, SPP 3950 PSI, RPM 45 , TRQ 4-18 KFT.LBS. - OBSERVED SUDDEN INCREASE IN TRQ TO 18 KFT.LBS SEVERAL TIMES. - OBSERVED NO CUTTING AT SHAKERS DURING BACK REAM
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 02:00 | 2:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. HARD BACK REAM WITH 12.25" BHA FROM 3136 M TO 3058 M. FR 500-780 GPM, SPP 1950-3950 PSI, RPM 45 , TRQ 4-18 KFT.LBS. - OBSERVED SUDDEN INCREASE IN TRQ TO 18 KFT.LBS SEVERAL TIMES. - OBSERVED NO CUTTING AT SHAKERS DURING BACK REAM
GZR-401 |  |  |  | 2023-05-22 02:00 | 2023-05-22 03:15 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH 12.25" BHA FROM 3058 M TO 2940 M ON ELEVATORS. - AT 3005 M AND 2980 M OBSERVED OVERPULL > 30-50 KLBS, ABLE TO PASS TIGHT SPOTS BY WORKING THE STRING UP \ DOWN MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 03:15 | 2023-05-22 06:00 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | AT 2940 M OBSERVED OVERPULL > 60 KLBS, UNABLE TO PASS TIGHT SPOT WITH WIPING STRING. - ATTEMPT TO PASS TIGHT SPOT WITH PUMP OUT - NO SUCCESS. HARD BACK REAM WITH 12.25" BHA FROM 2940 M TO 2880 M. FR: 780 GPM, SPP 3900 PSI, RPM 45 , TRQ 4-18 KFT.LBS. - STRING GOT STALLEDSEVERAL TIMES. - AT 2920 PUMP 50 BBL HI-VIS ( OBSERVED NO INCREASE IN CUTTING ONCE HI-VIS AT SHAKERS )
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 18:30 | 12:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. HARD BACK REAM WITH 12.25" BHA FROM 3058 M TO 2509 M. FR 700-780 GPM, SPP 1950-3950 PSI, RPM 45 , TRQ 4-18 KFT.LBS. - OBSERVED SUDDEN INCREASE IN TRQ TO 18 KFT.LBS SEVERAL TIMES. - OBSERVED 30% CUTTING AT SHAKERS DURING BACK REAM FROM KHUFF FORMATION. - FROM 2769 M TO 2740STRING GOT STALLED SEVERAL TIMES, FIRED HYDRAULIC JAR 2 TIMES, STRING GOT FREE. - BACK REAM FULL STAND F/2740 M TO 2711 M, THEN RUN BACK TO BOTTOM - RUN WAS SMOOTH. TRY TO POOH ON ELEVATOR OBSERVED OVERPULL > 50 KLBS AFTER POOH ONE SINGLE.
GZR-401 |  |  |  | 2023-05-22 18:30 | 2023-05-22 19:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH 12.25" BHA FROM 2509 M TO 2403 M ON ELEVATORS. MONITOR WELL THROUGH TRIP TANK. Page 67 of 120
GZR-401 |  |  |  | 2023-05-22 19:45 | 2023-05-23 | 4:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. BACK REAM WITH 12.25" BHA FROM 2403 M TO 2144 M. FR 780 GPM, SPP 3400 PSI, RPM 45 , TRQ 4 -18 KFT.LBS. - STRING GOT STALLEDSEVERAL TIMES. MONITOR WELL THROUGH ACTIVE SYSTEM.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 02:15 | 2:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. BACK REAM WITH 12.25" BHA FROM 2144 M TO 2028 M. FR 780 GPM, SPP 3200 PSI, RPM 45 , TRQ 4 -15 KFT.LBS. MONITOR WELL THROUGH ACTIVE SYSTEM.
GZR-401 |  |  |  | 2023-05-22 02:15 | 2023-05-22 03:30 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | POOH 12.25" BHA FROM 2028 M TO 1860 M ON ELEVATORS. MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 03:30 | 2023-05-22 06:00 | 2:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. BACK REAM WITH 12.25" BHA FROM 1860 M TO 1750 M. FR 780 GPM, SPP 3150 PSI, RPM 45 , TRQ 4 -15 KFT.LBS. MONITOR WELL THROUGH ACTIVE SYSTEM.
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 10:30 | 4:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. BACK REAM WITH 12.25" BHA FROM 1750 M TO 1597 M. FR 780 GPM, SPP 3150-3000 PSI, RPM 45 , TRQ 4 -15 KFT.LBS. MONITOR WELL THROUGH ACTIVE SYSTEM.
GZR-401 |  |  |  | 2023-05-22 10:30 | 2023-05-22 11:45 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. PUMP OUT WITH 12.25" BHA FROM 1597 M TO 1481 M. FR 780 GPM, SPP 3000 PSI. - AT 3005 M AND 2980 M OBSERVED OVERPULL > 30-50 KLBS - OBSERVED 100% CUTTING AT SHAKERS AND 40-50% CAVING DURING BACK REAM FROM NAHR-UMR FORMATION. MONITOR WELL THROUGH ACTIVE SYSTEM.
GZR-401 |  |  |  | 2023-05-22 11:45 | 2023-05-22 12:45 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. BACK REAM WITH 12.25" BHA FROM 1481 M TO 1452 M. FR 780-800 GPM, SPP 2950-3000 PSI, RPM 45 , TRQ 4 -17 KFT.LBS. MONITOR WELL THROUGH ACTIVE SYSTEM. Page 68 of 120
GZR-401 |  |  |  | 2023-05-22 12:45 | 2023-05-22 18:15 | 5:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. PUMP OUT WITH 12.25" BHA FROM 1452 M TO 1056 M ( 13-3/8'' CSG SHOE) FR 780 GPM, SPP 3000 PSI. MONITOR WELL THROUGH ACTIVE SYSTEM. NOTE: - AT 16:30 HRS SHIFT HANDOVER AND TBT
GZR-401 |  |  |  | 2023-05-22 18:15 | 2023-05-22 19:45 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | PUMP 50 BLLS HI-VIS - CIRCULATE HOLE CLEAN WITH 900 GPM,PSI 3100-3200 PSI - OBSERVED 20 % CAVING FROM NAHR-UMR FORMATION AND 10% CUTTING AT SHAKERS. - PUMP ANOTHER 50 BBLS HIVI-S AND CIRCULATED OUT WITH 900 GPM, SPP 3100-3200 PSI - NO MORE CAVING OR CUTTING AT SHAKER.
GZR-401 |  |  |  | 2023-05-22 19:45 | 2023-05-22 20:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - FLOW CHECK WELL-OK STATIC.
GZR-401 |  |  |  | 2023-05-22 20:00 | 2023-05-22 21:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | SLIP DRILL LINE - TBT PRIOR SLIP DRILL LINE. - R\B 2X 5" DP STANDS - HANG TRAVELING BLOCK - SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 21:30 | 2023-05-22 22:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PUMP 30 BBL OF 1.5 SG SLUG. - FLOW CHECK AT CASING SHOE AND AFTER PUMPING SLUG- WELL STATIC
GZR-401 |  |  |  | 2023-05-22 22:00 | 2023-05-22 22:30 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - INSTALL DP WIPER AND AIR SLIPS NOTE: - AT 22:10 HRS SHIFT HANDOVER AND TBT
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. POOH 12.25" BHA ON ELEVATOR FROM 980 M TO 444 M.TOP OF BHA. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 23:30 | 2023-05-22 23:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - FLOW CHECK AT TOP OF BHA- WELL STATIC
GZR-401 |  |  |  | 2023-05-22 23:45 | 2023-05-23 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. POOH 12 1/4" BHA FROM 444 M TO 370 M. - RACK BACK 3 STDS OF 5" HWDP. Page 69 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 04:45 | 4:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CONT. POH 12 1/4" BHAFROM 370 M TO SURFACE AS BELOW - RACK BACK 7 STDS OF 5" HWDP. - RACK BACK 1 X STD OF 8 1/4" DC. - L/D 8" JAR. - L/D 8" DOGLEG REAMER( 10% BALLDUP) - RACK BACK 4 X STD OF 8 1/4" DC. - L/D PBL SUB. - LAY DOWN STABS ( 40% BALLDUP ) - LAY DOWN FLOAT SUB WITH NON-PORTED FLOAT VALVE. - LAY DOWN 8" FILTER SUB AND MWD. - BREAK OUT THE BIT AND LAY DOWN I-CRUISE. ( OBSERVED ALL I-CRUISE PADS ARE LOOSE ) - BIT GRADING: 2-2-WT-A-X-I-HC-PR
GZR-401 |  |  |  | 2023-05-22 04:45 | 2023-05-22 05:15 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIG DOWN GEO-SPAN - CLEAN AND CLEAR RIG FLOOR
GZR-401 |  |  |  | 2023-05-22 05:15 | 2023-05-22 05:45 | 0:30 |  |  |  | DPRB |  |  | Productive |  |  | - TBT FOR BOP PRESSURE TEST - RETRIEVE WEAR BUSHING. - R/D WEAR BUSHING.
GZR-401 |  |  |  | 2023-05-22 05:45 | 2023-05-22 06:15 | 0:30 |  |  |  | DPRB |  |  | Productive |  |  | - MAKE UP CAMERON JETTING TOOL - JET WASH BOP - R/D JETTING TOOL
GZR-401 |  |  |  | 2023-05-22 06:15 | 2023-05-22 07:15 | 1:00 |  |  |  | DPRB |  |  | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY
GZR-401 |  |  |  | 2023-05-22 07:15 | 2023-05-22 07:30 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. - OBSERVED HIGH PRESSURE PUMP NOT WORKING.
GZR-401 |  |  |  | 2023-05-22 07:30 | 2023-05-22 10:15 | 2:45 |  |  |  | RREP |  |  | Non-Productive |  |  | TROUBLESHOOTING BOP TEST PUMP Page 70 of 120
GZR-401 |  |  |  | 2023-05-22 10:15 | 2023-05-22 15:45 | 5:30 |  |  |  | DPRB |  |  | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD . - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), LOW 250-350 PSI-LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK.
GZR-401 |  |  |  | 2023-05-22 15:45 | 2023-05-22 16:00 | 0:15 |  |  |  | DPRB |  |  | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
GZR-401 |  |  |  | 2023-05-22 16:00 | 2023-05-22 16:15 | 0:15 |  |  |  | DPRB |  |  | Productive |  |  | - INSTALLED WEAR BUSHING
GZR-401 |  |  |  | 2023-05-22 16:15 | 2023-05-22 18:00 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - RIH 5 STAND OF 8.1/4'' DC TO 166 M
GZR-401 |  |  |  | 2023-05-22 18:00 | 2023-05-22 20:45 | 2:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - POOH AND L/D 15 X JTS 8 1/4" DC. NOTE: - HAD TWO OVER TRQ CONNECTIONS USED MANUAL TONGS - AT 20:10 CREW HAND OVER AND TBT
GZR-401 |  |  |  | 2023-05-22 20:45 | 2023-05-22 21:00 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CLEAN & CLEAR RIG FLOOR
GZR-401 |  |  |  | 2023-05-22 21:00 | 2023-05-22 21:15 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PU , MU WEAR BUSHING RETRIEVE TOOL. - RETRIEVED WEAR BUSHING
GZR-401 |  |  |  | 2023-05-22 21:15 | 2023-05-22 21:45 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PU, MU JETTING TOOL - JET AND FLUSH BOP AND WELLHEAD - LAY DOWN JETTING TOOL AND WEAR BUSHING RUNING TOOL
GZR-401 |  |  |  | 2023-05-22 21:45 | 2023-05-22 22:30 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | - REMOVE BAILS AND ELEVATOR. - REMOVE SAVER SUB NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 22:30 | 2023-05-22 23:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - REMOVED DEFECTED ( BEND ) BAILS HYDRAULIC CYLINDER - INSTALLED NEW BAILS HYDRAULIC CYLINDER MAINTIME: - R\UP TRS TOOLS Page 71 of 120
GZR-401 |  |  |  | 2023-05-22 23:00 | 2023-05-23 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | -PJSM WITH ALL CREW PRIOR R/U FRANKS EQUIPMENT. - RIG UP FA-1 SERVICE LOOP. - PICK UP AND RIG UP CRT.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. RIG UP FA-1. - CONDUCT DROP INSPECTION. - R/UP HYDRAULIC ELEVATOR - MU SAFETY VALVE WITH 9.5/8" WATER BUSHING. NOTES: - MONITOR WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 01:30 | 2023-05-22 01:45 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | PJSM FOR 9 5/8" HANGER DUMMY RUN
GZR-401 |  |  |  | 2023-05-22 01:45 | 2023-05-22 02:45 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | 9-5/8'' CASING HANGER DUMMY RUN: - PU AND RIH 9-5/8'' CASING HANGER WITH LANDING JOINT. - LAND CASING HANGER IN WELL HEAD PROFILE. HOP 10.56 M BRT, STICK UP 1.09 M. - VERIFY YELLOW MARK THROUGH WH LOWER SOV™S. - POOH AND LD 9-5/8'' CASING HANGER ASSEMBLY.
GZR-401 |  |  |  | 2023-05-22 02:45 | 2023-05-22 03:15 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - REMOVE MASTER BUSHINGS. - INSTALLED FMS. - VERIFIED INTERLOCKING SYSTEM IS WORKING PROPERLY FOR CRT AND FMS.
GZR-401 |  |  |  | 2023-05-22 03:15 | 2023-05-22 03:30 | 0:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - PJSM WITH ALL CREW PRIOR P/U 9 5/8" SHOE TRACK AND RIH WITH CASING.
GZR-401 |  |  |  | 2023-05-22 03:30 | 2023-05-22 04:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIH WITH 9-5/8'' SHOE TRACK: - PICK UP 9 5/8" REAMER SHOE,FUNCTION TEST FLOAT. OK - P\UP MU AND RIH 2 X JOINTS OF 9-5/8" CSG - PU, MU AND RIH SHOE TRACK TO 51.16 M. TESTED FLOATS FUNCTIONING OK. - APPLIED BAKERLOCK ON SHOETRACK CONNECTIONS. Page 72 of 120
GZR-401 |  |  |  | 2023-05-22 04:30 | 2023-05-22 20:30 | 16:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 51 M TO 1577 M - FILLED UP EVERY JOINT USING FA-1 ( MAKE SURE STRING IS FULL EVERY 5 JNTS ) - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - BREAK CIRCULATION AT 13 3/8" SHOE, 420 GPM, 700 PSI, WT UP 203 KIP, WT DN 201 KIP NOTE: - AT 136 MHAD ISSUE WITH JT# 7 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 10 MINS MORE. - AT 700 MHAD ISSUE WITH JT# 53 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 15 MINS MORE. - AT 727 MHAD ISSUE WITH JT# 55 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 8 MINS MORE. - AT 779 MHAD ISSUE WITH JT# 59 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 10 MINS MORE. - AT 08:10 TBT AND CREW SHIFT HANDOVER - RUNNING SPEED10-11 JNT / HR
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-22 21:00 | 0:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE BOTTOMS UP WHILE RECIPROCATING STRING, 420 GPM, 720 PSI, WT UP 280 KIP, WT DN 268 KIP SHAKERS CLEAN.
GZR-401 |  |  |  | 2023-05-22 21:00 | 2023-05-23 | 3:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1577 M TO 1863 M - FILLED UP EVERY JOINT USING FA-1 ( MAKE SURE STRING IS FULL EVERY 5 JNTS ) - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. Page 73 of 120
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 17:15 | 17:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1863 M TO 3219 M (30 m ABOVE GHARIF) - AT 2939 MHAD ISSUE WITH JT# 233 M/U TORQUE. BREAK OUT, CLEAN AND REMADE THE SAME. TOOK 10 MINS MORE. - FILLED UP EVERY JOINT USING FA-1 ( MAKE SURE STRING IS FULL EVERY 5 JNTS ) - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED5-6 JNT / HR
GZR-401 |  |  |  | 2023-05-22 17:15 | 2023-05-22 18:30 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE BOTTOMS UP WHILE RECIPROCATING STRING, 420 GPM, 750 PSI, WT UP 550 KIP, WT DN 480 KIP SHAKERS CLEAN
GZR-401 |  |  |  | 2023-05-22 18:30 | 2023-05-22 19:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3219 M TO 3290 M - FILLED UP EVERY JOINT USING FA-1 ( MAKE SURE STRING IS FULL EVERY 5 JNTS ) - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED5-6 JNT / HR
GZR-401 |  |  |  | 2023-05-22 19:30 | 2023-05-22 20:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | - AT 3290 M, CASING TAKES WEIGHT, SLACK DOWN WEIGH UP 50 KLBS - ATTEMPT TO WASH DOWN WITH 420 GPM, 750 PSI, UNABLE TO PASS THROUGH, INCREASED SLACK WEIGHT GRADUALLY WITH 15 KLBS AT A TIME AND CHECK STRING UP FREE, MAX SLACK DOWN WEIGHT REACHED WHILE WASH DOWN WAS 100 KLBS. NO IMPROVEMENT. - PICK UP STRING TO NEUTRAL WEIGHT, ATTEMPT TO ROTATE, TQ REACHES 15 KFT.LB WITH NO ROTATION, RELEASE TORQUE, PICK UP STRING TO 3280 M AND ATTEMPT TO ROTATE, NO SUCCESS. - INCREASED TORQUE LIMIT TO 18500 KFT.LN, AND ROTATE STRING, OBSERVES STRING ROTATING WITH 18500 KFT.LB, FLOW RATE 420 GPM, SPP 770 PSI. - KEPT STRING STABLE AND ALLOWED TORQUE TO DECREASE AND STABILIZE AT 14-15 KFT.LB. Page 74 of 120
GZR-401 |  |  |  | 2023-05-22 20:30 | 2023-05-23 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3280 M TO 3293 M FR: 420 GPM, SPP: 770-1000 PSI, ROT: 45 RPM, TQ: 14-18.5 KFT.LBS NOTE: - SLOW PROGRESS DUE TO HIGH TORQUE AND STRING GOT STALL FEW TIMES. - OBSERVED INCREASE IN CUTTINGS AT SHAKERS, MAINLY FROM GHARIF.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:45 | 1:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3293 M TO 3308 M FR: 420 GPM, SPP: 770-1000 PSI, ROT: 45 RPM, TQ: 14-18.5 KFT.LBS
GZR-401 |  |  |  | 2023-05-22 01:45 | 2023-05-22 02:30 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | WASH DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3308 M TO 3321 M FR: 420 GPM, SPP: 820-1070 PSI, STRING TAKES WEIGHT AT 3321 M, UNABLE TO WASH DOWN WITH 100 KLBS DAWN WEIGHT. UP FREE
GZR-401 |  |  |  | 2023-05-22 02:30 | 2023-05-22 06:00 | 3:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3321 M TO 3328 M FR: 420 GPM, SPP: 800-950 PSI, ROT: 45 RPM, TQ: 15-18.5 KFT.LBS NOTE: - SLOW PROGRESS DUE TO HIGH TORQUE AND STRING GOT STALL FEW TIMES.
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-23 | 18:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3328 M TO 3396 M FR: 420 GPM, SPP: 800-950 PSI, ROT: 45 RPM, TQ: 15-18.5 KFT.LBS NOTE: - SLOW PROGRESS DUE TO HIGH TORQUE AND STRING GOT STALL FEW TIMES.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 03:45 | 3:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3396 M TO 3436 M FR: 420 GPM, SPP: 800-950 PSI, ROT: 45 RPM, TQ: 15-18.5 KFT.LBS NOTE: - SLOW PROGRESS DUE TO HIGH TORQUE AND STRING GOT STALL FEW TIMES.
GZR-401 |  |  |  | 2023-05-22 03:45 | 2023-05-22 05:15 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | WASH DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3436 M TO 3546 M FR: 420 GPM, SPP: 800-840 PSI Page 75 of 120
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 06:00 | 0:45 | [6 empty] | Productive |  |  | AT 3546 M, STRING TAKES WEIGHT, PICK UP TO 3540 M, UP FREE REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3540 M TO 3547 M FR: 420 GPM, SPP: 800-870 PSI, ROT: 45 RPM, TQ: 15-18.5 KFT.LBS
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 12:00 | 6:00 | [6 empty] | Productive |  |  | CONT. REAM DOWN WITH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3547 M TO 3551.5 M FR: 420 GPM, SPP: 800-870 PSI, ROT: 45 RPM, TQ: 15-18.5 KFT.LBS - SLOW PROGRESS DUE TO HIGH PRESSURE HARD REAMDOWN - DISCUSSED WITH TEAM, AGREE TO SET THE 9-5/8'' CASING AT 3551.5 M
GZR-401 |  | RIG |  | 2023-05-22 12:00 | 2023-05-22 14:45 | 2:45 | [6 empty] | Productive |  |  | - PUMPED 100 BBLS HIVIS AND CIRCULATED HOLE CLEAN WITH 420 GPM AND 40 RPM. - PRESSURE 800-1020 PSI, TRQ: 12-16 KFT.LBS - 5 % INCREASED IN CUTTING WITH TRACES OF CAVING WERE SEEN WHEN HIVIS WAS ON SURFACE (GHARIF) - HI-VIS AT SURFACE AFTER ~ 1000 STKS (100 BBLS)
GZR-401 |  | RIG |  | 2023-05-22 14:45 | 2023-05-22 16:30 | 1:45 | [6 empty] | Productive |  |  | - POOH & L/D EXTRA 3 CASING JOINTS. - P/U AND RIH WITH 9.25 M OF 9-5/8'' PUP TO 3534 M - PICK UP POWER TONG AND HYDRAULIC HOSES
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 16:45 | 0:15 | [6 empty] | Productive |  |  | TBT,PU AND MU 9-5/8'' CASING HANGER ASSEMBLY TO THE STRING AND REMOVE FMS AND INSTALL MASTER BUSHING
GZR-401 |  | RIG |  | 2023-05-22 16:45 | 2023-05-22 17:45 | 1:00 | [6 empty] | Productive |  |  | - MAKE UP HANGER ASSEMBLY BY USING POWER TONG. - REMOVE FRANKS FMS & INSTALL RIG'S MASTER BUSHING. - B/O RUNNING TOOL 2 TURNS AT RIG FLOOR W/ CHAIN TONGS AND M/U SAME - DRAIN BOP STACK AND CLEAN WELLHEAD FROM TOP AND THRU SOV'S. - LAND HANGER, STICK UP WITH SAME MARK AT RIG FLOOR, CASING STRING WEIGHT ~ 550 KLBS - CAMERON CONFIRM THRU SOV THAT HANGER FULLY LANDED THROUGH YELLOW MARKS (VERIFIED BY WSL) - 9-5/8" CASING SHOE AT 3547 M , FC AT 3508 M, FREE POCKET 4.61 M, TOTAL POCKET 68 M. Page 76 of 120
GZR-401 |  | RIG |  | 2023-05-22 17:45 | 2023-05-22 19:45 | 2:00 | [6 empty] | Productive |  |  | - M/U XO ON LANDING JNT , R/U HLB CEMENT HEAD AND CHICKSAN LINES - CIRCULATE HOLE CLEAN WITH 320 GPM 620 PSI PRESSURE. OFFLINE: - R/D FRANKS POWER TONG. - R/D FRANKS FMS - MIX CMT MIXING WATER. - HOLD TBT W/ CREW FOR CEMENT JOB.
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-22 20:15 | 0:30 | [6 empty] | Productive |  |  | - PRESSURE TEST LINE TO 300/6000 PSI HIGH FOR 5 MIN - OK - LINE UP TO RIG PUMP
GZR-401 |  | RIG |  | 2023-05-22 20:15 | 2023-05-22 20:45 | 0:30 | [6 empty] | Productive |  |  | - PUMP 80 BBLS OF TUNED SPACER WITH BRIDGEMAKER AT 250 GPM AT 415 PSI - SWITCH OVER TO THE HALLIBURTON UNIT - RELEASE THE BOTTOM PLUG & CONFIRMED BY WITNESSING THE FLAG INDICATOR.
GZR-401 |  | RIG |  | 2023-05-22 20:45 | 2023-05-23 | 3:15 | [6 empty] | Productive |  |  | - LINE UP TO CEMENT UNIT AND PUMP CEMENT SLURRY - 385.4 BBLS OF 1.57 SG LEAD @ 5-6 BPM - 100 BBLS OF 1.57 SG LEAD WITH BRIDGEMAKER @ 4-5 BPM - 376 BBLS OF 1.57 SG LEAD @ 5-6 BPM
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 | [6 empty] | Productive |  |  | - MIX & PUMP 78 BBLS OF 1.89 SG TAIL @ 4-5 BPM - RELEASE THE TOP PLUG & CONFIRMED BY THE FLAG INDICATOR. Page 77 of 120
GZR-401 |  | RIG |  | 2023-05-22 00:30 | 2023-05-22 03:30 | 3:00 | [6 empty] | Productive |  |  | - CEMENT UNIT PUMP 5 BBL MIX WATER @ 3 BPM - SWITCH TO RIG PUMPS TO DISPLACE WITH 1.25 SG HYDROGAURD MUD - PUMP 400 BBL AT 6 BPM , PRESSURE : 50-2300 PSI ** PRESSURE WAS GRADUALLY INCREASING FROM 140PSI TO 2300 PSI AFTER DISPLACING 157 BBLS. ** ADJUSTED DISPLACEMENT RATE FROM 6 BPM TO 5 BPM THEN TO 3 BPM TO MAINTAIN CONTINUES FLOW FROM THE WELL AND PREVENT PACK-OFF TENDENCY. ** AT 290 BBLS DISPLACED PRESSURE DECREASED TO 950 PSI AND FULL RETURN OBSERVED. - PUMP 370 BBL AT 5 BPM , PRESSURE : 900-1990 PSI - PUMP 20 BBL AT 4 BPM , PRESSURE : 1940-1960 PSI - PUMP 24 BBL AT 2 BPM , PRESSURE : 1780-1840 PSI - BUMP PLUG AND INCREASED PRESSURE TO 2380 PSI. (540PSI ABOVE FCP) - EQUALIZE PRESSURE IN CEMENT LINE AND LINE UP TO CEMENT UNIT - BLEED OFF TO ZERO. BLEED BACK VOLUME 5.5 BBL. CONFIRM FLOATS HOLDING. CEMENT IN PLACE AT 03:20 HRS NOTES: - DUMP 25 BBLS CONTAMINATED MUD AND SPACER. - DUMP 65 BBLS PURE SPACER. - DUMP 20 BBLS CONTAMINATED CEMENT. - DUMP 230 BBLS PURE CEMENT. - LOSSES THROUHGOT THE JOB WAS 90 BBL.
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 04:00 | 0:30 | [6 empty] | Productive |  |  | RIG DOWN HALIBURTON CEMENT HEAD AND HIGH PRESSURE LINES ON RIG FLOOR
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 05:00 | 1:00 | [6 empty] | Productive |  |  | - BACK OFF RUNNING TOOL FROM CASING HANGER. - BREAK OUT AND LAYDOWN LANDING JOINT AND RUNNING TOOL.
GZR-401 |  | RIG |  | 2023-05-22 05:00 | 2023-05-22 05:15 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR RIG DOWN FRANKS EQUIPMENT.
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 07:45 | 2:30 | [6 empty] | Productive |  |  | - RIG DOWN FRANKS TRS : - R/D FA-1 - R/D CONTROL PANEL - R\D FA-1 SERVICE LOOP
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 09:15 | 1:30 | [6 empty] | Productive |  |  | - INSTALL RIG SAVER SUB - INSTALL TDS BAILS - INSTALL ELEVATOR. Page 78 of 120
GZR-401 |  | RIG |  | 2023-05-22 09:15 | 2023-05-22 10:15 | 1:00 | [6 empty] | Productive |  |  | MAKE UP CAMERON JETTING TOOL - JET WASH BOP - FUNCTION BOP'S AND JET SEAL ASSEMBLY PROFILE. - FLUSH BOP STAK
GZR-401 |  | RIG |  | 2023-05-22 10:15 | 2023-05-22 11:00 | 0:45 | [6 empty] | Productive |  |  | M/U 9 5/8" CASING SSMC SEAL ASSEMBLY & LANDED IN THE WELLHEAD. - VERIFIED YELLOW MARKS FOR RUNNING TOOL THROUGH UPPER SOV. - SET SEAL ASSY WITH 3 1/2 TURNS. FOLLOWING CAM ENG INSTRUCTION. - VERIFIED LATCHING WITH 30 KLBS OVERPULL.
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 11:45 | 0:45 | [6 empty] | Productive |  |  | - INSTALL CAMERON TEST PUMP AND RECORDING CHART TO PRESSURE TEST SEAL ASSEMBLY. - PRESSURE TEST THE SEAL ASSEMBLY TO 300 PSI LOW & 8000 PSI HIGH FOR 15 MINUTES- GOOD TEST. - L\D SEAL ASSEMBLY RUNNING TOOL.
GZR-401 |  | RIG |  | 2023-05-22 11:45 | 2023-05-22 12:15 | 0:30 | [6 empty] | Productive |  |  | - INSTALL WEAR BUSHING.
GZR-401 |  | RIG |  | 2023-05-22 12:15 | 2023-05-22 13:30 | 1:15 | [6 empty] | Productive |  |  | - PERFORM DROPS INSPECTION AREA 1, 2 & 3 - SERVICE TDS
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 17:30 | 4:00 | [6 empty] | Productive |  |  | TBT AND P/U & M/U 8.5" MOTOR BHA #1 TO 134 M - 8.5" TKC73 BIT, NOZZLES:7X13, S/N S299951 - 6-3/4" MUD MOTOR WITH NON-PORTED FLOAT VALVE (0.28 REV/GAL) - 8 1/4" STRING STAB - 1 x 6-1/2'' DC JOINT - FILTER SUB - 8 1/4" STRING STAB W/ TOTCO RING - 14 x 6-1/2'' DC JOINT NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 450 GPM - SPP 900 PS 550 GPM - SPP 1100 PSI - MONITOR DISPLACEMENT THROUGH TRIP TANK - SINGLE IN 6-1/2'' DC JTS FROM PIPE CAT. - AT 17:00 HAD CREW HANDOVER AND TBT
GZR-401 |  | RIG |  | 2023-05-22 17:30 | 2023-05-22 18:15 | 0:45 | [6 empty] | Productive |  |  | CONDUCTED H2S WITH CREW D - GOOD RESPONSE FROM THE TEAM Page 79 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-22 21:30 | 3:15 | [6 empty] | Productive |  |  | TBT AND P/U & M/U 8.5" MOTOR BHA #1 FROM 134 TO 537 M - 8 1/4" STRING STAB W/ TOTCO RING - 7 x 6-1/2'' DC JOINT - 6-1/2'' JAR - 3 x 6-1/2'' DC JOINT - 15 x 5'' HWDP JOINTS (SINGLE IN) - 15 x 5'' HWDP JOINTS (5 STANDS FROM DERRICK) WEIGHT BELOW JARS : 50 KLBS TOTAL WEIGHT OF BHA : 100 KLBS
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-22 23:30 | 2:00 | [6 empty] | Productive |  |  | RIH REMAINING 5 x 5'' HWDP STANDS FROM DERRICK. POOH AND LAY DOWN 15 x 5'' HWDP JOINTS (DUE FOR INSPECTION)
GZR-401 |  | RIG |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 537 M TO 593 M - SINGLE IN 5'' 19.5 PPF DP FROM PIPE CAT - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 07:00 | 7:00 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 593 M TO 1690 M - SINGLE IN 5'' 19.5 PPF DP FROM PIPE CAT - MONITORED WELL ON TRIP TANK WITH TRIP SHEET NOTE: - AT 03:30 HRS, FUNCTION TEST BOP FROM DRILLER PANEL - AT 05:00 HRS, CREW CHANGE AND HANDOVER
GZR-401 |  | RIG |  | 2023-05-22 07:00 | 2023-05-22 09:15 | 2:15 | [6 empty] | Productive |  |  | - AT FILL UP THE STRING OBSERVED SHOOT-UP IN THE PRESSURE TO 1500 PSI AND NO FLOW OUT. - BLEED -OFF THE PRESSURE TO ZERO - TRY AGAIN TO DIRECT PRESSURE FROM STRING, OBSERVED PRESSURE SHOOT TO 2500 PSI, BLEED-OFF THE PRESSURE TO ZERO. - LINEUP FOR REVERSE CIRCULATION, PUMP THROUGH KILL LINE AND OBSERVED PRESSURE INCREASE TO 1000-1200PSI AND NO FLOW FROM THE STRING BLEED-OFF THE PRESSURE TO ZERO. - LINE THE STRING TO DIRECT PRESSURE FROM STRING TO 2700 PSI, SUDDENLY OBSERVED THE PRESSURE DROP AND FLOW OUT RETURN. - CONTINUES CIRCULATING BOTTOM-UP WITH 450 GPM, 1700-1750 PSI MEANWHILE RECIPROCATING THE STRING - OBSERVED 5-10% BRIDGEMAKER AND 90% DEBRIS. Page 80 of 120
GZR-401 |  | RIG |  | 2023-05-22 09:15 | 2023-05-22 11:00 | 1:45 | [6 empty] | Productive |  |  | CONT. RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 1690 M TO 1834 M - SINGLE IN 5'' 19.5 PPF DP FROM PIPE CAT - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 13:30 | 2:30 | [6 empty] | Productive |  |  | CONT. RIH HOLE WITH 8.5'' MOTOR BHA FROM 1834 M TO 2987 M - RUN 5'' DP FROM DERRICK - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 13:45 | 0:15 | [6 empty] | Productive |  |  | TBT FOR SLIP & CUT DRILL LINE
GZR-401 |  | RIG |  | 2023-05-22 13:45 | 2023-05-22 16:15 | 2:30 | [6 empty] | Productive |  |  | SLIP AND CUT DRILL LINE - PARKED TDS AND HANG BLOCK . - CUT 24 OF DRILL LINE AND SLIP 12 M. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
GZR-401 |  | RIG |  | 2023-05-22 16:15 | 2023-05-22 16:30 | 0:15 | [6 empty] | Productive |  |  | CREW SHIFT HANDOVER AND TBT FOR RIH 8.5'' BHA
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 17:00 | 0:30 | [6 empty] | Productive |  |  | CIRCULATION STRING VOLUME WITH 450 GPM, 1890 PSI
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 18:00 | 1:00 | [6 empty] | Productive |  |  | CONT. RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 2987 M TO 3448 M - SINGLE IN 5'' 19.5 PPF DP FROM PIPE CAT - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-22 18:30 | 0:30 | [6 empty] | Productive |  |  | - WASH DOWN WITH 8.5 " MOTORIZED BHA FROM 3448 M TO 3507.6 M. - TAGGED CEMENT AT 3507.6 M WITH 10KLBS.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 20:00 | 1:30 | [6 empty] | Productive |  |  | CIRCULATION BOTTOM UP VOLUME WITH 440 GPM, 1900 PSI, MEANWHILE RECIPROCATING STRING RU SURFACE LINE FOR CIT, SES AND FOSV BELOW
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-22 20:30 | 0:30 | [6 empty] | Productive |  |  | - TBT FOR 9 5/8" CIT - FLUSH SURFACE LINES - PRESSURE TEST SURFACE LINE TO 300/8500 PSI, OK
GZR-401 |  | RIG |  | 2023-05-22 20:30 | 2023-05-22 22:00 | 1:30 | [6 empty] | Productive |  |  | ****9.5/8"CASING INTEGRITY TEST (FIRST ATTEMPT) **** - PRESSURE UP 9 5/8" CSG AT SLOW PUMP RATE 0.5 BBL/MIN TO 8000 PSI - OBSERVED BUILD UP RATE DECLINED AFTER REACHING 7400 PSI. PRESSURE DROP RATE ~ 200-240 PSI/MIN - PUMPED VOLUME= 21 BBL, BLED VOLUME = 16 BBL. - CHECKED SURFACE LINES, NO VISIBLE LEAKS, NO INCREASE IN TRIP TANK AND NO SIGNS OF LEAKS THROUGH BLED OFF LINE. - TRAPPED 7600 PSI IN CHOKE LINE, MONITOR FOR 10 MINS, HOLDING Page 81 of 120
GZR-401 |  | RIG |  | 2023-05-22 22:00 | 2023-05-22 22:15 | 0:15 | [6 empty] | Productive |  |  | - PRESSURE TEST SURFACE LINE AGNAIST FOSV AND AUTO IBOP TO 300/8500 PSI, OK
GZR-401 |  | RIG |  | 2023-05-22 22:15 | 2023-05-23 | 1:45 | [6 empty] | Productive |  |  | ****9.5/8"CASING INTEGRITY TEST (SECOND ATTEMPT) **** - PRESSURE UP 9 5/8" CSG AT SLOW PUMP RATE 0.5 BBL/MIN TO 6000 PSI - OBSERVED BUILD UP RATE DECLINED AFTER REACHING 4500 PSI. PRESSURE DROP RATE ~ 120-160 PSI/MIN - PUMPED VOLUME= 20 BBL, BLED VOLUME = 16 BBL. - CHECKED SURFACE LINES, NO VISIBLE LEAKS, NO INCREASE IN TRIP TANK AND NO SIGNS OF LEAKS THROUGH BLED OFF LINE. - RIG DOWN SIDE ENTRY SUB TO ELIMINATE POSSIBLE LEAKS FROM AUTO IBOP - RIG UP CIRCULATING HEAD AND CONNECT SURFACE LINE DIRECTLY TO CIRCULATING HEAD
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:30 | 1:30 | [6 empty] | Productive |  |  | ****9.5/8"CASING INTEGRITY TEST (THIRD ATTEMPT) **** - PRESSURE UP 9 5/8" CSG AT SLOW PUMP RATE 0.5 BBL/MIN TO 6500 PSI - OBSERVED BUILD UP RATE DECLINED AFTER REACHING 4500 PSI. PRESSURE DROP RATE ~ 120-130 PSI/MIN - PUMPED VOLUME= 19 BBL, BLED VOLUME = 15 BBL. - CHECKED SURFACE LINES, NO VISIBLE LEAKS, NO INCREASE IN TRIP TANK AND NO SIGNS OF LEAKS THROUGH BLED OFF LINE.
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 02:00 | 0:30 | [6 empty] | Productive |  |  | - HOLD TBT AND DISCUSS THE ISSUE WITH TEAM - PRESSURE TEST CEMENT UNIT TO 8500 PSI, GOOD TEST - CLOSE MANUAL CHOKE VALVE.
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 03:30 | 1:30 | [6 empty] | Productive |  |  | ****9.5/8"CASING INTEGRITY TEST **** - PRESSURE UP 9 5/8" CSG AT SLOW PUMP RATE 1.0 BBL/MIN TO 8200 PSI - MONITOR PRESSURE FOR 33 MINS, DROP RATE 2-3 PSI/MIN IN LAST 15 MINS, GOOD TEST - PUMPED VOLUME= 14 BBL, BLED VOLUME = 14 BBL. - RIG DOWN SURFACE LINES Page 82 of 120
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 05:15 | 1:45 | [6 empty] | Productive |  |  | CONDUCT ,D4 & D5 DRILLS WITH CREW ( A ). - INSTALL FOSV, GRAY VALVE & 1 STD 5'' DP. CONNECT TDS - CLOSE ANNULAR PREVENTER & OPEN HCR & STRIPPING BOTTLE - REDUCE ANNULAR PRESSURE TO 600 PSI. - RAISE CASING PRESSURE TO 400 PSI. - PREPARED TOOL JOINT FOR STRIPPING. - STRIPPED IN WHILE MAINTAINING CONSTANT CASING PRESSURE. - STRIP TOOL JOINT WITH 50 KLB WEIGHT. - PERFORMED D4 DRILL WITH CREW, GOOD UNDERSTANDING AND CONTROL ON CHOKE. - HELD AFTER ACTION REVIEW WITH CREW. CREW PERFORMED WELL IN DISCUSSION AND THROUGHOUT THE DRILL. - BLEED BACK CSG PRESSURE TO ZERO. - FLUSH MGS AS PER ABRAJ PROCEDURES - LINE UP FOR DRILLING.
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 05:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK PRIOR DRILLING SHOE TRACK - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 05:30 | 2023-05-22 06:30 | 1:00 | [6 empty] | Productive |  |  | WASH DOWN FROM 3476 M TO 3504 M TAKE SCRS WITH MP 2 & 3. RECORDED PUMP OFF FINGERPRINT AT 550 GPM: 21 BBLS & 400 GPM : 19 BBLS (EX-LOG) AT 580 GPM: 24 BBLS & 400 GPM : 22 BBLS (RIG)
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 08:45 | 2:15 | [6 empty] | Productive |  |  | - DRILL CEMENT PLUGS AND FLOAT COLLAR FROM 3507.6 M TO 3509 M(30 MINS) FR 400 GPM, SPP 1650-1770 PSI, WOB 10-14 KLBS, RPM 40 , TRQ 5-7 KFT.LBS. - DRILL SHOE TRACKFROM 3509 M TO 3546 M(60 MINS) FR 400 GPM, SPP 1600-1700 PSI, WOB 3-8 KLBS, RPM 40 , TRQ 5-7 KFT.LBS. - DRILL REAMER SHOEFROM 3546 M TO 3547.5 M(30 MINS) FR 400 GPM, SPP 1600-1800 PSI, WOB 5-12 KLBS, RPM 40 , TRQ 5- 9 KFT.LBS. - CIRCULATE 5 MINS AT SHOE WIPE THROUGH FLOAT SHOE 2 TIMES WITH AND WITHOUT ROTATION TAKE UP/DOWN PARAMETERS WITH AND WITHOUT ROTATION Page 83 of 120
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 16:15 | 7:30 | [6 empty] | Productive |  |  | - CLEARED RAT HOLE FROM 3547.5 M TO 3619 M FR 510-550 GPM, SPP 2600-2700 PSI, WOB 1-5 KLBS, RPM 40 , TRQ 5 - 8 KFT.LBS. - AFTER REAMING 8 M OF RAT HOLE AND PUMP 20 BBLS HI-VIS. - AT 3619 M CIRCUALTE BOTTOM UP MEANWHILE RECIPROCATING THE STRING - OBSERVED 5% CAVING AT SHAKER FROM GHARIF FORMATION
GZR-401 |  | RIG |  | 2023-05-22 16:15 | 2023-05-22 16:30 | 0:15 | [6 empty] | Productive |  |  | - CONDUCTED FLOW CHECK PRIOR DRILLING NEW FORMATION. WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 17:15 | 0:45 | [6 empty] | Productive |  |  | DRILL OUT NEW FORMATION FROM 3619 M TO 3624 M. WOB: 15-17 KLB, FLOW RATE:400 GPM,SPP:1800-1900 PSI, SURFACE PRM 40, TRQ 7-9 KFT.LBS,DIFF PRESSURE 200 PSI.
GZR-401 |  | RIG |  | 2023-05-22 17:15 | 2023-05-22 18:45 | 1:30 | [6 empty] | Productive |  |  | CIRCULATE BOTTOMS UP WITH 400-500 GPM, SPP 1700-2600 PSI, RPM 45 , TRQ 5 - 7 KFT.LBS NOTE: - OBSERVED PACK OFF TENDENCY WHEN BIT AT NEW FORMATION INTERVAL, PRESSURE INCREASED FROM 1700 PSI TO 2600 PSI, TQ BECOME ERRATIC AND REACHED 14 KFT.LB - KEPT CIRCULATION UNTIL STABLE PRESSURE AND TORQUE WAS SEEN.
GZR-401 |  | RIG |  | 2023-05-22 18:45 | 2023-05-22 19:15 | 0:30 | [6 empty] | Productive |  |  | PUMP OUT AND RACK PACK STANDS FROM 3624 M TO 3533 M, (INSIDE 9 5/8" CSG)
GZR-401 |  | RIG |  | 2023-05-22 19:15 | 2023-05-22 19:30 | 0:15 | [6 empty] | Productive |  |  | R/U SURFACE LINES TO STRING.
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 19:45 | 0:15 | [6 empty] | Productive |  |  | - PJSM WITH ALL CREW PRIOR FIT P/T.
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-22 20:00 | 0:15 | [6 empty] | Productive |  |  | - FLUSH AND P/T SURFACE LINES TO 300/3500 PSI FOR 5MIN EACH-OK.
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-22 21:00 | 1:00 | [6 empty] | Productive |  |  | ************AL KHALATA FORMATION INTEGRITY TEST (MW=1.25 SG) ************* PERFORM FORMATION INTEGRITY TEST - PUMP AT 0.5 BPM UP TO 2473 PSI (1.74 SG EMW). - SHUT IN WELL & MONITOR PRESSURE FOR 30 MIN - INITIAL FIT SURFACE PRESSURE ACHIEVED = 2487 PSI - FINAL FIT SURFACE PRESSURE = 2176 PSI - MW IN/OUT = 1.25 SG - SHOE = 3547 M - EQUIVALENT MUD WEIGHT = 1.743 SG - VOLUME PUMPED = 4.9 BBLS - VOLUME BLED BACK = 4.5 BBLS
GZR-401 |  | RIG |  | 2023-05-22 21:00 | 2023-05-22 21:15 | 0:15 | [6 empty] | Productive |  |  | R/D SURFACE LINES AND LINE UP TO DRILLING MODE Page 84 of 120
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 22:15 | 1:00 | [6 empty] | Productive |  |  | PRECAUTIONARY REAM DOWN FROM 3533 M TO 3624 M - PUMP 40 BBL HIVIS PRIOR RESUME DRILLING 8.5" HOLE.
GZR-401 |  | RIG |  | 2023-05-22 22:15 | 2023-05-23 | 1:45 | [6 empty] | Productive |  |  | RESUME DRILLING 8-1/2" HOLE SECTION FROM 3624 M TO 3639 M DRILLING PARAMTERS:FR: 510 GPM, SPP: 2600-2700 PSI,DIFF PRESSURE 120-250 PSI , ROT: 40 RPM, TQ: 7-8K FT-LBS, WOB: 20-22 KLBS. AVG ROP: 11.9 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3639 M TO 3685 M DRILLING PARAMTERS:FR: 510 GPM, SPP: 2600-2700 PSI,DIFF PRESSURE 120-250 PSI , ROT: 40 RPM, TQ: 7-8K FT-LBS, WOB: 20-22 KLBS. AVG ROP: 8.6 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 13:00 | 7:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3685 M TO 3735 M DRILLING PARAMTERS:FR: 510 GPM, SPP: 2600-2700 PSI,DIFF PRESSURE 120-200 PSI , ROT: 40 RPM, TQ: 7-8K FT-LBS, WOB: 20-22 KLBS. AVG ROP: 7.5 M/HR
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 13:15 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS
GZR-401 |  | RIG |  | 2023-05-22 13:15 | 2023-05-23 | 10:45 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3735 M TO 3780 M DRILLING PARAMTERS:FR: 510 GPM, SPP: 2600-2700 PSI,DIFF PRESSURE 120-200 PSI , ROT: 40 RPM, TQ: 7-8K FT-LBS, WOB: 20-22 KLBS. AVG ROP: 4.5 M/HR NOTE: AT 19:05 HRS, PERFORM TDS TORQUE CHECK (10 MINS) AT 19:15 HRS, DUMP AND FILL SAND TRAP. DRILLING SUMMARY ================== FOOTAGE DRILLED: 165 M DAILY BIT HRS: 22.45 HR AVG ROP: 6.28 M/HR Page 85 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 04:30 | 4:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3780 M TO 3792 M DRILLING PARAMTERS:FR: 510-530 GPM, SPP: 2800-2950 PSI,DIFF PRESSURE 120-200 PSI , ROT: 40-50 RPM, TQ: 7-8K FT-LBS, WOB: 22-32 KLBS. AVG ROP: 3.0 M/HR NOTE: - TOP OF SAFIQ AT 3781 M - AT 04:20 HRS, GREASE WASH PIPE.
GZR-401 |  |  |  | 2023-05-22 04:30 | 2023-05-22 06:15 | 1:45 |  |  |  | RREP |  |  | Non-Productive |  |  | AFTER CONNECTION, OBSERVED HIGH SPP, REACHED TO 3400 PSI WITH 400 GPM. INVISTIGATE AND FOUND THAT AUTO IBOP IS NOT FULLY OPEN. - RACK BACK STAND AND CHECK AUTO IBOP, FOUND CRANK ROLLER BROKEN IN BOTH SIDES. - RACK BACK STAND FROM 3792 M TO 3763 M. - CHANGE OUT AUTO IBOP CRANKS.
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 21:45 | 15:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3792 M TO 3835 M DRILLING PARAMETERS:FR: 510-540 GPM, SPP: 2900-3000 PSI,DIFF PRESSURE 80-160 PSI , ROT: 50-60 RPM, TQ: 7-8K FT-LBS, WOB: 27-35 KLBS. AVG ROP: 3.1 M/HR - APPLY DRILL OFF TEST SEVERAL TIME TO IMPROVE THE ROP - AVG ROP LAST 6 HRS, 2.0 M/HR - DECISION MADE TO POOH FOR BIT CHANGE. - RECORD SCR NOTE: - AT 14:00 HRS, GREASE WASH PIPE.
GZR-401 |  | RIG |  | 2023-05-22 21:45 | 2023-05-22 22:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK- WELL STATIC , MEANWHILE PJSM PRIOR POOH 8.1/2" BHA.
GZR-401 |  | RIG |  | 2023-05-22 22:00 | 2023-05-22 23:00 | 1:00 | [6 empty] | Productive |  |  | POOH 8.1/2" BHA#1 ON ELEVATORFROM 3835 M TO 3531 M NOTES: - MONITOR DISPLACEMENT ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 23:00 | 2023-05-22 23:30 | 0:30 | [6 empty] | Productive |  |  | FLOW CHECK AT SHOE- WELL STATIC INSTALL DP WIPER AND AIR SLIPS
GZR-401 |  | RIG |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 | [6 empty] | Productive |  |  | POOH 8.1/2" BHA#1 ON ELEVATORFROM 3531 M TO 3272 M NOTES: - MONITOR DISPLACEMENT ON TRIP TANK WITH TRIP SHEET Page 86 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 04:30 | 4:30 | [6 empty] | Productive |  |  | POOH 8.1/2" BHA#1 ON ELEVATORFROM 3272 M TO 1711 M NOTES: - MONITOR DISPLACEMENT ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 04:45 | 0:15 | [6 empty] | Productive |  |  | OBSERVED BROKEN BOLT ON IRON ROUGHNECK CYLINDER
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 06:00 | 1:15 | [6 empty] | Productive |  |  | POOH 8.1/2" BHA#1 ON ELEVATORFROM 1711 M TO 1280 M NOTES: - MONITOR DISPLACEMENT ON TRIP TANK WITH TRIP SHEET - BREAK OUT CONNECTION USING MANUAL TONG.
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 08:00 | 2:00 | [6 empty] | Productive |  |  | POOH 8.1/2" BHA#1 ON ELEVATORFROM 1280 M TO 535 M (TOP OF BHA). NOTES: - MONITOR DISPLACEMENT ON TRIP TANK WITH TRIP SHEET - BREAK OUT CONNECTION USING MANUAL TONG.
GZR-401 |  | RIG |  | 2023-05-22 08:00 | 2023-05-22 08:15 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK WELL AT TOP OF BHA-OK WELL STATIC.
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 13:00 | 4:45 | [6 empty] | Productive |  |  | CONT. POOH 8.5" BHA #1 ON ELEVATOR FROM 535 M TO SURFACE. - R/B 10 STANDS OF HWDP. - R/B 1 STAND OF 6.1/2'' DC - LAYD DOWN 6.3/8'' JAR - R/B 7X6.1/2'' DC STANDS - LAY DOWN 8.1/4" S. STABILIZER - LAY DOWNFILTER SUB - LAY DOWN 1 X6.1/2" DC SINGLE - -LAY DOWN 8.1/4" S. STABILIZER - LAY DOWN SS100 MUD MOTOR. - LAY DOWN 8.5" NOV TKC73 BIT , DULL GRADING 2-2-CT-N-X-I-WT-PR NOTE: - MONITORED WELL ON TRIP TANK WITH TRIP SHEET. - BREAK OUT CONNECTION USING MANUAL TONG. - AT 08:10 HANDOVER, TBT - AT 09:20 R/D AIR SLIPS AND CHECK KEMS OFFLINE: - CONDUCT SURVEY WITH HLB TEAM FOR CORING OPERATION.
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 13:30 | 0:30 | [6 empty] | Productive |  |  | CLEAN & CLEAR RIG FLOOR TBT FOR P/U AND RUN 8.5'' BHA#2 Page 87 of 120
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 17:45 | 4:15 | [6 empty] | Productive |  |  | P/U & M/U 8.5" MOTOR BHA #2 TO 283 M - 8.5" TKC66 BIT, NOZZLES:6X14, S/N S294742 - 7" NITRO FORCE MOTOR(0.23 REV/GAL) - 8 1/4" STRING STAB - 1 x 6-1/2'' DC JOINT - FILTER SUB - 8 1/4" STRING STAB W/ TOTCO RING - 21 x 6-1/2'' DC JOINT - 6-1/2'' JAR - 3 x 6-1/2'' DC JOINT - 3 x 5'' HWDP JOINTS - WEIGHT BELOW JARS :55 KLBS - TOTAL WEIGHT OF BHA : 95 KLB NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 450 GPM - SPP 600 PS 550 GPM - SPP 820 PSI - MONITOR DISPLACEMENT THROUGH TRIP TANK - AT 17:45 RIG UP AIR SLIPS
GZR-401 |  | RIG |  | 2023-05-22 17:45 | 2023-05-22 18:15 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS MEANWHILE: REMOVE BROKEN BOLT FROM IRON ROUGHNECK AND INSTALL NEW ONE.
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-22 19:00 | 0:45 | [6 empty] | Productive |  |  | CONT. RIH 8.5" MOTOR BHA #2 FROM 283 M TO 537 M - 27 x 5'' HWDP JOINTS (9 STANDS FROM DERRICK)
GZR-401 |  | RIG |  | 2023-05-22 19:00 | 2023-05-22 23:45 | 4:45 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 537 M TO 3330 M - RIH WITH 5'' 19.5 PPF DP STANDS FROM DERRICK - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 23:45 | 2023-05-23 | 0:15 | [6 empty] | Productive |  |  | FUNCTION TEST BOP FROM DRILLER PANEL
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:15 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D1& D6 DRILL KICK WHILE TRIPPING WITH CREW # A - DRILLER AND ML NOTICE THE INCREASE IN TRIP TANK - GOOD RESPONSE FROM CREW IN SECURING THE WELL IN LESS THAN 2 MINS. - HAD AAR
GZR-401 |  | RIG |  | 2023-05-22 00:15 | 2023-05-22 01:00 | 0:45 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 3330 M TO 3593 M - RIH WITH 5'' 19.5 PPF DP STANDS FROM DERRICK - MONITORED WELL ON TRIP TANK WITH TRIP SHEET Page 88 of 120
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 01:30 | 0:30 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 3330 M TO 3593 M - SINGLE IN WITH 5'' 25.6 PPF DP JOINTS FROM PIPE CAT (12 JOINTS) - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 02:30 | 1:00 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 3593 M TO 3824 M - RIH WITH 5'' 25.6 PPF DP STANDS FROM DERRICK - MONITORED WELL ON TRIP TANK WITH TRIP SHEET - WASH DOWN LAST STAND - RECORD SCR
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 02:45 | 0:15 | [6 empty] | Productive |  |  | RECORDED PUMP OFF FINGERPRINT AT 480 GPM: 27 BBLS & 550 GPM : 29 BBLS (EX-LOG) AT 480 GPM: 28 BBLS & 550 GPM : 28 BBLS (RIG)
GZR-401 |  | RIG |  | 2023-05-22 02:45 | 2023-05-22 03:15 | 0:30 | [6 empty] | Productive |  |  | BED ON BIT AND RESUME DRILLING 8-1/2" HOLE SECTION FROM 3835 M TO 3836 M DRILLING PARAMTERS:FR: 490 GPM, SPP: 2300, ROT: 30 RPM, TQ: 7-8K FT-LBS, WOB: 1-15 KLBS. NOTE: - AT 3834 M, OBSERVED STICK/SLIP AND STRING STALL, PICK UP OFF BOTTOM AND REAM DOWN CARFULLY
GZR-401 |  | RIG |  | 2023-05-22 03:15 | 2023-05-22 03:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK DUE TO +10 BBL GAIN IN ACTIVE SYSTEM - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 06:00 | 2:30 | [6 empty] | Productive |  |  | RESUME DRILLING 8-1/2" HOLE SECTION FROM 3836 M TO 3890 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 2700-3150 PSI,DIFF PRESSURE 300-550 PSI , ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 20-30 KLBS. AVG ROP: 29 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 07:30 | 1:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3890 M TO 3937 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 3100-3200 PSI,DIFF PRESSURE 300-550 PSI , ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 20-30 KLBS. AVG ROP: 30 M/HR Page 89 of 120
GZR-401 |  | RIG |  | 2023-05-22 07:30 | 2023-05-22 11:00 | 3:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3937 M TO 3980 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2800-3100 PSI,DIFF PRESSURE 180-300 PSI , ROT: 45 RPM, TQ: 9-12 K FT-LBS, WOB: 20-30 KLBS. AVG ROP: 12.3 M/HR NOTE: - TOP OF GHUDUN FORMATION AT 3937 M
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 11:30 | 0:30 | [6 empty] | Productive |  |  | PERFORMED KICK WHILE DRILLING DRILL (D2) AND INFLUX DETECTION DRILL (D6) WITH CREW B, GOOD RESPONSE FROM DR AND MUDLOGGER IN DETECTING THE INCREASE IN ACTIVE SYSTEM. - DRILLER LINE UP TRIP TANK FOR FLOW CHECK MONITORING THE WELL VISUALLY, DR DETECTING THE INCREASE IN TRIP TANK. - DRILLER SECURING THE WELL AS PER PROCEDURE - AAR WITH CREW IN RIG FLOOR.
GZR-401 |  | RIG |  | 2023-05-22 11:30 | 2023-05-23 | 12:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 3980 M TO 4095 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2900-3200 PSI,DIFF PRESSURE 180-500 PSI , ROT: 45 RPM, TQ: 9-12 K FT-LBS, WOB: 20-33 KLBS. AVG ROP: 10.3 M/HR OFFLINE: - CONDUCTED SAFETY MEETING WITH CREW B - PERFORM H2S & FIRE DRILL WITH CREW B DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 260 M DAILY BIT HRS: 17.41 HR AVG ROP: 14.93 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4095 M TO 4120 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2900-3200 PSI,DIFF PRESSURE 180-400 PSI , ROT: 45 RPM, TQ: 9-12 K FT-LBS, WOB: 33-35 KLBS. AVG ROP: 4.3 M/HR NOTE: - AT 03:20 HRS, GREASE WASH PIPE Page 90 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 16:00 | 10:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4120 M TO 4168 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2950-3100 PSI,DIFF PRESSURE 180-400 PSI , ROT: 45-50 RPM, TQ: 9-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 4.9 M/HR OFFLINE: - CONDUCTED DROP INSPECTION FOR AREA #1&2
GZR-401 |  | RIG |  | 2023-05-22 16:00 | 2023-05-22 16:30 | 0:30 | [6 empty] | Productive |  |  | SERVICE & INSPECTION TDS
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-23 | 7:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4168 M TO 4195 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2950-3100 PSI,DIFF PRESSURE 180-400 PSI , ROT: 45-50 RPM, TQ: 9-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 3.62 M/HR NOTE: - AT 16:25 HRS TAKE SCR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 100 M DAILY BIT HRS: 22.81 HR AVG ROP: 4.38 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 08:45 | 8:45 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4195 M TO 4226 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 2950-3100 PSI,DIFF PRESSURE 180-400 PSI , ROT: 45-50 RPM, TQ: 9-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 3.8 M/HR
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 09:00 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS
GZR-401 |  | RIG |  | 2023-05-22 09:00 | 2023-05-22 21:15 | 12:15 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4226 M TO 4265 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3200 PSI,DIFF PRESSURE 170-400 PSI , ROT: 45-50 RPM, TQ: 8-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 3.35 M/HR
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 21:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK DUE TO +10 BBL INCREASE IN ACTIVE SYSTEM-WELL STATIC FOUND THE INCREASE WAS DUE TO FUNCTION TESTING OF VACUUM DEGASSER. Page 91 of 120
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-23 | 2:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4265 M TO 4272 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3200 PSI,DIFF PRESSURE 170-400 PSI , ROT: 45-50 RPM, TQ: 8-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 3.41 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 77 M DAILY BIT HRS: 22.16 HR AVG ROP: 3.47 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4272 M TO 4288 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3200 PSI,DIFF PRESSURE 100-400 PSI , ROT: 45-50 RPM, TQ: 8-12 K FT-LBS, WOB: 35-40 KLBS. AVG ROP: 2.71 M/HR NOTE: - AT 04:20 HRS, GREASE WASH PIPE
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 15:30 | 9:30 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4288 M TO 4312 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3100 PSI,DIFF PRESSURE 90-200 PSI , ROT: 45-50 RPM, TQ: 8-11 K FT-LBS, WOB: 35-43 KLBS. AVG ROP: 2.53 M/HR
GZR-401 |  | RIG |  | 2023-05-22 15:30 | 2023-05-22 15:45 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS
GZR-401 |  | RIG |  | 2023-05-22 15:45 | 2023-05-23 | 8:15 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4312 M TO 4332 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3100 PSI,DIFF PRESSURE 90-200 PSI , ROT: 45-55 RPM, TQ: 8-11 K FT-LBS, WOB: 35-45 KLBS. AVG ROP: 2.5 M/HR: DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 60 M DAILY BIT HRS: 22.82 HR AVG ROP: 2.63 M/HR Page 92 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4332 M TO 4343 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3100 PSI,DIFF PRESSURE 90-200 PSI , ROT: 45-55 RPM, TQ: 8-11 K FT-LBS, WOB: 40-45 KLBS. AVG ROP: 2.0 M/HR NOTE: - AT 04:45 HRS, GREASE WASH PIPE
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4343 M TO 4369 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3150 PSI,DIFF PRESSURE 90-160 PSI , ROT: 45-55 RPM, TQ: 8-10 K FT-LBS, WOB: 40-45 KLBS. AVG ROP: 2.2 M/HR OFFLINE: - CONDUCTED FIRE & H2S DRILL FOR CREW C
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8-1/2" HOLE SECTION FROM 4369 M TO 4377 M DRILLING PARAMETERS:FR: 530 GPM, SPP: 3000-3150 PSI,DIFF PRESSURE 90-150 PSI , ROT: 45-55 RPM, TQ: 7.6-9 K FT-LBS, WOB: 42-45 KLBS. AVG ROP: 1.6 M/HR - DECISION MADE TO POOH DUE TO SLOW ROP NOTE: - AT 19:00 HRS, GREASE WASH PIPE DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 45 M DAILY BIT HRS: 22.14 HR AVG ROP: 2 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:15 | 0:15 | [6 empty] | Productive |  |  | RECORD SCR RACK BACK STAND.
GZR-401 |  | RIG |  | 2023-05-22 00:15 | 2023-05-22 00:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK, WELL STATIC. INSTALL DP WIPER & AIR SLIPS
GZR-401 |  | RIG |  | 2023-05-22 00:30 | 2023-05-22 01:00 | 0:30 | [6 empty] | Productive |  |  | DROP GYRO INTO DRILL STRING WAIT FOR GYRO TOOL TO LAND INTO TOTCO RING.
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 01:30 | 0:30 | [6 empty] | Productive |  |  | POOH WITH 8.1/2" MOTORIZED BHA#2 ON ELEVATOR FROM 4369 M TO 4195 M. - MONITOR DISPLACEMENT ON TRIP TANK. Page 93 of 120
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 01:45 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D1 DRILL KICK WHILE TRIPPING WITH CREW # B - GOOD RESPONSE FROM CREWIN SECURING THE WELL IN LESS THAN 2 MINS. - HAD AN AFTER ACTION REVIEW AND DISCUSSED COMPLICATED SCENARIO, GOOD UNDERSTANDING FROM DRILLER AND CREW.
GZR-401 |  | RIG |  | 2023-05-22 01:45 | 2023-05-22 03:45 | 2:00 | [6 empty] | Productive |  |  | POOH WITH 8.1/2" MOTORIZED BHA#2 ON ELEVATOR FROM 4195 M TO 3525 M. ( INSIDE 9-5/8" CSG SHOE) - MONITOR DISPLACEMENT ON TRIP TANK. NOTE: IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 5" 25.6# STANDS #13,12,11,1 AND 5" 19.5# STANDS #106,105
GZR-401 |  | RIG |  | 2023-05-22 03:45 | 2023-05-22 04:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 04:15 | 0:15 | [6 empty] | Productive |  |  | PUMP 30 BBL OF 1.5 SG SLUG
GZR-401 |  | RIG |  | 2023-05-22 04:15 | 2023-05-22 04:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AFTER SLUG - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 04:30 | 2023-05-22 05:15 | 0:45 | [6 empty] | Productive |  |  | SLIP DRILL LINE - PARKED TDS AND HANG BLOCK . - SLIP 12 M OF DRILL LINE - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
GZR-401 |  | RIG |  | 2023-05-22 05:15 | 2023-05-22 09:15 | 4:00 | [6 empty] | Productive |  |  | POOH WITH 8.1/2" MOTORIZED BHA#2 ON ELEVATOR FROM 3525 M TO 2494 M. - MONITORED WELL ON TRIP TANK WITH TRIP SHEET. NOTE: - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 5" 19.5# STANDS #104 - #84 - AT 08:20 HRS TBT & HANDOVER
GZR-401 |  | RIG |  | 2023-05-22 09:15 | 2023-05-22 09:30 | 0:15 | [6 empty] | Productive |  |  | CONDUCTED D1 DRILL KICK WHILE TRIPPING WITH CREW # C - GOOD RESPONSE FROM CREWIN SECURING THE WELL IN LESS THAN 2 MINS. - HAD AN AFTER ACTION REVIEW AND DISCUSSED COMPLICATED SCENARIO, GOOD UNDERSTANDING FROM DRILLER AND CREW. Page 94 of 120
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 15:00 | 5:30 | [6 empty] | Productive |  |  | POOH WITH 8.1/2" MOTORIZED BHA#2 ON ELEVATOR FROM 2494 M TO 563 M. (TOP OF BHA). - MONITORED WELL ON TRIP TANK WITH TRIP SHEET. NOTE: - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 5" 19.5# STANDS #77-#36
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 15:15 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK WELL AT TOP OF BHA-OK WELL STATIC.
GZR-401 |  | RIG |  | 2023-05-22 15:15 | 2023-05-22 20:00 | 4:45 | [6 empty] | Productive |  |  | CONT. POOH 8.5" BHA #2 ON ELEVATOR FROM 535 M TO SURFACE. - LAY DOWN 5 STAND OF HWDP - R/B 5 STANDS OF HWDP. - R/B 1 STAND OF 6.1/2'' DC - LAY DOWN 6.3/8'' JAR - R/B 7X6.1/2'' DC STANDS - LAY DOWN 8.1/4" S. STABILIZER ( RETRIEVED GYRO) - LAY DOWNFILTER SUB - LAY DOWN 1 X6.1/2" DC SINGLE - -LAY DOWN 8.1/4" S. STABILIZER - LAY DOWN NITRO FORCE MOTOR - LAY DOWN 8.5" NOV TKC66 BIT, DULL GRADING 2-2-WT-A-X-I-CT-PR NOTE: - MONITORED WELL ON TRIP TANK WITH TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-22 20:15 | 0:15 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR
GZR-401 |  | RIG |  | 2023-05-22 20:15 | 2023-05-22 20:30 | 0:15 | [6 empty] | Productive |  |  | RETRIEVED WEAR BUSHING
GZR-401 |  | RIG |  | 2023-05-22 20:30 | 2023-05-22 21:15 | 0:45 | [6 empty] | Productive |  |  | MAKE UP CAMERON JETTING TOOL JET WASH BOP FUNCTION BOP'S AND JET SEAL ASSEMBLY PROFILE.
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 22:15 | 1:00 | [6 empty] | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY
GZR-401 |  |  |  | 2023-05-22 22:15 | 2023-05-23 | 1:45 |  |  |  | SFAL |  |  | Non-Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI - OBSERVED PRESSURE NOT HOLDING - FOUND FITTING OF TEST LINE LEAKING. FIX THE SAME - ATTEMPTED TO PERFORM TEST #1: LPR AND FOSV #1 TO 250-350 PSI. - OBSERVED PRESSURE NOT HOLDING - FOUND SES SEAL LEAKING. FIXED THE SAME Page 95 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 03:00 | 3:00 | [6 empty] | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK.
GZR-401 |  |  |  | 2023-05-22 03:00 | 2023-05-22 04:00 | 1:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | ATTEMPTED TO PERFORM TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 250-350 PSI. - OBSERVED PRESSURE NOT HOLDING. - FOUND NRV LEAKING REPLACE THE SAME.
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 07:15 | 3:15 | [6 empty] | Productive |  |  | CONT. PRESSURE TEST BOP AS PER ABRAJ PROCEDURE - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING. - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD. - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), LOW 250-350 PSI-LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. NOTE: - TEST #6 TOOK LONGER TIME THAN USUAL TO GET GOOD TEST. PRESSURE NOT HOLDING FROM FIRST ATTEMPT
GZR-401 |  | RIG |  | 2023-05-22 07:15 | 2023-05-22 07:30 | 0:15 | [6 empty] | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
GZR-401 |  | RIG |  | 2023-05-22 07:30 | 2023-05-22 07:45 | 0:15 | [6 empty] | Productive |  |  | - INSTALLED WEAR BUSHING
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 08:15 | 0:30 | [6 empty] | Productive |  |  | CREW SHIFT HANDOVER & TBT PRIOR P/U 8.5'' BHA#3 Page 96 of 120
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 12:30 | 4:15 | [6 empty] | Productive |  |  | P/U & M/U 8.5" MOTOR BHA #3 TO 538 M - 8.5" TKC66 BIT, NOZZLES:6X14, S/N S295210 - 7" NITRO FORCE MOTOR(0.23 REV/GAL) - 8 1/4" STRING STAB - 1 x 6-1/2'' DC JOINT - FILTER SUB - 8 1/4" STRING STAB W/ TOTCO RING - 21 x 6-1/2'' DC JOINT - 6-1/2'' JAR - 3 x 6-1/2'' DC JOINT - 15 x 5'' HWDP JOINTS FROM DERRICK - 15 X 5'' HWDP JOINTS SINGLING - WEIGHT BELOW JARS :55 KLBS - TOTAL WEIGHT OF BHA : 95 KLB NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 450 GPM - SPP 550 PS 550 GPM - SPP 800 PSI - MONITOR DISPLACEMENT THROUGH TRIP TANK
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 20:15 | 7:45 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8.5'' MOTOR BHA FROM 538 M TO 4344 M - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
GZR-401 |  | RIG |  | 2023-05-22 20:15 | 2023-05-22 20:30 | 0:15 | [6 empty] | Productive |  |  | - FUNCTIO TEST BOP
GZR-401 |  | RIG |  | 2023-05-22 20:30 | 2023-05-22 20:45 | 0:15 | [6 empty] | Productive |  |  | - RECORD SCR - WASH DOWN LAST STAND
GZR-401 |  | RIG |  | 2023-05-22 20:45 | 2023-05-22 21:00 | 0:15 | [6 empty] | Productive |  |  | RECORDED PUMP OFF FINGERPRINT AT 450 GPM: 29 BBLS & 550 GPM : 32 BBLS (EX-LOG) AT 450 GPM: 26 BBLS & 550 GPM : 30 BBLS (RIG)
GZR-401 |  | RIG |  | 2023-05-22 21:00 | 2023-05-23 | 3:00 | [6 empty] | Productive |  |  | BED ON BIT AND RESUME DRILLING 8-1/2" HOLE SECTION FROM 4377 M TO 4394 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 3000-3250, ROT: 45-50 RPM, TQ: 8-12 K FT-LBS, WOB: 10-32 KLBS, DIFF PRESSURE 50-250 PSI DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 17 M DAILY BIT HRS: 2.88 HR AVG ROP: 5.9 M/HR Page 97 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4394 M TO 4412 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 3000-3300, ROT: 45-50 RPM, TQ: 8-11 K FT-LBS, WOB: 30-37 KLBS DIFF PRESSURE 120-250 PSI AVG ROP: 3.5 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4412 M TO 4451 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 3100-3250, ROT: 45-50 RPM, TQ: 8-11 K FT-LBS, WOB: 38-40 KLBS DIFF PRESSURE 100-250 PSI AVG ROP: 3.3 M/HR NOTE: - AT 10:30 HRS GREASE WASHPIPE
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4451 M TO 4480 M DRILLING PARAMTERS:FR: 530 GPM, SPP: 3150-3550, ROT: 45-60 RPM, TQ: 8-12 K FT-LBS, WOB: 38-42 KLBS DIFF PRESSURE 100-500 PSI - TOP OF BARAKAT FORMATION AT 4468 M - AVG ROP: 5.1 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 85 M DAILY BIT HRS: 22.2 HR AVG ROP: 3.83 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 12:30 | 12:30 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4480 M TO 4543 M DRILLING PARAMTERS: FR: 530 GPM, SPP: 3200-3550, ROT: 60-65 RPM, TQ: 8-12 K FT-LBS, WOB: 40-43 KLBS DIFF PRESSURE 100-450 PSI - TOP OF MABROUK FORMATION AT 4530 M - AVG ROP: 5.25 M/HR NOTE: - AT 01:00 HRS GREASE WASHPIPE
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 13:00 | 0:30 | [6 empty] | Productive |  |  | - SERVICE TDS AND PERFORM DROP INSPECTION ON AREAS 1&2&3 OFFLINE: - FLOW CHECK Page 98 of 120
GZR-401 |  |  |  | 2023-05-22 13:00 | 2023-05-22 14:30 | 1:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | - RACK BACK STAND - TBT PRIOR WL GYRO RIG UP WIRELINE EQUIPMENT AND GYRO TOOL STRING - RIG UP THE SHEAVES ON RIG FLOOR AND IN THE ELEVATOR - PICK UP THE GYRO TOOL STRING.
GZR-401 |  |  |  | 2023-05-22 14:30 | 2023-05-22 18:00 | 3:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | PERFORM WIRELINE GYRO. - RIH TO 3100 M IN STATIONS AS PER TASK PROCEDURES. - POOH TO SURFACE IN STATIONS AS PER TASK PROCEDURES. NOTE: - MONITOR THE WELL THROUGH TRIP TANK.
GZR-401 |  |  |  | 2023-05-22 18:00 | 2023-05-22 18:30 | 0:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | - R/D GYRO WIRELINE TOOLS, CABLE AND SHEAVES.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-23 | 5:30 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4543 M TO 4581 M DRILLING PARAMTERS: FR: 530 GPM, SPP: 3200-3550, ROT: 60-65 RPM, TQ: 8-12 K FT-LBS, WOB: 40-43 KLBS DIFF PRESSURE 100-450 PSI - TOP OF MABROUK FORMATION AT 4530 M. - AT 22:50 HRS GREASE WASHPIPE - AVG ROP: 7.4 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 101 M DAILY BIT HRS: 16.5 HR AVG ROP: 6.2 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4581 M TO 4616 M DRILLING PARAMTERS: FR: 530 GPM, SPP: 3250-3600, ROT: 50-65 RPM, TQ: 8-12 K FT-LBS, WOB: 40-43 KLBS DIFF PRESSURE 150-500 PSI - AVG ROP: 6.42 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4691 M TO 4705 M DRILLING PARAMTERS: FR: 520 GPM, SPP: 3200-3500, ROT: 40-50 RPM, TQ: 8-12 K FT-LBS, WOB: 43-45 KLBS DIFF PRESSURE 150-300 PSI - AVG ROP: 2.6 M/HR Page 99 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4705 M TO 4733 M DRILLING PARAMTERS: FR: 520-530 GPM, SPP: 3200-3500, ROT: 40-50 RPM, TQ: 8-12 K FT-LBS, WOB: 25-45 KLBS DIFF PRESSURE 150-300 PSI - AVG ROP: 2.39 M/HR
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4733 M TO 4744 M DRILLING PARAMTERS: FR: 520-530 GPM, SPP: 3300-3500, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 150-250 PSI - AVG ROP: 1.85 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 53 M DAILY BIT HRS: 22.76 HR AVG ROP: 2.33 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4744 M TO 4755 M DRILLING PARAMETERS: FR: 530 GPM, SPP: 3300-3550, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 150-250 PSI - AVG ROP: 2.0 M/HR - AT 4744 @00:45GREASE WASH PIPE
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4755 M TO 4779 M DRILLING PARAMETERS: FR: 530 GPM, SPP: 3300-3550, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 42-45 KLBS DIFF PRESSURE 150-250 PSI - AVG ROP: 2.14 M/HR
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4779 M TO 4790 M DRILLING PARAMETERS: FR: 530 GPM, SPP: 3300-3550, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 150-300 PSI - AVG ROP: 1.90 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 46 M DAILY BIT HRS: 22.7 HR AVG ROP: 2.03 M/HR Page 100 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4790 M TO 4802 M DRILLING PARAMETERS: FR: 530 GPM, SPP: 3300-3600, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - AVG ROP: 1.90 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4802 M TO 4833 M DRILLING PARAMETERS: FR: 530 GPM, SPP: 3400-3600, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - AT 4802 @ 06:25GREASE WASH PIPE - AVG ROP: 2.9 M/HR
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4833 M TO 4844 M DRILLING PARAMETERS: FR: 530-550 GPM, SPP: 3400-3650, ROT: 40-50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - AT 4831 @ 16:40GREASE WASH PIPE - AVG ROP: 1.82 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 54 M DAILY BIT HRS: 22.76 HR AVG ROP: 2.37 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 03:15 | 3:15 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4844 M TO 4850 M DRILLING PARAMETERS: FR: 550 GPM, SPP: 3550-3700, ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-250 PSI - AT 4850 M STARTED INCREASING MW FROM 1.26 SG TO 1.28 SG - AVG ROP: 1.82 M/HR
GZR-401 |  | RIG |  | 2023-05-22 03:15 | 2023-05-22 03:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED KICK WHILE DRILLING DRILL (D2) AND INFLUX DETECTION DRILL (D6) WITH CREW C, GOOD RESPONSE FROM DR AND MUDLOGGER IN DETECTING THE INCREASE IN ACTIVE SYSTEM. - AAR WITH CREW IN RIG FLOOR.
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 06:00 | 2:30 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4850 M TO 4854 M DRILLING PARAMETERS: FR:530 GPM, SPP: 3350-3600, ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-250 PSI - AT 4853 M MW IN = MW OUT = 1.28 SG - AVG ROP: 1.65 M/HR Page 101 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 09:30 | 3:30 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4854 M TO 4859 M DRILLING PARAMETERS: FR:530 GPM, SPP: 3350-3600, ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-250 PSI - AVG ROP: 1.87 M/HR
GZR-401 |  | RIG |  | 2023-05-22 09:30 | 2023-05-22 09:45 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS MEANWHILE, PERFORM BOP FUNCTION TEST FROM TP PANEL.
GZR-401 |  | RIG |  | 2023-05-22 09:45 | 2023-05-22 18:00 | 8:15 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4859 M TO 4874M DRILLING PARAMETERS: FR:530 GPM, SPP: 3350-3600, ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-250 PSI - AVG ROP: 1.8 M/HR
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4874 M TO 4882M DRILLING PARAMETERS: FR:530 GPM, SPP: 3350-3600, ROT: 50 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-200 PSI - AVG ROP: 1.53 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 38 M DAILY BIT HRS: 22.36 HR AVG ROP: 1.7 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4882 M TO 4891M DRILLING PARAMETERS: FR:530-550 GPM, SPP: 3350-3800, ROT: 40-55 RPM, TQ: 9-10 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-200 PSI - AVG ROP: 1.63 M/HR
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4891 M TO 4916 M DRILLING PARAMETERS: FR:530-550 GPM, SPP: 3350-3800, ROT: 40-55 RPM, TQ: 9-10 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-200 PSI - MAX GAS PEAK = 4.2 AT DEPTH 4907 M. - TOP UPPER MIQRAT = 4907 M. - AVG ROP: 2.2 M/HR Page 102 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4916 M TO 4929 M DRILLING PARAMETERS: FR:530 GPM, SPP: 3350-3700, ROT: 40-55 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - AT 4917 @18:45GREASE WASHPIPE - AVG ROP: 2.35 M/HR DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 47 M DAILY BIT HRS: 22.44 HR AVG ROP: 2.09 M/HR
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 07:45 | 7:45 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4929 M TO 4946 M. DRILLING PARAMETERS: FR:530 GPM, SPP: 3450-3780, ROT: 40-55 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - AVG ROP: 2.31 M/HR
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 08:30 | 0:45 | [6 empty] | Productive |  |  | - TDS SERVICE - DROP INSPECTION ON AREAS A
GZR-401 |  | RIG |  | 2023-05-22 08:30 | 2023-05-22 18:30 | 10:00 | [6 empty] | Productive |  |  | DRILL 8-1/2" HOLE SECTION FROM 4946 M TO 4977 M. ( CORE POINT) DRILLING PARAMETERS: FR:530 GPM, SPP: 3450-3780, ROT: 40-55 RPM, TQ: 9-12 K FT-LBS, WOB: 45 KLBS DIFF PRESSURE 100-300 PSI - STARTED TRACING MUD BY ADDING DEUTRIUM IN PREPRATION FOR THE CORING JOB - REAM 2 M UP/DOWN ON CONNECTION. - AVG ROP: 3.3 M/HR
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 19:45 | 1:15 | [6 empty] | Productive |  |  | PUMP 50 BBLS HI VIS AND CIRCULTE HOLE CLEAN WITH F/R; 530 GPM, PRESSURE; 3600 PSI.
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-22 20:00 | 0:15 | [6 empty] | Productive |  |  | TOOK SCR L/D ONE SINGLE
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-22 20:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK THE WELL-STATIC DROP 2.57" HOLLOW DRIFT WITH 30M TAIL SLING
GZR-401 |  | RIG |  | 2023-05-22 20:15 | 2023-05-22 21:15 | 1:00 | [6 empty] | Productive |  |  | POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 4968 M TO 4664 M NO OVERPULL OBSERVED. MONITOR THE WELL THROUGH TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 21:15 | 2023-05-22 21:30 | 0:15 | [6 empty] | Productive |  |  | PUMP 30 BBL OF 1.52 SG SLUG
GZR-401 |  | RIG |  | 2023-05-22 21:30 | 2023-05-22 21:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AFTER SLUG- WELL STATIC Page 103 of 120
GZR-401 |  | RIG |  | 2023-05-22 21:45 | 2023-05-23 | 2:15 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 4664 M TO 3900 M. NO OVERPULL OBSERVED. MONITOR THE WELL THROUGH TRIP SHEET. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 9 CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:15 | 1:15 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 3900 M TO 3525 M. - NO OVERPULL OBSERVED. - MONITOR THE WELL THROUGH TRIP SHEET. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 5 CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 01:15 | 2023-05-22 01:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AT SHOE- WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 01:30 | 2023-05-22 04:00 | 2:30 | [6 empty] | Productive |  |  | SLIP & CUT DRILL LINE - HANG TRAVELING BLOCK - CUT 24 M AND SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 06:00 | 2:00 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 3525 M TO 2600 M. - NO OVERPULL OBSERVED. - MONITOR THE WELL THROUGH TRIP SHEET. - AT 05:00 CREW HANDOVER AND TBT.
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 10:45 | 4:45 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 2600 M TO 565 M. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 5 CONNECTIONS. - MONITOR THE WELL THROUGH TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 10:45 | 2023-05-22 11:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK BELOW BHA- WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 17:00 | 6:00 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 8.5" MOTORIZE BHA FROM 565 M TO SURFACE. - MONITOR THE WELL THROUGH TRIP SHEET. - L/D 15 JOINTS OF HW FOR INSPECTION - R/BACK 5 STANDS OF HW - L/D 25 JOINTS OF X 6.5" DC - L/D JAR - L/D 2 X S.STABS (ON GAUGE ) - L/D MOTOR - L/D BIT. BIT GRADING : 2-2-CT-A-X-I-BT-TD
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 18:15 | 1:15 | [6 empty] | Productive |  |  | TBT WITH ABRAJ CREW. - CHANGE OUT WASH PIPE DUE TO REACHING MAXIMUM CIRCULATING HOURS. Page 104 of 120
GZR-401 |  | RIG |  | 2023-05-22 18:15 | 2023-05-22 18:30 | 0:15 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 19:15 | 0:45 | [6 empty] | Productive |  |  | TBT WITH ABRAJ CREW & HLB CORING CREW.
GZR-401 |  | RIG |  | 2023-05-22 19:15 | 2023-05-22 19:45 | 0:30 | [6 empty] | Productive |  |  | P/U CORE HEAD, FLOAT SUB, CIRCULATING SUB AND HLB TOOLS TO RIG FLOOR
GZR-401 |  | RIG |  | 2023-05-22 19:45 | 2023-05-23 | 4:15 | [6 empty] | Productive |  |  | P/U & M/U 8 3/8"CORE BHA AND RIH SAME TO 56 M: - M/U FOSV TO HDT PIN X 4 1/2" IF BOX X-O. - P/U 1ST 6 3/4" CORE BARREL AND M\U WITH 8 3/8" X4" CORE HEAD (TYPE FC3843I) . - P/U & M/U 8 5/16" NEAR BIT STAB. - P/U & M/U 5 X 6 3/4" OUTER CORE BARREL TUBE + 5 X 8 4/16" CORE BARREL STABILIZERS, TORQUE UP ALL HDT CONNECTIONS TO 25800 FT.LB. USING MANUAL TONGS. - LAY DOWN OUTER BARREL LIFTING SUB AND PREPARE FOR PU INNER CORE BARREL. - P/U & M/U 6 X 4 3/4" ALUMINIUM INNER CORE TUBE AND RUN INSIDE OUTER CORE BARRELS. M/U INNER CORE TUBE USING PIPE WRENCH UNDER CORE ENGINEER INSTRUCTIONS. - SPACE OUT ALUMINUM INNER TUBE WITH 92 MM ABOVE CORE HEAD. NOTE: - 21:45 CREW HANDOVER AND TBT
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 01:15 | 1:15 | [6 empty] | Productive |  |  | - P/U & M/U LOWER COUPLING AND UPPER COUPLING. - P/U & M/U FLOAT SUB WITH FLAPPER FLOAT VALVE - P/U & M/U CIRCULATION SUB.
GZR-401 |  | RIG |  | 2023-05-22 01:15 | 2023-05-22 04:00 | 2:45 | [6 empty] | Productive |  |  | RIH WITH 8 3/8" CORE BHA FROM 59 M TO 319 M - SINGLE IN 12X 6-1/2'' DC JTS FROM PIPE CAT. - P/U & M/U 6 1/2 DRILLING JAR - INSTALL AIR SLIPS - P\U & M\UP - 5 x 5'' HWDP STANDS - WEIGHT BELOW JARS :30 KLBS - TOTAL WEIGHT OF BHA : 50 KLB
GZR-401 |  | RIG |  | 2023-05-22 04:00 | 2023-05-22 04:45 | 0:45 | [6 empty] | Productive |  |  | RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 319 M TO 433 . - SINGLE IN WITH 5'' 19.5 PPF DP JOINTS FROM PIPE CAT (12 JOINTS) - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 06:00 | 1:15 | [6 empty] | Productive |  |  | RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 433 M TO 1005 M. - FILL STRING EVERY 20 STDS. - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET. Page 105 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 12:15 | 6:15 | [6 empty] | Productive |  |  | RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 1005 M TO 3458 M. - RIH SPEED = 30 M/MIN - FILL STRING EVERY 20 STDS. - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  |  |  | 2023-05-22 12:15 | 2023-05-22 12:30 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | - OBSERVED ONE OF THE DP SINGLES WAS BEND JUST BELOW THE TOOL JOINT (SUSPECT REASON WHILE BREAKING OUT DURING LAST POOH) - LAY DOWN SINGLE AND P/UP NEW ONE FROM GROUND
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 13:00 | 0:30 | [6 empty] | Productive |  |  | CONT. RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 3458 M TO 3545 M. TAKE PARAMETERS AT THE SHOE: * WITH PUMP: P/U WEIGHT = 315 KLBS . SLACK OFF WEIGHT = 290 KLBS. * WITHOUT PUMP: P/U WEIGHT = 320 KLBS . SLACK OFF WEIGHT = 285 KLBS. * RPM = 50. TORQUE = 5-6 KFT.LB * FLOW RATE = 300 GPM. SPP = 1000 PSI - RIH SPEED = 30 M/MIN - FILL STRING EVERY 20 STDS. - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 15:00 | 2:00 | [6 empty] | Productive |  |  | CONT. RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 3545 M TO 4095 M. - RIH SPEED = 15 M/MIN - FILL STRING EVERY 20 STDS. - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  |  |  | 2023-05-22 15:00 | 2023-05-22 16:45 | 1:45 |  |  |  | RREP |  |  | Non-Productive |  |  | WHILE RIH A STAND OF 5" DP THE ROPE GUIDING THE STAND TO THE ELEVATOR BROKE CAUSING THE STAND TO LEAN TO THE OTHER SIDE OF THE DERRICK. - STOP OPERATION AND ASSESSED THE RISK - AGREED ON FORWARD PLAN TO RECOVER THE STAND - RECOVER STAND AND RESUME RIH
GZR-401 |  | RIG |  | 2023-05-22 16:45 | 2023-05-22 20:30 | 3:45 | [6 empty] | Productive |  |  | CONT. RIH 8 3/8" CORE BHA ON 5" DP STAND FROM 4095 M TO 4926 M. - RIH SPEED = 15 M/MIN - FILL STRING EVERY 20 STDS. - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 20:30 | 2023-05-22 22:00 | 1:30 | [6 empty] | Productive |  |  | WASH DOWN FROM 4926 M TO 4975 M. FLOW 250 GPM, RPM 30, TQ 8-9 KFT.LB , PRESSURE 1000 PSI TAG BOTTOM AT 4975 M. ( 2 M SHALLOWER ) CORING START DEPTH: 4975 M Page 106 of 120
GZR-401 |  | RIG |  | 2023-05-22 22:00 | 2023-05-22 23:45 | 1:45 | [6 empty] | Productive |  |  | CIRCULATE BOTTOM UP WITH 300 GPM, P 1370 PSI, RPM 30, TQ 9-9.5 KLB.FT. SHAKERS CLEAN WHILE WHOLE CIRCULATION
GZR-401 |  | RIG |  | 2023-05-22 23:45 | 2023-05-23 | 0:15 | [6 empty] | Productive |  |  | RECORD PRE-CORING PARAMETERS. PUMP ON: - DN WT: 395 KLB - UP WT 450 KLB - RT WT 425 KLB - SCR PUMP 1 30 SPM, 280 PSI. 40 SPM 400 SPI - SCR PUMP 2 30 SPM, 280 PSI. 40 SPM , 400 PSI
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:15 | 0:15 | [6 empty] | Productive |  |  | SPACE OUT TO START CORING WITH FULL STAND. L/D 1 SINGLE.
GZR-401 |  | RIG |  | 2023-05-22 00:15 | 2023-05-22 01:00 | 0:45 | [6 empty] | Productive |  |  | DROP 1 1/4'' BALL.M/U ONE STAND. CIRCULATE AT 100 GPM WITH 310 PSI. PRESSURE INCREASE TO 420 PSI AS BALL SET ON BALL CATCHER. TOOK SCR - SCR PUMP 1 30 SPM, 385 PSI. 40 SPM 570 SPI - SCR PUMP 2 30SPM, 360 PSI. 40 SPM , 550 PSI
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 06:00 | 5:00 | [6 empty] | Productive |  |  | BED ON CORE HEAD AND COMMENCED CORING 8-3/8'' HOLE SECTION FROM 4975 M TO 4977.7 M. -FR: 220 GPM, SPP: 1250 PSI, ROT: 40-60 RPM, TRQ: 9.5 - 11 KFT-LBS,WOB: 4-15 KLBS WOB. NOTE: AFTER DRILLED 0.5 M OBSERVED WOB INCREASE FROM 7 KLBS TO 17 KLBS GRADUALLY WITH NO STRING MOVEMENT NOR DRILL-OFF. P\UP TO NEUTRAL WEIGHT425 KLBSTHEN RESUME CORING. - SET TORQUE LIMIT AT 20 KFT.LBS
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-23 | 18:00 | [6 empty] | Productive |  |  | CONTINUE CORING 8-3/8'' HOLE SECTION FROM 4977 M TO 5016 M. - FR: 250-270 GPM, SPP: 1250-1520 PSI, ROT: 50-60 RPM, TRQ: 10 - 15 KFT-LBS,WOB: 4-15 KLBS WOB. NOTE: - AVG. ROP = 2.21 - AT 4986M, STRING STALLED. P/U TO NEUTRAL WEIGHT AND RELEASE TORQUE AND WORK ON RELEASING TORQUE - SET TORQUE LIMIT AT 22 KFT.LBS Page 107 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 | [6 empty] | Productive |  |  | CONTINUE CORING 8-3/8'' HOLE SECTION FROM 5016 M TO 5019 M: - FR: 270 GPM, SPP: 1450-1520 PSI, ROT: 50-60 RPM, TRQ: 10 - 15 KFT-LBS,WOB: 4-18 KLBS WOB. NOTE: - AT 5016.7 M, ROP DROPS TO 0.3-0.4 M/HR, SPP DECREASE BY 30-40 PSI, TQ DECREASE FROM 11 KFT.LBS TO 10 KFT.LBS, STOPPED ROTATION AND PICK UP TO NEUTRAL WEIGHT, START ROTATION AGAIN AND RESUME CORING, OBSERVED BETTER ROP (0.7-1.0 M/HR) AND TORQUE(10.5 KFT.LBS). - AT 5018.5 M, ROP DROPS TO 0.2-0.4 M/HR, SPP DECREASE BY 30-40 PSI, TQ DECREASE FROM 10.5 KFT.LBS TO 9.7 KFT.LBS, STOPPED ROTATION AND PICK UP TO NEUTRAL WEIGHT, START ROTATION AGAIN AND RESUME CORING, OBSERVED IMPROVEMENT IN ROP (0.7-0.8 M/HR)
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 09:45 | 3:45 | [6 empty] | Productive |  |  | CONTINUE CORING 8-3/8'' HOLE SECTION FROM 5019 M TO 5029 M: - FR: 270-300 GPM, SPP: 1520-1680 PSI, ROT: 50-70 RPM, TRQ: 10 - 12 KFT-LBS, WOB: 4-18 KLBS WOB. NOTE: - AVG. ROP = 2.84 M/H
GZR-401 |  | RIG |  | 2023-05-22 09:45 | 2023-05-22 10:00 | 0:15 | [6 empty] | Productive |  |  | BREAK CORE: - STOPPED ROTARY. PU STRING UNTILL 5KLBS OVERPULL OVER 450KLBS UP WEIGHT. WEIGHT DROP TO 450KLBS. INDICATION OF CORE BREAK. - PU STRING WITH 270GPM, 1050PSI FROM 5029M TO 5020M.
GZR-401 |  | RIG |  | 2023-05-22 10:00 | 2023-05-22 10:45 | 0:45 | [6 empty] | Productive |  |  | PUMP OUT OF HOLE FROM 5029 M TO 4973 M. - 270 GPM, 1460 PSI. - NO DRAG OBSERVED.
GZR-401 |  | RIG |  | 2023-05-22 10:45 | 2023-05-22 13:30 | 2:45 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN. - 270GPM, 1400PSI. - RECIPROCATED STRING BETWEEN 4973M - 4945 ( 1FULL STAND) WHILE CIRCULATING. - CIRCULATED 1 X BU CYCLE.
GZR-401 |  | RIG |  | 2023-05-22 13:30 | 2023-05-22 14:00 | 0:30 | [6 empty] | Productive |  |  | - TAKE SCR - FLOW CHECK WELL. STATIC. MEANWHILE, INSTALL AUTO SLIPS. Page 108 of 120
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 18:30 | 4:30 | [6 empty] | Productive |  |  | COMMENCE POOH WITH 8-3/8'' CORING ASSEMBLY ON 5'' DP FROM 4945M TO 3516 M. - CONTROLLED PULLING SPEED 1-1.5 MIN/STAND - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 18:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AT SHOE - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 18:45 | 2023-05-22 19:00 | 0:15 | [6 empty] | Productive |  |  | PUMP30 BBL OF 1.53 SG SLUG , 3.8 BBL INCREASE IN TRIP TANK
GZR-401 |  | RIG |  | 2023-05-22 19:00 | 2023-05-22 19:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AFTER SLUG - WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 19:15 | 2023-05-23 | 4:45 | [6 empty] | Productive |  |  | POOH WITH 8-3/8'' CORING ASSEMBLY ON 5'' DP FROM 3516 M TO 1932 M. - CONTROLLED PULLING SPEED 1-1.5 MIN/STAND - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 02:30 | 2:30 | [6 empty] | Productive |  |  | POOH WITH 8-3/8'' CORING ASSEMBLY ON 5'' DP FROM 1932 M TO 1000 M. - CONTROLLED PULLING SPEED 1-1.5 MIN/STAND - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 04:45 | 2:15 | [6 empty] | Productive |  |  | POOH WITH 8-3/8'' CORING ASSEMBLY ON 5'' DP FROM 1000 M TO 328 M. - CONTROLLED PULLING SPEED 4-5 MIN/STAND - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET.
GZR-401 |  | RIG |  | 2023-05-22 04:45 | 2023-05-22 05:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK PRIOR POOH BHA- WELL STATIC
GZR-401 |  | RIG |  | 2023-05-22 05:00 | 2023-05-22 08:15 | 3:15 | [6 empty] | Productive |  |  | POOH WITH 8-3/8'' CORING ASSEMBLY FROM 328 M TO 59 M. - CONTROLLED PULLING SPEED 7 MIN/STAND - MONITOR WELL TO TRIP TANK AND RECORD TRIP SHEET. - RACK BACK 15 X HWDP STANDS - RACK BACK 4 X DC STANDS - LAY DOWN JAR - LAY DOWN FILTER SUB AND FLOAT SUB
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 08:45 | 0:30 | [6 empty] | Productive |  |  | HOLD COMPREHENSIVE TOOL BOX TALK. DISCUSSED: - POOH AND LD 8-3/8'' CORING ASSEMBLY. - LIFTING PLAN - ROLES AND RESPONSIBILITIES. Page 109 of 120
GZR-401 |  | RIG |  | 2023-05-22 08:45 | 2023-05-22 15:00 | 6:15 | [6 empty] | Productive |  |  | POOH AND LD 8-3/8'' CORING BHA. - CUT INNER CORE BARREL AND LD IN 6 PIECES. - L/D AS PER HALLIBURTON PROCEDURE. - CHECK FOR H2S AFTER EACH CUT OF THE INNER BARREL - NO H2S RECORDED. CORED: 54 M RECOVERED: 54.71 M ( 101% )
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 18:00 | 3:00 | [6 empty] | Productive |  |  | POOH AND LAY DOWN 8 3/8" CORE HEAD BHA. - L/DOWN 6 X 6 3/4" OUTER CORE BARREL TUBE - L/D 6 X 8 3/8"CORE BARREL STABILIZERS + 8 3/8" NB STAB - CORE HEAD DULL GRADE: 1-1-WT-A-X-I-NO-TD
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-22 18:30 | 0:30 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 18:45 | 0:15 | [6 empty] | Productive |  |  | RETRIEVED WEAR BUSHING
GZR-401 |  | RIG |  | 2023-05-22 18:45 | 2023-05-22 19:30 | 0:45 | [6 empty] | Productive |  |  | MAKE UP CAMERON JETTING TOOL JET WASH BOP FUNCTION BOP'S AND JET SEAL ASSEMBLY PROFILE.
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 20:15 | 0:45 | [6 empty] | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY
GZR-401 |  | RIG |  | 2023-05-22 20:15 | 2023-05-23 | 3:45 | [6 empty] | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING. - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD. Page 110 of 120
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 00:30 | 0:30 | [6 empty] | Productive |  |  | CONT. PRESSURE TEST BOP AS PER ABRAJ PROCEDURE - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK.
GZR-401 |  | RIG |  | 2023-05-22 00:30 | 2023-05-22 00:45 | 0:15 | [6 empty] | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
GZR-401 |  | RIG |  | 2023-05-22 00:45 | 2023-05-22 01:00 | 0:15 | [6 empty] | Productive |  |  | - INSTALLED WEAR BUSHING
GZR-401 |  | RIG |  | 2023-05-22 01:00 | 2023-05-22 06:00 | 5:00 | [6 empty] | Productive |  |  | P/U & M/U 8.5" MOTOR BHA #4 TO 536 M - 8.3/8" HDBS (GTi75MKHO) BIT, NOZZLES:2X16+5X11, S/N 13856703 - 7" NITRO FORCE MOTOR(0.23 REV/GAL) - 8 1/4" STRING STAB - 1 x 6-1/2'' DC JOINT - FILTER SUB - 8 1/4" STRING STAB W/ TOTCO RING - 12 x 6-1/2''DC JOINT (SINGLE IN FROM PIPE CAT) - 9 x 6-1/2'' DC JOINT (3 STANDS FROM DERRICK) - 6-1/2'' JAR - 3 x 6-1/2'' DC JOINT - 15 x 5'' HWDP JOINTS (SINGLE IN FROM PIPE CAT) - 15 X 5'' HWDP JOINTS (5 STANDS FROM DERRICK) - WEIGHT BELOW JARS :50 KLBS - TOTAL WEIGHT OF BHA : 95 KLB NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 450 GPM - SPP 480 PS 550 GPM - SPP 950 PSI - MONITOR DISPLACEMENT THROUGH TRIP TANK
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 06:15 | 0:15 | [6 empty] | Productive |  |  | INSTALL AUTO SLIPS.
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 12:00 | 5:45 | [6 empty] | Productive |  |  | RIH WITH 8-3/8'' DRILLING BHA ON 5'' DP FROM 536 M TO 3329 M. - FILL UP EVERY 20TH STAND. - MONITOR CORRECT DISPLACEMENT OVER TRIP TANK. PERFORM D1 TRIP DRILL WITH CREW D
GZR-401 |  | RIG |  | 2023-05-22 12:00 | 2023-05-22 12:30 | 0:30 | [6 empty] | Productive |  |  | PERFORM D1 TRIP DRILL WITH CREW A
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 13:45 | 1:15 | [6 empty] | Productive |  |  | SLIP DRILL LINE - HANG TRAVELING BLOCK - SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. - CALIBRATED MUD LOGGERS BLOCK HEIGHT. Page 111 of 120
GZR-401 |  | RIG |  | 2023-05-22 13:45 | 2023-05-22 18:30 | 4:45 | [6 empty] | Productive |  |  | CONT. RIH WITH 8-3/8'' DRILLING BHA ON 5'' DP FROM 3329 M TO 4971 M. - FILL UP EVERY 20TH STAND. - MONITOR CORRECT DISPLACEMENT OVER TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 18:30 | 2023-05-22 19:15 | 0:45 | [6 empty] | Productive |  |  | - WASH DOWN LAST 2 STANDS FROM 4971 M TO 5026 M RECORDED PUMP OFF FINGERPRINT AT 530 GPM: 34 BBLS & 540 GPM : 30 BBLS (EX-LOG) AT 530 GPM: 34 BBLS & 540 GPM : 32 BBLS (RIG)
GZR-401 |  | RIG |  | 2023-05-22 19:15 | 2023-05-22 19:30 | 0:15 | [6 empty] | Productive |  |  | - RECORD SCR
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-23 | 4:30 | [6 empty] | Productive |  |  | BED ON BIT AND RESUME DRILLING 8-3/8" HOLE SECTION FROM 5029 M TO 5060 M DRILLING PARAMTERS:FR: 520 GPM, SPP: 4100-4200, ROT: 40 RPM, TQ: 10-14 K FT-LBS, WOB: 10-40 KLBS, DIFF PRESSURE 150-380 PSI AVG ROP: 8.27 M/HR NOTES: - GOOD ROP ACHEIVED WITH 35-40 KLBS WOB - OFFLINE, PREPARE LOW CHLORIDE THERMAL STABILITY PILL
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 02:00 | 2:00 | [6 empty] | Productive |  |  | DRILLING 8-3/8" HOLE SECTION FROM 5060 M TO 5079 M DRILLING PARAMTERS:FR: 520 GPM, SPP: 4100-4200, ROT: 40 RPM, TQ: 10-14 K FT-LBS, WOB: 38-40 KLBS, DIFF PRESSURE 150-380 PSI AVG ROP: 10 M/HR
GZR-401 |  | RIG |  | 2023-05-22 02:00 | 2023-05-22 02:30 | 0:30 | [6 empty] | Productive |  |  | - OBSERVED ROP DROPPED TO ZERO, PICK UP OFF BOTTOM, OBSERVED HOOK LOAD IS NOT RETURNING TO NORMAL, WOB SHOWS 35 KLBS - DISCONNECT TDS, OBSERVED NORMAL BLOCK WEIGHT 50 KLBS. - PUMP OIL TO DEAD LINE ANCHOR WEIGHT SENSOR. - CONNECT TDS AND OBSERVED HOOK LOAD RETURNED TO NORMAL.
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 04:15 | 1:45 | [6 empty] | Productive |  |  | DRILLING 8-3/8" HOLE SECTION FROM 5079 M TO 5092 M (WELL TD) DRILLING PARAMTERS:FR: 520 GPM, SPP: 4100-4200, ROT: 40 RPM, TQ: 10-14 K FT-LBS, WOB: 38-40 KLBS, DIFF PRESSURE 150-380 PSI AVG ROP: 9 M/HR NOTES: - AT 03:10 HRS, GREASE WASHPIPE. Page 112 of 120
GZR-401 |  | RIG |  | 2023-05-22 04:15 | 2023-05-22 06:00 | 1:45 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN, 530 GPM, 3830 PSI - RECIPROCATE STRING FROM 5092M TO 5064M WHILE CIRCULATING. - CIRCULATE 1.5 X BU CYCLE. SHAKERS CLEAN.
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 06:30 | 0:30 | [6 empty] | Productive |  |  | TAKE SCR AND FLOW CHECK WELL, STATIC
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 07:30 | 1:00 | [6 empty] | Productive |  |  | PUMP AND SPOT 120 BBLS OF 1.28 SG THERMAL PILL AT TD.
GZR-401 |  | RIG |  | 2023-05-22 07:30 | 2023-05-22 07:45 | 0:15 | [6 empty] | Productive |  |  | - L/DN 1 SINGLE. - P/UP GYRO TOOLS TO RIG FLOOR MEANWHILE FLOW CHECK WELL, STATIC.
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 08:15 | 0:30 | [6 empty] | Productive |  |  | DROP GYRO INTO DRILL STRING WAIT FOR GYRO TOOL TO LAND INTO TOTCO RING. MEANWHILE: - INSTALL AUTO SLIPS - HELD TBT AND HANDOVER WITH NEW CREW.
GZR-401 |  | RIG |  | 2023-05-22 08:15 | 2023-05-22 12:15 | 4:00 | [6 empty] | Productive |  |  | COMMENCE POOH WITH 8-3/8'' BHA ON 5'' DP FROM 5085 M TO 3533 M (INSIDE 9 5/8" CSG). - MONITOR CORRECT DISPLACEMENT OVER TRIP TANK.
GZR-401 |  | RIG |  | 2023-05-22 12:15 | 2023-05-22 12:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WELL PRIOR PUMPING SLUG- STATIC
GZR-401 |  | RIG |  | 2023-05-22 12:30 | 2023-05-22 12:45 | 0:15 | [6 empty] | Productive |  |  | PUMP 30 BBL OF 1.50 SG SLUG
GZR-401 |  | RIG |  | 2023-05-22 12:45 | 2023-05-22 13:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WELL POST PUMPING SLUG- STATIC
GZR-401 |  | RIG |  | 2023-05-22 13:00 | 2023-05-22 14:00 | 1:00 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA ON 5'' DP ON ELEVATORFROM 3533 M TO 2815 M. NOTES: - MONITORED WELL THROUGHTRIP TANK. - RACKED BACK TOTAL OF 85 STANDS.
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 16:30 | 2:30 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN 5'' DP FROM 2815 M TO 2500 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION, USED MANUAL TONGS FOR 3 CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 17:15 | 0:45 | [6 empty] | Productive |  |  | - PERFORM WEEKLY DROP INSPECTION IN AREAS 1,2,3,4 - CREW CHANGE AND TBT Page 113 of 120
GZR-401 |  | RIG |  | 2023-05-22 17:15 | 2023-05-22 17:30 | 0:15 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN 5'' DP FROM 2500 M TO 2444 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION, USED MANUAL TONGS FOR 1 CONNECTION.
GZR-401 |  | RIG |  | 2023-05-22 17:30 | 2023-05-22 18:00 | 0:30 | [6 empty] | Productive |  |  | PERFORM H2S DRILL WITH CREW D
GZR-401 |  | RIG |  | 2023-05-22 18:00 | 2023-05-23 | 6:00 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN 5'' DP FROM 2444 M TO 1555 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION, USED MANUAL TONGS FOR 11 CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 03:00 | 3:00 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN 5'' DP FROM 1555 M TO 1006 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION, USED MANUAL TONGS FOR 1 CONNECTIONS.
GZR-401 |  | RIG |  | 2023-05-22 03:00 | 2023-05-22 03:30 | 0:30 | [6 empty] | Productive |  |  | SERVICE PIPE CAT.
GZR-401 |  | RIG |  | 2023-05-22 03:30 | 2023-05-22 06:00 | 2:30 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN 5'' DP FROM 1006 M TO 536 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - AT 04:50 HRS, CREW CHANGE & HANDOVER
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 06:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK PRIOR BHA ENTER BOP - WELL STATIC Page 114 of 120
GZR-401 |  | RIG |  | 2023-05-22 06:15 | 2023-05-22 12:45 | 6:30 | [6 empty] | Productive |  |  | CONT. POOH WITH 8-3/8'' BHA AND LAY DOWN BHA TO SURFACE. R\B 1 STANDS OF HWDP. L\D 9 STANDS OF HWDP LD 3 X 6.1/2" DCS. LD JAR. LD 21 X 6.1/2" DCS. LD 8.1/4" STRING STAB LD 1 X 6.1/2" DCS. LD 8.1/4" STRING STAB LD 6-3/4" NITRO-FORCE MUD MOTOR LD 8 3/8" GTI75MKHO HDBS BIT, NOZZLES:5X11'' + 2X16'', S/N 13856703 ( BIT DULL GRADING 1-1-WT-A-X-I -NO-TD) NOTE: RETRIEVED GYRO TOOL - UNABLE TO BREAK CONNECTION OF HWDP DUE TO HIGH OVER TORQUE EVEN WITH MANUAL TONG (TORQUE REACHING MORE THAN 60 KFT-IB). RACK BACK HWDP STAND IN DRILLER SIDE - TOOK ALMOST 1 HR EXTRA AS INVISIBLE LOST TIME (ILT) DUE TO BREAKING OVER TORQUED JOINTS.
GZR-401 |  | RIG |  | 2023-05-22 12:45 | 2023-05-22 13:00 | 0:15 | [6 empty] | Productive |  |  | CLEAR AND CLEAN RIG FLOOR.
GZR-401 |  |  |  | 2023-05-22 13:00 | 2023-05-22 15:00 | 2:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | WORKING ON PREPARING WIRE LINE TOOLS AND CONFIRMING CERTIFICATES WITH BAKER. - FOUND SOME EQUIPMENT WITH OUT CERTIFICATION (WEB SLINGS, CHAIN, CAP). SEGREGATE ALL UNCERTIFIED EQUIPMENT.
GZR-401 |  |  |  | 2023-05-22 15:00 | 2023-05-22 16:30 | 1:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | PJSM PRIOR RU WIRELINE TOOLS RIG UP WIRELINE SHEAVES AND CABLE.
GZR-401 |  |  |  | 2023-05-22 16:30 | 2023-05-22 23:00 | 6:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | NOTICED WL UNIT DRUM IS NOT MOVING. WORK ON THE WIRELINE UNIT DRUM ISSUE. UNABLE TO FIX THE ISSUE. DECIDED TO DEMOBILIZE THE UNIT TO BAKER BASE FOR REPAIR.
GZR-401 |  |  |  | 2023-05-22 23:00 | 2023-05-23 | 1:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | RIG DOWN WIRELINE SHEAVES AND CABLE.
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 06:00 | 6:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | WAIT ON BAKER HUGHES WIRELINE LOGGING UNIT MEANWHILE: - LAY DOWN 18 STANDS OF 5" DRILL PIPE NOTE: IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION, USED MANUAL TONGS FOR ~30 CONNECTIONS. Page 115 of 120
GZR-401 |  |  |  | 2023-05-22 06:00 | 2023-05-22 17:00 | 11:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | WAIT ON BAKER HUGHES WIRELINE LOGGING UNIT MEANWHILE: - LAY DOWN 30 STANDS OF 5" DRILL PIPE - TOTAL 37 STANDS REMAINING RACKED BACK IN MAST NOTE: WIRE LINE UNIT ARRIVED AT 16:30. SPOTTED UNIT AND PREPARE COW DOCUMENTATION
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 19:30 | 2:30 | [6 empty] | Productive |  |  | PJSM PRIOR RU WIRELINE TOOLS RIG UP WIRELINE SHEAVES AND CABLE. PICK UP AND MAKE UP TOOL STRING FOR RUN 1A: QUAD COMBO (DENSITY, NEUTRON, RESISTIVITY, SONIC & GAMMA) TOOL STRING (GR-SP- XMAC- RTEX- CNC- ZDL-WGI- JAR)
GZR-401 |  | RIG |  | 2023-05-22 19:30 | 2023-05-22 20:00 | 0:30 | [6 empty] | Productive |  |  | TBT PRIOR PU AND LOAD THE RADIOACTIVE SOURCE LOAD RADIOACTIVE SOURCE
GZR-401 |  | RIG |  | 2023-05-22 20:00 | 2023-05-23 | 4:00 | [6 empty] | Productive |  |  | - STARTED RIH AND LOG WITH RUN 1A - RIH TO 5080 M - OPEN 6 ARMS CALIPER AND START RECORD REPEAT PASS FROM 5040 M TO 4960 M NOTE: LIMIT RIH SPEED AT 10 M/MIN DUE TO ISSUE WITH DRUM CHAIN. ** OFFLINE: - CONT. PREPARE AND SERVICE 4.5" AND 5.5" TUBING - CHANGE LINER SIZE TO 6'' IN MP#3
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 06:30 | 6:30 | [6 empty] | Productive |  |  | CONT. LOG WITH RUN 1A - CONT. RECORD REPEAT PASS TO 4940 M - RIH TO TD AT 5098.5 M (WL DEPTH) - START RECORD MAIN PASS 50 M ABOVE SHOE. SHOE WL DEPTH 3546.8 M. - LOG WITH GR TO SURFACE - TEMPRETURE AT TD 148.8 C NOTE: OBSERVE OVERPULL WHIL LOGGING UP WITH 800 IBS OP IN THE INTERVAL 4331-4328M.
GZR-401 |  | RIG |  | 2023-05-22 06:30 | 2023-05-22 09:15 | 2:45 | [6 empty] | Productive |  |  | - SENT LOGGING DATA TO OFFICE AND WAIT FOR ACCEPTANCE. - REMOVE RADIOACTIVE SOURCES AND LAY DOWN RUN 1A LOGING TOOLS. - R/D BAKER WIRELINE TOOLS 1A RUN: (GR-SP- XMAC- RTEX- CNC- ZDL-WGI- JAR)
GZR-401 |  |  |  | 2023-05-22 09:15 | 2023-05-22 14:30 | 5:15 |  |  |  | SFAL |  |  | Non-Productive |  |  | TROUBLESHOOTING AND WORKING ON TIGHTENING UNIT DRUM CHAIN THAT WAS FOUND LOOSE.
GZR-401 |  | RIG |  | 2023-05-22 14:30 | 2023-05-22 15:00 | 0:30 | [6 empty] | Productive |  |  | PREPARE FOR LOG RUN 1B (MREX-GR-ZDL) Page 116 of 120
GZR-401 |  | RIG |  | 2023-05-22 15:00 | 2023-05-22 15:15 | 0:15 | [6 empty] | Productive |  |  | PJSM PRIOR WIRELINE RUN 1B
GZR-401 |  | RIG |  | 2023-05-22 15:15 | 2023-05-22 16:00 | 0:45 | [6 empty] | Productive |  |  | P/UP AND M/UP WIRELINE TOOLS FOR 1B: MREX(NUCLEAR MAGNETIC RESONANCE, GR, ZDL) - TOOL STRING (MREX-GR-JAR-ZDL) NOTE: ZDL (DENSITY TOOL) WAS ADDED IN THIS RUN AS THE DENSITY DATA RETRIEVED IN RUN 1A WAS NOT SATISFIED. REQUEST WAS MADE BY BP SUBSURFACE TEAM.
GZR-401 |  |  |  | 2023-05-22 16:00 | 2023-05-22 16:30 | 0:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | LAY DOWN SWIVEL AND P/UP BACKUP SWIVEL DUE TO THE SWIVEL NOT FEEDING THROUGH THE CONNECTOR.
GZR-401 |  | RIG |  | 2023-05-22 16:30 | 2023-05-22 17:30 | 1:00 | [6 empty] | Productive |  |  | CONTINUE P/UP AND M/UP WIRELINE TOOLS FOR 1B: MREX (NUCLEAR MAGNETIC RESONANCE, GR, ZDL) - TBT PRIOR TO LOAD THE SOURCE - LOAD RADIOACTIVE SOURCE
GZR-401 |  | RIG |  | 2023-05-22 17:30 | 2023-05-23 | 6:30 | [6 empty] | Productive |  |  | STARTED RIH AND LOG WITH RUN 1B MREX (NUCLEAR MAGNETIC RESONANCE, GR, ZDL). RIH TO 5050 M, RECORD REPEAT PASS ACROSS MIDDLE MIQRAT, SPEED 0.5 M/MIN RE-RUN TO 5030 M
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 07:45 | 7:45 | [6 empty] | Productive |  |  | RECORD MAIN PASS FROM 5030 M TO 4975 M - SPEED 0.8 M/MIN POOH TO 4731 M RECORD BARIK MAIN PASS FROM 4731 M TO 4619 M -SPEED 0.8 M/MIN POOH TO SURFACE - SPEED 15 M/MIN, OPEN HOLE - SPEED 45-50 M/MIN, CASED HOLE
GZR-401 |  | RIG |  | 2023-05-22 07:45 | 2023-05-22 09:30 | 1:45 | [6 empty] | Productive |  |  | - TBT - REMOVE RADIOACTIVE SOURCES AND LAY DOWN RUN 1B LOGING TOOLS.
GZR-401 |  |  |  | 2023-05-22 09:30 | 2023-05-22 10:30 | 1:00 |  |  |  | SFAL |  |  | Non-Productive |  |  | WIRE LINE CREW SPENT SOME TO ORGANIZE TOOLS FOR 1C RUN FROM BASKET AND ALSO BACKLOAD TOOLS FROM 1B RUN IN THE TRUCK. THIS WAS SUPPOSED TO BE DONE OFFLINE AHEAD OF TIME
GZR-401 |  | RIG |  | 2023-05-22 10:30 | 2023-05-22 11:15 | 0:45 | [6 empty] | Productive |  |  | PREPARE TOOLS IN THE PIPE CAT FOR LOG RUN 1C GR-RCI (STRADDLE PACKER)-RCX-JARS)
GZR-401 |  | RIG |  | 2023-05-22 11:15 | 2023-05-22 11:30 | 0:15 | [6 empty] | Productive |  |  | PJSM PRIOR WIRELINE RUN 1C
GZR-401 |  | RIG |  | 2023-05-22 11:30 | 2023-05-22 14:00 | 2:30 | [6 empty] | Productive |  |  | P/UP AND M/UP WIRELINE TOOLS FOR 1C: GR-RCI (STRADDLE PACKER)-RCX-JARS Page 117 of 120
GZR-401 |  | RIG |  | 2023-05-22 14:00 | 2023-05-22 17:00 | 3:00 | [6 empty] | Productive |  |  | RIH AND LOG WITH RUN 1C GR-RCI (STRADDLE PACKER)-RCX-JARS RIH TO SHOE3500 M. WAIT AT THE SHOE FOR 30 MINUTES TO WARM UP
GZR-401 |  | RIG |  | 2023-05-22 17:00 | 2023-05-22 19:00 | 2:00 | [6 empty] | Productive |  |  | CONT. RIH TO 4900M, CORRECTED BY GAMMA CORRELATION BY 5M, ENCOUNTERED HELD UP AT 4905M ( 600 IBS), PICK UP AND RIH AGAIN, NO ISSUE. RIH TO 5050M TO CHECK CORRELATION. NOTE: PERFORM H2S DRILL WITH CREW B.
GZR-401 |  |  |  | 2023-05-22 19:00 | 2023-05-22 23:30 | 4:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | AT 5000 M LOST COMMUNICATION WITH RCI TOOLS, DECIDED TO POOH TO SHOE FOR TROUBLESHOOTING. REACH CASING SHOE, TRY TO GET BACK THE COMMUNICATION WITH THE TOOLS WITH NO SUCCESS, DECIDED TO POOH TO SURFACE. REACH TO SURFACE, REPLACE RCI HYDRAULIC POWER+ RCI ELECTRONICS AND REMOVE RCI SIX TANK SECTION
GZR-401 |  |  |  | 2023-05-22 23:30 | 2023-05-23 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | START PICK UP THE TOOLS & RIH
GZR-401 |  |  |  | 2023-05-22 | 2023-05-22 01:15 | 1:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONT. PICK UP THE TOOLS & RIH
GZR-401 |  |  |  | 2023-05-22 01:15 | 2023-05-22 01:45 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | POWER UP & SURFACE CHECK
GZR-401 |  |  |  | 2023-05-22 01:45 | 2023-05-22 05:15 | 3:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | OBSERVED HYDRAULIC OIL SPILL BELOW WL UNIT. CONTAIN THE SPILL USING SPILL KIT AND CONTAINER INVESTIGATE AND FOUND THAT THE OIL COMING FROM DAMAGED HYDRAULIC HOSE THAT SUPPLY WL DRUM MOTOR. REPLACE THE DAMAGED HOSE, CHECK OIL LEVEL AND RE-FILL FUNCTION TEST AND CHECK FOR ANY LEAKS. BAKER TEAM CONFIRM THE READINESS OF THE UNIT TO RESUME OPERATION.
GZR-401 |  |  |  | 2023-05-22 05:15 | 2023-05-22 09:45 | 4:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | RESUME OPERATION AND RIH WITH WL LOGGING RUN 1C TO 5000 M.
GZR-401 |  | RIG |  | 2023-05-22 09:45 | 2023-05-22 10:30 | 0:45 | [6 empty] | Productive |  |  | PERFORM CORRELATION LOG. Page 118 of 120
GZR-401 |  | RIG |  | 2023-05-22 10:30 | 2023-05-23 | 13:30 | [6 empty] | Productive |  |  | PERFORM PRESSURE PRETEST AQUISITION AT SELECTED POINTS (14 POINTS WERE SELECTED INITIALLY BY SUB-SURFACE TEAM): STOP AT 4983.902M, CONDUCTED SINGLE PROBE PRESSURE POINT# 1, TIGHT FORMATION MOVE TO 4986.529M, CONDUCTED SINGLE PROBE PRESSURE POINT# 2, SUPERCHARGED MOVE TO 4989.313M, CONDUCTED SINGLE PROBE PRESSURE POINT# 3, TIGHT FORMATION MOVE TO 4990.259M, CONDUCTED SINGLE PROBE PRESSURE POINT# 4, TIGHT FORMATION MOVE TO 4993.411M, CONDUCTED SINGLE PROBE PRESSURE POINT# 5, NO SEAL, MOVE TO 4992.91M, CONDUCTED SINGLE PROBE PRESSURE POINT# 5, SUPERCHARGED RECORRELATE GAMMA WITH RUN 1A, CORRECTED DEPTH +0.1M MOVE TO 4995.68M, CONDUCTED SINGLE PROBE PRESSURE POINT# 6, SUPERCHARGED MOVE TO 4996.464M, CONDUCTED SINGLE PROBE PRESSURE POINT# 7, GOOD MOVE TO 4998.297M, CONDUCTED SINGLE PROBE PRESSURE POINT# 8, GOOD MOVE TO 4999.926M, CONDUCTED SINGLE PROBE PRESSURE POINT# 9, SUPERCHARGED MOVE TO 5006.598M, CONDUCTED SINGLE PROBE PRESSURE POINT# 10
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 05:30 | 5:30 | [6 empty] | Productive |  |  | CONT. CONDUCTING SINGLE PROBE PRESSURE POINT# 10, GOOD MOVE TO 5007.281M, CONDUCTED SINGLE PROBE PRESSURE POINT# 11, GOOD MOVE TO 5011.8M, CONDUCTED SINGLE PROBE PRESSURE POINT# 12, GOOD MOVE TO 5015.490M, CONDUCTED SINGLE PROBE PRESSURE POINT# 13, TIGHT, CHANGE TO 5015.8M, TIGHT MOVE TO 5017.154M, CONDUCTED SINGLE PROBE PRESSURE POINT# 14, TIGHT, CHANGE TO 5017.44, GOOD Page 119 of 120
GZR-401 |  | RIG |  | 2023-05-22 05:30 | 2023-05-22 06:00 | 0:30 | [6 empty] | Productive |  |  | RETRACT THE PROBE AND ATTEMPT TO POH TO MOVE TO DUAL PACKER PRESSURE POINT. OBSERVED GETTING OVERPULL. TRY TO FREE BY SLACKING DOWN AND OVER PULL TO 1.8 KLBS (UP WEIGHT WAS 8.2 KLBS) NO SUCCESS. APPLIED OVER PULL UP 2.1 KLBS, (10.3 KLBS UP WEIGHT) AND MANAGED TO FREE THE STRING WITH OVERPULL OF 2.1 KLBS. CONTINUE POH AT 0.8 M/MIN TO CHECK FOR ANY DRAG. CORELATE DEPTH BEFORE THE FIRST STRADDLE POINT. - NOTE: DECISION MADE TO DROP THE DEEPEST STRADDLE POINT AS IT IS CLOSE TO THE STICKING DEPTH AT 5015.490
GZR-401 |  | RIG |  | 2023-05-22 06:00 | 2023-05-22 07:00 | 1:00 | [6 empty] | Productive |  |  | RIH TO 4996 M . MAKE CORRELATION WITH FIRST LOG. CHECK UP WEIGHT ~ 8200 LBS
GZR-401 |  | RIG |  | 2023-05-22 07:00 | 2023-05-22 11:00 | 4:00 | [6 empty] | Productive |  |  | POINT #1 @ 4996 M INFLATE STRADDLE PACKER ELEMENTS. MONITOR AND RECORD THE PRESSURE BUILD UP. DEFLATE THE ELEMENTS AND WAITED FOR 30 MINS TO COMPLETELY DEFLATE THE STRADDLE PACKER. PU THE STRING AND NOTE OVERPULL, NOTICED 400 LBS OVERPULL PRIOR BACK TO NORMAL UP WEIGHT
GZR-401 |  | RIG |  | 2023-05-22 11:00 | 2023-05-22 17:15 | 6:15 | [6 empty] | Productive |  |  | POINT #2 @ 4992.85 M INFLATE STRADDLE PACKER ELEMENTS. MONITOR AND RECORD THE PRESSURE BUILD UP. DEFLATE THE ELEMENTS AND WAITED FOR 15 MINS TO COMPLETELY DEFLATE THE STRADDLE PACKER. PU THE STRING AND NOTE OVERPULL , NOTICED 1700 LBS OVERPULL PRIOR BACK TO NORMAL UP WEIGHT.
GZR-401 |  | RIG |  | 2023-05-22 17:15 | 2023-05-22 23:15 | 6:00 | [6 empty] | Productive |  |  | POINT #3 @ 4983.155 M INFLATE STRADDLE PACKER ELEMENTS. MONITOR AND RECORD THE PRESSURE BUILD UP. DEFLATE THE ELEMENTS AND WAITED FOR 15 MINS TO COMPLETELY DEFLATE THE STRADDLE PACKER. PU THE STRING AND NOTE OVERPULL , NOTICED 1800 LBS OVERPULL PRIOR BACK TO NORMAL UP WEIGHT. OFFLINE: CONDUCT SPILL DRILL WITH CREW B
GZR-401 |  | RIG |  | 2023-05-22 23:15 | 2023-05-23 | 0:45 | [6 empty] | Productive |  |  | POOH WITH WL LOGGING STRING TO 4400 M - SPEED 15 M/MIN, OPEN HOLE
GZR-401 |  | RIG |  | 2023-05-22 | 2023-05-22 02:30 | 2:30 | [6 empty] | Productive |  |  | POOH WITH WL LOGGING STRING FROM 4400 M TO SURFACE - SPEED 15 M/MIN, OPEN HOLE - SPEED 40-70 M/MIN, CASED HOLE
GZR-401 |  | RIG |  | 2023-05-22 02:30 | 2023-05-22 05:00 | 2:30 | [6 empty] | Productive |  |  | LAY DOWN LOGGING TOOLS.
GZR-401 |  | RIG |  | 2023-05-22 05:00 | 2023-05-22 05:45 | 0:45 | [6 empty] | Productive |  |  | RIG DOWN WL CABLE AND SHEAVES.
GZR-401 |  | RIG |  | 2023-05-22 05:45 | 2023-05-22 06:00 | 0:15 | [6 empty] | Productive |  |  | CLEAR AND CLEAN RIG FLOOR