## Sheet
Borehole | Daily Cost | Phase | Borehole Section | Start Time | End Time | Duration(h) | Start Depth(m) | End Depth(m) | Operation Code | Activity Code | Sub Code | Planned | Time Classification | NPT Reason | NPT Vendor | Comments | Translated Comments | Perforation | Additional Code
KZN-377 |  | SURF |  | 2023-08-23 17:00 | 2023-08-24 | 7:00 | [6 empty] | Productive |  |  | ACCEPT RIG AT 17:00 - **BEGIN DON EVENT** - CONTINUE TO P/U AND RACK BACK5'' 25.6#G3 DP (35 STAND ). - P/U, M/U & RACK BACK 5 STANDS OF 5" HWDP. - R\D AIR SLIPS. - PICK UP LIFTING SUB, P/U, M/U & RACK BACK 1 STAND OF 8.1/4" DC. - PU, MU & RB 4X DRILLABLE DCS STANDS ( 2X8.1/4" DCS + XO + 1X 5" HWDP) OFFLINE: - HOLD PRE-SPUD MEETING WITH DAY CREW. - CREW CHANGE AT 20:00 HRS. - MIX SPUD MUD - CONTINUE TO CLOSE OUT PRE-SPUD CHECKLIST - PT GROUND AND STAND PIPE MANIFOLDS VALVES AS PER ABRAJ PROCEDURES .
KZN-377 |  | PRE |  | 2023-08-23 | 2023-08-23 03:30 | 3:30 | [6 empty] | Productive |  |  | - R\U AIR SLIPS. - CONT, P/U AND RACK BACK 5" 25.6" G3 DP ( TOTAL 50 STANDS). OFFLINE: - HOLD PRE-SPUD MEETING WITH NIGHT CREW AND 3RD PARTY - CONT. MIXING SPUD MUD - PREPARE & STRAP ALL 24" BHA COMPONENTS - WORK ON BOP / ANNULAR MPI.
KZN-377 |  | PRE |  | 2023-08-23 03:30 | 2023-08-23 05:00 | 1:30 | [6 empty] | Productive |  |  | PJSM AND TBT, - PT STAND PIPE MANIFOLDS VALVES AS PER ABRAJ PROCEDURES .
KZN-377 |  | PRE |  | 2023-08-23 05:00 | 2023-08-23 13:15 | 8:15 | [6 empty] | Productive |  |  | -P/U AND RACK BACK5'' 19.5#G2 DP (TOTAL 20 STANDS ).
KZN-377 |  | SURF |  | 2023-08-23 13:15 | 2023-08-23 13:45 | 0:30 | [6 empty] | Productive |  |  | PJSM FOR P\U & M\U 24" BHA AND DRILLING 24" HOLE SECTION
KZN-377 |  | SURF |  | 2023-08-23 13:45 | 2023-08-23 16:15 | 2:30 | [6 empty] | Productive |  |  | - PREPARE FOR BHA HANDLING. - PU 24" KYMERA BIT (SN/ 5308152) - PU BIT BREAKER - M/U 24'' KYMERA BIT WITH BIT SUB & 12'' SHOCK SUB, 9 1/2" DC AND XO - MAKE UP ABOVE WITH DRILLABLE STAND FROM DERRICK. - CONNECT TDS - STAGE UP PUMPS TO 450 GPM - TAG BOTTOM AT 14 M Page 2 of 80
KZN-377 |  | SURF |  | 2023-08-23 16:15 | 2023-08-23 22:15 | 6:00 | [6 empty] | Productive |  |  | *** SPUD IN KZN-377 AT 24/08/2023 16:15 HRS DRILL 24" HOLE FROM 14 M TO 42 M LIMITING ROP TO 5 M/HR WITH FOLLOWING PARAMETERS: - WOB: 2-20 KLBS - RPM: 60-70 RPM - SPP: 250-260 PSI - FLOW RATE: 450 GPM
KZN-377 |  | SURF |  | 2023-08-23 22:15 | 2023-08-24 | 1:45 | [6 empty] | Productive |  |  | POOH AND RACKBACK TWICE DC DRILLABLE STAND WITH XO. PU, MU AND RIH WITH : - 23 15/16"STRING STABILIZER - 9.1/2" DC - 23 15/16"STRING STABILIZER
KZN-377 |  | SURF |  | 2023-08-23 | 2023-08-23 00:30 | 0:30 | [6 empty] | Productive |  |  | COMP. MU AND RIH WITH : - 23 15/16"STRING STABILIZER - 9.1/2" DC - 23 15/16"STRING STABILIZER
KZN-377 |  | SURF |  | 2023-08-23 00:30 | 2023-08-23 06:00 | 5:30 | [6 empty] | Productive |  |  | CONT. DRILLING 24’’ SECTION WITH ROTARY BHA FROM 44 M TO 96 M FOLLOWING RECOMMENDED DRILLING PARAMETERS. - RPM : 60-100 - TORQUE : 1400-5800 FT.IBS - WOB : 5-20 KIBS - FLOW RATE : 550-750 GPM - SPP: 430-940 PSI NOTES: - NO LOSSES / NO FLOW OBSERVED - PUMP 50 BBLS HV SWEEPS ON LAST SINGLE OF EVERY STAND DRILLED. - NO OVERPULL WAS OBSERVED BEFORE/AFTER MAKING ANY CONNECTION - RETURN TAKEN FROM CELLAR. - AT 60 M STAGE UP FR TO 750 GPM, AT 80M STAGE UP RPM TO 100 RPM,
KZN-377 |  | SURF |  | 2023-08-23 06:00 | 2023-08-23 06:15 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK THE WELL ( WIHTOUT THE RISER) -STATIC. - CLOSE THE RISER VALVE AND TAKE RETURNS THROUGH SHALE SHAKERS. Page 3 of 80
KZN-377 |  | SURF |  | 2023-08-23 06:15 | 2023-08-24 | 17:45 | [6 empty] | Productive |  |  | RESUME DRILLING 24" HOLE FROM 96 M TO 358M WITH FOLLOWING PARAMETERS. FR 1000 GPM , SPP 2000-2350 PSIWOB 20-40 KLBS , RPM 80-100 , TRQ 3-10KFT.LBS AVG ROP 18.12 M/HR. - NO LOSSES OR SWF. - PUMP HIVIS PILL SWEEP EVERY STAND TO IMPROVE HOLE CLEANING. - AT 333M OBSERVED LOSSES(180-200 BPH) STOPPED AFTER DRILLING TO 339M. - MIXING 120 BBL 80 PPB STOPPIT PILL AS PER LCM DECISION TREE - MW: 1.15 SG NOTE: - AT 20:00 TBT AND CREW SHIFT HANDOVER
KZN-377 |  | SURF |  | 2023-08-23 | 2023-08-23 14:15 | 14:15 | [6 empty] | Productive |  |  | CONT. DRILLING 24" HOLE FROM 358 M TO 568 M (SECTION TD) WITH FOLLOWING PARAMETERS. FR 1000 GPM , SPP 2350-2630 PSIWOB 25-40 KLBS , RPM 110-130 , TRQ 6-12 KFT.LBS AVG ROP 18.13 M/HR. - NO LOSSES OR SWF. - PUMP HI-VIS PILL SWEEP EVERY STAND TO IMPROVE HOLE CLEANING. - MW: 1.16 -1.22SG AT SECTION TD. - ARADA TOP AT 460 M. OFFLINE: - PREPARE 18-5/8" CSG. INSTALL CENTERLISERS. - PREPARE BOP FOR STUMP TEST. - RU CEMENT UNIT/ HARD LINE.
KZN-377 |  | SURF |  | 2023-08-23 14:15 | 2023-08-23 15:15 | 1:00 | [6 empty] | Productive |  |  | PUMP 100 BBLS HI-VIS SWEEP AND CIRC TELL SHAKERS CLEAN WITH 1000 GPM, 2600 PSI - 20 BBLS DOWN HOLE LOSSES OBSERVED WHILE CIRCULATION. - MUD IN/OUT =1.22 SG
KZN-377 |  | SURF |  | 2023-08-23 15:15 | 2023-08-23 15:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WITHOUT RISER MARGIN -- NO FLOW. MEANWHILE: TBT FOR POOH
KZN-377 |  | SURF |  | 2023-08-23 15:30 | 2023-08-23 16:15 | 0:45 | [6 empty] | Productive |  |  | - POOH ON ELEVATORWITH 24" BHA FROM 568 M TO 400 M. - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | SURF |  | 2023-08-23 16:15 | 2023-08-23 16:30 | 0:15 | [6 empty] | Productive |  |  | -SPOT 80 BBL OF LCM ACROSS LOSSES ZONE. Page 4 of 80
KZN-377 |  | SURF |  | 2023-08-23 16:30 | 2023-08-23 17:30 | 1:00 | [6 empty] | Productive |  |  | -CONT. POH ON ELEVATOR WITH 24" BHA FROM 400 M TO 285 M. - MONITOR WELL THROUGH TRIP TANK. -HAD 2 CONNECTIONES WITH OVERTORQUE CONNECTION AND BRAKE THE SAME USING THE MANUAL TONG.
KZN-377 |  | SURF |  | 2023-08-23 17:30 | 2023-08-23 17:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WITHOUT RISER MARGIN -- NO FLOW.
KZN-377 |  | SURF |  | 2023-08-23 17:45 | 2023-08-23 18:15 | 0:30 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATORWITH 24" BHA FROM 285 M TO 142 M. - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | SURF |  | 2023-08-23 18:15 | 2023-08-23 18:45 | 0:30 | [6 empty] | Productive |  |  | - FLOW CHECK WELL WITHOUT THE RISER AT TOP OF FIRST DRILL COLLAR STAND. - OBSERVE LOSSES 22 BBL/HR.
KZN-377 |  | SURF |  | 2023-08-23 18:45 | 2023-08-23 20:00 | 1:15 | [6 empty] | Productive |  |  | CONT. POOH ON ELEVATOR WITH 24" BHA AND R/B 8.1/4'' DC FROM 142 M TO 30 M.
KZN-377 |  | SURF |  | 2023-08-23 20:00 | 2023-08-23 20:15 | 0:15 | [6 empty] | Productive |  |  | CREW CHANGE AND HANDOVER.
KZN-377 |  | SURF |  | 2023-08-23 20:15 | 2023-08-23 23:00 | 2:45 | [6 empty] | Productive |  |  | - CONT. POOH ON ELEVATOR WITH 24" BHA R/B 8.1/4'' DC STD AND L/D REMAINING BHA ITEMS FROM 30 M TO SURFACE. - TOP STAB & LOWER WERE IN GAUGE, 60% BALLED UP. - LAY DOWN 2X 9 1/2" DC. - LAY DOWN SHOCK SUB - LAY DOWN BIT SUB - LAY DOWN BIT, 100% BALLED UP NOTE: BIT DULL GRADING: 1-1-SS-A-1-I-BU-TD - MONITOR WELL ON TRIP TANK, STATIC LOSSES 20 BBLS/HR.
KZN-377 |  | SURF |  | 2023-08-23 23:00 | 2023-08-23 23:15 | 0:15 | [6 empty] | Productive |  |  | TOFS, CLEAN AND CLEAR RIG FLOOR.
KZN-377 |  | SURF |  | 2023-08-23 23:15 | 2023-08-23 23:30 | 0:15 | [6 empty] | Productive |  |  | HOLD TBT/PJSM FOR REMOVING THE RAISER.
KZN-377 |  | SURF |  | 2023-08-23 23:30 | 2023-08-24 | 0:30 | [6 empty] | Productive |  |  | - DRAIN RISER - COMMENCE DISCONNECTINGFLOW LINE FROM RISER - MAINTAIN HOLE FULL TILL DISCONNECT RISER.
KZN-377 |  | SURF |  | 2023-08-23 | 2023-08-23 02:00 | 2:00 | [6 empty] | Productive |  |  | - DISCONNECT FLOW LINE FROM RAISER - REMOVE MOUSE HOLE - PULL RISER & LAY DOWN SAME. - R/U 20" MASTER BUSHING. - MAINTAIN FULL HOLE TILL DISCONNECT RISER. RUN TT ON CELLAR AFTER RISER DISCONNECTED. . Page 5 of 80
KZN-377 |  | SURF |  | 2023-08-23 02:00 | 2023-08-23 03:30 | 1:30 | [6 empty] | Productive |  |  | TBT R/U FRANKS TRS 18 5/8'' CSG HANDLING EQUIPMENTS. INSPECT SAME. - RIG UP SDE - RIG UP BOWL, SLIPS LIFTER, SLIPS AND CONTROL PANEL. - RIG UP POWER TONG. NOTE: - MONITOR CELLAR AND MAINTAIN HOLE FULL
KZN-377 |  | SURF |  | 2023-08-23 03:30 | 2023-08-23 03:45 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 18.5/8" CASING RUNNING.
KZN-377 |  | SURF |  | 2023-08-23 03:45 | 2023-08-23 13:30 | 9:45 | [6 empty] | Productive |  |  | RIH WITH 18 5/8" CSG (R3 K-55 87.5# BTC ) FROM SURFACE TO 540 M. - FUNCTION TEST FLOAT SHOE. - BAKER LOCK THE FIRST TWO CONNECTIONS. - USE BACK-UP TONGS AND SAFETY CALMP FOR FIRST JOINTS. - FILL UP CASING EVERY JOINT WHILE RIH THROUGH TDS. - MU JTS TO MU DIAMOND. - MONITOR WELL ON CELLAR, STATIC LOSSES 6-10 B/HR. - TOTAL JTS RUN FS JT + 41 OF 42 JTS. NOTE: - AT 8:00 TBT AND CREW SHIFT HANDOVER.
KZN-377 |  | SURF |  | 2023-08-23 13:30 | 2023-08-23 14:00 | 0:30 | [6 empty] | Productive |  |  | - RIG DOWN FRANKS SLIP LIFTER. - REMOVE CASING BUSHING TO ALLOW MODIFIED CENTRALIZER TO PASS THOUGH ROTARY.
KZN-377 |  | SURF |  | 2023-08-23 14:00 | 2023-08-23 14:45 | 0:45 | [6 empty] | Productive |  |  | - P/U LAST JOINT CSG WITH MODIFIED CENTRALIIZER - INSTALL CASING BUSHING AND PLACE STRING IN MANUAL SLIPS. - CHANGE OUT ELEVATOR TO 5" DP ELEVATOR.
KZN-377 |  | SURF |  | 2023-08-23 14:45 | 2023-08-23 15:15 | 0:30 | [6 empty] | Productive |  |  | MU 18.5/8" WATER BUSHING TO HWDP STAND THEN MU STAND TO LAST CASING JOINT #42.
KZN-377 |  | SURF |  | 2023-08-23 15:15 | 2023-08-23 16:15 | 1:00 | [6 empty] | Productive |  |  | - RIH AND WASH DOWN WITH 200 GPM, 50 PSI PRESSURE. - PLACE WATER BUSHING ABOUT 0.5 M ABOVE CELLAR FLOOR - INSTALL ANT TIGHT BASE CLAMP - LANDED OFF CASING ON BASE CLAMP - 18.5/8'' CSG SHOE AT 564.7 M
KZN-377 |  | SURF |  | 2023-08-23 16:15 | 2023-08-23 16:30 | 0:15 | [6 empty] | Productive |  |  | FILL UP CASING & BREAK CIRCULATION
KZN-377 |  | SURF |  | 2023-08-23 16:30 | 2023-08-23 17:15 | 0:45 | [6 empty] | Productive |  |  | - B/O WATER BUSHING AND L/D. - RACK BACK HWDP STAND. - INSTALL 26" MASTER BUSHING Page 6 of 80
KZN-377 |  | SURF |  | 2023-08-23 17:15 | 2023-08-23 20:00 | 2:45 | [6 empty] | Productive |  |  | - TBT - M/U STING-IN SUB WITH 5'' DP G3 STD - INSTALL PIPE CENTERLIZER AND SECURE SAME. - RIH INNER STRING TO 563 M - TAG SHOE STING-INAT 564.17 M - M/U SURFACE LINE WITH FOSV+ SES+ FOSV+PUP. - STING IN AND SET 20 KLBS ON STINGER.
KZN-377 |  | SURF |  | 2023-08-23 20:00 | 2023-08-23 20:45 | 0:45 | [6 empty] | Productive |  |  | - CIRCULATE AND CONDITION HOLE WITH 200 GPM, 60 PSI. OFFLINE: - CONDUCT PJSM PRIOR TO PERFORM CMT JOB. - PREPARE PVC PIPES FOR TOP FILL JOB.
KZN-377 |  | SURF |  | 2023-08-23 20:45 | 2023-08-23 21:00 | 0:15 | [6 empty] | Productive |  |  | - FLUSH SURFACE LINES. - PRESSURE TEST CEMENT LINES 300/2000 PSI H FOR 5/ 5 MIN. - rig LINE UP TO CMT UNIT, CLOSE UPPER FOSV AND APPLY 500 PSI ON TDS.
KZN-377 |  | SURF |  | 2023-08-23 21:00 | 2023-08-23 23:30 | 2:30 | [6 empty] | Productive |  |  | PERFROM 18-5/8" CEMENT AS FOLLOW: - MIX AND PUMP 362 BBL OF LEAD SLURRY (1.43 SG) WITH FR: 5-6 BBL/MIN, - MIX AND PUMP 151 BBL OF TAIL SLURRY (1.67 SG) WITH FR: 4-5 BPM - CEMENT RETURN TO CELLAR AFTER PUMPING 20 BBLS OF TAIL CMT. - DISPLACE CMT WITH 5 BBLS MIX WATER FOLLOWED BY 17.8 BBLS 1.22 SG MUD. (5 BBLS UNDER DISPLACEMENT) - BLED BACK0 BBLS RETURNED - CHECK FLOAT HOLDING. - CEMENT IN PLACE AT 23:30 hrs..
KZN-377 |  | SURF |  | 2023-08-23 23:30 | 2023-08-24 | 0:30 | [6 empty] | Productive |  |  | - BREAK OUT CEMENT LINES FROM SIDE ENTRY SUB. - STING OUT CEMENT STRINGER AND LD CEMENT ASSEMBLY - LOAD FOAM BALL INTO DRILL PIPE STRING. POOH UP WITH FULL STAND. - CIRCULATE 120% STRING VOLUME, 850-900 GPM. - POOH AND RACK BACK 1 STAND MEANWHILE, LEVEL IN CELLAR WAS DROPPING, FILL UP WITH 1.22 SG MUD. Page 7 of 80
KZN-377 |  | SURF |  | 2023-08-23 | 2023-08-23 01:15 | 1:15 | [6 empty] | Productive |  |  | ** CEMENT TOP FILL JOB #1 *** - IMMEDIATELY SWITCH TO CELLAR FOR TOP FILL - PUMPED 1000 LTR OF ECONOLITE - POOH PVC PIPE FOR ECONOLITE TO SURFACE. - PUMP CEMENT WITH GOOD RETURNS.START SEEN CEMENT AT CELLAR AFTER~ 10 BBL PUMPED, CONT PUMP CEMENT TILL TOTAL OF 40 BBLS - PULL PVC PIPE. - CLEAN AND CLEAR CEMENT FROM CELLAR. FILL CELLAR AND KEPT WATCHING THE LEVEL - OBSERVE DROP IN CEMENT LEVEL FILL UP WITH 1.22 SG MUD.
KZN-377 |  | SURF |  | 2023-08-23 01:15 | 2023-08-23 02:00 | 0:45 | [6 empty] | Productive |  |  | WAIT ON CEMENT. KEPT FILLING CELLAR WITH 1.22 SG MUD,OBSERVE MUDLEVEL IN CELLAR DROP. MEANWHILE: - RD CEMENT LINES AND POOH & RACKBACK REMAINING 5" DP STANDS. - CHECK TOC OBSERVED AT +/- 4M DEEP INSIDE BELOW CELLAR.
KZN-377 |  | SURF |  | 2023-08-23 02:00 | 2023-08-23 03:00 | 1:00 | [6 empty] | Productive |  |  | ** CEMENT TOP FILL JOB #2 ** - RUN 2X CEMENT PVC PIPES TO 4 M BELOW CELLAR. - PUMP CEMENT WITH GOOD RETURNS.START SEEN CEMENT AT CELLAR AFTER 8 BBL PUMPED ,CONT PUMP CEMENT TILL TOTAL OF 20 BBLS. - CLEAN AND CLEAR CEMENT FROM CELLAR. WATCHING THE LEVEL - STATIC AT BASE CLAMP.
KZN-377 |  | SURF |  | 2023-08-23 03:00 | 2023-08-23 03:30 | 0:30 | [6 empty] | Productive |  |  | WOC, KEEP MONITOR MUD LEVEL AT CELLAR- STATIC. MEANWHILE: - CLEAR RIG FLOOR. - TBT AND ARRANGE 20" RISER.
KZN-377 |  | SURF |  | 2023-08-23 03:30 | 2023-08-23 05:30 | 2:00 | [6 empty] | Productive |  |  | - REMOVE MASTER BUSHING. - R/U 20'' RISER , ENERGISE SEALS. - CONNECT FLOW LINE, INSTALL KILL LINE, TRIP TANK LINE AND DUMP VALVE - RU MOUSE HOLE. ** OFFLINE: - TBT AND PREPARING 17.5" BHA AT RIG FLOOR. - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CLEAN MUD PITS AND PREPARED HYDROGAURD MUD 1.28 SG. NOTE: - CREW CHANGE AT 05:00 HRS.
KZN-377 |  | SURF |  | 2023-08-23 05:30 | 2023-08-23 05:45 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR PU AND RIH 17.5" BHA Page 8 of 80
KZN-377 |  | SURF |  | 2023-08-23 05:45 | 2023-08-23 09:00 | 3:15 | [6 empty] | Productive |  |  | P/U & M/U AND RIH 17.1/2" BHA TO 180 M : - NOV BIT ,TYPE: TK625 ,SN: E268398 (6 X 13), - BIT SUB (WITH FLOAT VALVE) - 2 X 9 1/2" DC - 17 3/8" STRING STAB + 7.5/8" REG X 6.5/8" REG XO - 9X 8 1/4"DC - 8” POWER STROKE HYDRAULIC JARS - 3X 8 1/4" DC - 6.5/8" REG X 4.1/2 NC50 XO - 4 X 5" HWDP. WEIGHT BELOW THE JAR IS 50 KLBS OFFLINE: - CONTINUE MONITORING LEVEL IN CELLAR, STATIC. - CONT. PREPARE TANKSFOR DISPLACEMENT WITH HYDROGAURD MUD 1.28 SG.
KZN-377 |  | SURF |  | 2023-08-23 09:00 | 2023-08-23 09:30 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS.
KZN-377 |  | SURF |  | 2023-08-23 09:30 | 2023-08-23 10:30 | 1:00 | [6 empty] | Productive |  |  | CONT. RIH 17.1/2" BHA F 284 M TO 516 M WITH 11 X 5" HWDP AND 5" 25.6# G3 DP STANDS. TOTAL BHA WEIGHT 80 KLBS.
KZN-377 |  | SURF |  | 2023-08-23 10:30 | 2023-08-23 11:30 | 1:00 |  |  |  | RREP |  |  | Non-Productive |  |  | ATTEMPT TO DUMP TRIP TANK ( SPUD MUD) BUT UNABLE DUE TO TRIP TANK PUMP FAILURE , TROUBLESHOT THE SAME.
KZN-377 |  | SURF |  | 2023-08-23 11:30 | 2023-08-23 12:30 | 1:00 | [6 empty] | Productive |  |  | - WASH DOWN PRECAUTIONARY FROM 516 M TO 562 M - TAGGED ON CEMENT AT 562 M - COMMENCED DISPLACING WELL TO HYDROGAURD MUD.
KZN-377 |  | SURF |  | 2023-08-23 12:30 | 2023-08-23 13:30 | 1:00 | [6 empty] | Productive |  |  | - DRILL OUT CEMENT, FLOAT SHOE & RAT HOLE FROM 562 M TO 568 M USING BELOW PARAMETERS WOB: 5 -12 K, ROT: 50-80 RPM, TQ: 3-6.5 KFT-LBS, FR: 700-800 GPM, SPP: 1700-2300 PSI. - WIPE STRING THROUGH THE SHOE SEVERAL TIMES WITHOUT ISSUE. - PUMP 50 BBLS HI-VIS ON FLY AFTER CLEARING RAT HOLE - MW IN \ MW OUT = 1.28 SG Page 9 of 80
KZN-377 |  | INT1 |  | 2023-08-23 13:30 | 2023-08-24 | 10:30 | [6 empty] | Productive |  |  | DRILL 17.5'' HOLE SECTION FROM 568 M TO 905 M - WOB: 2-18 KLBS, ROT: 80-120 RPM, TQ: 4-12 KFT-LBS, FR: 1050-1100 GPM, SPP: 3600-3800 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HI-VIS EVERY CONNECTION - DRILL WITH 3 PUMPS. - GREASE WASH PIPE AT 860M. - COMMENCE INCEASE MW TO IN STAGES 1.32 SG FROM +/- 950M. * TOP OF FIQA SHARGI AT 586 M (6 M DEEPER). AVG ROP : 48.14 M\HR NOTE: - CREW CHANGE AT 21:00 HRS. - PREPARE 13-3/8" CASING, MEASURE, DRIFTAND CLEAN.
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 04:00 | 4:00 | [6 empty] | Productive |  |  | DRILL 17.5'' HOLE SECTION FROM 905 M TO 1021 M (SECTION TD 35 M INTO NATIH A/B) - WOB: 10-20 KLBS, ROT: 110-140 RPM, TQ: 4-15 KFT-LBS, FR: 1000-1050 GPM, SPP: 3700-3900 PSI. - BACK REAM EVERY STAND WITH 75 RPM - PUMP 30-50 BBL HI-VIS EVERY CONNECTION - DRILL WITH 3 PUMPS. - CONT. INCEASE MW TO IN STAGES 1.32 SG BEFORE TD.. - TQ FLUCTAUTED F/ 982M - 995M WITH DROP IN ROP TREND. MITIGATE AND INC RPM F/115-140 RPM * TOP OF NATIH A/B AT 986 M (18 M SHALLOWER). AVG ROP : 43.28 M\HR NOTE: - PREPARE 13-3/8" CASING, DRIFT, CLEAN AND COMMENCE INSTALLING CENTERLISER. - AFTER MU CONNECTION AT 1004M, STD #26 WASH OUT, RACK BACK SAME.
KZN-377 |  | INT1 |  | 2023-08-23 04:00 | 2023-08-23 05:30 | 1:30 | [6 empty] | Productive |  |  | - PUMP 100 HI VIS AND CIRCULATE MIN 2X BTMS UP AND HOLE CLEAN - FR: 1015 GPM, SPP: 3750-3850 PSI, 75 RPM,TRQ1-2 KFT-LBS. - NO LOSSES WAS ENCOUNTERED. OFFLINE: - CONDUCT PJSM PRIOR POOH WITH REAM BACK. Page 10 of 80
KZN-377 |  | INT1 |  | 2023-08-23 05:30 | 2023-08-23 13:15 | 7:45 | [6 empty] | Productive |  |  | - BACK REAM WITH 17.1/2'' BHA FROM 1021 M TO 564 M (INSIDE 18.5/8" CSG). - FR: 800-1000 GPM, SPP: 3780- 3320 PSI, ROT: 75 RPM, TQ: 2-10 KFT-LBS. - MONTIOR WELL, SHORT SYSTEM - WIPE ONE SINGLE DOWN AND CIRCULATE FOR 2 MINUTES BEFORE CONNECTION. -OBSERVE 3 OVERTORQUE CONNECTIONS.
KZN-377 |  | INT1 |  | 2023-08-23 13:15 | 2023-08-23 14:00 | 0:45 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN AT CSG SHOE. FR 1000 GPM , SPP 3220 PSI, 75 RPM, TRQ 1-2 KFT.LBS. MAINLY CUTTING FROM SHARGI.
KZN-377 |  | INT1 |  | 2023-08-23 14:00 | 2023-08-23 16:00 | 2:00 | [6 empty] | Productive |  |  | UNABLED TO PULL ON ELEVATOR INSIDE CASING , CONTINUE WITH PUMP OUT AND BACK REAM. - BACK REAMWITH 17.1/2'' BHA FROM 564 M TO 429 M. FR: 800-1000 GPM, SPP: 3200-3600 PSI, RPM: 75, TQ: 2-5 KLB.FT NOTE: - AT 486 M PUMP AND CIRCULATE 50 BBL OF HI-VIS.
KZN-377 |  | INT1 |  | 2023-08-23 16:00 | 2023-08-23 17:15 | 1:15 | [6 empty] | Productive |  |  | CONT. PUMP OUT OF HOLE 17.1/2" BHA F/ 429 M TO 285 M . FR: 800-850 GPM , SPP: 1800-2200 PSI.
KZN-377 |  | INT1 |  | 2023-08-23 17:15 | 2023-08-23 18:15 | 1:00 | [6 empty] | Productive |  |  | CONT POOH ON ELEVATOR FROM 285 M TO 145M. - RACK BACK 5 STANDS HWDP.
KZN-377 |  | INT1 |  | 2023-08-23 18:15 | 2023-08-23 19:00 | 0:45 | [6 empty] | Productive |  |  | PERFROM DROP INSPECTION AND SERVICE RIG.
KZN-377 |  | INT1 |  | 2023-08-23 19:00 | 2023-08-23 21:45 | 2:45 | [6 empty] | Productive |  |  | CONT. POOH 17 1/2" BHA FROM 145 M TO SURFACE. - RACK BACK 1X STAND 8 1/4" DC - L\D 8" HYDRAULIC JAR - RACK BACK 3X STANDS 8 1/4" DC - L\D 17-3/8"STAB ( 5% BALLED UP) - L\D 2X 9 1/2" DC - L\D BIT SUB - L\D NOV TK 625 BIT ( 30 % BALLED UP). AT SURFACE 21:15 HRS. NOTES: - BIT GRADING: 1-1-WT-A-X-I-NO-TD - CREW CHANGE HANDOVER AND TBT AT 20:00HRS. - MONITOR WELL ON TT.
KZN-377 |  | INT1 |  | 2023-08-23 21:45 | 2023-08-23 22:00 | 0:15 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR
KZN-377 |  | INT1 |  | 2023-08-23 22:00 | 2023-08-23 23:00 | 1:00 | [6 empty] | Productive |  |  | TBT, - DISCONNECT FLOW LINE. - RIG DOWN RISER USING CRANE. OFFLINE: PREPARED FRANKS TRS EQUIPMENT
KZN-377 |  | INT1 |  | 2023-08-23 23:00 | 2023-08-23 23:15 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR RU FRANKS TRS EQUIPMENTS Page 11 of 80
KZN-377 |  | INT1 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 | [6 empty] | Productive |  |  | RIG UP FRANKS TRS EQUIPMENT: SERVICE LOOP, FA-1, POWER UNIT OFFLINE: - REMOVE LANDING BASE. - COMMENCE MIXING CEMENT SPACER
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 02:15 | 2:15 | [6 empty] | Productive |  |  | CONT. RIG UP FRANKS TRS EQUIPMENT: SERVICE LOOP, FA-1, POWER UNIT. - PERFROM TEMP 3RD PARTY DROP INSPECTION. OFFLINE: - REMOVE LANDING BASE AND FLUSH CUT 18 5/8" CSG. COVER THE HOLE WITH A GRATING. - HOT CUT 18-5/8" COUPLING VERTICALLY FROM BOTH SIDES TO ENABLE TO REMOVE AND PULL THE CLAMP (LL).
KZN-377 |  | INT1 |  | 2023-08-23 02:15 | 2023-08-23 02:30 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 13.3/8" CASING RUNNING
KZN-377 |  | INT1 |  | 2023-08-23 02:30 | 2023-08-23 03:45 | 1:15 | [6 empty] | Productive |  |  | - REMOVE MASTER BUSHING - P/U WELLHEAD BY & INSTALL IN ROTARY. - INSTALL BACK MASTER BUSHING AND PUT WELLHEAD PUP JOINT ON CASING SLIPS - P/U 13 3/8", L-80, 72PPF, BTC LANDING JOINT AND MADE UP THE SAME TO WELLHEAD. (MUT 16.3 KFT-LBS) - L/D WELL HEAD WITH LANDING JOINT.
KZN-377 |  | INT1 |  | 2023-08-23 03:45 | 2023-08-23 04:15 | 0:30 | [6 empty] | Productive |  |  | - REMOVE MASTER BUSHING. - RU FRANKS FMS SLIPS
KZN-377 |  | INT1 |  | 2023-08-23 04:15 | 2023-08-23 05:30 | 1:15 | [6 empty] | Productive |  |  | PU 13.3/8" REAMER SHOE ASSEMBLY - RUN SHOE AND FUNCTION TEST-OK. - P/U 13 3/8", 72PPF, L-80 BTC CROSSOVER PUP JT ( DINO VAM PIN X BTC BOX) - MU13 3/8", 72PPF, L-80BTC FLOAT COLLAR ASSEMBLY & M/U TO REAMER SHOE JOINT ( M\UP WITH FA-1 ) - FILLED UP THE SHOE TRACK & FUNCTION TESTED - OK. - APPLIED THREAD LOCK ON SHOE TRACK CONNECTIONS.
KZN-377 |  | INT1 |  | 2023-08-23 05:30 | 2023-08-23 15:00 | 9:30 | [6 empty] | Productive |  |  | P/U 13 3/8", L-80, 72PF BTC CASING JOINTS & RIH TO 992 M. - MONITOR ANNULAS LEVEL & CLEAR CELLAR VOLUME USING CELLAR PUMP. - FILL UP EVERY JOINT WHILE RIH VIA FA-1. - TORQUE UP CONNECTIONS TO THE DIAMOND MARK, USING FA-1 (~11000FT.LBS). - TRIPPING SPEED: 9-11 JNT/HR. AT 08:15 CREW CHANGE AND HANDOVER. Page 12 of 80
KZN-377 |  | INT1 |  | 2023-08-23 15:00 | 2023-08-23 15:30 | 0:30 | [6 empty] | Productive |  |  | AT 992 M STRING START TO TAKE WEIGHT. APPLY UP TO 60 KLBS , NO PROGRESS. ATTEMPT TO WASH DOWN WITH 250 GPM , STRING TAKE WEIGHT.
KZN-377 |  | INT1 |  | 2023-08-23 15:30 | 2023-08-23 23:45 | 8:15 | [6 empty] | Productive |  |  | WASH AND REAM DOWN WITH 13.3/8" CASING FROM 992 M TO 1010 M FR 250-350 GPM, SPP 500-700 PSI, WOB UP TO 30 KLBS, RPM 40-70 , TRQ6-8 KFT.LBS( LIMITED TORQUE TO 9 KFT.LBS) UNABLE TO PROGRESS FURTHER THAN 1010 M AS STRING STALLED AND TORQUE REACHED TL MAX 9 KFT.LBS AND PRESSURE INC F/550 TO 850 PSI. DECISSION MADE TO SET CASING SHOE AT 1006 M.( 20M INTO NATIH) AT 20:00 CREW CHANGE AND HANDOVER.
KZN-377 |  | INT1 |  | 2023-08-23 23:45 | 2023-08-24 | 0:15 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN WHILE RECIPROCATING STRING. FR 350 GPM, SPP 520 PSI
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN WHILE RECIPROCATING STRING. - FR 350 GPM, SPP 520 PSI. - TAG BOTTOM AT 1010M WITH NO ROTATION OK. - NO GAIN NO LOSS. OFFLINE: - LOAD CEMENT HEAD WITH 13-3/8"NR BOTTOM AND TOP PLUGS, NWSL WITNESS.
KZN-377 |  | INT1 |  | 2023-08-23 01:00 | 2023-08-23 02:00 | 1:00 | [6 empty] | Productive |  |  | LAY DOWN 2JOINTS ( #83 AND 82). - CHECK THREAD OK.
KZN-377 |  | INT1 |  | 2023-08-23 02:00 | 2023-08-23 02:15 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR P/U & M/U WELLHEAD
KZN-377 |  | INT1 |  | 2023-08-23 02:15 | 2023-08-23 04:45 | 2:30 | [6 empty] | Productive |  |  | - P/U AND MADE UP WELL HEAD ASSEMBLY TO CASING STRING, ORIENTATE STRING FOR SOV. - GOT DIFFICULTIES MU WH ASSY TO CAING STRING - RD FMS SLIPS AND RU MASTER BUSHING - CLEAN CELLAR FROM CUTTINGS - RAN IN, M/U LANDING BASE IN CELLAR AND LANDED OFF STRING CONFIRMING CENTRAL. DN WT 235 KLBS. - WRONG CENTERLISER INSTALLED BELOW WH, REMOVE SAME - 13 3/8" CSG SHOE @ 1005.9 M,FLOAT COLLAR @ 989.27 M.
KZN-377 |  | INT1 |  | 2023-08-23 04:45 | 2023-08-23 05:15 | 0:30 | [6 empty] | Productive |  |  | CONT. CIRCULATE HOLE CLEAN WITH 350 GPM, SPP 510 PSI. MEANWHILE: RU CEMENT LINES RDTRS EQUIPMENT Page 13 of 80
KZN-377 |  | INT1 |  | 2023-08-23 05:15 | 2023-08-23 05:45 | 0:30 | [6 empty] | Productive |  |  | RIG UP CEMENT HEAD. FLUSH CEMENT LINE. CONNECT CEMENT LINE TO CEMENT HEAD.
KZN-377 |  | INT1 |  | 2023-08-23 05:45 | 2023-08-23 06:30 | 0:45 | [6 empty] | Productive |  |  | PUMP FROM RIG PUMP THROGH CEMENT HEAD WITH 250 GPM, SPP 160 PSI MEANWHILE - PREPARE FOR MIX FLUID AND SURFACE LINE TEST. - PJSM FOR CEMENT JOB.
KZN-377 |  | INT1 |  | 2023-08-23 06:30 | 2023-08-23 06:45 | 0:15 | [6 empty] | Productive |  |  | PRESSURE TEST CEMENT LINE TO 4500 PSI- GOOD TEST
KZN-377 |  | INT1 |  | 2023-08-23 06:45 | 2023-08-23 07:15 | 0:30 | [6 empty] | Productive |  |  | - PUMP 100 BBL OF TUNED SPACER BY RIG PUMP WITH 250 GPM/ XX PSI. MEANWHILE: CEMENTERS MIXING RETARDER AND THEN START PREPARING LEAD SLURRY.
KZN-377 |  | INT1 |  | 2023-08-23 07:15 | 2023-08-23 09:45 | 2:30 | [6 empty] | Productive |  |  | DROP BOTTOM PLUG AND VERIFIED THE DROP OF THE PLUG BY FLAG INDICATOR. - MIX AND PUMP 422 BBL OF 1.57SG LEAD SLURRY AT 5-6 BBL/MIN - MIX AND PUMP 103 BBL OF 1.89SG TAIL SLURRY AT 4-5 BBLMIN
KZN-377 |  | INT1 |  | 2023-08-23 09:45 | 2023-08-23 11:15 | 1:30 | [6 empty] | Productive |  |  | - DROP TOP PLUG - CMT UNIT PUMPED 10 BBL SPACER BEHIND. - SWITCH OVER TO RIG PUMPS AND CONT. CEMENT DISPLACEMENT PUMPING 473.4 BBLS OF 1.25 SG HYDROGARD MUD. - BUMPED PLUG WITH 510 PSI FINAL CIRCULATING PRESSURE, INCREASE THE PRESSURE TO 3200 PSI. - NO RECORDABLE LOSSES WHILE CMT. - DUMP TOTAL OF 195 BBL AS BELOW : 31 BBL OF CONTAMINATED MUD WITH SPACER. 68BBL OF NET SPACER. 42 BBL OF SPACER WITH CEMENT. 54 BBL NET CEMENT
KZN-377 |  | INT1 |  | 2023-08-23 11:15 | 2023-08-23 12:00 | 0:45 | [6 empty] | Productive |  |  | ****13.3/8"CASING INTEGRITY TEST TO 3200 PSI**** - LINE UP TO CEMENT UNIT FOR CASING TEST AND CHECK FLOATS. - EQUALIZE PRESSURE TO 3200 PSI AND OPEN LO-TRQ VALVE ON RIG FLOOR,ISOLATE RIG STANDPIPE MANIFOLD. - MONITOR PRESSURE FOR 30 MINS - PRESSURE STABLE. - BLED BACK VOLUME TO CEMENT UNIT - VOLUME RETURN 5.5 BBL MORE THAN CALCULATED MBV AND FLOW STREAM IS HIGH ( FLOATS NOT HOLDING). Page 14 of 80
KZN-377 |  | INT1 |  | 2023-08-23 12:00 | 2023-08-23 19:00 | 7:00 | [6 empty] | Non-Productive |  |  | * FLOATS ARE NOT HOLDING.* - STOP BLEEDING OFF MUD TO THE CEMENT UNIT DISPLACEMENT TANKS AND CLOSE THE WELL IN UNTIL CEMENT HAS REACHED 50 PSI COMPRESSIVE STRENGTH PLUS 2 HRS ( TOTAL WOC 5+2=7 HRS). - MEANWHILE MONITOR PRESSURE DURING WOC , OBSERVE PRESSURE BUILD UP TO 510 PSI.
KZN-377 |  | INT1 |  | 2023-08-23 19:00 | 2023-08-23 19:30 | 0:30 | [6 empty] | Productive |  |  | BLEED OFF PRESSURE TO TT AND FLOW CHECK 15 MINS. STATIC - BLLED OF TO 300 PSI (0.3 BBLS RETURENED), CLOSE BLEED OF VALVE, NO PRESSURE BUILD UP. - BLEED OFF TO ZERO (0.5 BBLS RETURENED). CLOSE BLEED OFF VALVE AND MONITOR FOR 5 MINS, NO PRESSURE. - TOTAL VOLUME RETURNED 0.8 BBLS.
KZN-377 |  | INT1 |  | 2023-08-23 19:30 | 2023-08-23 20:00 | 0:30 | [6 empty] | Productive |  |  | TBT, R/D CEMENT LINES AND CEMENT HEAD.
KZN-377 |  | INT1 |  | 2023-08-23 20:00 | 2023-08-23 20:45 | 0:45 | [6 empty] | Productive |  |  | - DISCONNECT WELLHEAD RUNNING TOOL FROM WELL HEAD. - POH AND DISCONNECT LANDING JOINT FROM RUNNING TOOL.
KZN-377 |  | INT1 |  | 2023-08-23 20:45 | 2023-08-23 23:00 | 2:15 | [6 empty] | Productive |  |  | - RD FRANKS TRS EQUIPMENTS
KZN-377 |  | INT1 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 | [6 empty] | Productive |  |  | - INSTALL CELLAR FRAMS & GRATING
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 03:00 | 3:00 | [6 empty] | Productive |  |  | - INSTALL SOVS ON WELLHEAD USING RIG WINCH AND TIGHTENED THE SAME - CONDUCT TBT AND REVIEW PRESSURE CHECK LIST WITH CAMERON - CAMERON P/T SOVS. - P/T LOWER SOVS TO 300/5000 PSI - 5/15 MINS. - P/T UPPER SOVS TO 300/10000 PSI - 5/15 MINS
KZN-377 |  | INT1 |  | 2023-08-23 03:00 | 2023-08-23 07:00 | 4:00 | [6 empty] | Productive |  |  | CREW TBT PRIOR NU BOP - N/U BOP ON WELLHEAD STACK. - TIGHTEN FASTLOCK CONNECTION. - REMOVE BOP SKID. - CONNECT KILL LINE AND CHOKE LINE. - CONNECT HYDRULIC CONTROL LINES.
KZN-377 |  | INT1 |  | 2023-08-23 07:00 | 2023-08-23 08:00 | 1:00 | [6 empty] | Productive |  |  | - NU MUD RISER AND FLOW LINE. - INSTALL MOUSE HOLE
KZN-377 |  | INT1 |  | 2023-08-23 08:00 | 2023-08-23 19:00 | 11:00 |  |  |  | RREP |  |  | Productive |  |  | - HAD ISSUE WITH SERIAL NUMBER AND COC'S OF THE UPPER AND LOWER RAM BLOCK. - OPEN THE UPPER AND LOWER TO GET THE SERIAL NUMBER OF BOTH SIDES AND CONFIRM WITH COS AND COC. - CLOSE BACK THE UPPER AND LOWER PIPE RAM.
KZN-377 |  | INT1 |  | 2023-08-23 19:00 | 2023-08-23 21:30 | 2:30 |  |  |  | RREP |  |  | Productive |  |  | REPLACE CHOKE LINE HOSE WITH NEW ONE. - SN 8960011, NEW OCT-22,TESTED TO 15000 PSI 3/61 MINS ON 21-OCT-2022, TESTED TO 10,000 PSI ON 02-09-2023)
KZN-377 |  | INT1 |  | 2023-08-23 21:30 | 2023-08-23 21:45 | 0:15 | [6 empty] | Productive |  |  | TBT PRIOR BOP PRESSURE TEST Page 15 of 80
KZN-377 |  | INT1 |  | 2023-08-23 21:45 | 2023-08-23 22:45 | 1:00 | [6 empty] | Productive |  |  | - P/UP AND M/UP TEST ASSEMBLY (TEST PLUG+DP TEST PIPE+SES+FOSV AND TDS) - RUN AND SETTEST PLUG INTO WH. - FLUSH THROUGH AND FILL BOP STACK WITH WATER. - TEST TEST PUMP AND LINES. - OPEN WH SOVS FOR LEAK PATH FOR TEST PLUG. MONITOR SAME.
KZN-377 |  | INT1 |  | 2023-08-23 22:45 | 2023-08-23 23:00 | 0:15 | [6 empty] | Productive |  |  | - FUNCTION TEST BOP RAMS. - BSR FUNCTIONED PRIOR RUNNG TEST ASSY.
KZN-377 |  | INT1 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 | [6 empty] | Productive |  |  | """ BOP PRESSURE TEST#1 """ - PERFORM BOP CONNECTION PRESSURE TEST TO 300 PSI /10000 PSI FOR 5 /5 MINS AGAINST LOWER PIPE RAM (MANUALLY LOCKED) & FOSV. GOOD TEST. - MANUALLY CLOSING LPR. ACCUMULATOR ISOLATED AND MANIFOLD PRESSURE BLED OFF TO ZERO. - ALL TDSIBOP VALES AND STAND PIPE MANIFOLD VALVES OPEN. - WH SOV OPEN AND MONITORED.
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | """ BOP PRESSURE TEST#2 """ - PERFORM BOP PRESSURE TEST TO 300 PSI /10000 PSI FOR 5 /5 MINS AGAINST UPPER PIPE RAM (MANUALLY LOCKED), HCR & FOSV.GOOD TEST. - MANUALLY CLOSING UPR. ACCUMULATOR ISOLATED AND MANIFOLD PRESSURE BLED OFF TO ZERO. - ALL TDSIBOP VALES AND STAND PIPE MANIFOLD VALVES OPEN. - WH SOV OPEN AND MONITORED. Page 16 of 80
KZN-377 |  | INT1 |  | 2023-08-23 01:00 | 2023-08-23 02:30 | 1:30 | [6 empty] | Productive |  |  | """ BOP PRESSURE TEST#5 """ - PERFORM BOP PRESSURE TEST TO 300 PSI /10000 PSI FOR 5 /5 MINS AGAINST BLIND SHEAR RAM (MANUALLY LOCKED), - PT BLIND/ SHEAR RAM, CHOKE LINE, KILL LINE, LO- TORQUE VALVE ON KILL LINE AND CHOKE MANIFOLD VALVES # 61, 62 AND 79.GOOD TEST. NOTE: - BACK OUT TEST STRING OFF TEST PLUG. PULL OUT TEST STRING. - CONNECT TEST UNIT ON CHOKE MANIFOLD, CLOSE VALVES # 61,62& 79 AND OPEN VALVE#78 ON CHOKE MANIFOLD - MANUALLY CLOSING BSR. ACCUMULATOR ISOLATED AND MANIFOLD PRESSURE BLED OFF TO ZERO. - ALL OTHER TDSIBOP VALES AND STAND PIPE / CHOKE MANIFOLD VALVES OPEN. - WH SOV OPEN AND MONITORED. - AFTER TEST COMPLETED, DE-ISOLATE ACCULATOR BACK TO NORMAL CONDITION.
KZN-377 |  | INT1 |  | 2023-08-23 02:30 | 2023-08-23 02:45 | 0:15 | [6 empty] | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
KZN-377 |  | INT1 |  | 2023-08-23 02:45 | 2023-08-23 03:00 | 0:15 | [6 empty] | Productive |  |  | - INSTALL WEAR BUSHING AND L/D RUNNING TOOL.
KZN-377 |  | INT1 |  | 2023-08-23 03:00 | 2023-08-23 03:30 | 0:30 | [6 empty] | Productive |  |  | - INSTALL MOUSE HOLE. - SERVICE BREAK TEST ASSY. - RU AND INSTALL AUTO SLIPS.
KZN-377 |  | INT1 |  | 2023-08-23 03:30 | 2023-08-23 03:45 | 0:15 | [6 empty] | Productive |  |  | - TBT FOR P/U AND RACK BACK DP.
KZN-377 |  | INT1 |  | 2023-08-23 03:45 | 2023-08-23 08:15 | 4:30 | [6 empty] | Productive |  |  | - PU AND RIH WITH 72 X G2 5" DP (19.5#) SINGLES - MONITOR WELL ON TT.
KZN-377 |  | INT1 |  | 2023-08-23 08:15 | 2023-08-23 08:30 | 0:15 | [6 empty] | Productive |  |  | - TBT AND CREW CHANGE.
KZN-377 |  | INT1 |  | 2023-08-23 08:30 | 2023-08-23 10:00 | 1:30 | [6 empty] | Productive |  |  | - POH AND RACK 24 X G2 5" DP (19.5#) STANDS TO THE MAST.
KZN-377 |  | INT1 |  | 2023-08-23 10:00 | 2023-08-23 10:15 | 0:15 | [6 empty] | Productive |  |  | - TBT PRIOR P/U, M/U AND RIH 12-1/4" BHA.
KZN-377 |  | INT1 |  | 2023-08-23 10:15 | 2023-08-23 11:15 | 1:00 | [6 empty] | Productive |  |  | - P/U AND M/U 12.1/4" BIT WITH NOV RSS VX800 AND FILTER SUB. Page 17 of 80
KZN-377 |  | INT1 |  | 2023-08-23 11:15 | 2023-08-24 | 12:45 |  |  |  | RREP |  |  | Non-Productive |  |  | WAIT ON DEDICATED SHEARING UNIT REGULATOR - OBSERVED THE SHEAR BOOSTER REGULATOR NOT HOLDING PRSSURE. - PREPARE COW DOC, ISOLATE DEDICATED SHEARING UNIT , REMOVE OLD REGULATOR. - NEW REGULATOR ON LOCATION 23:00 HRS. - RECIEVED REGULATOR HAS MAX PRESSURE IN/OUT 3000 PSI. MEAMWHILE - SERVICE MP# 1, 2 &3. - GREASING CHOKE MANIFOLD, GROUND MANIFOLDS. - HOUSE KEEPING.
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 02:00 | 2:00 |  |  |  | RREP |  |  | Non-Productive |  |  | WAIT ON DEDICATED SHEARING UNIT REGULATOR. MEAMWHILE - TABLE DISCUSSION WITH CREW ON WC DRILLS. - LD BIT AND RSS TOOL
KZN-377 |  | INT1 |  | 2023-08-23 02:00 | 2023-08-23 08:00 | 6:00 | [6 empty] | Productive |  |  | - PU, MU AND RIH 15 JTS HWDP+54 JTS G2 DP. - PERFORM BOP FUNCTION TEST FROM DRILLER PANEL. - POOH AND RACK BACK TUBULAR IN STANDS. - SLIP DRILL LINE. MEANWHILE, CONTINUE WAITING ON DEDICATED SHEARING UNIT REGULATOR. Page 18 of 80
KZN-377 |  | INT1 |  | 2023-08-23 08:00 | 2023-08-23 23:15 | 15:15 |  |  |  | RREP |  |  | Non-Productive |  |  | - RACK BACK 5 STANDS OF HWDPAND 18 STANDS OF 5" G. - SARA ENGINEER ARRIVE WITH UPDATED CERTIFICATE OF TEST. - FIXED THE SHEARING UNIT REGULATOR. - ATTEMPT TO FUNCTION TEST FROM THE REMOTE PANEL ( OFFICE AND DRILLER) , UNABLE TO FUCNTION FROM THE DRILLER PANEL. FIXED. *** DEDICATED SHEAR DRAWDOWN TEST** - PERFORM FUNCTION TEST FROM DRILLER REMOTE PANEL OK, 17 SEC CLOSING BLIND SHEAR RAM. - ELEC PUMP JUMP IN AT +/- 4700 PSI - AIR PUMPS JUMP IN AT 4500 PSI - AIR PUMP CUT OUT AT 4750-4800 PSI. - ELEC PUMP CUT OUT AT 5000 PSI. - OPEN SHEAR RAM FROM KOOMEY UNIT. - SWITCH OFF BOTH AIR AND ELEC PUMPS. - PERFROM FUNCTION TEST FROM TP PANEL, 15 SEC CLOSING BLIND SHEAR RAM. - FINAL PRESSURE 3200 PSI. - BLEED OFF REMAINING ACCUMULATOR PRESSURE. - SWITCH ON BOTH PUMPS - RECHARGE ACCUMULATORS BANKS IN 11 MINS. - AIR PUMP CUT OUT AT 4750 PSI. - ELEC PUMP CUT OUT AT 5000 PSI. MEANWHILE: - WORKING ON CALIBRATING GAUGES.
KZN-377 |  | INT1 |  | 2023-08-23 23:15 | 2023-08-23 23:30 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | PJSM PRIOR P/U, M/U AND RIH 12-1/4" BHA.
KZN-377 |  | INT1 |  | 2023-08-23 23:30 | 2023-08-24 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | P/U, M/U AND RIH 12-1/4"BHA TO 10 M AS FOLLOW: - PICK UP NEW 12-1/4” PDC BITNOV, TKC66, S423, HDBS GTi75WKHO (3x12 & 6X13/32 NOZZLES) - 8" NOV RSS VX800 (C/W 12-1/8" SLEEVE STAB.) - 8.25" FILTER SUB NOTES: - USED MANUAL TONGS TO MU NOV TOOLS.
KZN-377 |  | INT1 |  | 2023-08-23 | 2023-08-23 01:45 | 1:45 | [6 empty] | Productive |  |  | P/U, M/U AND RIH 12-1/4"BHA TO 100 M AS FOLLOW: - 8" FLOAT SUB. - 12.1/8" STABILIZER - 8" PBL SUB. - 9 X 8.1/4" DC (3 STDS F/ DERRICK). Page 19 of 80
KZN-377 |  | INT1 |  | 2023-08-23 01:45 | 2023-08-23 02:00 | 0:15 | [6 empty] | Productive |  |  | PERFORM KICK DRILL WITH CREW D - DISCUSS SECURE WELL WITH DC ACROSS BOP (NON-SHEARABLE). - CROSS OVER WITH FOSV READY, DC LIFT SUB NC 50 CONNECTION AND CAN PUMP THRU - DISCUSS DROPPING STRING SCENARIO.
KZN-377 |  | INT1 |  | 2023-08-23 02:00 | 2023-08-23 03:30 | 1:30 | [6 empty] | Productive |  |  | RESUME P/U, M/U AND RIH 12-1/4"BHA TO 195 M AS FOLLOW: - 1 X 8.1/4" DC (FROM GROUND). - DLR - 2 X 8 1/4" DC (FROM GROUND). - 8" POWER STROKE DRILLING JAR. ( WT BELOW JAR 50 KLBS) - 3 X 8 1/4" DC (ONE STAND FROM DERRICK) - XO - 1 STAND HWDP FROM DERRICK.
KZN-377 |  | INT1 |  | 2023-08-23 03:30 | 2023-08-23 03:45 | 0:15 | [6 empty] | Productive |  |  | MU TDS, BREAK CIRC, SHALLOW TEST NOV VX800 TOOL AT FR: 750 GPM; SPP:1320 PSI. - INC: 0.21 DEG, AZM: 178.45 DEG, TEMP: BELOW 50 DEG C
KZN-377 |  | INT1 |  | 2023-08-23 03:45 | 2023-08-23 04:30 | 0:45 | [6 empty] | Productive |  |  | RESUME P/U, M/U AND RIH 12-1/4" BHA TO 448 M AS FOLLOW: - 9 STANDS HWDP FROM DERRICK. NOTES: - TOTAL BHA LENGTH: 448.14 M ,TOTAL BHA WT: 90 KLBS, WT BELOW JAR: 50 KLBS. - MAINTAIN TRIP SHEET.
KZN-377 |  | INT1 |  | 2023-08-23 04:30 | 2023-08-23 04:45 | 0:15 | [6 empty] | Productive |  |  | - REPLACED WASH OUT SINGLE OF G3 DP STAND.
KZN-377 |  | INT1 |  | 2023-08-23 04:45 | 2023-08-23 05:00 | 0:15 | [6 empty] | Productive |  |  | CREW CHANGE AND HANDOVER.
KZN-377 |  | INT1 |  | 2023-08-23 05:00 | 2023-08-23 05:15 | 0:15 | [6 empty] | Productive |  |  | RIH 12-1/4"BHA FROM 448M TO 564 ON 5" DP.
KZN-377 |  | INT1 |  | 2023-08-23 05:15 | 2023-08-23 05:30 | 0:15 | [6 empty] | Productive |  |  | MU TDS, BREAK CIRC, SURVEY AT 18-5/8" SHOE AT FR: 700 GPM; SPP:1750 PSI. - INC: 0.46 DEG, AZM: 193.43 DEG, TEMP: BELOW 50 DEG
KZN-377 |  | INT1 |  | 2023-08-23 05:30 | 2023-08-23 06:45 | 1:15 | [6 empty] | Productive |  |  | RIH 12-1/4"BHA FROM 564 M TO 938 M ON 5" DP. - MONITOR DISPLACEMENT ON TRIP TANK
KZN-377 |  | INT1 |  | 2023-08-23 06:45 | 2023-08-23 07:15 | 0:30 | [6 empty] | Productive |  |  | WASH DOWN FROM 938 M UNTIL TAG CEMENT/ WIPER PLUGS AT 988 M FR: 350 GPM, SPP: 580 PSI
KZN-377 |  | INT1 |  | 2023-08-23 07:15 | 2023-08-23 07:30 | 0:15 | [6 empty] | Productive |  |  | SURVEY AT 984.89 AT FR: 700 GPM; SPP:1950 PSI. - INC: 0.09 DEG, AZM: 344.44 DEG.
KZN-377 |  | INT1 |  | 2023-08-23 07:30 | 2023-08-23 08:15 | 0:45 | [6 empty] | Productive |  |  | PERFORM D1 & D4 WELL CONTROL DRILLS WITH CREW # A - GOOD RESPONSE FROM CREW, AD AND DR TRAINED IN CHOKE, HAD AFTER ACTION REVIEW Page 20 of 80
KZN-377 |  | INT1 |  | 2023-08-23 08:15 | 2023-08-23 09:00 | 0:45 | [6 empty] | Productive |  |  | - TOOK SCR - TOOK FLOW BACK BASE LINE WITH 700 GPM , RIG RECORDED 31 BBL, MUD LOGGER RECORDED 21 BBL - TOOK FLOW BACK BASE LINE WITH 900 GPM , RIG RECORDED 40 BBL, MUD LOGGER RECORDED 30 BBL
KZN-377 |  | INT1 |  | 2023-08-23 09:00 | 2023-08-23 11:30 | 2:30 | [6 empty] | Productive |  |  | DRILL SHOE TRACK DRILL CEMENT WIPER PLUGS AND FLOAT COLLAR FROM 988 M TO 995 M FR 800 GPM, SPP 2400-2600 PSI, WOB 10 - 15 KLBS, RPM 80 , TRQ 2 -7 KFT.LBS.
KZN-377 |  | INT1 |  | 2023-08-23 11:30 | 2023-08-23 12:00 | 0:30 | [6 empty] | Productive |  |  | DRILL OUT SHOE TRACK FROM 995 M TO 1004.7 M FR 800 GPM, SPP 2400-2800 PSI, WOB 10 - 15 KLBS, RPM 80 , TRQ 2 -7 KFT.LBS. TAG REMER SHOE AT 1004.7 M.
KZN-377 |  | INT1 |  | 2023-08-23 12:00 | 2023-08-23 13:00 | 1:00 | [6 empty] | Productive |  |  | DRILL OUT REAMER SHOE FROM 1004.7 M TO 1006 M FR 800 GPM, SPP 2400-2800 PSI, WOB 10 - 15 KLBS, RPM 80 , TRQ 2 -12 KFT.LBS.
KZN-377 |  | INT1 |  | 2023-08-23 13:00 | 2023-08-23 14:15 | 1:15 | [6 empty] | Productive |  |  | DRILL OUT RAT FROM 1006 M TO 1021 M FR 800 GPM, SPP 2400-2600 PSI, WOB 5 - 15 KLBS, RPM 80 , TRQ 2 -5 KFT.LBS.
KZN-377 |  | INT1 |  | 2023-08-23 14:15 | 2023-08-23 14:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK - WELL STATIC
KZN-377 |  | INT1 |  | 2023-08-23 14:30 | 2023-08-23 15:00 | 0:30 | [6 empty] | Productive |  |  | DRILL NEW FORMATION FROM 1021 M TO 1024 M. FR 800 GPM, SPP 2400-2600 PSI, WOB 5 - 11 KLBS, RPM 80 , TRQ 2 -5 KFT.LBS.
KZN-377 |  | INT1 |  | 2023-08-23 15:00 | 2023-08-23 15:30 | 0:30 | [6 empty] | Productive |  |  | - CIRCULATE & CONDITION MUD - CONFIRM 100% FRESH FORMATION AT SURFACE - MW IN = MW OUT = 1.25 SG
KZN-377 |  | INT1 |  | 2023-08-23 15:30 | 2023-08-23 15:45 | 0:15 | [6 empty] | Productive |  |  | - POOH TO INSIDE CASING - LINE UP TO PUMP THROUG KILL LINE AND STRING FOR FIT
KZN-377 |  | INT1 |  | 2023-08-23 15:45 | 2023-08-23 16:45 | 1:00 | [6 empty] | Productive |  |  | ***** FIT AT 13-3/8 CASING SHOE (NATIH A/B) TO 1.66 SG OVER 1.25 SG MUD IN HOLE USING MUD PUMPS ***** - PJSM. - CLOSED UPPER PIPE RAMS. - START PUMPING WITH RIG PUMPS AT 0.5 BBL/MIN PUMP RATE. - PRESSURE UP WELL TO 600 PSI. - MONITOR PRESSURE FOR 30 MINUTES. - BLED OFF PRESSURE. - FIT PRESSURE REACHED WAS 600 PSI WITH 1.25 SG TEST FLUID, EMW ACHIEVED WAS 1.66 SG. - PUMPED VOLUME 1BBL, BLED BACK VOLUME 1BBL.
KZN-377 |  | INT2 |  | 2023-08-23 16:45 | 2023-08-23 17:15 | 0:30 | [6 empty] | Productive |  |  | WASH DOWN TO 1024M, MEANWHILE FLUSH THROUGH CHOKE MANIFOLD AND MGS Page 21 of 80
KZN-377 |  | INT2 |  | 2023-08-23 17:15 | 2023-08-24 | 6:45 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1024 M TO 1110 M. FR 800-850 GPM, SPP 2470-2750 PSI, WOB 10-20 KLBS , RPM 60-80 , TQ 2-8KFT.LBS - REAM 3 M UP/DN EVERY CONNECTION AT 45 RPM. - CONTROL DRILLING PARAMETERS TILL DLR GET OUT FROM SHOE - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY STAND - SLOW AND DROP IN ROP AT 1042 M, 1053 M, 1063 M, 1085 M, DRILLING SUMMARY ================== FOOTAGE DRILLED: 89 M DAILY BIT HRS: 5.68 HR AVG ROP: 15.67 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1050.130.01309.8 1079.480.04175.37
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1110 M TO 1117M. (DLR EXIT SHOE WHEN BIT AT 1117 M). FR 850 GPM, SPP 2470-2750 PSI, WOB 10-20 KLBS , RPM 60-80 , TQ 2-8KFT.LBS - MAKE CONNECTION AND TAKE SURVEY - CONTROL DRILLING PARAMETERS TILL DLR GET OUT FROM SHOE - SLOW AND DROP IN ROP AT 1113 M, VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1107.210.01159.36
KZN-377 |  | INT2 |  | 2023-08-23 01:00 | 2023-08-23 01:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK DUE TO DISCRIPENCY IN FLOW BACK . WELL STATIC
KZN-377 |  | INT2 |  | 2023-08-23 01:15 | 2023-08-23 01:30 | 0:15 | [6 empty] | Productive |  |  | PERFROM D2 DRILL (KICK WHILE DRILLING).
KZN-377 |  | INT2 |  | 2023-08-23 01:30 | 2023-08-23 02:00 | 0:30 | [6 empty] | Productive |  |  | RIG SERVICE AND ADJUST HOOK LOAD. Page 22 of 80
KZN-377 |  | INT2 |  | 2023-08-23 02:00 | 2023-08-23 06:00 | 4:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1117 MTO 1207 M. FR 850-900 GPM, SPP 2670-2750 PSI, WOB 20-25 KLBS , ROT 140-150 RPM, TQ 5-10 KFT.LBS - REAM 3 M UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - RECORD MWD SURVEY EVERY 1 STAND. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - FROM 1578M, USING TWO MUD PUMPS W/870 GPM.(MP# CHANGE SEAL AND WEAR PLATE) - AVG ROP = 34 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1136.670.01278.13 1166.150.03127.32
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 07:00 | 1:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1207 MTO 1212 M. FR 900 GPM, SPP 2980-3030 PSI, WOB 25-30 KLBS , ROT 160 RPM, TQ 1-3 KFT.LBS - AVG ROP = 2-3 M/HR
KZN-377 |  | INT2 |  | 2023-08-23 07:00 | 2023-08-23 07:45 | 0:45 | [6 empty] | Productive |  |  | - OBSERVED SLOW ROP TO 2-3 M/HR. - P/UP OFF BOTTOM FULL STAND - CIRCULATE WITH 100-120 RPM FOR 5 MINUTES, STOP ROTATION, CIRCULATE AGAIN WITH 100 RPM - RUN BACK TO BOTTOM AND APPLY WOB GRADUALLY TO 35 KLBS Page 23 of 80
KZN-377 |  | INT2 |  | 2023-08-23 07:45 | 2023-08-23 16:00 | 8:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1212 M TO 1485 M. FR 900 GPM, SPP 2670-3380 PSI, WOB 30 KLBS, ROT 150-170 RPM, TQ 2-10 KFT.LBS - OBSERVED ROP STARTED PICKING UP AGAIN FROM 1213M. - REAM 3 M FOR 1-1.5MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - RECORD MWD SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 44.3 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1199.860.07237.54 1222.100.06338.01 1280.970.3821.67 1367.50.31120.77 1453.60.52210.92
KZN-377 |  | INT2 |  | 2023-08-23 16:00 | 2023-08-23 16:15 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE.
KZN-377 |  | INT2 |  | 2023-08-23 16:15 | 2023-08-24 | 7:45 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1485 M TO 1723 M. FR 870-900 GPM, SPP 3240-3380 PSI, WOB 30-35 KLBS, ROT 150-170 RPM, TQ 8-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - RECORD MWD SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 43.51 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1539.670.41304.85 1625.670.27222.30 1712.890.24017.10 HOLD TBT AND HANDOVER WITH CREW AT 20:00 HRS. LAST 24 HRS DRILLING SUMMARY ================== FOOTAGE DRILLED: 613 M DAILY BIT HRS: 16.42 HR AVG ROP: 37.33 M/HR Page 24 of 80
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 05:15 | 5:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 1723 M TO 1838 M. FR 870-900 GPM, SPP 3250-3430 PSI, WOB 30-35 KLBS, ROT 140-160 RPM, TQ 9-11 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - RECORD SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 33.5 M/HR NOTE: MUD PUMP #2 ISOLATED DUE TO MODULE FAILURE. WORKING ON REPLACING MODULE. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1770.670.19153.32 1827.670.25238.10
KZN-377 |  | INT2 |  | 2023-08-23 05:15 | 2023-08-23 06:15 | 1:00 | [6 empty] | Productive |  |  | CONT. DRILLING 12 1/4" HOLE SECTION FROM 1838 M TO 1851M. FR 800 GPM, SPP 2950-2980 PSI, WOB 15-20 KLBS , RPM 140-150 , TRQ 5-8 KFT.LBS - CONTROL ROP TO +/-15 M/HR PRIOR ENTERING HABSHAN. - OBSERVE LOSSES START FROM DEPTH 1838M. 20 BPH. - EXPERIENCE LATERAL VIBRATION IN HABSHAN FORMATIONS- MITIGATE IT BY REDUCING WOB AND RPM OR P\U OFF-BOTTOM.
KZN-377 |  | INT2 |  | 2023-08-23 06:15 | 2023-08-23 06:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK WELL, STATIC LOSSES = 16 BBLS/HR
KZN-377 |  | INT2 |  | 2023-08-23 06:30 | 2023-08-23 07:00 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | WORK ON MUD PUMP #1 PISTON, MEANWHILE CIRCULATE OFF BOTTOM WITH 330 GPM. Page 25 of 80
KZN-377 |  | INT2 |  | 2023-08-23 07:00 | 2023-08-23 11:00 | 4:00 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 1851 M TO 1897 M. FR 800 GPM, SPP 2900-2990 PSI, WOB 30-35 KLBS, ROT 140-160 RPM, TQ 9-11 KFT.LBS - LOAD ACTIVE SYSTEM SLOWLY WITH BAROFIBER AND BAROCARB AS PER DECISION TREE. - LOSSES START TO DROP TO NO LOSSES FROM 1856 M. - HABSHAN AT 1851 M. - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 15 M/HR
KZN-377 |  | INT2 |  | 2023-08-23 11:00 | 2023-08-23 14:00 | 3:00 |  |  |  | RREP |  |  | Non-Productive |  |  | OBSERVE LEAK IN THE SUCETION LINE BUTTERFLY VALVE OF MUD PUMP #2 WHILE CHANGING MODULE. STOP DRILLING TO FIX LEAK AS IT IS NOT POSSIBLE TO CONTINUE WITH 2 PUMPS DUE TO LINE UP WHERE BOTH MUD PUMP # 2 & 3 USING THE SAME SUCTION LINE. P/UP OFF BOTTOM AND CIRCULATE WELL WITH 370 GPM, 804 PSI WHILE FIXING THE LEAK.
KZN-377 |  | INT2 |  | 2023-08-23 14:00 | 2023-08-23 17:30 | 3:30 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 1897 M TO 1975 M. FR 800 GPM, SPP 2900-3000 PSI, WOB 30-35 KLBS, ROT 140 RPM, TQ 9-11 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 30 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 24.3 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 1914.90.12230.11
KZN-377 |  | INT2 |  | 2023-08-23 17:30 | 2023-08-23 17:45 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE.
KZN-377 |  | INT2 |  | 2023-08-23 17:45 | 2023-08-23 19:00 | 1:15 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 1975 M TO 2003 M. FR 800 GPM, SPP 2900-3000 PSI, WOB 30-35 KLBS, ROT 140 RPM, TQ 9-12 KFT.LBS.
KZN-377 |  | INT2 |  | 2023-08-23 19:00 | 2023-08-23 19:15 | 0:15 | [6 empty] | Productive |  |  | BEFORE MAKING CONNECTION PERFROM D2 DRILL WITH CREW B. - GOOD RESPONSE FROM ML/DRILLER. Page 26 of 80
KZN-377 |  | INT2 |  | 2023-08-23 19:15 | 2023-08-24 | 4:45 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 2003 M TO 2100 M. FR 800-850-900 GPM,SPP 2940-3300-3520 PSI, WOB 25-35 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 24.1 M/HR - VX800: LEVEL II LATERAL VIBRATION 2068, 2081M.MITIGATE SAME. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2003.70.11183.11 2087.70.09226.77 HOLD TBT AND HANDOVER WITH CREW AT 20:00 HRS. LAST 24 HRS DRILLING SUMMARY ================== FOOTAGE DRILLED: 377 M DAILY BIT HRS: 15.42 HR AVG ROP: 24.45 M/HR
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 2100 M TO 2226 M. FR 850-900 GPM, SPP 3250-3670 PSI, WOB 30-40 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 26.81 M/HR - VX800: LEVEL II LATERAL VIBRATION 2134M, 2174M.2203M. - AT 2148 M TAKE SCRS. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2003.700.11183.11 2087.780.09226.77 2174.670.12221.71 Page 27 of 80
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 08:45 | 2:45 | [6 empty] | Productive |  |  | CONT. DRILL 12.25" HOLE AS PER ROAD MAP FROM 2226 M TO 2290 M. FR 850-900 GPM, SPP 3250-3670 PSI, WOB 30-45 KLBS, ROT 130-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 27.2 M/HR NOTE: MWD LOST SIGNAL WHILE DRILLING AND PRIOR TO HAVE A PRESSURE DROP ISSUE. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2261.70.3115.26
KZN-377 |  | INT2 |  | 2023-08-23 08:45 | 2023-08-23 10:00 | 1:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - OBSERVE A SUDDEN DECREASE IN SPP FROM 3780 PSI TO 3370 PSI (400 PSI). - P/UP OFF BOTTOM, SPP CONTINUED DROPPING TO 3110 PSI. - CHECK SURFACE LINES AND MUD PUMPS EACH ONE BY ONE, COULDN'T FIND ANY ISSUE WITH PUMPS. - CHECK EACH PUMP INDIVIDUALLY, MP#FR (GPM)PRESSURE (PSI) 1320630 2312616 3311620 - ISOLATE MP#1 AND OPEN SCREEN, FOUND CLEAN. (MP #2 SCREEN WAS CLEANED 1 DAY BEFORE) - AT 9:30, OBSERVE PRESSURE INCREASING SLOWLY BACK TO NORMAL FOR MP# 2 &3 - LINE UP MP#1 BACK AND CHECKED SPP WITH ALL MUD PUMPS, FOUND IT SIMILAR TO NORMAL FR (GPM)SPP (PRESSURE) 8002930 8503310 9003670 Page 28 of 80
KZN-377 |  | INT2 |  | 2023-08-23 10:00 | 2023-08-23 11:45 | 1:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | - OBSERVE STILL NO SIGNAL WITH MWD TOOL. - TROUBLESHOOT THE TOOL BY RECYCLING MUD PUMPS, NO SUCCESS - CHANGE OUT AND REPLACE THE NOV PRESSURE TRANCEDUCER AND RECYCLE PUMPS, NO SUCCESS. MWD TOOL FAILED. - PUMP 50 BBLS OF HI VIS AND CIRCULATE HOLE CLEAN, MEANWHILE DISCUSS THE WAY FORWARD WITH OFFICE. - ONCE HI VIS ON SURFACE, RECYCLE PUMPS, STILL NO SIGNAL. - DECISION MADE TO POOH AND CHANGE BHA.
KZN-377 |  | INT2 |  | 2023-08-23 11:45 | 2023-08-23 12:15 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | - FLOW CHECK WELL, STATIC. - TOOK SCR. - INSTALL AIR SLIPS
KZN-377 |  | INT2 |  | 2023-08-23 12:15 | 2023-08-23 12:30 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | POOH 12 1/4" BHA ON ELEVATOR FROM 2290 MTO 2225 M. NOTES: - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | INT2 |  | 2023-08-23 12:30 | 2023-08-23 14:15 | 1:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | - OBSERVE OVERPULL MORE THAN 60 KLB AT 2225 M, WORK STRING TO PASS THROUGH THE TIGHT SPOT, NO SUCCESS. - ATTEMPT TO PUMP OUT WITH 800 GPM, 2920 PSI, NO SUCCESS AS OVER PULL REACHED 60 KLBS AT THE SAME SPOT. - BACK REAM FROM 2225 M TO 2195 M WITH 45 RPM, 900 GPM, 3600 PSI. -> SLOW PROGRESS WHILE BACKREAMING AT 2225 M AS STRING WAS GETTING STALLED SEVERAL TIMES AS TORQUE WAS HITTING AT 16-17 KFT.IBF. AFTER PASSING THE TIGHT SPOT, CLEAR THE AREA UP/DOWN BEFORE BREAKING CONNECTION
KZN-377 |  | INT2 |  | 2023-08-23 14:15 | 2023-08-23 14:30 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | PUMP OUT FROM 2195 M TO 2166 M, WITH 900 GPM, SPP 3670 PSI.
KZN-377 |  | INT2 |  | 2023-08-23 14:30 | 2023-08-23 17:00 | 2:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONTINUE POOH 12 1/4" BHA ON ELEVATOR FROM 2166 M TO 1595 M. NOTES: - MONITOR WELL THROUGH TRIP TANK. - TIGHT SPOT AT 1818 M. UNABLE TO PASS THROUGH AS OVERPULL REACH 60 KLBS. PUMP OUT THE TIGHT SPOT THEN CONTINUE POOH ON ELEVATOR. Page 29 of 80
KZN-377 |  | INT2 |  | 2023-08-23 17:00 | 2023-08-23 22:30 | 5:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - WHILE PULLING UP, OBSERVE OVER PULL 60-90 KLBS. - ATTEMPT TO GO DOWN, OBSERVE HELD UP. - ATTEMPT TO CIRCULATE AND PUMP OUT, MANAGED TO GET FULL CIRCULATION WITH NO PUMP RESTRICTION BUT UNABLE TO MOVE STRING. - ATTEMPT TO ESTABLISH ROTATION, NO SUCCESS AS STRING WAS GETTING STALLED. SET TORQUE LIMIT TO 20 KFT.IBF (80 % OF THE LEAST MAKE UP TORQUE OF 26K). - ATTEMPT TO FREE STRING BY WORKING STRING UP/DOWN, NO SUCESS. STRING GOT STUCK. - ACTIVATE JARRING DOWN/UP WITH NO SUCCESS. - DISCUSSED WITH OFFICE AGREED TO CONT. JARRING DOWN AND MEANTIME PREPARE FOR N-FLOW PILL - REMOVE AUTO SLIPS AND INSTALL HOLE COVER. CREW CHANGE AND TBT AT 20:00 HRS.
KZN-377 |  | INT2 |  | 2023-08-23 22:30 | 2023-08-23 23:15 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | CIRCULATE BOTTOMS UP WITH TRACES OF SMALL CUTTING OVER SHAKERS (MAINLY SHUAIBA LS AND MAFRAQ CLAYSTONE) - FR: 810 GPM WITH PP: 2800 PSI. - VISUAL DROPS INSPECTION.
KZN-377 |  | INT2 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 |  |  |  | DPRB |  |  | Non-Productive |  |  | WORK ON STUCK PIPE. - CONT. JARRING DOWN AND MEANTIME PREPARE FOR N-FLOW PILL.
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 04:30 | 4:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. JARRING DOWN AND MEANTIME PREPARE FOR N-FLOW PILL. WORK ON STUCK PIPE.
KZN-377 |  | INT2 |  | 2023-08-23 04:30 | 2023-08-23 05:30 | 1:00 |  |  |  | DPRB |  |  | Non-Productive |  |  | PUMP HV PILL AND CIRCULATE BOTTOMS UP WITH TRACES OF SMALL CUTTING OVER SHAKERS (MAINLY SHUAIBA/N-UMRLS AND MAFRAQ RED CLAYSTONE) - FR: 810 GPM WITH PP: 2820 PSI. - POST JARRING DROPS INSPECTION.
KZN-377 |  | INT2 |  | 2023-08-23 05:30 | 2023-08-23 07:00 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CONT. JARRING DOWN AND MEANTIME PREPARE FOR N-FLOW PILL. NOTE: - PERFORM POST JARRING INSPECTION Page 30 of 80
KZN-377 |  | INT2 |  | 2023-08-23 07:00 | 2023-08-23 09:15 | 2:15 |  |  |  | RREP |  |  | Non-Productive |  |  | BEFORE START CLEANING MIX TANKS AND SUCTION TANK, TRANSFERE MUD FROM THE TANKS TO RESERVE TANKS TO ACCOMODATE N FLOW PILL AND BRINE. OBSERVE A LEAK IN THE TRANSFER LINE VALVE THAT IS CONNECTING BETWEEN THE TANKS. WORK ON FIXTING AIR SEAL IN THE LINE. MEANWHILE, CONTINUE WORKING ON STRING. - RECIEVED N-FLOW PILL CHEMICALS AT 09:00. PROCEED TO PREPARE AND MIX THE PILL.
KZN-377 |  | INT2 |  | 2023-08-23 09:15 | 2023-08-23 12:30 | 3:15 |  |  |  | DPRB |  |  | Non-Productive |  |  | - CLEAN MIXING TANKS A, B & C AND SUCTION B. - FLUSH MUD PUMP #3 WITH WATER TO CLEAN THE MUD PUMP. MEANWHILE, CONTINUE WORKING ON JARRING DOWN STRING.
KZN-377 |  | INT2 |  | 2023-08-23 12:30 | 2023-08-23 14:00 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - START MIXING AND PREPARING N FLOW PILL WITH BRINE SPACER. MEANWHILE, - CONTINUE WORKING ON JARRING DOWN STRING. - WHILE JARRING DOWN, GOT STRING FREE SUCCEFULLY.
KZN-377 |  | INT2 |  | 2023-08-23 14:00 | 2023-08-23 15:30 | 1:30 |  |  |  | DPRB |  |  | Non-Productive |  |  | - ESTABLISH ROTATION WITH 45 RPM, INCREASE FLOW RATE TO 800 GPM TILL GOT FULL RETURN. - REAM DOWN FULL STAND TO 1617M WITH ROT 120 RPM, TQ 2-4 KFT-LBS, FR 850 GPM, PP 3000 PSI. - BACKREAM FULL STAND WITH 45 RPM, 900 GPM, 3300 PSI. OBSERVE ERATIC TORQUE FROM 1595 M TO 1592 M. NOTE: - CIRCULATE BOTTOMS UP AFTER GETTING STRING FREE. BU AT SURFACE SHOW 30-40% CAVING 0.5-1.5 (CM) ANGULAR, SPLINTERY, SUB ANGULAR CLAYSONE MAINLY GENERATED FROM NAHR UMAR - PUMP 50 BBLS HIVIS AND CIRCULATE HOLE CLEAN. AT SURFACE, SAMPLE SHOW 30-40% CAVING 2-5 (CM) ANGULAR, PLATY, TUBLAR CLAYSONE MAINLY GENERATED FROM NAHR UMAR Page 31 of 80
KZN-377 |  | INT2 |  | 2023-08-23 15:30 | 2023-08-23 18:00 | 2:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | - ATTEMPT TO PUMP OUT WITH 900 GPM, OBSERVE 40 KLBS OVER PULL AT 1582 M. - BACK REAM FROM 1585 M TO 1493 M WITH 45 RPM, 900 GPM, 3260 PSI. - TIGHT SPOTS AT 1566, 1554, 1550, 1542, 1537 M. - 2 X OVERTORQUED CONNECTIONS OBSERVED
KZN-377 |  | INT2 |  | 2023-08-23 18:00 | 2023-08-24 | 6:00 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONT. PUMP OUT AND BACK REAM OUT OF HOLE FROM 1493M TO 1108M WITH 850-900 GPM, 45 RPM - BACK REAM F/1387 - 1357M, F/1328-1270M, F/1242-1136M WITH 45 RPM, 900 GPM, 3200 -3050 PSI. - PUMP OUT F/1474 - 1387 M & F/1357-1328M, F/1270-1242M, F/1136-1108 WITH 900-850 GPM, 3260-2670 PSI. - TIGHT SPOTS AT F/1495-1476M, 1396M, F/1384-1365M, 1301M, 1296M, 1281M, 1273M, F/1238-1214M, F/1203-1194M, F/1174-1158M, 1145M, 1091M, 1033M. - 3 X OVERTORQUED CONNECTIONS OBSERVED. - CONTINUEOS STREAM OF CUTTING OVER SHAKER WHILE CIRCULATION, - F/ 1360-1120M, 40-60% CAVINGS, ANGULAR PLATY AND TUBULAR , CLAYSTONE: OLIVE GREY, GREENISH GREY, MEDIUM GREY IN PARTS. MAINLY GENERATED FROM NAHR UMAR FM. PRETOUR AND HANDOVER MEETING AT 20:00 HRS.
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONT. PUMP OUT AND BACK REAM OUT OF HOLE FROM 1108M TO 994M (INSIDE CASING) WITH 850-900 GPM, 45 RPM - CLEAN OUT 17.5" POCKET. - PRECAUTIONARY ENTERING DLR, STABLISERS AND BIT INSIDE 13-3/8" SHOE,
KZN-377 |  | INT2 |  | 2023-08-23 01:00 | 2023-08-23 02:15 | 1:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | - PUMP 50 BBLS HI VIS PILL ANC CIRCULATE HOLE CLEAN. - FR 800-850 GPM, 2300-2650 PSI,ROT 44 RPM, TQ 1.2-1.6 KFT-LBS. - CLEAN OUT 17.5" BOCKET. - HI-VIS AT SURFACE, SAMPLE SHOW 50-60% CAVING 3-6 (CM) ANGULAR, PLATY, TUBLAR CLAYSONE
KZN-377 |  | INT2 |  | 2023-08-23 02:15 | 2023-08-23 02:30 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | FLOW CHECK WELL STATIC. - LOST 0.3 BBLS/ 15 MINS.
KZN-377 |  | INT2 |  | 2023-08-23 02:30 | 2023-08-23 03:00 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | - PERFROM POST JARRING DROPS INSPECTION.
KZN-377 |  | INT2 |  | 2023-08-23 03:00 | 2023-08-23 03:30 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | - SERVICE RIG/TDS - SERVICE MP#1 - MONITOR WELL ON TT, LOST 1.4 BBLS / 1 HR. Page 32 of 80
KZN-377 |  | INT2 |  | 2023-08-23 03:30 | 2023-08-23 05:45 | 2:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | POOH 12.25" BHA ON ELEVATOR FROM 994 M TO 467 M.TOP OF BHA. NOTES: - MONITOR WELL THROUGH TRIP TANK. - GOT 18 X CONNECTIONS WITH OVERTORQUE. - USED MANUAL TONGS TO BREAK-OUT ALL CONNECTION WITH 50-65 KLB.FT - F/ 3-7 MINS EXTRA TIME TAKEN USING TONGS EACH CONNECTION.
KZN-377 |  | INT2 |  | 2023-08-23 05:45 | 2023-08-23 06:00 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | - FLOW CHECK AT TOP OF BHA. WELL STATIC
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 10:45 | 4:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | POOH 12.25" BHA FROM 467M TO SURFACE. - RACK BACK 10 X STANDS OF 5" HWDP - RACK BACK 5 X STANDS OF 8.25" DC - L/D JAR, DLR (60-70% BALLED UP), PBL, STRING STAB (45-50% BALLED UP), FLOAT SUB AND FILTER SUB - BREAK OUT AND L/D RSS (PHYSICALLY IN GOOD CONDITION) AND BIT - BIT GRADING: 3-3-WI-A-X-I-CT-TF NOTE: - NO PHYSICAL DAMAGE OBSERVED ON BHA - FUNCTION TEST BSR FROM TP PANEL.
KZN-377 |  | INT2 |  | 2023-08-23 10:45 | 2023-08-23 13:30 | 2:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | P/U, M/U AND RIH 12-1/4"BHA#2 TO 110 M AS FOLLOW: - PICK UP NEW 12-1/4” PDC BITNOV, TKC66, S423, (3x12 & 6X13/32 NOZZLES) - 8" NOV RSS VX800 (C/W 12-1/8" SLEEVE STAB.) - 8.25" FILTER SUB - 8" FLOAT SUB. - 12.1/8" STABILIZER - 8" PBL SUB. - 10 X 8.1/4" DC - DLR - 2 X 8 1/4" DC NOTES: - USED MANUAL TONGS TO MU NOV TOOLS. Page 33 of 80
KZN-377 |  | INT2 |  | 2023-08-23 13:30 | 2023-08-23 14:45 | 1:15 |  |  |  | RREP |  |  | Non-Productive |  |  | WHILE MAKING UP BHA CONNECTION BETWEEN JAR & DC, RIGHT SIDE COVER OF IRON ROUGHNECK (WEIGHT, 6.5 KG), THAT PROTECTS HYDRAULIC CYLINDER AND HOSES, DISENGAGED AND FELL DOWN FROM APPROXIMATE HEIGHT OF 1.6-1.7 M TO ROTARY LEVEL. THE IRON ROUGHNECK OPERATOR WAS OPERATING THE ROUGHNECK AT THAT TIME STANDING ON THE LEFT SIDE OF THE IRON ROUGHNECK CONTROL PANEL. NO INJURIES. - SUSPEND THE OPERATION AND RETRACTED THE IRON ROUGHNECK BACK. - HELD TOFS WITH CREW AND INFORM WSL AND TP AND CHEIF MECHANIC. - CHECK AND INSPECT THE ROUGHNECK. FOUND OUT THE COVER FELL DOWN DUE TO WORN OUT PROFILE WHERE THE BOLTS SECURE THE COVER. - RE-INSTALL NEW BOLTS AND NIUTS TYPE WITH WASHERS AND SECURE BOTH COVERS AGAIN. - INSTALL SAFETY SLINGS IN BOTH COVERS AS A SECONDARY RETENTION. - INSPECT THE WHOLE IRONROUGHNECK FROM ANY OTHER DEFECTS AND LOOSE ITEMS. - HELD SAFETY STAND DOWN WITH THE CREW AND DISCUSS THE FINDINGS AND LL WITH NEW NIGHT CREW AS WELL. - INFORM WSUP AND RIG SUP ABOUT THE INCIDENT. - AGREED TO RESUME OPERATION AND FREQUENTLY CHECKING THE BOLTS WHILE RIH.
KZN-377 |  | INT2 |  | 2023-08-23 14:45 | 2023-08-23 15:15 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONT. P/U, M/U AND RIH 12-1/4"BHA#2 TO 195 M AS FOLLOW: - 8" POWER STROKE DRILLING JAR. ( WT BELOW JAR 50 KLBS) - 3 X 8 1/4" DC (ONE STAND FROM DERRICK) - XO - 1 STAND HWDP FROM DERRICK. NOTES: - USED MANUAL TONGS TO MU NOV TOOLS. Page 34 of 80
KZN-377 |  | INT2 |  | 2023-08-23 15:15 | 2023-08-23 16:00 | 0:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | MU TDS, BREAK CIRC, SHALLOW TEST NOV VX800 TOOL AT FR: 750 GPM; SPP:1350 PSI. - UNABLE TO GET SURVEY. RECYCLE PUMPS, STILL NO SURVEY. - CHANGE OUT DECODER BOX AND PRESSURE SENSOR AND REBOOT THE SYSTEM. - MANAGED TO GET SURVEY AS FOLLOW: INC: 0.21 DEG, AZM: 275.67 DEG, TEMP: BELOW 50 DEG C
KZN-377 |  | INT2 |  | 2023-08-23 16:00 | 2023-08-23 16:45 | 0:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | RESUME P/U, M/U AND RIH 12-1/4" BHA TO 448 M AS FOLLOW: - 9 STANDS HWDP FROM DERRICK. NOTES: - TOTAL BHA LENGTH: 448.17 M ,TOTAL BHA WT: 105 KLBS, WT BELOW JAR: 53 KLBS. - MAINTAIN TRIP SHEET.
KZN-377 |  | INT2 |  | 2023-08-23 16:45 | 2023-08-23 17:00 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | - PERFORM D1 DRILL WITH CREW B - FUNCTION TEST BOP FROM TP PANEL
KZN-377 |  | INT2 |  | 2023-08-23 17:00 | 2023-08-23 23:30 | 6:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | RIH 12-1/4"BHA FROM 448 M TO 2265 M ON 5" DP. - MONITOR DISPLACEMENT ON TRIP TANK - AT 1696 M, OBSERVED TIGHT SPOT, SLACK OF UP TO 40 KLBS, NO SUCCESS, CONNECT TDS AND CLEAR IT WITH 100 RPM, 700 GPM, 2400 PSI, TQ~2.5-3.7 KFT.LB NOTE: - AT 20:00 HRS, PTSM WITH NIGHT CREW, DISCUSS IRON ROUGHNECK COVER DROPS INCIDENT.
KZN-377 |  | INT2 |  | 2023-08-23 23:30 | 2023-08-24 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | - TOOK SCR - TOOK FLOW BACK BASE LINE WITH 800 GPM , RIG RECORDED 46 BBL, MUD LOGGER RECORDED 43 BBL - TOOK FLOW BACK BASE LINE WITH 900 GPM , RIG RECORDED 49 BBL, MUD LOGGER RECORDED 46 BBL
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 00:45 | 0:45 |  |  |  | DFAL |  |  | Non-Productive |  |  | ATTEMPT TO WASH DOWN WITH LAST STAND, OBSERVED STRING TAKING WEIGHT UP TO 40 KLBS. REAM DOWN FROM 2265 M TO 2290 M - FR 860 GPM, 3600-3800 PSI,ROT 100 RPM, TQ 2-4 KFT-LBS. WOB 0-20 KLBS Page 35 of 80
KZN-377 |  | INT2 |  | 2023-08-23 00:45 | 2023-08-23 06:00 | 5:15 | [6 empty] | Productive |  |  | BED ON BIT AND DRILL 12.25" HOLE AS PER ROAD MAP FROM 2290 M TO 2387 M. FR 890 GPM, SPP 3700-3900 PSI, WOB 30-40 KLBS, ROT 140-150 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 23.9 M/HR VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2347.670.31290.49 2376.700.37256.17
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 15:00 | 9:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 2387 M TO 2580 M. FR 890-850 GPM, SPP 3300-3900 PSI, WOB 35-40 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 31 M/HR - AT 2380 M, MP #2 PISTON FAILED. CONTINUE WITH MP 1 & 3 WITH 850 GPM. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2463.20.3131.76 2549.70.23320.92
KZN-377 |  | INT2 |  | 2023-08-23 15:00 | 2023-08-23 15:15 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE. Page 36 of 80
KZN-377 |  | INT2 |  | 2023-08-23 15:15 | 2023-08-23 17:00 | 1:45 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 2580 M TO 2609 M. FR 890-900 GPM, SPP 3700-3800 PSI, WOB 35-45 KLBS, ROT 140-150 RPM, TQ 9-14 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - SURVEY EVERY 3 STANDS. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 31 M/HR PERFORM FIRE DRILL WITH CREW B. TAKE SCR AT 2608 M. VX800 SURVEYS: --------------------------------------------------- DEPTH.INCL.AZM. 2549.70.23320.92
KZN-377 |  | INT2 |  | 2023-08-23 17:00 | 2023-08-23 21:00 | 4:00 |  |  |  | DFAL |  |  | Non-Productive |  |  | AFTER CONNECTION, COULDN'T GET SIGNAL FROM MWD TOOL. - RESTART PUMPS WITH 900 GPM, NO SIGNAL - RESTART PUMP WITH 800, 950, 975 GPM, STILL NO SIGNAL - UN ABLE TO GO TO 1000 GPM AS SPP WAS REACHING 4250 PSI (MAX. SETTING LIMIT) - TROUBLESHOOT WITH NO SUCCESS. OBSERVED INTERRUPTED SIGNELS FEW TIMES. - DISCUSS WITH TOWN AND AGREED TO CONTINUE DRILLING UNTIL SOURCING BACK UP RSS. Page 37 of 80
KZN-377 |  | INT2 |  | 2023-08-23 21:00 | 2023-08-24 | 3:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 2609 M TO 2670 M. FR 890-900 GPM, SPP 3500-3900 PSI, WOB 35-40 KLBS, ROT 140-150 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 27.85 M/HR NOTES: - AT 21:55 HRS, OBSERVED PRESSURE DROP FROM 3900 PSI TO 3600 PS. CHECKED SURFACE LINES AND MUD PUMPS, ALL GOOD. STOPPED DILUTION IN MUD SYSTEM, OBSERVED PRESSURE RETURN BACK TO 3800-3900 PSI - UNABLE TO GET VX800 SIGNALS. LAST VX800 SURVEY RECORDED: --------------------------------------------------- DEPTH.INCL.AZM. 2606.670.10242.29 LAST 24 HRS DRILLING SUMMARY ================== FOOTAGE DRILLED: 380 M DAILY BIT HRS: 14 HR AVG ROP: 27.14 M/HR
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 2670 M TO 2790 M. FR 850-900 GPM, SPP 3300-3900 PSI, WOB 35-40 KLBS, ROT 140-150 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 25 M/HR - UNABLE TO GET VX800 SIGNAL. Page 38 of 80
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 20:00 | 14:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 2790 M TO 3057 M. FR 900 GPM, SPP 3900-4500 PSI, WOB 35-40 KLBS, ROT 140-150 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 24 M/HR - NO VX800 SIGNAL. - PERFORM H2S DRILL WITH CREW B - AT 2855 M, STARTED RAISING MUD WEIGHT GRADUALLY FROM 1.25 SG PRIOR TO ENTERING GHARIF. - AT 2929 M, MUD WEIGHT IN = OUT = 1.30 SG
KZN-377 |  | INT2 |  | 2023-08-23 20:00 | 2023-08-23 21:30 | 1:30 | [6 empty] | Non-Productive |  |  | PUMP HIVIS AND CIRCULATE HOLE CLEAN. - 900 GPM, 4200 PSI OFFLINE: - PREPARE WL GYRO TOOL
KZN-377 |  | INT2 |  | 2023-08-23 21:30 | 2023-08-23 22:00 | 0:30 | [6 empty] | Non-Productive |  |  | POOH AND RACK BACK 2 STANDS. - BIT DEPTH AT 3011 M NOTE: UNABLE TO BREAK THE CONNECTIONS WITH IRON ROUGHNECK, USED MANUAL TONGS. TQ~25 KFT.LBS
KZN-377 |  | INT2 |  | 2023-08-23 22:00 | 2023-08-23 22:15 | 0:15 | [6 empty] | Non-Productive |  |  | FLOW CHECK MEANWHILE TBT FOR WL GYRO
KZN-377 |  | INT2 |  | 2023-08-23 22:15 | 2023-08-23 23:00 | 0:45 | [6 empty] | Non-Productive |  |  | RIG UP WL GYRO EQUIPMENT. - RIG UP WL SHEAVE ON TDS AND RIG FLOOR. - RIG UP WL CABLE TO THE SHEAVES. - PERFORM DROPS CHECK LIST - PICK UP WL GYRO TOOL NOTE: - MONITOR WELL IN TRIP TANK
KZN-377 |  | INT2 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 |  |  |  | DFAL |  |  | Non-Productive |  |  | RIH WITH WL GYRO. - RECORD IN-RUN SURVEY
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 03:30 | 3:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | CONT. WL GYRO. - RECORD IN-RUN SURVEY - RECORD OUT-RUN SURVEY - MAX INC 0.63 DEG AT 1960 M - DEEPEST SURVEY INC 0.31 DEG AT 2980 M - INCLINATION HOLDING AT LESS THAN 1 DEG. NOTE: - MONITOR WELL IN TRIP TANK. LOSSES RATE OF 3 BBL/HR
KZN-377 |  | INT2 |  | 2023-08-23 03:30 | 2023-08-23 04:00 | 0:30 |  |  |  | DFAL |  |  | Non-Productive |  |  | RIG DOWN GYRO TOOL AND WL SHEAVES. Page 39 of 80
KZN-377 |  | INT2 |  | 2023-08-23 04:00 | 2023-08-23 04:15 | 0:15 |  |  |  | DFAL |  |  | Non-Productive |  |  | WASH DOWN FROM 3011 M TO 3041 M FR 900 GPM, SPP 4100-4200 PSI,
KZN-377 |  | INT2 |  | 2023-08-23 04:15 | 2023-08-23 04:30 | 0:15 |  |  |  | RREP |  |  | Non-Productive |  |  | MP#1 STROKES MALFUNCTIONING, WORK ON SAME
KZN-377 |  | INT2 |  | 2023-08-23 04:30 | 2023-08-23 06:00 | 1:30 | [6 empty] | Productive |  |  | WASH DOWN TO 3057 M AND RESUME DRILLING 12.25" HOLEFROM 3057M TO 3067 M. FR 850 GPM, SPP 4050-4200 PSI, WOB 35-40 KLBS, ROT 150 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 12 M/HR - CONTROLLED WOB AT 20-24 KLBS AS PER ROAD MAP PRIOR ENTERING GHARIF - AT 05:30 HRS, MP#2 PISTON FAILURE, SWITCH TO MP#1 & 3
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 10:00 | 4:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3067 M TO 3128 M. FR 850-860 GPM, SPP 3900-4250 PSI, WOB 35-40 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 25 M/HR - NO VX800 SIGNAL. - PUMP 50 BBL OF NUT SHELL AT 3098 M. AT 9:15 MP# 3 HAD TEMP. SENSOR NOT READING. CONTINUE WITH 2 MUD PUMPS WITH 850 GPM. BACK at 10:00 TOP GHARIF @ 3070M.
KZN-377 |  | INT2 |  | 2023-08-23 10:00 | 2023-08-23 10:15 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE. Page 40 of 80
KZN-377 |  | INT2 |  | 2023-08-23 10:15 | 2023-08-23 14:00 | 3:45 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3128 M TO 3214 M. FR 850-860 GPM, SPP 3900-4250 PSI, WOB 35-45 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - NO VX800 SIGNAL. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4300 PSI - PUMP 50 BBL OF NUT SHELL AT 3155 M. AT 12:10 MP# 2 HAD VALVE ISSUE. CONTINUE WITH 2 MUD PUMPS WITH 850 GPM. TOP GHARIF @ 3070M.(3M SHALLOWER)
KZN-377 |  | INT2 |  | 2023-08-23 14:00 | 2023-08-23 14:45 | 0:45 |  |  |  | RREP |  |  | Non-Productive |  |  | OBSERVE WASH OUT IN THE UPPER FACE OF THE BOX SIDE OF THE TOP JOINT OF STAND # 29. LAY DOWN THE WASHED OUT SINGLE. P/UP NEW STAND.
KZN-377 |  | INT2 |  | 2023-08-23 14:45 | 2023-08-23 20:00 | 5:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3214 M TO 3293 M. FR 850-840 GPM, SPP 4200-4250 PSI, WOB 35-45 KLBS, ROT 140-160 RPM, TQ 9-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 26.6 M/HR - NO VX800 SIGNAL. - UNABLE TO ACHIEVE900 GPM DUE TO HIGH SPP ~4250 PSI - PUMP 50 BBL OF NUT SHELL AT 3233 M. AT 12:10 MP# 2 HAD VALVE ISSUE. CONTINUE WITH 2 MUD PUMPS WITH 850 GPM. TOP HAUSHI LIMESTONE @ 3236 M.(1M DEEPER)
KZN-377 |  | INT2 |  | 2023-08-23 20:00 | 2023-08-23 20:30 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | OBSERVE WASH OUT IN THE UPPER FACE OF THE BOX SIDE OF THE TOP JOINT OF STAND # 32, RACK BACK STAND#32 AND MAKE UP STAND #33 Page 41 of 80
KZN-377 |  | INT2 |  | 2023-08-23 20:30 | 2023-08-24 | 3:30 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3293 M TO 3319 M. FR 840 GPM, SPP 4170-4250 PSI, WOB 35-45 KLBS, ROT 120-160 RPM, TQ 7-12 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = XX M/HR. - ROP DROPPED F/3302M, TQ SMOOTHING F/3313M - NO VX800 SIGNAL. AT 23:30 MP# 3 HAD VALVE/SEAT ISSUE. CONTINUE WITH 2 MUD PUMPS WITH 800 GPM/3950PSI. TOP BASAL SAND AT 3292 M (1M DEEPER) TOP AL KHALATA AT 3304 M (ON DEPTH). LAST 24 HRS DRILLING SUMMARY ================== FOOTAGE DRILLED: 262 M DAILY BIT HRS: 13.8 HRS AVG ROP: 18.99 M/HR
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 00:15 | 0:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3319 M TO 3321 M. FR 800 GPM, SPP 3950 PSI, WOB 45 KLBS, ROT 120 RPM, TQ 6-7 KFT.LBS
KZN-377 |  | INT2 |  | 2023-08-23 00:15 | 2023-08-23 00:45 | 0:30 |  |  |  | RREP |  |  | Non-Productive |  |  | OBSERVE WASH OUT IN THE UPPER FACE OF THE BOX SIDE OF THE TOP JOINT OF STAND # 34, RACK BACK STAND#32 AND MAKE UP STAND #35
KZN-377 |  | INT2 |  | 2023-08-23 00:45 | 2023-08-23 06:00 | 5:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3321 M TO 3349 M. FR 825-840 GPM, SPP 4150-4250 PSI, WOB 40-45 KLBS, ROT 110-120 RPM, TQ 6-8 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 5.25 M/HR. - NO VX800 SIGNAL. - AT 05:00-05:15 HRS, MP#1 CHANGE SEAL, CONT. WITH MP#2 & 3 Page 42 of 80
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 09:30 | 3:30 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3349 M TO 3363 M. FR 825-840 GPM, SPP 4150-4250 PSI, WOB 40-45 KLBS, ROT 110-120 RPM, TQ 6-8 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 4.1 M/HR. - NO VX800 SIGNAL.
KZN-377 |  | INT2 |  | 2023-08-23 09:30 | 2023-08-23 09:45 | 0:15 | [6 empty] | Productive |  |  | PERFORM D2 DRILL WITH CREW C.
KZN-377 |  | INT2 |  | 2023-08-23 09:45 | 2023-08-23 15:00 | 5:15 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3363 M TO 3378 M. FR 825-840 GPM, SPP 4150-4250 PSI, WOB 40-45 KLBS, ROT 120 RPM, TQ 6-8 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 3.2 M/HR. - NO VX800 SIGNAL.
KZN-377 |  | INT2 |  | 2023-08-23 15:00 | 2023-08-23 15:15 | 0:15 | [6 empty] | Non-Productive |  |  | OBSERVE WASH OUT IN THE UPPER FACE OF THE BOX SIDE OF THE TOP JOINT OF STAND # 38, RACK BACK STAND#38 AND MAKE UP STAND #39
KZN-377 |  | INT2 |  | 2023-08-23 15:15 | 2023-08-23 18:00 | 2:45 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3378 M TO 3386 M. FR 825-840 GPM, SPP 4150-4250 PSI, WOB 40-45 KLBS, ROT 120 RPM, TQ 6-8 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - AVG ROP = 2.33 M/HR. - NO VX800 SIGNAL. Page 43 of 80
KZN-377 |  | INT2 |  | 2023-08-23 18:00 | 2023-08-24 | 6:00 | [6 empty] | Productive |  |  | DRILL 12.25" HOLE AS PER ROAD MAP FROM 3386 M TO 3404 M. (SECTION TD, 168M BELOW GHARIF). FR 825-840 GPM, SPP 4150-4250 PSI, WOB 45-50 KLBS, ROT 120 RPM, TQ 4-6 KFT.LBS - REAM 3 M F/1-1.5 MINS UP/DN EVERY CONNECTION AT 45 RPM. - PUMP 50 BBL OF HI-VIS EVERY 5 STANDS DRILLED. - STAGE-UP / STAGE DN PUMPS BEFORE / AFTER EACH CONNECTION. - PREPARE WEIGHTED PILL TO INCREASE MWFROM 1.30 SG TO 1.32 SG PRIOR POOH - COMMENCE INCREASING MW F/1.30 TO 1.32 FROM 3403M. - AVG ROP = 3.0 M/HR. - NO VX800 SIGNAL.
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 02:15 | 2:15 | [6 empty] | Productive |  |  | - PUMP 50 BBLS HVP AND CIRCULATE HOLE CLEAN. MEANWHILE RECIPROCATE THE STRING UP \ DOWN. - MW IN \ OUT = 1.32 SG. - NO LOSSES. - AVERAGE HOLE SIZE BASED ON SWEEP LAG TIME 12.90 IN (14 %WASH OUT)
KZN-377 |  | INT2 |  | 2023-08-23 02:15 | 2023-08-23 02:45 | 0:30 | [6 empty] | Productive |  |  | - TAKE SCR. - FLOW CHECK WELL-OK STATIC. - INSTALL AIR SLIPS
KZN-377 |  | INT2 |  | 2023-08-23 02:45 | 2023-08-23 06:00 | 3:15 | [6 empty] | Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 3404 M TO 2627 M. - SMOOTH POOH ON ELEVATOR . NOTES: - MONITOR WELL THROUGH TRIP TANK. - OBSERVE SLIGHT OVERPULL FROM 2765M TO 2737M UP TO 40 KLBS. CLEAR TIGHT SPOT WITH ELEVATOR ANC CONTINUE POOH.
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 06:30 | 0:30 | [6 empty] | Productive |  |  | - CONTINUE POOH 12 1/4" BHA ON ELEVATOR FROM 2627 M TO 2543 M. - OBSERVE OVER PULL REACHING 40-50 KLBS. ATTEMPT TO WORK STRING TO CLEAR TIGHT SPOT, NO SUCCESS. NOTES: - MONITOR WELL THROUGH TRIP TANK. Page 44 of 80
KZN-377 |  | INT2 |  | 2023-08-23 06:30 | 2023-08-23 14:30 | 8:00 | [6 empty] | Productive |  |  | - ATTEMPT TO PUMP OUT WITH 12 1/4" BHA FROM 2543 M WITH FR = 840 GPM, SPP = 3770-3600 PSI,OBSERVE OVER PULL UP TO 50 KLBS AFTER SEVERAL ATTEMPTS. - BACK REAM WITH 12 1/4" BHA FROM 2543 M TO 2261 M. FR 840-780 GPM,SPP 2700-3200 PSI, RPM 45 , TRQ 4 -18 KFT.LBS. - TIGHT SPOTS FROM 2543 M TO 2516 M - SMOOTH BACK REAM FROM 2516 M TO 2469 M - TIGHT SPOTS FROM 2469 M TO 2443 M - SMOOTH BACK REAM FROM 2443 M TO 2426 M - PUMP OUT FROM 2426 M TO 2406 M. TIGHT SPOT AT 2406 M - BACK REAM FROM 2406 M TO 2377 M - PUMP OUT FROM 2377 M TO 2345 M. TIGHT SPOT AT 2345 M - BACK REAM FROM 2345 M TO 2286 M. (HARD BACKREAM AT 2345-2344 M). - PUMP OUT FROM 2286 M TO 2261 M. - OBSERVE 2 X OVERTORQUED CONNECTIONS. USED MANUAL TONGS TO BREAK (60 KFT.IBF).
KZN-377 |  | INT2 |  | 2023-08-23 14:30 | 2023-08-23 15:15 | 0:45 | [6 empty] | Productive |  |  | POOH 12 1/4" BHA ON ELEVATOR FROM 2261 M TO 2086 M. - PULL 6 STANDS SMOOTH. - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | INT2 |  | 2023-08-23 15:15 | 2023-08-23 18:30 | 3:15 | [6 empty] | Productive |  |  | RIH FROM 2086 M TO 3404 M (AS A CHECK TRIP) - RIH SLICK WITH NO HELD UP OBSERVED. - TAG SLIGHT HELD UP AT 3400M. CLEAR IT WHILE WASHING DOWN. - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | INT2 |  | 2023-08-23 18:30 | 2023-08-23 20:30 | 2:00 | [6 empty] | Productive |  |  | PUMP 50 BBLS HVP AND CIRCULATE HOLE CLEAN. MEANWHILE WASHED DOWN F/ 3399 M TO 3404 M HOLE OK. RECIPROCATE THE STRING & UP \ DOWN.- MW IN \ OUT = 1.32 SG.- NO LOSSES.- AVERAGE HOLE SIZE BASED ON SWEEP LAG TIME 12.90 IN (14 % WASH OUT) - NO INCREASE ON CUTTINGS AT SURFACE.
KZN-377 |  | INT2 |  | 2023-08-23 20:30 | 2023-08-23 21:00 | 0:30 | [6 empty] | Productive |  |  | TAKE SCR. - FLOW CHECK WELL-OK STATIC. - INSTALL AIR SLIPS Page 45 of 80
KZN-377 |  | INT2 |  | 2023-08-23 21:00 | 2023-08-24 | 3:00 | [6 empty] | Productive |  |  | - POOH 12 1/4" BHA ON ELEVATOR FROM 3404 M TO 2283 M. - SMOOTH POOH ON ELEVATOR . NOTES: - MONITOR WELL THROUGH TRIP TANK. - OBSERVE SLIGHT OVERPULL FROM 2765M TO 2737M UP TO 40 KLBS. CLEAR TIGHT SPOT WITH ELEVATOR ANC CONTINUE POOH. - L/D ONE SINGLE FOR CONNECTION CHANGE
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 04:15 | 4:15 | [6 empty] | Productive |  |  | POOH 12 1/4" BHA ON ELEVATOR FROM 3404 M TO 995 M - SMOOTH POOH ON ELEVATOR . - @ STD 41 HAD CONNECTION OVER TQED, USED RIG TONG. - REPORTED 20 BBLS LOS100SES DURING ENTIRE TRIP OUT.
KZN-377 |  | INT2 |  | 2023-08-23 04:15 | 2023-08-23 04:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK @ 13 3/8" CSG SHOW, WELL STATIC.
KZN-377 |  | INT2 |  | 2023-08-23 04:30 | 2023-08-23 05:45 | 1:15 | [6 empty] | Productive |  |  | PUMPED 50 BBLS HVP AND CIRCULATE HOLE CLEAN. MEANWHILE CLEANED OUT 13 3/8" POCKET HOLE OK. RECIPROCATE THE STRING & UP \ DOWN.- MW IN \ OUT = 1.32 SG.- NO LOSSES.
KZN-377 |  | INT2 |  | 2023-08-23 05:45 | 2023-08-23 08:00 | 2:15 | [6 empty] | Productive |  |  | SLIP & CUT DRILL LINE - TBT PRIOR SLIP AND CUT DRILL LINE. - HANG TRAVELING BLOCK - CUT 24 M AND SLIP 12 M OF DRILL LINE. - SET CROWN-O-MATIC & KEMS AS PER ABRAJ PROCEDURE. - PERFORM BOP FUNCTION TEST FROM DRILLER PANEL.
KZN-377 |  | INT2 |  | 2023-08-23 08:00 | 2023-08-23 08:30 | 0:30 | [6 empty] | Productive |  |  | TBT AND CREW CHANGE HANDOVER. MEANWHILE, PUMP SLUG AND FLOW CHECK WELL.
KZN-377 |  | INT2 |  | 2023-08-23 08:30 | 2023-08-23 10:00 | 1:30 | [6 empty] | Productive |  |  | CONT. POOH 12.25" BHA#2 ON ELEVATOR FROM 995 M TO 495 M.TOP OF BHA. - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | INT2 |  | 2023-08-23 10:00 | 2023-08-23 10:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AT TOP OF BHA- WELL STATIC
KZN-377 |  | INT2 |  | 2023-08-23 10:15 | 2023-08-23 11:00 | 0:45 | [6 empty] | Productive |  |  | CONT. POH 12 1/4" BHA FROM 495 M TO 190 M. - RACK BACK ALL 5" HWDP. Page 46 of 80
KZN-377 |  | INT2 |  | 2023-08-23 11:00 | 2023-08-23 15:00 | 4:00 | [6 empty] | Productive |  |  | CONT. POH 12 1/4" BHA#2 FROM 190 M TO SURFACE AS BELOW: - 8-1/4" X-OVER. - 3 X 8 1/4" DC. - L/D 8" JAR. - L/D 2 X 8 1/4" DC. - L/D 8" DLR - L/D 10 X 8 1/4" DC. - L/D PBL SUB - L/D 1 X 12 1/8"STRING STAB.(30 % BALLED UP) - L/D FILTER SUB & FLOAT SUB. - L/D RSS - L/D 12 1/4" BIT - BIT GRADING: 1-1-WT-A-X-I-NO-TD - MONITOR WELL THROUGH TRIP TANK.
KZN-377 |  | INT2 |  | 2023-08-23 15:00 | 2023-08-23 15:15 | 0:15 | [6 empty] | Productive |  |  | - PU, MU WEAR BUSHING RETRIEVE TOOL. - RETRIEVED WEAR BUSHING
KZN-377 |  | INT2 |  | 2023-08-23 15:15 | 2023-08-23 16:00 | 0:45 | [6 empty] | Productive |  |  | - PU, MU JETTING TOOL - JET AND FLUSH BOP AND WELLHEAD - LAY DOWN JETTING TOOL AND WEAR BUSHING RUNING TOOL
KZN-377 |  | INT2 |  | 2023-08-23 16:00 | 2023-08-23 17:15 | 1:15 | [6 empty] | Productive |  |  | - REMOVE BAILS AND ELEVATOR. - REMOVE SAVER SUB
KZN-377 |  | INT2 |  | 2023-08-23 17:15 | 2023-08-23 17:30 | 0:15 | [6 empty] | Productive |  |  | PJSM WITH ALL CREW PRIOR R/U FRANKS EQUIPMENT.
KZN-377 |  | INT2 |  | 2023-08-23 17:30 | 2023-08-23 20:30 | 3:00 | [6 empty] | Productive |  |  | - RIG UP FA-1 SERVICE LOOP. - PICK UP AND RIG UP CRT. - CONDUCT DROP INSPECTION. - R/UP HYDRAULIC ELEVATOR - MU SAFETY VALVE WITH 9.5/8" WATER BUSHING.
KZN-377 |  | INT2 |  | 2023-08-23 20:30 | 2023-08-23 20:45 | 0:15 | [6 empty] | Productive |  |  | PJSM FOR 9 5/8" HANGER DUMMY RUN
KZN-377 |  | INT2 |  | 2023-08-23 20:45 | 2023-08-23 23:00 | 2:15 | [6 empty] | Productive |  |  | 9-5/8'' CASING HANGER DUMMY RUN: - PU AND RIH 9-5/8'' CASING HANGER ACROSS ROTARY. - PU, MU LANDING JOINT TO 9-5/8'' CASING HANGER. - LAND CASING HANGER IN WELL HEAD PROFILE. HOP 10.58 M BRT, STICK UP 1.37 M. - VERIFY YELLOW MARK THROUGH WH LOWER SOV’S. - POOH AND LD 9-5/8'' CASING HANGER ASSEMBLY.
KZN-377 |  | INT2 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 | [6 empty] | Productive |  |  | REMOVE MASTER BUSHINGS. - INSTALLED FMS. - VERIFIED INTERLOCKING SYSTEM IS WORKING PROPERLY FOR CRT AND FMS. - EXPRO EXPERIENCED SIGNAL DETECTIONWITH WIRELESS CRT UNIT Page 47 of 80
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 01:15 | 1:15 | [6 empty] | Productive |  |  | RIH WITH 9-5/8'' SHOE TRACK: - PICK UP 9 5/8" REAMER SHOE,FUNCTION TEST FLOAT. OK - PU, MU AND RIH SHOE TRACK TO 51.5 M. TESTED FLOATS FUNCTIONING OK. - APPLIED BAKERLOCK ON SHOETRACK CONNECTIONS. - USED POWER TONGS FOR MAKE UP
KZN-377 |  | INT2 |  | 2023-08-23 01:15 | 2023-08-23 06:00 | 4:45 | [6 empty] | Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 51 M TO 517 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED8-11 JNT / HR
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 11:15 | 5:15 | [6 empty] | Productive |  |  | RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 517 M TO 1185 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED9-10 JNT / HR NOTE: 9:30 BREAK CIRCULATION AT 13 3/8" SHOE AT 997 M: FRSPPWT UP WT DOWN 420 GPM550 PSI200 KLBS 200 KLBS 00202 KLBS 205 KLBS
KZN-377 |  | INT2 |  | 2023-08-23 11:15 | 2023-08-23 11:45 | 0:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | - HAD ISSUE WITH JT# 91 M/U TORQUE ( HIGH SHOULDER). - BREAK OUT, CLEAN AND REMADE THE SAME.
KZN-377 |  | INT2 |  | 2023-08-23 11:45 | 2023-08-23 12:15 | 0:30 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1185 M TO 1219 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED9-10 JNT / HR
KZN-377 |  | INT2 |  | 2023-08-23 12:15 | 2023-08-23 12:30 | 0:15 |  |  |  | SFAL |  |  | Non-Productive |  |  | - HAD ISSUE WITH JT# 95 M/U TORQUE ( HIGH SHOULDER). - BREAK OUT, CLEAN AND REMADE THE SAME.
KZN-377 |  | INT2 |  | 2023-08-23 12:30 | 2023-08-23 17:30 | 5:00 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1219 M TO 1806 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED9-10 JNT / HR Page 48 of 80
KZN-377 |  | INT2 |  | 2023-08-23 17:30 | 2023-08-23 18:00 | 0:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | - HAD ISSUE WITH JT# 140 M/U TORQUE ( HIGH SHOULDER). - BREAK OUT, CLEAN AND REMADE THE SAME.
KZN-377 |  | INT2 |  | 2023-08-23 18:00 | 2023-08-23 19:00 | 1:00 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1806 M TO 1970 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED9-10 JNT / HR
KZN-377 |  | INT2 |  | 2023-08-23 19:00 | 2023-08-23 19:30 | 0:30 |  |  |  | SFAL |  |  | Non-Productive |  |  | HAD ISSUE WITH JT# 152 M/U TORQUE ( HIGH SHOULDER). - BREAK OUT, CLEAN AND REMADE THE SAME.
KZN-377 |  | INT2 |  | 2023-08-23 19:30 | 2023-08-24 | 4:30 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 1970 M TO 2600 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED10-11 JNT / HR OFFLINE: PREPARE AND MIX SPACER
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 2600 M TO 3285 M - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED6-7 JNT / HR
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 07:15 | 1:15 | [6 empty] | Productive |  |  | CONT. RIH 9 5/8", 53.5PPF, P-110, VAM TOP CASING USING FA-1 FROM 3285 M TO 3385 M. - FILLED UP EVERY JOINT USING FA-1 - MONITORED CORRECT DISPLACEMENT OVER SHORT ACTIVE TANKS. - RUNNING SPEED6-7 JNT / HR
KZN-377 |  | INT2 |  | 2023-08-23 07:15 | 2023-08-23 09:30 | 2:15 | [6 empty] | Productive |  |  | - COMMENCE WASHING DOWN WITH EXTRA JNTS # 264 & 265 OF 9 5/8" CASING FROM 3386 M TO 3402 M. - 420-380 GPM, 820-1000 PSI - TAG HELD UP AND HOLE FILL FROM 3394 M. - MAX. SLACK WEIGHT = 95 KLBS - OBSERVE CUTTINGS ON SURFACE ONCE BU AT SHAKERS. 70 % CUTTINGS MAINLY FROM GHARIF - SLOW PROGRESS WITH WASHING DOWN AT 3402 M. - REAM DOWN WITH 40 RPM, 7-9 KFT.LBS, 420 GPM, 800-1150 PSI FROM 3402 M UNTIL TAG BOTTOM AT 3404 M Page 49 of 80
KZN-377 |  | INT2 |  | 2023-08-23 09:30 | 2023-08-23 12:15 | 2:45 | [6 empty] | Productive |  |  | - PUMPED 100 BBLS HIVIS AND CIRCULATED HOLE CLEAN WITH 420 GPM AND 40 RPM. - PRESSURE 770-800 PSI, TRQ: 7.5-12 KFT.LBS - 5%CAVING INCREASE SEEN WHEN HIVIS WAS ON SURFACE (MAINLY FROM GHARIF)
KZN-377 |  | INT2 |  | 2023-08-23 12:15 | 2023-08-23 13:00 | 0:45 | [6 empty] | Productive |  |  | - POOH & L/D EXTRA 2 CASING JOINTS. - PICK UP POWER TONG AND HYDRAULIC HOSES
KZN-377 |  | INT2 |  | 2023-08-23 13:00 | 2023-08-23 13:45 | 0:45 | [6 empty] | Productive |  |  | TBT,PU AND MU 9-5/8'' CASING HANGER ASSEMBLY TO THE STRING.
KZN-377 |  | INT2 |  | 2023-08-23 13:45 | 2023-08-23 14:45 | 1:00 | [6 empty] | Productive |  |  | - MAKE UP HANGER ASSEMBLY BY USING POWER TONG. - REMOVE FRANKS FMS & INSTALL RIG'S MASTER BUSHING. - B/O RUNNING TOOL 2 TURNS AT RIG FLOOR W/ CHAIN TONGS AND M/U SAME - DRAIN BOP STACK AND CLEAN WELLHEAD FROM TOP AND THRU SOV'S. - LAND HANGER, STICK UP WITH SAME MARK AT RIG FLOOR, CASING STRING WEIGHT ~ 490 KLBS - CAMERON CONFIRM THRU SOV THAT HANGER FULLY LANDED THROUGH YELLOW MARKS (VERIFIED BY WSL) - 9-5/8" CASING SHOE AT 3399.8 M , FC AT 3360 M.
KZN-377 |  | INT2 |  | 2023-08-23 14:45 | 2023-08-23 15:30 | 0:45 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN WITH 420 GPM 770 PSI PRESSURE. OFFLINE: - R/D FRANKS POWER TONG. - R/D FRANKS FMS - MIX CMT MIXING WATER. - LOADED CMT PLUGS ON CMT HEAD
KZN-377 |  | INT2 |  | 2023-08-23 15:30 | 2023-08-23 16:45 | 1:15 | [6 empty] | Productive |  |  | - R/U HLB CEMENT HEAD AND CHICKSAN LINES - FLUSH CEMENT LINE, CONNECT TO CEMENT HEAD - PJSM WITH ALL CREW PRIOR P/T CEMENT LINES.
KZN-377 |  | INT2 |  | 2023-08-23 16:45 | 2023-08-23 17:15 | 0:30 | [6 empty] | Productive |  |  | PRESSURE TEST LINE TO 300/6000 PSI HIGH FOR 5 MIN - OK
KZN-377 |  | INT2 |  | 2023-08-23 17:15 | 2023-08-23 17:45 | 0:30 | [6 empty] | Productive |  |  | - PJSM WITH ALL CREW PRIOR CONDUCTING CEMENT JOB. MEANWHILE: - HALLIBURTON PREPARE THE MIX FLUID FOR THE JOB.
KZN-377 |  | INT2 |  | 2023-08-23 17:45 | 2023-08-23 18:15 | 0:30 | [6 empty] | Productive |  |  | - PUMP 80 BBLS OF 1.40 SG TUNED SPACER WITH 5 LBS/BBLS BRIDGEMAKER AT 250 GPM AT 252 PSI. - SWITCH OVER TO THE HALLIBURTON UNIT. - RELEASE THE BOTTOM PLUG & CONFIRMED BY WITNESSING THE FLAG INDICATOR. Page 50 of 80
KZN-377 |  | INT2 |  | 2023-08-23 18:15 | 2023-08-23 21:45 | 3:30 | [6 empty] | Productive |  |  | - LINE UP TO CEMENT UNIT AND PUMP CEMENT SLURRY 397.5 BBLS OF 1.58 SG LEAD @ 5-6 BPM 100 BBLS OF 1.58 SG LEAD WITH 5 LBS/BBL BRIDGEMAKER @ 4-5 BPM 332.3 BBLS OF 1.58 SG LEAD @ 5-6 BPM 78.6 BBLS OF 1.89 SG TAIL @ 4-5 BPM - RELEASE THE TOP PLUG & CONFIRMED BY WITNESSING THE FLAG INDICATOR. NOTE: - OVERALL CONSTANT DENSITY DURING THE JOB. Page 51 of 80
KZN-377 |  | INT2 |  | 2023-08-23 21:45 | 2023-08-24 | 2:15 | [6 empty] | Productive |  |  | DISPLACE 9-5/8" CEMENT - CEMENT UNIT PUMP 5 BBL MIX WATER @ 3 BPM - SWITCH TO RIG PUMPS TO DISPLACE WITH 1.19 SG SALT POLYMERMUD - PUMP 370 BBLS @ 6 BPM UNTIL THE PLUG REACHED THE TOP OF CEMENT, THE PRESSURE INCREASED FROM 250 PSI TO 890 PSI. - AFTER DISPLACING 447 BBLS STARTED RECEIVING CONTAMINATED SPACER. - AFTER DISPLACING 480 BBLS STARTED RECEIVING PURE SPACER. - AFTER DISPLACING 558 BBLS STARTED RECEIVING CONTAMINATED CEMENT. - AFTER DISPLACING 603 BBLS STARTED RECEIVING PURE CEMENT AT SURFACE. - AFTER DISPLACING 755 BBLS, RATE WAS DECREASED FROM 5 BPM TO 4 BPM AND PRESSURE DECREASED FROM 2350 PSI TO 2170 PSI. - AFTER DISPLACING 775 BBLS, RATE WAS DECREASED FROM 4 BPM TO 2 BPM AND PRESSURE DECREASED FROM 2255 PSI TO 2100 PSI. - BUMP PLUG AFTER TOTAL DISPLACEMENT OF 789.6 BBLS WITH FINAL CIRCULATION PRESSURE OF 2500 PSI. - INCREASED THE PRESSURE BY 500 PSI. - LINE UP TO CEMENT UNITEQUALIZE SPP. - BLEED OFF TO ZERO. BLEED BACK VOLUME 6.2 BBL. MONITOR FOR 10 MIN AND CONFIRM FLOATS HOLDING. - NO LOSSES WERE REPORTED WHILE PUMPING CEMENT AND WHILE DISPLACEMENT. CEMENT IN PLACE AT 24:00 HRS NOTES: - DUMP 47 BBLS CONTAMINATED MUD AND SPACER. - DUMP 68 BBLS PURE SPACER. - DUMP 48 BBLS CONTAMINATED CEMENT. - DUMP 193 BBLS PURE CEMENT.
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | - FLUSH CEMENT LINE AND BOP STAK. - R/D CEMENT LINE AND CROSS-OVER - R\D CEMENT HEAD
KZN-377 |  | INT2 |  | 2023-08-23 01:00 | 2023-08-23 02:00 | 1:00 | [6 empty] | Productive |  |  | - BACK OFF RUNNING TOOL FROM CASING HANGER. - BREAK OUT AND LAYDOWN LANDING JOINT AND RUNNING TOOL. Page 52 of 80
KZN-377 |  | INT2 |  | 2023-08-23 02:00 | 2023-08-23 04:30 | 2:30 | [6 empty] | Productive |  |  | RIG DOWN FRANKS TRS : - R\D FA-1 - R\ D CONTROL PANEL - R\D FA-1 SERVICE LOOP MONITOR WELL THROUGH TRIP TANK, STATIC.
KZN-377 |  | INT2 |  | 2023-08-23 04:30 | 2023-08-23 05:30 | 1:00 | [6 empty] | Productive |  |  | INSTALL RIG SAVER SUB - INSTALL TDS BAILS - INSTALL ELEVATOR.
KZN-377 |  | INT2 |  | 2023-08-23 05:30 | 2023-08-23 06:00 | 0:30 | [6 empty] | Productive |  |  | MAKE UP CAMERON JETTING TOOL JET WASH BOP. JET WASH BOP FUNCTION BOP'S AND JET SEAL ASSEMBLY PROFILE.
KZN-377 |  | INT2 |  | 2023-08-23 06:00 | 2023-08-23 06:45 | 0:45 | [6 empty] | Productive |  |  | M/U 9 5/8" CASING SSMC SEAL ASSEMBLY & LANDED IN THE WELLHEAD. - VERIFIED YELLOW MARKS FOR RUNNING TOOL THROUGH UPPER SOV. - SET SEAL ASSY WITH 3 1/2 TURNS. FOLLOWING CAM ENG INSTRUCTION. - VERIFIED LATCHING WITH 30 KLBS OVERPULL.
KZN-377 |  | INT2 |  | 2023-08-23 06:45 | 2023-08-23 08:00 | 1:15 | [6 empty] | Productive |  |  | - INSTALL CAMERON TEST PUMP AND RECORDING CHART TO PRESSURE TEST SEAL ASSEMBLY. - PRESSURE TEST THE SEAL ASSEMBLY TO 300 PSI LOW & 8000 PSI HIGH FOR 15 MINUTES- GOOD TEST. - L\D SEAL ASSEMBLY RUNNING TOOL.
KZN-377 |  | INT2 |  | 2023-08-23 08:00 | 2023-08-23 08:45 | 0:45 | [6 empty] | Productive |  |  | HELD TBT AND PREPARE TO CHANGE OUT KILL LINE HCR. ISOLATE HCR 4 WAY VALVE (PUT IN NEUTRAL POSITION). - PREPARE TO P/UP DRILL PIPES IN MOUSE HOLE.
KZN-377 |  | INT2 |  | 2023-08-23 08:45 | 2023-08-23 11:45 | 3:00 | [6 empty] | Productive |  |  | - CHANGE OUT KILL SIDE HCR TO A BACKUP INSPECTED ONE (SN# IO00122267-2) - FUNCTION TEST THE VALVE - MEANWHILE, P/UP AND RACK BACK 12 X 19.5# 5" DP STANDS
KZN-377 |  | INT2 |  | 2023-08-23 11:45 | 2023-08-23 12:15 | 0:30 | [6 empty] | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY OFFLINE: LINE UP TO TEST KILL SIDE HCR FROM OPPOSITE DIRECTION OF FLOW.
KZN-377 |  | INT2 |  | 2023-08-23 12:15 | 2023-08-23 13:15 | 1:00 | [6 empty] | Productive |  |  | P/T KILL SIDE HCR FROM OPPOSITE DIRECTION OF FLOW TO 300/10000 PSI. GOOD TEST. Page 53 of 80
KZN-377 |  | INT2 |  | 2023-08-23 13:15 | 2023-08-23 18:15 | 5:00 | [6 empty] | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 10000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING. - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD . - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), LOW 250-350 PSI-LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - PERFORM CHAMBER TEST FOR THE NEW KILL SIDE HCR TO 3000 PSI 5 MIN OPEN/CLOSE.
KZN-377 |  | INT2 |  | 2023-08-23 18:15 | 2023-08-23 18:45 | 0:30 | [6 empty] | Productive |  |  | - RIG DOWN TEST ASSEMBLY.
KZN-377 |  | INT2 |  | 2023-08-23 18:45 | 2023-08-23 19:15 | 0:30 | [6 empty] | Productive |  |  | - INSTALL WEAR BUSHING
KZN-377 |  | INT2 |  | 2023-08-23 19:15 | 2023-08-23 20:30 | 1:15 | [6 empty] | Productive |  |  | *********9.5/8"CASING INTEGRITY TEST ********* PRESSURE UP 9 5/8" CSG AT SLOW PUMP RATE 0.4-0.5 BBL/MIN. - PERFORMED 9.5/8"' CASING INTEGRITY TEST TO 6600PSI -GOOD TEST. PUMPED VOLUME= BLED VOLUME = 13.4 BBL. - RIG DOWN SURFACE LINES - FUNCTION TEST SHEAR RAM Page 54 of 80
KZN-377 |  | INT2 |  | 2023-08-23 20:30 | 2023-08-24 | 3:30 | [6 empty] | Productive |  |  | TBT AND P/U & M/U 8 3/8" MOTOR BHA #1 TO 136 M - 8 3/8" TKC66 BIT, NOZZLES:6X14, S/N S298559 - 6-3/4" MUD MOTOR WITH NON-PORTED FLOAT VALVE (0.28 REV/GAL) - 8 1/4" STRING STAB W/ TOTCO RING - 1 x 6-1/2'' DC JOINT - 8 1/4" STRING STAB - 13 x 6-1/2'' DC JOINT NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 420 GPM - SPP 440 PS 480 GPM - SPP 545 PSI - MONITOR DISPLACEMENT THROUGH TRIP TANK
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 03:00 | 3:00 | [6 empty] | Productive |  |  | CONT. P/U & M/U 8 3/8" MOTOR BHA #1 FROM 220 M TO 537 M - 9 x 6 1-2" DC JOINTS - 6-1/2'' JAR - 3 x 6-1/2'' DC JOINT - 30 x 4'' HWDP JOINTS - WEIGHT BELOW JARS : 55 KLBS - TOTAL WEIGHT OF BHA : 100 KLB - MONITOR DISPLACEMENT THROUGH TRIP TANK - SINGLE IN 6-1/2'' DC JTS FROM PIPE CAT.
KZN-377 |  | INT2 |  | 2023-08-23 03:00 | 2023-08-23 06:30 | 3:30 | [6 empty] | Productive |  |  | RUN IN HOLE WITH 8 3/8'' MOTOR BHA FROM 537 M TO 1070 M - SINGLE IN 5'' 19.5 PPF DP FROM PIPE CAT. TOTAL 54 JOINTS. - MONITORED WELL ON TRIP TANK WITH TRIP SHEET - PERFORMED D1 DRILL FOR CREW - C - PERFORMEDFUNCTION TEST BOP - FILL STRG EVERY 20 STDS
KZN-377 |  | INT2 |  | 2023-08-23 06:30 | 2023-08-23 12:00 | 5:30 | [6 empty] | Productive |  |  | CONT. RIH HOLE WITH 8 3/8'' MOTOR BHA FROM 1070 M TO 3304 M - RUN 5'' DP FROM DERRICK - FILLUP STRING EVERY 15 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET PERFORM D1 DRILL WITH CREW D
KZN-377 |  | INT2 |  | 2023-08-23 12:00 | 2023-08-23 12:45 | 0:45 | [6 empty] | Productive |  |  | - WASH DOWN WITH 8 3/8 " MOTORIZED BHA FROM 3304 M TO 3360 M. - TAGGED FLOAT COLLAR AT 3360 M WITH 10KLBS. - 400 GPM, 1450 PSI
KZN-377 |  | INT2 |  | 2023-08-23 12:45 | 2023-08-23 13:00 | 0:15 | [6 empty] | Productive |  |  | - PULL OUT AND RACK BACK 2 STANDS.
KZN-377 |  | INT2 |  | 2023-08-23 13:00 | 2023-08-23 13:15 | 0:15 | [6 empty] | Productive |  |  | - TBT FOR SLIP DRILL LINE. Page 55 of 80
KZN-377 |  | INT2 |  | 2023-08-23 13:15 | 2023-08-23 14:15 | 1:00 | [6 empty] | Productive |  |  | SLIP DRILL LINE - PARKED TDS AND HANG BLOCK . - SLIP 12 M OF DRILL LINE. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT. MEANWHILE, MONITOR WELL THROUGH TRIP TANK, STATIC
KZN-377 |  | INT2 |  | 2023-08-23 14:15 | 2023-08-23 15:00 | 0:45 | [6 empty] | Productive |  |  | SERVICE TDS.
KZN-377 |  | INT2 |  | 2023-08-23 15:00 | 2023-08-23 17:45 | 2:45 | [6 empty] | Productive |  |  | CONDUCT, D4 & D5 DRILLS WITH CREW ( D ). - INSTALL FOSV, GRAY VALVE & 1 STD 5'' DP. CONNECT TDS - CLOSE ANNULAR PREVENTER & OPEN HCR & STRIPPING BOTTLE - REDUCE ANNULAR PRESSURE TO 600 PSI. - RAISE CASING PRESSURE TO 600 PSI. (NOTE: UNABLE TO SEAL PRESSURE WITH 400 PSI CLOSING PRESSURE, INCREASE GRADUALLY TO 600 PSI) - PREPARED TOOL JOINT FOR STRIPPING. - STRIPPED IN WHILE MAINTAINING CONSTANT CASING PRESSURE. - STRIP TOOL JOINT WITH 50 KLB WEIGHT. - PERFORMED D4 DRILL WITH CREW, GOOD UNDERSTANDING AND CONTROL ON CHOKE. - HELD AFTER ACTION REVIEW WITH CREW. CREW PERFORMED WELL IN DISCUSSION AND THROUGHOUT THE DRILL. - BLEED BACK CSG PRESSURE TO ZERO. - FLUSH MGS AS PER ABRAJ PROCEDURES - LINE UP FOR DRILLING. NOTE: FOUND STRIP LINE AND MGS MUD SEAL LINES BLOCKED, CLEAN BOTH.
KZN-377 |  | INT2 |  | 2023-08-23 17:45 | 2023-08-23 18:45 | 1:00 | [6 empty] | Productive |  |  | WASH DOWN FROM TO 3360 M TAKE SCRS WITH MP1 & 2. RECORDED PUMP OFF FINGERPRINT AT 400 GPM: RIG (22 BBLS), ML (22 BBLS) AT 530 GPM: RIG (33 BBLS), ML (33 BBLS) AT 550 GPM: RIG (34 BBLS), ML (34 BBLS) Page 56 of 80
KZN-377 |  | INT2 |  | 2023-08-23 18:45 | 2023-08-23 20:30 | 1:45 | [6 empty] | Productive |  |  | WASH DOWN AND TAG TOC AT 3360 M. - DRILL CEMENT PLUGS AND FLOAT COLLAR FROM 3360 M TO 3361.25 M(30 MINS) FR 405 GPM, SPP 1450-1550 PSI, WOB 8-12 KLBS, RPM 40 , TRQ 2-7 KFT.LBS. - DRILL SHOE TRACKFROM 3361.25 M TO 3389.75 M(45 MINS) FR 405GPM, SPP 1700-2050 PSI, WOB 3-8 KLBS, RPM 40 , TRQ 3-8 KFT.LBS.
KZN-377 |  | INT2 |  | 2023-08-23 20:30 | 2023-08-23 20:45 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK PRIOR DRILLING SHOE TRACK. - SPACED OUTDRILLING STING SO NO CONNECTION REQUIRED WHILE DRILLING RAT HOLE
KZN-377 |  | INT2 |  | 2023-08-23 20:45 | 2023-08-23 21:30 | 0:45 | [6 empty] | Productive |  |  | WASH DOWN AND TAG TOC AT 3389.75 M. - DRILL SHOE TRACKAND REAMER SHOEFROM 3389.75 M TO 3400..3 M(30 MINS) FR 405GPM, SPP 1250-1450 PSI, WOB 3-8 KLBS, RPM 40 , TRQ 3-8 KFT.LBS. - CLEARED RAT HOLE FROM 3400.3 M TO 3404.7 M (15 MINS) FR 405 GPM, SPP 1200-1400 PSI, WOB 3-12 KLBS, RPM 40 , TRQ 4 - 7 KFT.LBS. -WIPE FULL STAND THROUGH FLOAT SHOE 2 TIMES WITH AND WITHOUT PUMP
KZN-377 |  | INT2 |  | 2023-08-23 21:30 | 2023-08-23 21:45 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK PRIOR DRILLING NEW FORMATION.
KZN-377 |  | INT2 |  | 2023-08-23 21:45 | 2023-08-23 22:30 | 0:45 | [6 empty] | Productive |  |  | DRILL OUT NEW FORMATION FROM 3404 M TO 3410 M. WOB: 10-15 KLB, FLOW RATE: 405 GPM,SPP: 1480PSI, SURFACE PRM 40 , TRQ 4-7KFT.LBS,DIFF PRESSURE 100-150 PSI.
KZN-377 |  | INT2 |  | 2023-08-23 22:30 | 2023-08-23 23:30 | 1:00 | [6 empty] | Productive |  |  | CIRCULATE BOTTOMS UP WITH 450-500 GPM, SPP 2250-3050 PSIMW IN 1.19 SG MW OUT 1.19 SG
KZN-377 |  | INT2 |  | 2023-08-23 23:30 | 2023-08-23 23:45 | 0:15 | [6 empty] | Productive |  |  | RIG UP SURFACE LINE FOR FIT
KZN-377 |  | INT2 |  | 2023-08-23 23:45 | 2023-08-24 | 0:15 | [6 empty] | Productive |  |  | PJSM WITH CREW PRIOR FIT.
KZN-377 |  | INT2 |  | 2023-08-23 | 2023-08-23 03:00 | 3:00 | [6 empty] | Productive |  |  | ****** FIT AT ALKHALATA FORMATION (9-5/8" CASING SHOE) (MW - 1.19 SG) (EMW=1.638 SG) ****** - LINE UP FOR FIT. - PUMP AT 0.4 BPM UP TO 2175 PSI - INITIAL FIT SURFACE PRESSURE ACHIEVED = 2200 PSI - FINAL FIT SURFACE PRESSURE = 2085 PSI - AL KHALATA FIT EMW: 1.64 SG EMW - BLED OFF PRESSURE TO ZERO - VOL PUMPED: 4.6 BBL, VOL RETURNED = 4.5 BBLS. - CONFIRM ZERO PRESSURE BELOW BOP. OPEN UPR. Page 57 of 80
KZN-377 |  | INT2 |  | 2023-08-23 03:00 | 2023-08-23 03:30 | 0:30 | [6 empty] | Productive |  |  | RD DOWN SURFACE LINES. - FLUSH KILL LINE, CHOCK LINE AND MGS AS PER ABRAJ PROCEDURE.
KZN-377 |  | PROD1 |  | 2023-08-23 03:30 | 2023-08-23 06:00 | 2:30 | [6 empty] | Productive |  |  | WASH DOWN TO 3410 MAND RESUME DRILLING 8.3/8" SECTION FROM 3410 M TO 3421 M. FR 405 GPM , SPP 1300 -1450PSI, WOB 5-15 KLB , RPM 40 , TRQ 3-7 KFT.LBS , DIFF PRESSURE140 PSI. AVG ROP: 4.42 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 23:30 | 17:30 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3421 M TO 3683 M. FR 405-530 GPM , SPP 1450-2500 PSI, WOB 15-25 KLB, RPM 40-55 , TRQ 3-7 KFT.LBS, DIFF PRESSURE 200-300 PSI. AVG ROP: 17.21 M/HR - DRILLED WITH CONTROL PARAMETERS TILL UPPER STAB IS OUT OF THE CASING SHOE. - TOP OF SAFIQ = 3445 M. DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 279 M DAILY BIT HRS: 17.23 HR AVG ROP: 17.21 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 23:30 | 2023-08-23 23:45 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICES ( GREASE WASH PIPE)
KZN-377 |  | PROD1 |  | 2023-08-23 23:45 | 2023-08-24 | 0:15 | [6 empty] | Productive |  |  | TAKE SCR. PUMP#2 30 SPM 200 PSI 40 SPM 285 PSI - TOOK FLOW BACK BASE LINE WITH 540 GPM =>> 33 BBLS
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3683 M TO 3766M. FR 540-550 GPM , SPP 2250-2500 PSI, WOB 28-35 KLB, RPM 50-60 , TRQ 6-8 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG ROP: 16.89M/HR - TOP OF UPPER GHUDUN= 3708 M.
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 09:00 | 3:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3766 M TO 3793 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 28-35 KLB, RPM 50-60 , TRQ 6-8 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG ROP: 8.62M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 09:00 | 2023-08-23 09:15 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE. Page 58 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 09:15 | 2023-08-23 15:00 | 5:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3793 M TO 3867 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 28-35 KLB, RPM 50-60 , TRQ 6-8 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG ROP: 15.4M/HR PERFORM FIRE AND H2S FOR CREW D.
KZN-377 |  | PROD1 |  | 2023-08-23 15:00 | 2023-08-23 15:15 | 0:15 | [6 empty] | Productive |  |  | PERFORM D2 AND D6 DRILLS WITH CREW D. ADDED VOLUME TO THE ACTIVE SYSTEM SLOWLY. BOTH DRILLER AND ML RESPONDED TO THE INCREASE. DRILLER FOLLOWED PROCEDURE BY PICKING UP AND FLOW CHECK WELL. GOOD RESPONCE.
KZN-377 |  | PROD1 |  | 2023-08-23 15:15 | 2023-08-23 18:00 | 2:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3867 M TO 3880 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 28-35 KLB, RPM 50-60 , TRQ 6-8 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG ROP: 5M/HR PERFORM FIRE AND H2S FOR CREW D.
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-23 23:45 | 5:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3880 M TO3910 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 35-40 KLB, RPM 50-60 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 227 M DAILY BIT HRS: 21.32 HR AVG ROP: 10.65 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 23:45 | 2023-08-24 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES - GREASED WASH PIPE-
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3910 M TO3936 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 35-40 KLB, RPM 50-60 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 26 M DAILY BIT HRS: 6 HR AVG ROP: 4.62M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3936 M TO 3982 M. FR 540-550 GPM, SPP 2450-2600 PSI, WOB 30-38 KLB, RPM 40-50 , TRQ 6-8 KFT.LBS, DIFF PRESSURE 100-200 PSI. ================== FOOTAGE DRILLED: 46 M DAILY BIT HRS: 12 HR AVG ROP: 4.2 M/HR Page 59 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-23 21:00 | 3:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3982 M TO3994 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 35-40 KLB, RPM 50-60 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 12 M DAILY BIT HRS: 3 HR AVG ROP: 4M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 21:00 | 2023-08-23 21:15 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES - GREASED WASH PIPE-
KZN-377 |  | PROD1 |  | 2023-08-23 21:15 | 2023-08-24 | 2:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 3994 M TO4008 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 35-40 KLB, RPM 50-60 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. DAILY DRILLING SUMMARY ================== FOOTAGE DRILLED: 13 M DAILY BIT HRS: 2.75HR AVG ROP: 4.73 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 06:00 | 6:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4008 M TO4032 M. FR 540-550 GPM, SPP 2450-2500 PSI, WOB 35-39 KLB, RPM 40-50 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. DAILY DRILLING SUMMARY AVG ROP: 4.42 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 10:45 | 4:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4032 M TO 4050 M. FR 540-550 GPM, SPP 2450-26500 PSI, WOB 35-36 KLB, RPM 40-50 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG. ROP = 4.2 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 10:45 | 2023-08-23 11:00 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE.
KZN-377 |  | PROD1 |  | 2023-08-23 11:00 | 2023-08-23 17:45 | 6:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4050 M TO 4078 M. FR 540-550 GPM, SPP 2450-2650 PSI, WOB 35-36 KLB, RPM 40-50 , TRQ 4-9 KFT.LBS, DIFF PRESSURE 100-200 PSI. AVG. ROP = 3.9 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 17:45 | 2023-08-23 19:00 | 1:15 |  |  |  | RREP |  |  | Non-Productive |  |  | - OBSERVE LEAK FROM TDS WASH PIPE. - STOP DRILLING AND RACK BACK 1 STAND - CHANGE OUT WASH PIPE AS PER ABRAJ PROCEDURE - PRESSURE TEST WASH PIPE TO 1500 PSI MEANWHILE, MONITOR WELL THROPUGH TRIP TANK. Page 60 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 19:00 | 2023-08-24 | 5:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4078 M TO 4097 M. FR 540-550 GPM, SPP 2450-2680 PSI, WOB 35-38 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-225 PSI. ================== FOOTAGE DRILLED: 89 M DAILY BIT HRS: 22.3 HR AVG ROP: 3.99 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 04:45 | 4:45 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4097 M TO 4114 M. FR 540-550 GPM, SPP 2550-2780 PSI, WOB 35-38 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-225 PSI. AVG ROP 3.93 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 04:45 | 2023-08-23 05:00 | 0:15 | [6 empty] | Productive |  |  | OBSERVED INCREASE IN FLOW OUT PERFORMED FLOW CHECK, WELL STATIC FOUND RIG FLOWBACK SENSORE GAVE FALSE READING
KZN-377 |  | PROD1 |  | 2023-08-23 05:00 | 2023-08-23 06:00 | 1:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4114 M TO 4117M. FR 540-550 GPM, SPP 2550-2780 PSI, WOB 35-38 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-225 PSI. AVG ROP3M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 18:00 | 12:00 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4117 M TO 4158 M. FR 540-550 GPM, SPP 2600-2780 PSI, WOB 35-41 KLB, RPM 40-50, TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-225 PSI. PERFORM DRILL OFF TEST WITH DIFFERENT PARAMETERS AS FOLLOW: WOBRPMAVG. ROP 37503.6 39403.2 41403.6 41503.5 AVG ROP = 3.56 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-23 21:15 | 3:15 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4158 M TO 4167 M. FR 540-550 GPM, SPP 2600-2780 PSI, WOB 38-43 KLB, RPM 40-50, TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-225 PSI. PERFORM DRILL OFF TEST WITH DIFFERENT PARAMETERS AS FOLLOW: WOBRPMAVG. ROP 43402.8
KZN-377 |  | PROD1 |  | 2023-08-23 21:15 | 2023-08-23 21:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES ( GREASED WASH PIPE) Page 61 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 21:30 | 2023-08-24 | 2:30 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4167 M TO 4174 M. FR 540-550 GPM, SPP 2725-2825 PSI, WOB 38-40 KLB, RPM 40-50, TRQ 5-10 KFT.LBS, DIFF PRESSURE 100-150 PSI. ================== FOOTAGE DRILLED: 77 M DAILY BIT HRS: 22.9HR AVG ROP: 3.36 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 17:15 | 17:15 | [6 empty] | Productive |  |  | DRILLING 8.3/8" SECTION FROM 4174 M TO 4224 M. FR 540-550 GPM, SPP 2800-2950 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-150 PSI. PERFORM DOT @ WOB 43 KLB NO CHANGE IN ROP. RELAXED BIT AVG ROP 3.1M/HR. - AT 08:00 HRS FUNCTION TEST BOP FROM DRILLER PANEL.
KZN-377 |  | PROD1 |  | 2023-08-23 17:15 | 2023-08-23 17:45 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS.
KZN-377 |  | PROD1 |  | 2023-08-23 17:45 | 2023-08-23 18:30 | 0:45 | [6 empty] | Non-Productive |  |  | ATTEMPT TO BREAK CONNECTION AFTER TDS SERVICE -UNABLE. HAD ISSUE WITH TDS DRILLER SIDE MOTOR PHASE LOST , CONT. DRILLING WITH ONE MOTOR ODS. MEANWHILE TROUBLSHOT THE ISSUE WITH THE FAULT ON THE DS TDS MOTOR.
KZN-377 |  | PROD1 |  | 2023-08-23 18:30 | 2023-08-23 23:15 | 4:45 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4224 M TO 4235 M FR550 GPM, SPP 2950-3000 PSI, WOB 40-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-150 PSI. -AT 21:30 HRS THE TDS MOTOR ISSUE IS RESOLVED. ================== FOOTAGE DRILLED: 61 M DAILY BIT HRS: 21.1 HR AVG ROP: 3.12M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 | [6 empty] | Non-Productive |  |  | OBSERVED LEAK IN TDS SAVER SUB. CHANGED SAME
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 03:30 | 3:30 | [6 empty] | Non-Productive |  |  | OBSERVED LEAK IN TDS SAVER SUB. -CHANGED SAVER SUB -CHANGED GRABBER DIES
KZN-377 |  | PROD1 |  | 2023-08-23 03:30 | 2023-08-23 11:45 | 8:15 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4135 M TO 4253 M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-150 PSI. AVG ROP 2.4M/HR.
KZN-377 |  | PROD1 |  | 2023-08-23 11:45 | 2023-08-23 12:15 | 0:30 | [6 empty] | Productive |  |  | SERVICE TDS. Page 62 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 12:15 | 2023-08-23 12:45 | 0:30 | [6 empty] | Non-Productive |  |  | UNABLE TO BREAK BETWEEN THE SAVER SUB AND DP DUE TO HIGH TORQUE , REACH UP TO 46 KFT.LB. USED THE MANUAL TONG TO BREAK OUT THE CONNECTION BETWEEN THE DP AND SAVER SUB.
KZN-377 |  | PROD1 |  | 2023-08-23 12:45 | 2023-08-23 23:15 | 10:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4253 M TO 4283M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. ================== FOOTAGE DRILLED: 48 M DAILY BIT HRS: 18.4HR AVG ROP: 2.61M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 | [6 empty] | Non-Productive |  |  | CHANGED TDS SAVER SUB.
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 00:15 | 0:15 | [6 empty] | Non-Productive |  |  | CHANGED TDS SAVER SUB.
KZN-377 |  | PROD1 |  | 2023-08-23 00:15 | 2023-08-23 00:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED SERVICE TDS
KZN-377 |  | PROD1 |  | 2023-08-23 00:30 | 2023-08-23 06:00 | 5:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4283 M TO4293 M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. - REDUCED RPM TO 40 RPM SINCE 05:00 AM. AVG ROP2.1M/HR.
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 13:30 | 7:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4293 M TO4310 M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. AVG ROP 2.27M/HR.
KZN-377 |  | PROD1 |  | 2023-08-23 13:30 | 2023-08-23 13:45 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES ( GREASED WASH PIPE)
KZN-377 |  | PROD1 |  | 2023-08-23 13:45 | 2023-08-23 18:00 | 4:15 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4310 M TO4320 M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. AVG ROP =2.34 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-24 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4320 M TO4333 M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. ================== FOOTAGE DRILLED: 50 M DAILY BIT HRS: 22.61HR AVG ROP: 2.21M/HR Page 63 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 03:45 | 3:45 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4333 M TO 4341M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. AVG ROP =2.13 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 03:45 | 2023-08-23 04:00 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICE - GREASED WASHPIPE- MEANWHILE PERFORM SCR.
KZN-377 |  | PROD1 |  | 2023-08-23 04:00 | 2023-08-23 13:15 | 9:15 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4341 M TO 4368M. FR 540-550 GPM, SPP 2850-3000 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-100 PSI. AVG ROP = 2.92M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 13:15 | 2023-08-23 13:30 | 0:15 | [6 empty] | Productive |  |  | TDS SERVICE.
KZN-377 |  | PROD1 |  | 2023-08-23 13:30 | 2023-08-23 22:00 | 8:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4368 M TO 4405M. FR 540-550 GPM, SPP 2850-3150 PSI, WOB 38-43 KLB, RPM 40-50 , TRQ 5-10 KFT.LBS, DIFF PRESSURE 50-200 PSI. TOP OF BARAKT AT 4365 M. ================== FOOTAGE DRILLED: 72 M DAILY BIT HRS: 20.29HR AVG ROP: 3.55M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 22:00 | 2023-08-23 22:15 | 0:15 | [6 empty] | Productive |  |  | RECORD SCR RACK BACK STAND.
KZN-377 |  | PROD1 |  | 2023-08-23 22:15 | 2023-08-23 22:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK, WELL STATIC. INSTALL DP WIPER & AIR SLIPS
KZN-377 |  | PROD1 |  | 2023-08-23 22:30 | 2023-08-23 23:00 | 0:30 | [6 empty] | Productive |  |  | DROP GYRO INTO DRILL STRING WAIT FOR GYRO TOOL TO LAND INTO TOTCO RING.
KZN-377 |  | PROD1 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA#1 ON ELEVATOR FROM 4405 M TO 4110 M. - MONITOR DISPLACEMENT ON TRIP TANK. - NO OVERPULL OBSERVED.
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 02:15 | 2:15 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA#1 ON ELEVATOR FROM 4110 M TO 3391 M ( 9.5/8" CSG SHOE). - NO OVERPULL OBSERVED. - MONITOR THE WELL THROUGH TRIP SHEET. - CONTROL TRIPPING SPEED AS PER RECOMMNEDED TRIPPING SPEED.
KZN-377 |  | PROD1 |  | 2023-08-23 02:15 | 2023-08-23 02:30 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK - WELL STATIC.
KZN-377 |  | PROD1 |  | 2023-08-23 02:30 | 2023-08-23 02:45 | 0:15 | [6 empty] | Productive |  |  | PUMP SLUG
KZN-377 |  | PROD1 |  | 2023-08-23 02:45 | 2023-08-23 03:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AFTER SLUG - WELL STATIC Page 64 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 03:00 | 2023-08-23 09:00 | 6:00 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA#1 ON ELEVATOR FROM 3391 M TO 1560M. - MONITOR THE WELL THROUGH TRIP SHEET. - IRON-ROUGHNECK UNABLE TO BREAK-OUT CONNECTION USED MANUAL TONGS FOR 7 CONNECTIONS. - AT 08:00 CREW HANDOVER AND TBT.
KZN-377 |  | PROD1 |  | 2023-08-23 09:00 | 2023-08-23 09:15 | 0:15 | [6 empty] | Productive |  |  | PERFORMED KICK WHILE TRIPPING DRILL 'D1' WITH CREW# A. GOOD RESPONSE FROM RIG FLOOR CREW IN SECURING THE WELL IN ~ 2 MINS. HELD AAR WITH CREW.
KZN-377 |  | PROD1 |  | 2023-08-23 09:15 | 2023-08-23 10:45 | 1:30 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA#1 ON ELEVATOR FROM 1560 M TO 537 M ( TOP OF BHA). - MONITOR THE WELL THROUGH TRIP SHEET.
KZN-377 |  | PROD1 |  | 2023-08-23 10:45 | 2023-08-23 11:00 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AT TOP OF BHA - WELL STATIC.
KZN-377 |  | PROD1 |  | 2023-08-23 11:00 | 2023-08-23 15:30 | 4:30 | [6 empty] | Productive |  |  | CONT. POOH WITH 8.3/8" MOTORIZED BHA#2 ON ELEVATOR FROM 537 M TO SURFACE. RACK BACK 5 X 5" HWDP STANDS AND LAY DOWN 5 X 5" HWDP AS THEY REACH 450 HRS. RACK BACK 1 X6.1/2" DC STAND LAY DOWN 6.45" JAR RACK BACK 7 X 6.1/2" DC STANDS. LAY DOWN 8.1/4" S. STABILIZER LAY DOWN 1 X6.1/2" DC SINGLE. LAY DOWN 8.1/4" S. STABILIZER BREAK OUT BIT ANDLAY DOWN 7" NITRO-FORCE FORCE MOTOR. 8 3/8"TKC66 PDC BIT BIT DULL GRADING: (1-1-WT-A-X- IN-NO-BHA ) MONITOR WELL THROUGH TRIP TANK FUNCTION TEST BOP FROM OFFICE REMOTE PANEL.
KZN-377 |  | PROD1 |  | 2023-08-23 15:30 | 2023-08-23 15:45 | 0:15 | [6 empty] | Productive |  |  | CLEAR AND CLEAN RIG FLOOR.
KZN-377 |  | PROD1 |  | 2023-08-23 15:45 | 2023-08-23 16:30 | 0:45 | [6 empty] | Productive |  |  | PERFORM MAST DROP INSPECTION. Page 65 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 16:30 | 2023-08-23 21:00 | 4:30 | [6 empty] | Productive |  |  | TBT AND P/U & M/U 8 3/8" MOTOR BHA #2 TO 545 M - 8 3/8" SMITH XS616 BIT, NOZZLES: 9X11, S/N QF9440 - 7" NITORFORCE MOTOR WITH NON-PORTED FLOAT VALVE (0.23 REV/GAL) - 8 1/4" STRING STAB W/ TOTCO RING - PBL SUB - 1 x 6-1/2'' DC JOINT - 8 1/4" STRING STAB - 7x 6-1/2'' DC STANDS. - 6-1/2'' JAR - 1x 6-1/2'' DC STAND - 10 x 5'' HWDP STANDS NOTE: SHALLOW TEST MUD MOTOR AS PER MOTOR ENG: 550 GPM - 870 SPPPSI WEIGHT BELOW JARS :55 KLBS - TOTAL WEIGHT OF BHA : 100 KLB - MONITOR DISPLACEMENT THROUGH TRIP TANK - INSTALLED AIR SLIPS - P/UP, M/UP 15JTS X 5" HWDP F/ CAT WALK -P/UP , M/UP 3JTS X 5" G2 DP
KZN-377 |  | PROD1 |  | 2023-08-23 21:00 | 2023-08-23 22:45 | 1:45 | [6 empty] | Productive |  |  | CONT. RIH HOLE WITH 8 3/8'' MOTOR BHA #2 FROM 545 M TO 1120M. - FILLUP STRING EVERY 20 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
KZN-377 |  | PROD1 |  | 2023-08-23 22:45 | 2023-08-23 23:00 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK, WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 23:00 | 2023-08-24 | 1:00 | [6 empty] | Productive |  |  | SLIP AND CUT DRILL LINE - PARKED TDS AND HANG BLOCK . - CUT 24 OF DRILL LINE AND SLIP 12 M.
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:30 | 1:30 | [6 empty] | Productive |  |  | CONT. SLIP AND CUT DRILL LINE. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
KZN-377 |  | PROD1 |  | 2023-08-23 01:30 | 2023-08-23 02:00 | 0:30 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES
KZN-377 |  | PROD1 |  | 2023-08-23 02:00 | 2023-08-23 05:45 | 3:45 | [6 empty] | Productive |  |  | RIH HOLE WITH 8 3/8'' MOTOR BHA #2 FROM 1120 M TO 2875 M. - FILLUP STRING EVERY 20 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
KZN-377 |  | PROD1 |  | 2023-08-23 05:45 | 2023-08-23 06:00 | 0:15 | [6 empty] | Productive |  |  | PERFORMED KICK WHILE TRIPPING DRILL 'D1' WITH CREW# D. GOOD RESPONSE FROM RIG FLOOR CREW IN SECURING THE WELL IN ~ 2 MINS. HELD AAR WITH CREW. Page 66 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 08:45 | 2:45 | [6 empty] | Productive |  |  | RIH HOLE WITH 8 3/8'' MOTOR BHA #2 FROM 2875 M TO 3778 M. - FILLUP STRING EVERY 20 STANDS RIH - MONITORED WELL ON TRIP TANK WITH TRIP SHEET
KZN-377 |  | PROD1 |  | 2023-08-23 08:45 | 2023-08-23 09:30 | 0:45 | [6 empty] | Productive |  |  | OBSERVED DRAG 20-40 KLBS AND OVERPULL TO 30 KLBS AS GOING BELOW 3778 M. UNABLE TO CLEAR THE DRAG WITH WIPING THE STRING UP AND DOWN. REAM DOWN THE STAND FROM 3778 M TO 3811 M WITH FR 400 , SPP 1850 PSI , RPM 35 , TRQ 4-5 KFT.LBS NCREASED TO 6 -7 KFT.LBS BETWEEN 3778 AND 3794 M.
KZN-377 |  | PROD1 |  | 2023-08-23 09:30 | 2023-08-23 11:00 | 1:30 | [6 empty] | Productive |  |  | AFTER CONNECTION ATTEMPT TO RUN BACK STRING ON ELEVATOR WITH ON ISSUES. CONT. RIH 8.3/8" MOTOR BHA # 2 FROM 3811 M TO 4271 M.
KZN-377 |  | PROD1 |  | 2023-08-23 11:00 | 2023-08-23 11:15 | 0:15 | [6 empty] | Productive |  |  | AT 4271 M OBSERVED DRAG 30 KLBS. REAM DOWN THE STAND FROM 4271 M TO 4283 M WITH FR 400 ,SPP 1950 PSI , RPM 35 , TRQ 4-5 KFT.
KZN-377 |  | PROD1 |  | 2023-08-23 11:15 | 2023-08-23 12:15 | 1:00 | [6 empty] | Productive |  |  | CONT. RIH ON ELEVATOR WITH 8 3/8'' MOTOR BHA #2 FROM 4283 M TO 4402 M. TAKE SCR. RECORDED PUMP OFF FINGERPRINT AT 400 GPM: RIG (20 BBLS), ML (18 BBLS) AT 500 GPM: RIG (26 BBLS), ML (25 BBLS)
KZN-377 |  | PROD1 |  | 2023-08-23 12:15 | 2023-08-23 13:30 | 1:15 | [6 empty] | Productive |  |  | CIRCULATE HOLE CLEAN FR 550 GPM, SPP 3140 PSI. - PERFORM TBT FOR STRESS CAGE JOB.
KZN-377 |  | PROD1 |  | 2023-08-23 13:30 | 2023-08-23 13:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK - WELL STATIC.
KZN-377 |  | PROD1 |  | 2023-08-23 13:45 | 2023-08-23 14:45 | 1:00 | [6 empty] | Productive |  |  | PERFORM SHORT CHECK TRIP FROM 4402 M TO 4335 M. THEN RUN BACK TO BOTTOM.
KZN-377 |  | PROD1 |  | 2023-08-23 14:45 | 2023-08-23 15:30 | 0:45 | [6 empty] | Productive |  |  | DROP 1 X2" PBL ACTIVATION BALL AND CIRCULATE WITH 300 GPM , SPP 1170 PSI.AFTER CIRCULATING ~ 0.8 STRING VOLUME OBSERVED PRESSURE DROPPED TO 960 PSI ( PBL ACTIVATED).
KZN-377 |  | PROD1 |  | 2023-08-23 15:30 | 2023-08-23 16:30 | 1:00 | [6 empty] | Productive |  |  | PUMPED 156 BBL OF STRESS CAGE PILL TO COVER 20 M BELOW GHUDUN AND 20 M ABOVE GHUDUN. FR 300 GPM, SPP 900-800 PSI DISPLACE PILL WITH STRING VOLUME FR 300 GPM , SPP 800-950 PSI
KZN-377 |  | PROD1 |  | 2023-08-23 16:30 | 2023-08-23 16:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK PRIOR POOH TO TOP OF THE PILL - WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 16:45 | 2023-08-23 19:45 | 3:00 | [6 empty] | Productive |  |  | POOH WITH 8.3/8"BHA # 2 ON ELEVATOR FROM 4400 M TO 3650 M ( ONE STAND ABOVE STRESS CAGE PILL). POH SPEED 10 M/MIN. Page 67 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 19:45 | 2023-08-23 21:30 | 1:45 | [6 empty] | Productive |  |  | CIRCULATED STRING VOLUME TO REMOVE EXCESS MATERIAL ACROSS PBL SUB WITH 500 GPM, 1870 PSI. - BROKE OUT STRING AND DROPPED 2 X 1 3/8" DEACTIVATION STEEL BALLS. - PUMP WITH 300 GPM, 760 PSI , OBSERVED INCREASE IN STANDPIPE PRESSURE UPTO 1010PSI. - CIRCULATE STRING VOLUME AFTER DEACTIVATION OF PBL SUB AT 550 GPM , 2750 PSI. MEANWHILE CREW HANDOVER AND TBT FOR STRESS CAGE JOB WHILE CIRCULATION.
KZN-377 |  | PROD1 |  | 2023-08-23 21:30 | 2023-08-23 21:45 | 0:15 | [6 empty] | Productive |  |  | RIG UP SURFACE LINE TO BE ABLE TO PUMP FROM STRING AND KILL LINE. - FLUSH SURFACE LINES - CONNECTED SURFACE LINE TO HLB CEMENT UNIT.
KZN-377 |  | PROD1 |  | 2023-08-23 21:45 | 2023-08-23 22:00 | 0:15 | [6 empty] | Productive |  |  | PRESSURE TEST SURFACE LINE. - P/T SURFACE LINE TO 4000 PSI.- GOOD TEST - FLUSH THROUGH STRING AND KILL LINE. - CLOSE UPER PIPE RAM.
KZN-377 |  | PROD1 |  | 2023-08-23 22:00 | 2023-08-24 | 2:00 | [6 empty] | Productive |  |  | *** PERFORMED STRESS CAGE INTO GHUDUN FORMATION TO 1.75 SG *** - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2436 PSI AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 10 PSI/MIN. - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2595 PSI AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 8.5 PSI/MIN. - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2701 PSI AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 7 PSI/MIN. - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2806 PSI AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE MORE THAN 30PSI/MIN. -CAN NOT HOLD, STOP PUMPING AND CONSULT OFFICE - VOLUME PUMPED DURING STRESS-CAGE WAS 10.4 BBL, BLED VOLUME 5.7 BBL. ( FORMATION TAKE 4.7 BBLS)
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 00:30 | 0:30 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK , WELL STATIC NO LOSSES Page 68 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 00:30 | 2023-08-23 02:00 | 1:30 | [6 empty] | Productive |  |  | *** PERFORMED STRESS CAGE INTO GHUDUN FORMATION TO 1.75 SG *** - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2436 PSI ( EMW= 1.65 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 20 PSI/MIN. - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2595 PSI( EMW= 1.68 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE MORE THAN 30 PSI/MIN. - CONTINUE TO WAIT FOR 15 MINS - FINAL PRESSURE AT 15 MINUTES = 2100 PSI - VOLUME PUMPED DURING STRESS-CAGE WAS 12.1 BBL, BLED VOLUME 5.8 BBL(FORMATION TAKE 6.3 BBLS)
KZN-377 |  | PROD1 |  | 2023-08-23 02:00 | 2023-08-23 08:00 | 6:00 | [6 empty] | Productive |  |  | WASHED DOWNW/ 8 3/8" BHA # 2F/ 3650 M TO 4405 M , FR. 400 GPM , SPP, 1800-2000 PSI. OBSERVE WASH OUT IN STAND # 35 AND #36, RACK BACK THE SAME. AT 07:45 , TBT AND CREW HANDOVER.
KZN-377 |  | PROD1 |  | 2023-08-23 08:00 | 2023-08-23 10:30 | 2:30 | [6 empty] | Productive |  |  | BED ON BIT AND CONT. DRILLING8.3/8" SECTION FROM 4405 M TO 4422 M. FR 400-550 GPM , SPP 1950-3550 PSI, WOB 5-35 KLB , RPM 30-50 , TRQ 4-11 KFT.LBS , DIFF PRESSURE 100-500 PSI.
KZN-377 |  | PROD1 |  | 2023-08-23 10:30 | 2023-08-23 21:00 | 10:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4422 M TO 4491 M. FR 550 GPM , SPP 3150-3270 PSI , WOB 15-20 KLB, RPM 40-50, TRQ6-10 KFT.LBS , DIFF PRESSURE 150-200 PSI. TOP OF MABROUK AT 4427 M. - PREPARE STRESS CAGE PILL - CONTROL ROP TO 5-7 M/HR TO 50 M ABOVE BARIK , MEANWHILE DISCUSSING THE PLAN FOR STRESS CAGING GHUDUN.
KZN-377 |  | PROD1 |  | 2023-08-23 21:00 | 2023-08-23 22:15 | 1:15 | [6 empty] | Productive |  |  | CIRC. SHAKER CLEAN .
KZN-377 |  | PROD1 |  | 2023-08-23 22:15 | 2023-08-23 22:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK, NO LOSSES WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 22:30 | 2023-08-23 23:15 | 0:45 | [6 empty] | Productive |  |  | PERFORMED SHROT TRIP F/ 4491 FT. TO 4340 M - PULL BACK 6 STDS - RIH BACK TWO STDS
KZN-377 |  | PROD1 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 | [6 empty] | Productive |  |  | DROP 1 X2" PBL ACTIVATION BALL AND CIRCULATE WITH 300 GPM , SPP 1120 PSI.AFTER CIRCULATING - PRESSURE DROPPED TO 930 PSI ( PBL ACTIVATED). - HELD TBT FOR PUMPING SC Page 69 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:15 | 1:15 | [6 empty] | Productive |  |  | PUMPED 156 BBL OF STRESS CAGE PILL TO COVER 20 M BELOW GHUDUN AND 20 M ABOVE GHUDUN. FR 300 GPM, SPP 900-800 PSI DISPLACE PILL WITH STRING VOLUME FR 300 GPM , SPP 800-950 PSI
KZN-377 |  | PROD1 |  | 2023-08-23 01:15 | 2023-08-23 03:30 | 2:15 | [6 empty] | Productive |  |  | POOH WITH 8.3/8"BHA # 2 ON ELEVATOR FROM 4400 M TO 3650 M ( ONE STAND ABOVE STRESS CAGE PILL). POH SPEED 10 M/MIN.
KZN-377 |  | PROD1 |  | 2023-08-23 03:30 | 2023-08-23 04:30 | 1:00 | [6 empty] | Productive |  |  | CIRCULATED STRING VOLUME TO REMOVE EXCESS MATERIAL ACROSS PBL SUB WITH 500 GPM, 1870 PSI. - BROKE OUT STRING AND DROPPED 2 X 1 3/8" DEACTIVATION STEEL BALLS. - PUMP WITH 300 GPM, 760 PSI , OBSERVED INCREASE IN STANDPIPE PRESSURE UPTO 1010PSI. - CIRCULATE STRING VOLUME AFTER DEACTIVATION OF PBL SUB AT 550 GPM , 2750 PSI. MEANWHILE CREW HANDOVER AND TBT FOR STRESS CAGE JOB WHILE CIRCULATION.
KZN-377 |  | PROD1 |  | 2023-08-23 04:30 | 2023-08-23 04:45 | 0:15 | [6 empty] | Productive |  |  | RIG UP SURFACE LINE TO BE ABLE TO PUMP FROM STRING AND KILL LINE. - FLUSH SURFACE LINES - CONNECTED SURFACE LINE TO HLB CEMENT UNIT.
KZN-377 |  | PROD1 |  | 2023-08-23 04:45 | 2023-08-23 05:00 | 0:15 | [6 empty] | Productive |  |  | PRESSURE TEST SURFACE LINE. - P/T SURFACE LINE TO 4000 PSI.- GOOD TEST - FLUSH THROUGH STRING AND KILL LINE. - CLOSE UPER PIPE RAM. Page 70 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 05:00 | 2023-08-23 06:00 | 1:00 | [6 empty] | Productive |  |  | *** PERFORMED STRESS CAGE INTO GHUDUN FORMATION TO 1.75 SG *** - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2436 PSI (EMW=1.65 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 32 PSI/MIN- 8.8 BBLS PUMPED - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2436 PSI (EMW=1.65 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 31.5PSI/MIN.- 9.4 PUMPED VLUME - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2436 PSI (EMW=1.65 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 22.5 PSI/MIN.- 9.9 BBLS PUMPED VOLUME - PRESSURE UP GHUDUN FORMATION AT 0.5 BPM TO 2535 PSI AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 28 PSI/MIN. 10.8 PUMPED VOLUME - VOLUME PUMPED DURING STRESS-CAGE WAS 10.8 BBL, BLED VOLUME 5.5 BBL. ( FORMATION TAKE 5.3 BBLS) - STOPED STRESS CAGE OPERATION FOR 2 BBLS PUMPED INTO FORMATION AS PER PROGRAM.
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 10:45 | 4:45 | [6 empty] | Productive |  |  | WASH DOWN AND RIH W/ 8 3/8" BHA # 2 F/ 3650 M TO 4491 M , FR. 400 GPM , SPP, 1800-2000 PSI. -TAKE SCR.
KZN-377 |  | PROD1 |  | 2023-08-23 10:45 | 2023-08-23 13:00 | 2:15 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4491 M TO 4521 M. FR 550 GPM , SPP 3300-3500 PSI , WOB 33-36 KLB, RPM 50, TRQ6-11 KFT.LBS , DIFF PRESSURE 200-400 PSI. AVG ROP: 14.21 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 13:00 | 2023-08-23 13:15 | 0:15 | [6 empty] | Productive |  |  | PERFORM D2 AND D6 DRILLS WITH CREW A. ADDED VOLUME TO THE ACTIVE SYSTEM SLOWLY. BOTH DRILLER AND ML RESPONDED TO THE INCREASE. DRILLER FOLLOWED PROCEDURE BY PICKING UP AND FLOW CHECK WELL. GOOD RESPONCE.
KZN-377 |  | PROD1 |  | 2023-08-23 13:15 | 2023-08-23 16:45 | 3:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4521 M TO 4544 M. FR 550 GPM , SPP 3300-3500 PSI , WOB 35-40 KLB, RPM 50, TRQ6-11 KFT.LBS , DIFF PRESSURE 190-400 PSI. TOP BARIK SS AT 4535 M. AVG ROP: 7.41 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 16:45 | 2023-08-23 17:00 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS. Page 71 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 17:00 | 2023-08-24 | 7:00 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4544 M TO 4600 M. FR 550 GPM , SPP 3300-3500 PSI , WOB 40-45 KLB, RPM 50, TRQ7-12 KFT.LBS , DIFF PRESSURE 200-400 PSI. ================== FOOTAGE DRILLED: 109 M DAILY BIT HRS: 11.8 HR AVG ROP: 9.24M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 00:15 | 0:15 | [6 empty] | Productive |  |  | PERFORMED RIG SERVICES - GREASED WASH PIPE-
KZN-377 |  | PROD1 |  | 2023-08-23 00:15 | 2023-08-23 12:30 | 12:15 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4600 M TO 4657 M. FR 550 GPM , SPP 3100-3300 PSI , WOB 40-45 KLB, RPM 45- 50, TRQ7-12 KFT.LBS , DIFF PRESSURE 80-200 PSI. AVG ROP: 5.12M/HR BASE BARIK SAND AT 4652 M.
KZN-377 |  | PROD1 |  | 2023-08-23 12:30 | 2023-08-23 12:45 | 0:15 | [6 empty] | Productive |  |  | SERVICE TDS.
KZN-377 |  | PROD1 |  | 2023-08-23 12:45 | 2023-08-23 17:45 | 5:00 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4657 M TO 4667 M. FR 550 GPM , SPP 3100-3300 PSI , WOB 40-45 KLB, RPM 45 , TRQ7-12 KFT.LBS , DIFF PRESSURE 80-200 PSI. AVG ROP: 3.1 M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 17:45 | 2023-08-23 18:00 | 0:15 | [6 empty] | Productive |  |  | PERFORM D2 AND D6 DRILLS WITH CREW B. ADDED VOLUME TO THE ACTIVE SYSTEM SLOWLY. BOTH DRILLER AND ML RESPONDED TO THE INCREASE. DRILLER FOLLOWED PROCEDURE BY PICKING UP AND FLOW CHECK WELL. GOOD RESPONCE.
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-24 | 6:00 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4667 M TO 4684 M. FR 550 GPM , SPP 3100-3300 PSI , WOB 40-45 KLB, RPM 45 , TRQ7-12 KFT.LBS , DIFF PRESSURE 80-200 PSI. ================== FOOTAGE DRILLED: 84 M DAILY BIT HRS: 21.87HR AVG ROP: 3.84M/HR
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:45 | 1:45 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4684 M TO 4687M. FR 550 GPM , SPP 3100-3300 PSI , WOB 40-45 KLB, RPM 45- 50, TRQ7-12 KFT.LBS , DIFF PRESSURE 80-200 PSI. AVG ROP: 1.75 M/HR.
KZN-377 |  | PROD1 |  | 2023-08-23 01:45 | 2023-08-23 02:00 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES - GREASED WASH PIPE. Page 72 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 02:00 | 2023-08-23 15:30 | 13:30 | [6 empty] | Productive |  |  | CONT. DRILLING 8.3/8" SECTION FROM 4687 M TO SECTION TD AT4717M. FR 550 GPM , SPP 3100-3300 PSI , WOB 40-45 KLB, RPM 45- 50, TRQ7-12 KFT.LBS , DIFF PRESSURE80-200 PSI. AVG ROP: 2.5M/HR.
KZN-377 |  | PROD1 |  | 2023-08-23 15:30 | 2023-08-23 17:30 | 2:00 | [6 empty] | Productive |  |  | CIRC. SHAKER CLEAN - ONE & HALF BTM UP - SPOT 41 BBLS THERMAL PILL
KZN-377 |  | PROD1 |  | 2023-08-23 17:30 | 2023-08-23 17:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK, WELL STATIC. INSTALL DP WIPER & AIR SLIPS
KZN-377 |  | PROD1 |  | 2023-08-23 17:45 | 2023-08-23 23:00 | 5:15 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA#2 ON ELEVATOR FROM 4417 M TO 3390M.- MONITOR DISPLACEMENT ON TRIP TANK.- POOH SPEED AS SWAP CALCULATIONS
KZN-377 |  | PROD1 |  | 2023-08-23 23:00 | 2023-08-23 23:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK, WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 23:15 | 2023-08-23 23:30 | 0:15 | [6 empty] | Productive |  |  | PUMP SLUG
KZN-377 |  | PROD1 |  | 2023-08-23 23:30 | 2023-08-23 23:45 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK AFTER SLUG - WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 23:45 | 2023-08-24 | 0:15 | [6 empty] | Productive |  |  | PERFORMED TDS SERVICES
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 06:30 | 6:30 | [6 empty] | Productive |  |  | POOH WITH 8.3/8" MOTORIZED BHA # 2 ONELEVATOR FROM 3390 M TO 539 M (TOP OF BHA). - MONITOR DISPLACEMENT ON TRIP TANK. .- POOH SPEED AS SWAP CALCULATIONS.
KZN-377 |  | PROD1 |  | 2023-08-23 06:30 | 2023-08-23 06:45 | 0:15 | [6 empty] | Productive |  |  | - FLOW CHECK WELL AT TOP OF BHA, OK WELL STATIC.
KZN-377 |  | PROD1 |  | 2023-08-23 06:45 | 2023-08-23 10:45 | 4:00 | [6 empty] | Productive |  |  | CONT. POOH 8.3/8" BHA #5 ON ELEVATOR F/600 M TO SURFACE. -R/B 10 STANDS OF HWDP. -LAY DOWN 6.45" JAR. - R/B 7 X 6.1/2" DC STANDS. -LAY DOWN 8.1/4" S. STABILIZER -LAY DOWN 1 X6.1/2" DC SINGLE. - LAY DOWN 8 1/4" S. STABILIZER. - BREAK OUT BIT ANDLAY DOWN NITRO-FORCE FORCE MOTOR. - 8 3/8" SMITH XS616 BIT BIT DULL GRADING: (1-1-WT-A-X-I-CT-TD) - MONITOR DISPLACEMENT ON TRIP TANK.
KZN-377 |  | PROD1 |  | 2023-08-23 10:45 | 2023-08-23 11:00 | 0:15 | [6 empty] | Productive |  |  | -CLEAN AND CLEAR RIG FLOOR.
KZN-377 |  | PROD1 |  | 2023-08-23 11:00 | 2023-08-23 11:45 | 0:45 | [6 empty] | Productive |  |  | MAKE UP CAMERON JETTING TOOL JET WASH BOP FUNCTION BOP'S AND JET SEAL ASSEMBLY PROFILE.
KZN-377 |  | PROD1 |  | 2023-08-23 11:45 | 2023-08-23 12:45 | 1:00 | [6 empty] | Productive |  |  | TBT FOR BOP PRESSURE TEST - P/UP AND M/UP TEST ASSEMBLY. - RUN AND INSTALL TEST ASSEMBLY Page 73 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 12:45 | 2023-08-23 16:30 | 3:45 | [6 empty] | Productive |  |  | PRESSURE TEST BOPS AS PER ABRAJ PROCEDURE - TEST 1: LPR AND FOSV #1 FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 2: UPR, INNER KILL VALVE #54, INNER CHOKE VALVE #56MKV, MCV, AND L-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 3: UPR, OUTER KILL HCR VALVE #55, OUTER CHOKE HCR V #57 HCR AND U-IBOP FOR 250-350 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 4: CHOKE LINE COFLEX HOSE, KILL LINE HCR, CHOKE MANIFOLD MASTER VALVE (# 78) AND U-IBOP FOR 300 PSI LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK. - TEST 5: ANNULAR WITH 5'' DP FOR 250-350 PSI LOW / 3500 PSI HIGH FOR 5 MINS. TEST OK. - BACKOUT TEST PLUG AND RETRIEVE TEST STRING - CHANGE OVER LINE UP TO PUMP THROUGH CHOKE MANIFOLD . - TEST 6: ( TEST BLIND SHEAR RAM, CHOKE LINE, KILL LINE AND LO-TORQ VALVE, CHOKE MANIFOLD VALVES 61, 62, AND 79 ), LOW 250-350 PSI-LOW / 8000 PSI HIGH FOR 5 MINS. TEST OK.
KZN-377 |  | PROD1 |  | 2023-08-23 16:30 | 2023-08-23 16:45 | 0:15 | [6 empty] | Productive |  |  | RIG DOWN TEST ASSEMBLY.
KZN-377 |  | PROD1 |  | 2023-08-23 16:45 | 2023-08-23 17:00 | 0:15 | [6 empty] | Productive |  |  | INSTALL WEAR BUSHING.
KZN-377 |  | PROD1 |  | 2023-08-23 17:00 | 2023-08-23 18:00 | 1:00 | [6 empty] | Productive |  |  | PERFORM MAST DROP INSPECTION , AREA 1, 2 AND 3.
KZN-377 |  | PROD1 |  | 2023-08-23 18:00 | 2023-08-23 21:00 | 3:00 | [6 empty] | Productive |  |  | PJSM PRIOR RU WIRELINE TOOLS RIG UP WIRELINE SHEAVES AND CABLE. PICK UP AND MAKE UP TOOL STRING FOR RUN 1A: QUAD COMBO (DENSITY, NEUTRON, RESISTIVITY, SONIC & GAMMA) TOOL STRING (GR-SP- ZDL-CN-XMAC-RTEX-JAR)
KZN-377 |  | PROD1 |  | 2023-08-23 21:00 | 2023-08-23 21:30 | 0:30 | [6 empty] | Productive |  |  | TBT PRIOR PU AND LOAD THE RADIOACTIVE SOURCE LOAD RADIOACTIVE SOURCES
KZN-377 |  | PROD1 |  | 2023-08-23 21:30 | 2023-08-24 | 2:30 | [6 empty] | Productive |  |  | - STARTED RIH AND LOG WITH RUN 1A - RIH TO 4717 M ( 4719M WL DEPTH) - RECORDED REPEATED INTERVAL ACROSS BARIK
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | - STARTED RIH AND LOG WITH RUN 1A - RIH TO 4717 M( 4719 M WLDEPTH) - RECORDED REPEATED INTERVAL ACROSS BARIK Page 74 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 01:00 | 2023-08-23 08:00 | 7:00 | [6 empty] | Productive |  |  | - STARTED RIH AND LOG WITH RUN 1A (GR-SP- ZDL-CN-XMAC-RTEX-JAR) - RIH TO TD - RECORD MAIN PASS TO 50 M INSIDE 9 5/8" CSG. - WL TD4717M ( 4719 M WIRELINE DEPTH ) SPEED, 8M/MIN SHOE @ 3400 M. ( 3403M WL DEPTH) - LOG WITH GR TO SURFACE. - SENT LOGGING DATA TO OFFICE , ACCEPTAED OK - PULLED TOOL TO SURFACE. . - R/D BAKER WIRELINE TOOLS FOR 1A RUN.
KZN-377 |  | PROD1 |  | 2023-08-23 08:00 | 2023-08-23 11:00 | 3:00 | [6 empty] | Productive |  |  | PREPARE TOOLS IN THE PIPE CAT FOR LOG RUN 1B GR-RCI (STRADDLE PACKER)-RCX-JARS) -PJSM , PRIOR TO WIRELINE RUN 1B. -P/UP AND M/UP WIRELINE TOOLS FOR 1B: GR-RCI (STRADDLE PACKER)-RCX-JARS -POWER UP & SURFACE CHECK
KZN-377 |  | PROD1 |  | 2023-08-23 11:00 | 2023-08-23 15:45 | 4:45 | [6 empty] | Productive |  |  | STARTED RIH AND LOG WITH RUN 1B TO 4577 -STOP FOR THERMAL STABILIZATION AT 3350 M. CORRECTED DEPTH BY 3 M - CORRELATED PASS - DEPTH CORRECTED BY GR CORRELATION BY 4.3M TOTAL - - RECORDED STICK TRIAL #1 AT 4590 M - CHT 2570 LBS - TTEN 7850 LBS FOR 10 MIN. - RECORDED STICK TRIAL #2 AT 4577 M - CHT 2580 LBS - TTEN 7880 LBSFOR 20 MIN. Page 75 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 15:45 | 2023-08-23 22:45 | 7:00 | [6 empty] | Productive |  |  | PERFORM PRESSURE PRETEST AQUISITION AT SELECTED POINTS (13 POINTS WERE SELECTED INITIALLY BY SUB-SURFACE TEAM): STOP AT 4577 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 1, GOOD TEST GOT 800 LBS OVERPULL . 16 MIN. MOVE TO 4581.5 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 2,GOOD TEST GOT 200 LBS OVERPULL . 18 MIN MOVE TO 4589.9M, CONDUCTED SINGLE PROBE PRESSURE POINT# 3, STILL BUILDING , GOT 1000 LBS OVERPULL . 30 MIN. MOVE TO 4594.5 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 4,GOOD TEST GOT 700 LBS OVERPULL . 20 MIN. MOVE TO 4596.2 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 5, GOOD TEST GOT 1500LBS OVERPULL . 28 MIN MOVE TO 4602.9 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 6, GOOD TEST GOT 1000LBS OVERPULL . 23 MIN MOVE TO 4611.5 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 7,STILL BUILDING , GOT 2800 LBS. OVERPULL30 MIN. CONDUCT MEETING WITH TOWN DUE TO INCREASING OVERPULL OBSERVED WHILE TAKING PP MOVE TO 4556.7 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 15,STILL BUILDING , NO OVERPULL . 30 MIN. MOVE TO 4561.1 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 14,GOOD TESTNO OVERPULL . 30 MIN MOVE TO 4569.8 M, CONDUCTED SINGLE PROBE PRESSURE POINT# 13,STILL BUILDING , NO OVERPULL . 30 MIN. - STOP TAKING PP TO AVOID TOOL STICKING.
KZN-377 |  | PROD1 |  | 2023-08-23 22:45 | 2023-08-24 | 1:15 | [6 empty] | Productive |  |  | POOH WITH WL LOGGING STRING FROM 4569.8 M TO 3000 M - SPEED 15 M/MIN, OPEN HOLE - SPEED 40-70 M/MIN, CASED HOLE
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:15 | 1:15 | [6 empty] | Productive |  |  | POOH WITH WL LOGGING STRING FROM 3000 M TO SURFACE - SPEED 15 M/MIN, OPEN HOLE - SPEED 40-70 M/MIN, CASED HOLE
KZN-377 |  | PROD1 |  | 2023-08-23 01:15 | 2023-08-23 03:15 | 2:00 | [6 empty] | Productive |  |  | LAY DOWN LOGGING TOOLS.
KZN-377 |  | PROD1 |  | 2023-08-23 03:15 | 2023-08-23 04:00 | 0:45 | [6 empty] | Productive |  |  | RIG DOWN WL CABLE AND SHEAVES.
KZN-377 |  | PROD1 |  | 2023-08-23 04:00 | 2023-08-23 04:15 | 0:15 | [6 empty] | Productive |  |  | CLEAN AND CLEAR RIG FLOOR.
KZN-377 |  | PROD1 |  | 2023-08-23 04:15 | 2023-08-23 04:30 | 0:15 | [6 empty] | Productive |  |  | TBT , PRIOR TO PICK UP 8.3/8" ROTARY BHA # 3 Page 76 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 04:30 | 2023-08-23 06:45 | 2:15 | [6 empty] | Productive |  |  | P/U & M/U 8 3/8" ROTARY BHA#3 TO 524 M: - 8 3/8" TKC73, OPEN JET , S/N S293476 - 6 5/8" BIT SUB - 6 3/8" FLOAT SUB - 1 x 6-1/2'' DC JOINT - 8 1/4" STRING STAB - 7 x 6-1/2'' DC STANDS - 6-1/2'' JAR - 1 x 6-1/2'' DC STAND - 10 X 5" HWDP STANDS - WEIGHT BELOW JARS : 52 KLBS -TOTAL BHA WEIGHT: 100 KLB NOTE: - MONITOR DISPLACEMENT THROUGH TRIP TANK
KZN-377 |  | PROD1 |  | 2023-08-23 06:45 | 2023-08-23 12:45 | 6:00 | [6 empty] | Productive |  |  | CONT. RIH 8.3/8" ROTARY BHA F/ 524 M TO 3133 M. - MONITOR DISPLACEMENT ON TRIP TANK - FILL-UP STRING EVERY 20 STANDS.
KZN-377 |  | PROD1 |  | 2023-08-23 12:45 | 2023-08-23 13:00 | 0:15 | [6 empty] | Productive |  |  | PERFORMED KICK WHILE TRIPPING DRILL 'D1' WITH CREW # B BY INTRODUCING GAIN IN TRIP TANK WHICH WAS RECOGNIZED BY DRILLER AND MUD LOGGER. GOOD RESPONSE FROM RIG FLOOR CREW IN STABBING FOSV IN +/- 1 MINS. HELD AAR WITH CREW DISCUSSED THE ROLE AND RESPONSIBILITIES OF EACH CREW MEMBER IN KICK WHILE TRIPPING .
KZN-377 |  | PROD1 |  | 2023-08-23 13:00 | 2023-08-23 13:15 | 0:15 | [6 empty] | Productive |  |  | CONT. RIH 8.3/8" ROTARY BHA F/ 3133 M TO 3377 M. - MONITOR DISPLACEMENT ON TRIP TANK - FILL-UP STRING EVERY 20 STANDS.
KZN-377 |  | PROD1 |  | 2023-08-23 13:15 | 2023-08-23 13:30 | 0:15 | [6 empty] | Productive |  |  | BREAK CIRCULATE AT THE SHOE , F.R: 300 GPM , SPP:320 PSI.
KZN-377 |  | PROD1 |  | 2023-08-23 13:30 | 2023-08-23 14:30 | 1:00 | [6 empty] | Productive |  |  | SLIP DRILL LINE - HANG BLOCK AND PARKED TDS. - SLIP 12 MOF DRILL LINE. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
KZN-377 |  | PROD1 |  | 2023-08-23 14:30 | 2023-08-23 18:30 | 4:00 | [6 empty] | Productive |  |  | CONT. RIH 8.3/8" ROTARY BHA F/ 3377M TO 4717 M. - MONITOR DISPLACEMENT ON TRIP TANK - FILL-UP STRING EVERY 20 STANDS. - TAKE SCR. Page 77 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 18:30 | 2023-08-23 21:30 | 3:00 | [6 empty] | Productive |  |  | CIRCULATE 3 BOTTOM UP , FR 550 GPM, SPP 2800 PSI. MEANWHILE MIXING SC PILL AS PER PROGRAM. - PERFORM TBT FOR STRESS CAGE JOB.
KZN-377 |  | PROD1 |  | 2023-08-23 21:30 | 2023-08-23 23:15 | 1:45 | [6 empty] | Productive |  |  | PUMPED 310 BBL OF STRESS CAGE PILL TO COVER ALL THE OPEN HOLE ( 8.3/8" SECTION ). FR 300 GPM, SPP 900-1000 PSI - DISPLACE PILL WITH STRING VOLUME FR 300 GPM , SPP 800-950 PSI - CONSIDER 5% WASH OUT.
KZN-377 |  | PROD1 |  | 2023-08-23 23:15 | 2023-08-24 | 0:45 | [6 empty] | Productive |  |  | HELD REMOTLY MEETING W/ OFFICE REGARDING SC RISKSAND FORMATION PP
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:00 | 1:00 | [6 empty] | Productive |  |  | HELDMEETING W/ OFFICE REGARDING SC RISKSAND FORMATION PP.
KZN-377 |  | PROD1 |  | 2023-08-23 01:00 | 2023-08-23 04:15 | 3:15 | [6 empty] | Productive |  |  | CIRCULATE BOTTOM UP , FR 500 GPM, SPP 2300 PSI. MEANWHILE MIXING ANOTHER SC PILL AS PER PROGRAM. - PERFORM TBT FOR STRESS CAGE JOB. - CIRCULATE OUT 310 BBLS SC PILL - RECIPROCATE STRING W/ 20 RPM.
KZN-377 |  | PROD1 |  | 2023-08-23 04:15 | 2023-08-23 04:30 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK - WELL STATIC.
KZN-377 |  | PROD1 |  | 2023-08-23 04:30 | 2023-08-23 05:00 | 0:30 | [6 empty] | Productive |  |  | PUMP OUT OF HOLE F/ 4717 M TO 4640 M W/ 250 GPM SRPM 20 RPM, 700 PSISPP - PERFORM TBT FOR STRESS CAGE JOB.
KZN-377 |  | PROD1 |  | 2023-08-23 05:00 | 2023-08-23 05:30 | 0:30 | [6 empty] | Productive |  |  | PUMPED 160 BBL OF STRESS CAGE PILL TO COVERINTERVAL 4620 M TO 4550 M FR 300 GPM, SPP 900 - 980PSI. 15 TDS RPM - DISPLACEEDSURFACE LINES & SPOTTED 20 BBLS SCINTO OPEN HOLE
KZN-377 |  | PROD1 |  | 2023-08-23 05:30 | 2023-08-23 06:00 | 0:30 | [6 empty] | Productive |  |  | PUMP OUT OF HOLE F/ 4640 M TO 4528 M W/ 250 GPM RPM 20 RPM, 700 PSISPP
KZN-377 |  | PROD1 |  | 2023-08-23 06:00 | 2023-08-23 07:00 | 1:00 | [6 empty] | Productive |  |  | CIRCULATESTRING VOLUME500 GPM, 20 TDS RPM,2300 PSI SPP. - FLUSH SURFACE LINE - PRESSURE TEST 300/3000 PSI Page 78 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 07:00 | 2023-08-23 09:00 | 2:00 | [6 empty] | Productive |  |  | *** PERFORMED STRESS CAGE INTO BARIKFORMATION TO 1.58 SG *** - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 1345 PSI ( EMW=1.39 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 16 PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 1550 PSI ( EMW=1.42 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 11PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 1745 PSI ( EMW=1.45 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 15 PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 1945 PSI ( EMW=1.48 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 16 PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 2083 PSI ( EMW=1.50 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 13PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 2216 PSI ( EMW=1.52 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 27 PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 2350 PSI ( EMW=1.54 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 22 PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 2483 PSI ( EMW=1.56 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 24PSI/MIN. - PRESSURE UP BARIK FORMATION AT 0.5 BPM TO 2619 PSI ( EMW=1.58 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 35 PSI/MIN GREATER THAN 30 PSI/MIN , CONTINUE TO WAIT FOR 15 MINS. - PRESSURE UP BARIK FORMATION AT 0.5 BPM AGAIN TO 2619 PSI ( EMW=1.58 S.G) AND WAIT 3 MIN TO STABILIZE PRESSURE - DROP RATE 26 PSI/MIN - CONT. TO WAIT FOR 15 MINS -FINAL PRESSURE AT 15 MINS =2411 PSI. - SUCCESSFUL STRESS CAGE TO REQUIRED VALUE 2619 PSI = 1.58 EMW. - VOLUME PUMPED DURING STRESS-CAGE WAS 10.1 BBL, BLED VOLUME 6.1 BBL. - R/D CIRCULTION HEAD.
KZN-377 |  | PROD1 |  | 2023-08-23 09:00 | 2023-08-23 10:15 | 1:15 | [6 empty] | Productive |  |  | WASH DOWN AND RIH W/ 8 3/8" BHA # 3 F/ 4528 M TO 4642 M , FR. 400 GPM , SPP, 400-450 PSI. Page 79 of 80
KZN-377 |  | PROD1 |  | 2023-08-23 10:15 | 2023-08-23 12:45 | 2:30 | [6 empty] | Productive |  |  | - OBSERVED DRILL LINE DAMAGED , TOFS DISCUSSED THE WAY FORWARD WITH TEAM ON THE SLIP AND CUT FOR THE DRILL LINE. - CIRCULATE HOLE CLEAN TO REMOVE EXCESS STRESS CAGEWITH F.R. 570 GPM , SPP: 2800-2850 PSI. - R/UP CIRCULATION HEAD. WHILE CIRCULTION TBT WITH THE CREW ON THE SLIP AND CUT.
KZN-377 |  | PROD1 |  | 2023-08-23 12:45 | 2023-08-23 15:15 | 2:30 | [6 empty] | Non-Productive |  |  | SLIP AND CUT DRILL LINE DUE TO DAMAGE DRILL LINE - PARKED TDS AND HANG BLOCK . - CUT 130 OF DRILL LINE AND SLIP 120 M. - CALIBRATED RIG BLOCK HEIGHT AND SET KEMS & CROWN-O-MATIC. - CALIBRATED MUD LOGGERS BLOCK HEIGHT.
KZN-377 |  | PROD1 |  | 2023-08-23 15:15 | 2023-08-23 15:30 | 0:15 | [6 empty] | Productive |  |  | CLEAR AND CLEAN RIG FLOOR. R/D CIRCULTION HEAD .
KZN-377 |  | PROD1 |  | 2023-08-23 15:30 | 2023-08-23 15:45 | 0:15 | [6 empty] | Productive |  |  | PJSM , PRIOR TO POH 8.3/8" BHA # 3.
KZN-377 |  | PROD1 |  | 2023-08-23 15:45 | 2023-08-24 | 8:15 | [6 empty] | Productive |  |  | PUMP OUT OF HOLE 8.3/8" ROTARY BHA # 3 FROM 4642 M TO2870 M W/ 250 GPM - CONDUCTED FLOW CHECK AT 9 5/8" CSG SHOW- WELL STATIC-
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 03:30 | 3:30 | [6 empty] | Productive |  |  | PUMP OUT OF HOLE 8.3/8" ROTARY BHA # 3 FROM 2870 M TO 1995 M W/ 250 GPM AND RACK BACK.
KZN-377 |  | PROD1 |  | 2023-08-23 03:30 | 2023-08-23 13:00 | 9:30 | [6 empty] | Productive |  |  | POH WITH 8 3/8" ROTARY BHA AND LAY DOWN 5" DPF/ 1995 M TO 524 M. - MONITOR WELL THROUGH TRIP TANK WELL STATIC - INSTALLED WIPER - HANDOVER & TBT FOR CREW CHANGE - OVER TQ IN STAND #34.
KZN-377 |  | PROD1 |  | 2023-08-23 13:00 | 2023-08-23 13:15 | 0:15 | [6 empty] | Productive |  |  | FLOW CHECK PRIOR BHA ENTER BOP - WELL STATIC
KZN-377 |  | PROD1 |  | 2023-08-23 13:15 | 2023-08-23 15:15 | 2:00 | [6 empty] | Productive |  |  | CONT. POH WITH 8.3/8" ROTARY BHA AND LAY DOWN BHA TO 207 M. -R/B 1 STAND OF 5" HWDP. -L/D 27 JTS OF 5" HWDP. -L/D 3 X 6.1/2" DCS. -L/D JAR.
KZN-377 |  | PROD1 |  | 2023-08-23 15:15 | 2023-08-23 17:00 | 1:45 | [6 empty] | Productive |  |  | - RIH WITH 25 STANDS OF 5" DP TO 920 M FROM THE MAST ON 8.3/8" BHA # 3 TO LAY DOWN EXCESS PIPIES FROM THE MAST. AT 15:45 CREW CHANGE HANDOVER AND TBT.
KZN-377 |  | PROD1 |  | 2023-08-23 17:00 | 2023-08-24 | 7:00 | [6 empty] | Productive |  |  | -POH AND LAY DOWN 5"DP FROM 920 M TO 300 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - OBSERVE 9 CONNECTION WITH OVER TQ CONNECTIONS
KZN-377 |  | PROD1 |  | 2023-08-23 | 2023-08-23 01:30 | 1:30 | [6 empty] | Productive |  |  | -POH AND LAY DOWN 5"DP FROM 300 M TO 207 M. NOTES: - MONITORED WELL THROUGH TRIP TANK. - OVER TQ CONNECTIONS
KZN-377 |  | PROD1 |  | 2023-08-23 01:30 | 2023-08-23 01:45 | 0:15 | [6 empty] | Productive |  |  | PERFORMED FLOW CHECK ON TOP OF BHA - WELL STATIC-
KZN-377 |  | PROD1 |  | 2023-08-23 01:45 | 2023-08-23 05:00 | 3:15 | [6 empty] | Productive |  |  | CONT. POH WITH 8.3/8" ROTARY BHA AND LAY DOWN BHA TO SURFACE . - 21 x 6-1/2'' DC JOINTS - 8 1/4" STRING STAB - 1 x 6-1/2'' DC JOINT - 6 3/8" FLOAT SUB - 6 5/8" BIT SUB - 8 3/8" TKC73, OPEN JET , S/N S293476 NOTES: - MONITORED WELL THROUGH TRIP TANK. ***END OF DRILLING PHASE, SEE CON REPORT #1