## DDR#52
MARI PETROLEUM COMPANY LIMITED
[22 empty] | Report No. |  | 52
DAILY DRILLING REPORT
WELL NAME: |  | ZARGHUN SOUTH-3 |  |  |  | CONTRACTOR / RIG: |  | MPCL / RIG MARI-1 | [5 empty] | DATE: (DD-MM-YY) | [5 empty] | 2016-11-11
CLASSIFICATION: |  | DEVELOPMENT |  |  |  | R.T. - G.L. ELEV. (M) |  | 09 METER | [5 empty] | SPUD DATE: (DD-MM-YY) |  |  | 42061 |  |  | 2016-09-20 10:00
BLOCK / COUNTRY |  | ZARGHUN SOUTH D&P LEASE |  |  |  | PLANNED MD/TVD (M): |  | 1926 / 1705 METER | [5 empty] | PLANNED DAYS: |  |  |  | Days Ahead |  | 53 DAYS
MPCL REPRESENTATIVE: |  | MASOOD KAMAL / M.MEHDI |  |  |  | MD/TVD @ 00:00HRS: |  | 1477 / 1425.82 METER | [5 empty] | DAYS SINCE SPUD: |  | #REF! |  |  |  | 51.583
RIG REPRESENTATIVE: |  | JAVED / FRANCIS |  |  |  | MD/TVD @ 06:00HRS: |  | 1519 / 1461.7 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [5 empty] | 133
2016-11-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | HYDRO-GUARD |  | HOLE SIZE (IN) |  | 12.25 |  | BIT No. |  |  | 10 |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 71.8
CHECK TIME | 6:00 | 23:59 | MD @ 00:00HR (M) |  | 1477 |  | SIZE (IN) |  |  | 12 1/4" |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 589.7
DEPTH (M) | 1374 | 1477 | TVD @ 00:00HR (M) |  | 1425.8 |  | MANUFACTURER |  |  | HLB |  | BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.31 |  |  | PITS (BBL) | 688.4
MW IN (SG) | 1.73 | 1.73 | DAILY PROGRESS (M) |  | 133 |  | TYPE |  |  | SF66H |  | Geo-Pilot 9600 EDL |  |  | 12 | 2.375 |  | 6 5/8 REG |  | 6.59 |  |  | ACT. SYS (BBL) | 1349.9
MW OUT (SG) | 1.73 | 1.73 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 12843572 |  | 8" PCDC Collar |  |  | 8 | 1.92 |  | 6 5/8 REG |  | 2.8 |  |  | RESV. SYS (BBL) | 567.7
FL TEMP. °F | 144 | 145 | AVG. ROP (M/HR) |  | 8.46 |  | IADC CODE |  |  |  |  | 12-1/8" Inline Stab |  |  | 12.125 | 1.92 |  | 6 5/8 REG |  | 1.21 |  |  | KILL MUD (BBL) | 516
ECD |  | 1.75 | AVG. WOB (TON) |  | 5-6 |  | NOZZLES |  |  | 4 x 13 + 5 x 14 |  | 8" PWD |  |  | 8 | 1.92 |  | 6 5/8 REG |  | 2.4 |  |  | KILL MW (SG)
µ FUNNEL (SEC) | 57 | 57 | AVG. RPM SURF |  | 110-120 |  | DEPTH IN (M) |  |  | 1226 |  | 8" HCIM Collar |  |  | 8 | 1.92 |  | 6 5/8 REG |  | 1.41 |  |  | TOTAL | 2433.6
PV | 34 | 34 | AVG. RPM DOWNHOLE |  | 110-120 |  | DEPTH OUT (M) |  |  |  |  | 8" Pulsar sub |  |  | 8 | 4 |  | 6 5/8 REG |  | 3.04 |  |  | DIESEL (LTR)
YIELD POINT | 29 | 29 | FLOWRATE (GPM) |  | 700 |  | METERAGE (M) |  |  | 251 |  | 8" Float sub |  |  | 8 | 2.83 |  | 6 5/8 REG |  | 0.82 |  |  | RIG TANK | 22190
GEL ST. | 11/39 | 11/39 | PRESSURE (PSI) |  | 3000-3300 |  | RPM SURF. |  |  | 110-120 |  | 4 X DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 35.34 |  |  | CAMP TANK | 3885
WL (ml/30 min.) | 5 | 5 | TORQ. ON-BTM (KLB-FT) |  | 3-7 |  | RPM BTM. |  |  | 110-120 |  | HMD JAR |  |  | 8 | 2.9375 |  | 6 5/8 REG |  | 5.43 |  |  | CONSUMED | 9769
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1-4.2 |  | WOB (TON) |  |  | 5-10 |  | DC |  |  | 8 | 3 |  | 6 5/8 REG |  | 9.07 |  |  | RECEIVED
ALK (MUD) | 0.48 | 0.42 | STRING WT. (TON) |  | 69 |  | AVG. ROP (M/HR) |  |  | 8.4626 |  | X-OVER |  |  | 7 | 2.875 |  | 4 1/2 IF |  | 1.11 |  |  | TOTAL | 26075
ALK (FILT.) | 0.23/0.35 | 0.2/0.27 | PICK-UP WT. (TON) |  | 70.4 |  | BIT ROT HRS. |  |  | 29.66 |  | DC |  |  | 6.5 | 2.25 |  | 4 1/2 IF |  | 9.24 |  |  | WATER (BBL)
PH | 9.6 | 9.5 | SLACK-OFF WT. (TON) |  | 67.6 |  | K-REVS IN 24 HRS |  |  | 96.17 |  | 15 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 139.34 |  |  | RIG STORAGE | 2500
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  |  | 160.86 | [12 empty] | CAMP STORAGE | 200
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  | 60.6 | [12 empty] | CONSUMED
KCl % | 9.2 | 9.1 | JAR | 72 | NMDC |  | JET VELOCITY (M/SEC) |  |  | 53.6 | [12 empty] | RECEIVED
CHLORIDES | 75000 | 76500 | STAB-1 |  | RSS | 53.2 | TFA (IN²) |  |  | 1.27 | [12 empty] | TOTAL | 2700
CALCIUM | 80 | 80 | STAB-2 |  | MWD | 53.2 | HSI |  |  | 1.4 | [12 empty] | POB
OIL% |  |  | ANY OTHER |  | ANY OTHER |  | DULL CODE |  |  | (I/O/D/L/B/G/O/R) |  | TOTAL BHA LENGTH (M) | [7 empty] | 218.11 |  |  | MPCL | 5
SAND % |  |  | BHA ROT. HRS |  | 74.8 |  | BIT NO.9 |  |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 20
SOLIDS % | 23.8 | 23.4 | ON BOTTOM HRS |  | 36.09 |  | BIT NO.8 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 11 |  |  | SECURITY | -
M.B.T. | 12 | 11.8 | CIRC. HRS |  | 58.75 |  | BIT NO.7 |  |  |  |  | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE/SPECIFICATIONS |  |  |  | Shoe (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (° N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 11758000 | SHAKER-1 | 120 | 120 | 4 | 42" STOVE PIPE |  |  |  | 14 | 1393 /1352.6 |  | 28.28 |  | 141.31 |  |  | 0.284 |  | MWD |  | TOTAL | 100
DAILY WELL COST (US$) |  | 62126 | SHAKER-2 | 120 | 120 | 4 | 30" CONDUCTOR PIPE |  |  |  | 40 | 1424 / 1379.83 |  | 29.42 |  | 142.41 |  |  | 1.217 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 4811248 | SHAKER-3 | 140 | 140 | 3 | 20" CGS,BTC,K-55,133/94PPF |  |  |  | 400 | 1452 / 1404.2 |  | 29.57 |  | 144.06 |  |  | 0.885 |  | MWD |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 40.92% | MUD CLEANER | 230 |  | 4 | 13 3/8" CGS,BTC/VT,P-110/L-80,72/68PPF |  |  |  | 1219.5 | 1481 / 1429.3 |  | 30.93 |  | 142.72 |  |  | 1.571 |  | MWD |  | FIT/LOT (EMW) | 2 SG
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 460
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL.(BBL)
BOP DRILL |  |  | ANNULAR | CHINESE | 13.625 | 5000 | P-1 - F-1600HP |  | 6 1/2" |  | 12" | 3977 PSI | 96 |  | 0.118 |  | 30 |  | 1460 |  | 280 |  | FORMATION TOP DEPTH (M)
H2S DRILL |  |  | UPPER RAMS | CHINESE | 13.625 | 10000 | P-2 - F-1600HP |  | 6 1/2" |  | 12" | 3977 PSI | 96 |  | 0.118 |  | 40 |  | 1460 |  | 390 |  | SWALIKS | SURFACE
FIRE DRILL | 24/09/2016 |  | MIDDLE RAMS |  | 13.625 | 10000 | P-3 - F-1300HP |  | 6 1/2" |  | 12" | 3977 PSI | 96 |  | 0.118 |  | 50 |  | 1460 |  | 590 |  | KIRTHAR | 38
PIT DRILL |  |  | LOWER RAMS | CHINSE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | FLUID LOSSES | [10 empty] | GHAJIZ | 189
KICK DRILL | 2016-11-10 |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | DUNGHAN
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2016-10-31 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES
KILL DRILL | 2016-05-10 |  | NEXT BOP TEST DATE |  | 2016-11-15 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2016-11-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
42684 | 42684.3646 | 8.75 | DRL | PT-P | DM | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1344M TO 1403M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION).
42684.3646 | 42684.4271 | 1.5 | DRL | PT-P | CIR | PUMPED HI-VIS AND CIRCULATED OUT.
42684.4271 | 42684.5625 | 3.25 | DRL | PT-P | POOH | POOH FROM 1403M TO 1201M. WHILE POOH PUMPED OUT FROM 1374M TO 1201M.
42684.5625 | 42684.6042 | 1 | DRL | NPT-P | RS | SERVICED TDS.
42684.6042 | 42684.6562 | 1.25 | DRL | PT-P | RIH | RIH DOWN TO 1403M.
42684.6562 | 42685 | 8.25 | DRL | PT-P | DM | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1403M TO 1477M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2016-11-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
42685 | 42685.25 | 6 | DRL | PT-P | DM | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1477M TO 1519M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION).
TOTAL |  | 6
FORMATION/LITHOLOGY |  |  | GHAZIJ / CLAYSTONE, LIMESTONE, MARL
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 12 1/4" HOLE FROM 1344M TO 1477M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL 12 1/4" HOLE AS PER DIRECTIONAL PLAN.
REMARKS