## Sheet1
WellGUID | WellName | WellboreName | WellboreDiameter | StartDate | EndDate | ActivityStartDepthMD | ActivityEndDepthMD | TopDepthMD | BottomDepthMD | TopDepthTVD | BottomDepthTVD | ActivityCodeL1 | ActivityCodeL2 | ActivityCodeL3 | ActivityCodeL4 | ActivityCodeL5 | ActivityCodeL6 | Description | TimeClassification | NPTReason | NPTDetail | UPDATE_DATE
hvjg | gvjgv | vjhv | 0 | 02/19/15 07:00 | 02/19/15 16:00 | [12 empty] | Preparation for spud-in well.Function tested Rig equipment prior to acceptance of Rig.
hvjg | gvjgv | vjhv | 0 | 02/19/15 16:00 | 02/19/15 17:00 | [12 empty] | Conducted pre-spud safety meeting, sacrified two goats and post prayers, spudded-in Well Halini Deep-1 at 1700 HRS on February 18, 2015 with 1.03 S.G mud in Circ. | Productive
hvjg | gvjgv | vjhv | 24 | 02/19/15 17:00 | 02/19/15 05:00 |  |  | 45 | 76 | [8 empty] | Tagged bottom with circulation @ 45m. Drilled 24" hole from 45m to 76m with slick rotary BHA. | Productive
hvjg | gvjgv | vjhv | 0 | 02/19/15 05:00 | 02/19/15 06:00 | [12 empty] | Circ / Swept hole with 25 BBL Hi-Vis Pill till shakers clean.
hvjg | gvjgv | vjhv | 0 | 02/19/15 06:00 | 02/19/15 07:00 | [12 empty] | P/Back to 65m & conducted deviation survey on slickline (0.25 deg @ 65m). Adding 24" S.Stab in BHA is in progress. | Productive
hvjg | gvjgv | vjhv | 24 | 02/20/15 07:00 | 02/20/15 16:00 |  |  | 76 | 96 | [8 empty] | Added 24" S.Stab in BHA & drilled 24" hole from 76m to 96m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 02/20/15 16:00 | 02/20/15 17:00 | [12 empty] | Added DC in BHA & observed hole fill at 86m. M/up TDS & reamed/washed down to BTM. | Productive
hvjg | gvjgv | vjhv | 0 | 02/20/15 17:00 | 02/20/15 18:00 | [12 empty] | Circ/swept hole with 40 bbl Hi-Vis Pill.
hvjg | gvjgv | vjhv | 24 | 02/20/15 18:00 | 02/20/15 21:00 |  |  | 96 | 105 | [8 empty] | Resumed drilling & drilled 24" hole from 96m to 105m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 02/20/15 21:00 | 02/20/15 22:00 | [12 empty] | Circ/swept hole with 40 bbl Hi-Vis Pill.
hvjg | gvjgv | vjhv | 24 | 02/20/15 22:00 | 02/21/15 07:00 |  |  | 105 | 120 | [8 empty] | Added DC & Jar in BHA & drilled 24" hole from 105m to 120m. | Productive
hvjg | gvjgv | vjhv | 24 | 02/21/15 07:00 | 02/22/15 05:00 |  |  | 120 | 160 | [8 empty] | Drilled 24" hole from 120m to 160m. Added 6 x 8" DCs in BHA while drilling. Reamed twice & swept hole with 40 bbl Hi-Vis pill at each connection. Added detergent in mud. | Productive
hvjg | gvjgv | vjhv | 0 | 02/22/15 05:00 | 02/22/15 05:30 | [12 empty] | Circ / Cleaned hole.
hvjg | gvjgv | vjhv | 0 | 02/22/15 05:30 | 02/22/15 06:00 | [12 empty] | P/back to 146m. Recorded deviation survey on slickline (0.25 deg @ 146m). | Productive
hvjg | gvjgv | vjhv | 24 | 02/22/15 06:00 | 02/22/15 09:00 |  |  | 160 | 162 | [8 empty] | Drilled 24" hole from 160m to 162m. Stopped drilling due to slow ROP. | Productive
hvjg | gvjgv | vjhv | 0 | 02/22/15 09:00 | 02/22/15 12:00 | [12 empty] | POOH 24" bit to surface. L/Down bit.
hvjg | gvjgv | vjhv | 0 | 02/22/15 12:00 | 02/22/15 15:30 | [12 empty] | M/Up new 24" bit & added 24" S.Stab at top of Shock Sub & RIH. Tagged compression @ 141m. Racked back 8" DC stand.
hvjg | gvjgv | vjhv | 0 | 02/22/15 15:30 | 02/22/15 17:30 | [12 empty] | Reamed / washed down from 141m to BTM. | Productive
hvjg | gvjgv | vjhv | 24 | 02/22/15 17:30 | 02/23/15 04:00 |  |  | 162 | 207 | [8 empty] | Resumed drilling & drilled 24" hole from 162m to 207m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 02/23/15 04:00 | 02/23/15 04:30 | [12 empty] | Circ / Cleaned hole.
hvjg | gvjgv | vjhv | 0 | 02/23/15 04:30 | 02/23/15 05:00 | [12 empty] | P/back to 197m. Recorded deviation survey on slickline (0.10 deg @ 197m). | Productive
hvjg | gvjgv | vjhv | 24 | 02/23/15 05:00 | 02/23/15 06:00 |  |  | 207 | 212 | [8 empty] | RIH to BTM & drilled 24" hole from 207m to 212m. | Productive
hvjg | gvjgv | vjhv | 24 | 02/23/15 06:00 | 02/24/15 02:00 |  |  | 212 | 293 | [8 empty] | Drilled 24" hole from 212m to 293m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 02/24/15 02:00 | 02/24/15 02:30 | [12 empty] | Swept hole with 20 bbl hi-vis pill. Circ / Cleaned hole.
hvjg | gvjgv | vjhv | 0 | 02/24/15 02:30 | 02/24/15 03:00 | [12 empty] | P/back to 281m. Recorded deviation survey on slickline (0.25 deg @ 281m). | Productive
hvjg | gvjgv | vjhv | 24 | 02/24/15 03:00 | 02/24/15 06:00 |  |  | 293 | 303 | [8 empty] | RIH to BTM. Resumed drilling & drilled 24" hole from 293m to 303m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | NOTE: Observed mud returns ceased for 01 min @ 218m while drilling & lost 12 bbl mud. Thereafter observed no loss. | Productive
hvjg | gvjgv | vjhv | 24 | 02/24/15 06:00 | 02/24/15 07:30 |  |  | 303 | 308 | [8 empty] | Drilled 24" hole from 303 m to 308 m. Observed complete loss. Stopped drilling & observed well for returns. Lost 300 bbl. | Productive
hvjg | gvjgv | vjhv | 0 | 02/24/15 07:30 | 02/24/15 08:00 | [12 empty] | Spotted 106 bbl of 100 PPB concentration LCM pill at bottom. Displaced with 11 bbl of mud - No Returns.
hvjg | gvjgv | vjhv | 0 | 02/24/15 08:00 | 02/24/15 10:00 | [12 empty] | Pulled back to 207 m & allowed soaking time.
hvjg | gvjgv | vjhv | 0 | 02/24/15 10:00 | 02/24/15 10:30 | [12 empty] | Top filled with 180 bbls - No Returns.
hvjg | gvjgv | vjhv | 24 | 02/24/15 10:30 | 02/24/15 12:30 |  |  | 308 | 312 | [8 empty] | RIH to BTM. Resumed blind drilling & drilled 24" hole from 308 m to 312 m. Pumped 25 bbl each of 100 PPB LCM pill & Hi-Vis pill. No returns. Lost 630 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 02/24/15 12:30 | 02/24/15 23:00 | [12 empty] | POOH 24" bit surface. While POOH replaced 8" DCs (NC56 Connection) with new 8" DCs (6-5/8" Reg Connection) single by single. L/Down Bit & S.Stabs. Meanwhile prepared fresh mud & arranged conventional LCM locally. | Productive
hvjg | gvjgv | vjhv | 0 | 02/24/15 23:00 | 02/25/15 02:00 | [12 empty] | RIH 24" Bit (Open Jets) with slick rotary BHA to 107m.
hvjg | gvjgv | vjhv | 0 | 02/25/15 02:00 | 02/25/15 02:30 | [12 empty] | Observed Manual Rotary Tong Torque Sensor Oil leaked. Repaired it. | Non Productive
hvjg | gvjgv | vjhv | 0 | 02/25/15 02:30 | 02/25/15 04:30 | [12 empty] | Resumed RIH from 107m to BTM.
hvjg | gvjgv | vjhv | 0 | 02/25/15 04:30 | 02/25/15 05:30 | [12 empty] | Spotted 100 bbl of 150 PPB concentration LCM pill at bottom. Displaced with 11 bbl of mud - No Returns.
hvjg | gvjgv | vjhv | 0 | 02/25/15 05:30 | 02/25/15 06:00 | [12 empty] | P/back to 192m & allowed soaking time. Observed mud level at 114m while POOH.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud Lost during 24 hrs: 1338 BBL
hvjg | gvjgv | vjhv | 0 | 02/25/15 06:00 | 02/25/15 08:30 | [12 empty] | Allowed soaking time to LCM pill.
hvjg | gvjgv | vjhv | 0 | 02/25/15 08:30 | 02/25/15 09:00 | [12 empty] | RIH down to bottom.
hvjg | gvjgv | vjhv | 0 | 02/25/15 09:00 | 02/25/15 09:30 | [12 empty] | Pumped 100 bbls LCM pill of 71 PPB Concentration - No Returns. | Productive
hvjg | gvjgv | vjhv | 24 | 02/25/15 09:30 | 02/25/15 11:30 |  |  | 312 | 315 | [8 empty] | Resumed blind drilling & drilled 24" hole from 312m to 315m. Pumped 25 bbl each of 100 PPB LCM pill & Hi-Vis pill. No returns. Lost 700 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 02/25/15 11:30 | 02/25/15 12:30 | [12 empty] | Spotted 60 bbls of 71 ppb wheat husk concentration LCM pill. Displaced with 11 bbl of mud - No Returns. POOH to 212m. Found mud level mark on DPs @ 30m depth.
hvjg | gvjgv | vjhv | 0 | 02/25/15 12:30 | 02/25/15 15:00 | [12 empty] | Allowed soaking time to LCM pill. Meanwhile prepared fresh bentonite mud. | Productive
hvjg | gvjgv | vjhv | 0 | 02/25/15 15:00 | 02/25/15 15:30 | [12 empty] | RIH to bottom & POOH for checking mud level in hole. Found @ 86 m.
hvjg | gvjgv | vjhv | 0 | 02/25/15 15:30 | 02/25/15 17:30 | [12 empty] | RIH to bottom & spotted 100 bbl wheat husk LCM of 71 ppb. Displaced with 20 bbl of mud - No Returns.
hvjg | gvjgv | vjhv | 0 | 02/25/15 17:30 | 02/25/15 18:00 | [12 empty] | P/back to 201m. Found mud level mark on DPs @ 68m depth.
hvjg | gvjgv | vjhv | 0 | 02/25/15 18:00 | 02/25/15 21:00 | [12 empty] | Allowed soaking time to LCM pill.
hvjg | gvjgv | vjhv | 0 | 02/25/15 21:00 | 02/26/15 02:30 | [12 empty] | POOH 24" bit to surface. L/down Jar, 2x11" DCs, Shock sub & bit.
hvjg | gvjgv | vjhv | 0 | 02/26/15 02:30 | 02/26/15 03:30 | [12 empty] | RIH 5" OEDPs to 256m.
hvjg | gvjgv | vjhv | 0 | 02/26/15 03:30 | 02/26/15 06:00 | [12 empty] | Making arrangements for placing cement plug.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud Lost during 24 hrs: 991 BBL
hvjg | gvjgv | vjhv | 0 | 02/26/15 06:00 | 02/26/15 17:00 | [12 empty] | Made arrangements for placing Cement Bentonite Gunk Plug. Meanwhile P/Back DPs & found mud level mark @ 86m. RIH 5" OEDPs to 307m.
hvjg | gvjgv | vjhv | 0 | 02/26/15 17:00 | 02/26/15 18:00 | [12 empty] | Held PJSM. R/Up SLB lines. Flushed & Press Tested SLB lines to 1500 psi with diesel.
hvjg | gvjgv | vjhv | 0 | 02/26/15 18:00 | 02/26/15 22:00 | [12 empty] | Waited rain to stop to prepare/mix Gunk Plug. | Productive
hvjg | gvjgv | vjhv | 0 | 02/26/15 22:00 | 02/26/15 23:00 | [12 empty] | Spotted 100 bbl LCM pill of 150 ppb. Displaced LCM with 17 bbl mud. No Returns.
hvjg | gvjgv | vjhv | 0 | 02/26/15 23:00 | 02/27/15 03:00 | [12 empty] | Prepared 100 bbl Cement-Bentonite Gunk Plug. Pumped 5 bbl diesel as pre-flush followed by 100 bbl Gunk plug & 5 bbl diesel as post-flush. Displaced with 17 bbl mud. Meanwhile filled up annulus with mud during pumping Gunk plug. No Returns. | Productive
hvjg | gvjgv | vjhv | 0 | 02/27/15 03:00 | 02/27/15 04:30 | [12 empty] | POOH 5" OEDPS to surface.
hvjg | gvjgv | vjhv | 0 | 02/27/15 04:30 | 02/27/15 06:00 | [12 empty] | Allowed soaking time to Gunk Plug. Meanwhile M/Up 24" bit with 9" DCs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 203 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Gunk Plug: 100 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Diesel: 10 BBL
hvjg | gvjgv | vjhv | 0 | 02/27/15 06:00 | 02/27/15 08:30 | [12 empty] | Allowed soaking time to Gunk Plug.
hvjg | gvjgv | vjhv | 0 | 02/27/15 08:30 | 02/27/15 10:00 | [12 empty] | M/Up 24" Bit + Bit sub + 3x9" DCs & RIH. Tagged commpression @ 253m. Resumed pumping & returns surfaced after 76 bbl. | Productive
hvjg | gvjgv | vjhv | 0 | 02/27/15 10:00 | 02/27/15 11:30 | [12 empty] | M/Up TDS & cleaned / reamed down to 315m. Lost 160 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 02/27/15 11:30 | 02/27/15 12:30 |  |  |  | 315.5 | [8 empty] | Drilled half meter down to 315.5m & observed partial loss. Stopped drilling. Lost 36 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 02/27/15 12:30 | 02/27/15 17:30 | [12 empty] | P/Up off bottom. Checked & observed static losses. Lost 45 bbl.
hvjg | gvjgv | vjhv | 0 | 02/27/15 17:30 | 02/27/15 19:00 | [12 empty] | POOH to surface. L/Down bit.
hvjg | gvjgv | vjhv | 0 | 02/27/15 19:00 | 02/27/15 20:30 | [12 empty] | RIH open ended DPs down to 314m.
hvjg | gvjgv | vjhv | 0 | 02/27/15 20:30 | 02/27/15 21:30 | [12 empty] | Filled up annulus with 107bbl mud.
hvjg | gvjgv | vjhv | 0 | 02/27/15 21:30 | 02/27/15 23:00 | [12 empty] | R/Up & pressure tested SLB lines to 2500 psi. Batch mixed 55 bbl cement slurry of 15.80 ppg. Pumped 30 bbl water as spacer follwed by 55 bbl cement slurry & 16.3 bbl water as post flush. Observed no return during cement plug job. | Productive
hvjg | gvjgv | vjhv | 0 | 02/27/15 23:00 | 02/28/15 06:00 | [12 empty] | WOC. POOH 5" OEDPS to surface. Observed mud level mark @ 10m. While POOH flushed DPs with 10 bbl mud.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 434 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Cement Plug: 55 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 46.3 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 3189 BBL
hvjg | gvjgv | vjhv | 0 | 02/28/15 06:00 | 02/28/15 20:00 | [12 empty] | WOC. Topped up hole with 57 bbl mud. Meanwhile M/Up new 24" tricone bit.
hvjg | gvjgv | vjhv | 0 | 02/28/15 20:00 | 03/01/15 00:30 | [12 empty] | RIH new 24" tricone bit with S.Stabs to 308m & tagged cement.
hvjg | gvjgv | vjhv | 0 | 03/01/15 00:30 | 03/01/15 01:30 | [12 empty] | Circ / cleaned hole & checked for losses. Observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/15 01:30 | 03/01/15 02:30 | [12 empty] | Clean out cement (COC) from 308m to 315.5m.
hvjg | gvjgv | vjhv | 24 | 03/01/15 02:30 | 03/01/15 06:00 |  |  |  | 330 | [8 empty] | Resumed drilling & drilled 24" hole down to 330m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 57 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 3246 BBL
hvjg | gvjgv | vjhv | 24 | 03/01/15 06:00 | 03/01/15 16:00 |  |  | 330 | 368 | [8 empty] | Drilled 24" hole from 330m to 368m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/15 16:00 | 03/01/15 16:30 | [12 empty] | Observed partial losses. Picked up off-bottom & spotted 55 bbl LCM of 112.5 PPB. Lost 18 bbl mud & 35 bbl LCM.
hvjg | gvjgv | vjhv | 0 | 03/01/15 16:30 | 03/01/15 17:30 | [12 empty] | Soaked LCM.
hvjg | gvjgv | vjhv | 24 | 03/01/15 17:30 | 03/01/15 21:00 |  |  | 368 | 375 | [8 empty] | Run down to bottom. Resumed drilling & drilled 24" hole from 368m to 375m. Meanwhile pumped 216 bbl LCM of 2.5 PPB wheat husk. Lost 135 bbl LCM & 76 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/15 21:00 | 03/01/15 22:00 | [12 empty] | Stopped drilling & spotted 100 bbl LCM pill of 110 PPB. Displaced LCM with 20 bbl mud. Lost 5 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/15 22:00 | 03/02/15 00:00 | [12 empty] | P/back to 145m & allowed soaking time to LCM pill.
hvjg | gvjgv | vjhv | 0 | 03/02/15 00:00 | 03/02/15 01:00 | [12 empty] | Topped up hole with 14 bbl mud & observed static loss @ 6 bbl/hr. Lost total 20 bbl mud.
hvjg | gvjgv | vjhv | 0 | 03/02/15 01:00 | 03/02/15 04:00 | [12 empty] | Run down to bottom. Circ & checked for losses. Observed dynamic loss @ 18 - 20 bbl/hr. Lost 46 bbl.
hvjg | gvjgv | vjhv | 24 | 03/02/15 04:00 | 03/02/15 06:00 |  |  | 375 | 380 | [8 empty] | Resumed drilling & drilled 24" hole from 375m to 380m. Lost 24 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 359 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 3605 BBL
hvjg | gvjgv | vjhv | 24 | 03/02/15 06:00 | 03/02/15 10:00 |  |  | 380 | 389 | [8 empty] | Drilled 24" hole from 380m to 389 m. Swept HV pill during drilling @ 387m. Lost 16 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/02/15 10:00 | 03/02/15 11:00 | [12 empty] | Pulled back to 375m. Conducted Dev Survey on slick line. Recorded 0.6 degree @ 375m. | Productive
hvjg | gvjgv | vjhv | 24 | 03/02/15 11:00 | 03/03/15 06:00 |  |  | 389 | 426 | [8 empty] | RIH to bottom. Resumed drilling & drilled 24" hole from 389m to 426m. Reamed twice at connection. Lost 70 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 86 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 3691 BBL
hvjg | gvjgv | vjhv | 24 | 03/03/15 06:00 | 03/03/15 09:00 |  |  | 426 | 431 | [8 empty] | Drilled 24" hole from 426m to 431m. Observed complete loss. Lost 341 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/03/15 09:00 | 03/03/15 11:00 | [12 empty] | Spotted 76 bbl LCM pill of 110 PPB. Displaced LCM with 17 bbl mud. Lost 93 bbl mud.
hvjg | gvjgv | vjhv | 0 | 03/03/15 11:00 | 03/03/15 13:30 | [12 empty] | P/back to 316m & soaked LCM. RIH to bottom.
hvjg | gvjgv | vjhv | 24 | 03/03/15 13:30 | 03/03/15 16:00 |  |  | 431 | 434 | [8 empty] | Blind drilled 24" hole from 431m to 434m. Pumped 166 bbl wheat husk LCM of 2.5 ppb & 90 bbl LCM of 80 ppb. Lost 863 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/03/15 16:00 | 03/03/15 17:00 | [12 empty] | POOH to check mud level. Found mud level mark @ 66m.
hvjg | gvjgv | vjhv | 0 | 03/03/15 17:00 | 03/03/15 18:00 | [12 empty] | RIH to 423m. Dropped totco & recorded deviation.
hvjg | gvjgv | vjhv | 0 | 03/03/15 18:00 | 03/03/15 23:00 | [12 empty] | POOH to surface. R/back BHA & L/down Jar + S.Stab + Bit. Found mud level mark @ 90m. Retrieved totco (Deviation: 0.4 Deg @ 423m).
hvjg | gvjgv | vjhv | 0 | 03/03/15 23:00 | 03/04/15 00:30 | [12 empty] | RIH 5" OEDPS to 429m to place Gunk Plug.
hvjg | gvjgv | vjhv | 0 | 03/04/15 00:30 | 03/04/15 04:00 | [12 empty] | Waited rain to stop for preparing / mixing Gunk Plug.
hvjg | gvjgv | vjhv | 0 | 03/04/15 04:00 | 03/04/15 06:00 | [12 empty] | Spotted 100 bbl LCM pill of 110 ppb. Displaced LCM with 32 bbl mud. Lost 132 bbl mud. Meanwhile preparing Gunk Plug.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 1429 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 5120 BBL
hvjg | gvjgv | vjhv | 0 | 03/04/15 06:00 | 03/04/15 07:30 | [12 empty] | Prepared 100 bbl Cement-Bentonite Gunk Plug. Pumped 5 bbl diesel as pre-flush followed by 100 bbl Gunk plug & 5 bbl diesel as post-flush. Displaced with 25 bbl mud. Meanwhile filled up annulus with 63 bbl mud during pumping Gunk plug. No Returns. | Productive
hvjg | gvjgv | vjhv | 0 | 03/04/15 07:30 | 03/04/15 09:00 | [12 empty] | POOH 5" OEDPS to surface.
hvjg | gvjgv | vjhv | 0 | 03/04/15 09:00 | 03/04/15 10:30 | [12 empty] | Allowed soaking time to Gunk Plug. Filled up hole with 85 bbl mud.
hvjg | gvjgv | vjhv | 0 | 03/04/15 10:30 | 03/04/15 16:00 | [12 empty] | M/up & RIH new 24" tricone bit with same BHA & tagged Gunk Plug @ 393.5m.
hvjg | gvjgv | vjhv | 0 | 03/04/15 16:00 | 03/04/15 18:30 | [12 empty] | Reamed / Washed down from 393.5m to 426m. Observed complete loss. Cont'd washed down to 434m. Lost 148 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/04/15 18:30 | 03/04/15 23:30 | [12 empty] | POOH to surface. R/back BHA & L/down Jar + S.Stab + Bit.
hvjg | gvjgv | vjhv | 0 | 03/04/15 23:30 | 03/05/15 01:00 | [12 empty] | RIH 5" OEDPS to 433m.
hvjg | gvjgv | vjhv | 0 | 03/05/15 01:00 | 03/05/15 03:00 | [12 empty] | R/Up & pressure tested SLB lines to 2500 psi. Batch mixed 55 bbl cement slurry of 15.80 ppg. Pumped 30 bbl water as spacer follwed by 55 bbl cement slurry & 23 bbl water as post flush. Added CemNET @ 1.82 lbs/bbl while pumping cement slurry. Received 16 bbl mud return during displacement. | Productive
hvjg | gvjgv | vjhv | 0 | 03/05/15 03:00 | 03/05/15 03:30 | [12 empty] | P/back to 310m & circulated for 10 min. Lost 22 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/05/15 03:30 | 03/05/15 06:00 | [12 empty] | WOC. POOH 5" OEDPS to surface.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 343 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Diesel: 10 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Gunk Plug: 100 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Cement: 55 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 37 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 5665 BBL
hvjg | gvjgv | vjhv | 0 | 03/05/15 06:00 | 03/05/15 17:00 | [12 empty] | WOC - Observed surface sample hard.
hvjg | gvjgv | vjhv | 0 | 03/05/15 17:00 | 03/05/15 21:00 | [12 empty] | M/Up & RIH 24" bit with same BHA & tagged compression @ 333m.
hvjg | gvjgv | vjhv | 0 | 03/05/15 21:00 | 03/05/15 22:00 | [12 empty] | M/Up TDS & filled up hole with 13 bbl mud. Reamed / Washed down from 333m to 366m with 1 - 2 ton WOB & then with 0 WOB to 396m. Observed Gunk plug cuttings at shakers on bottom up. | Productive
hvjg | gvjgv | vjhv | 0 | 03/05/15 22:00 | 03/06/15 01:30 | [12 empty] | Tagged soft cement @ 396m & hard cement @ 401m. Cleaned out cement (COC) from 401m to 434m. Lost 42 bbl mud during COC.
hvjg | gvjgv | vjhv | 24 | 03/06/15 01:30 | 03/06/15 06:00 |  |  | 434 | 449 | [8 empty] | Drilled 24" hole from 434m to 449m. Observed partial losses @ 25 - 30 bbl/hr. Swept hole with 50 bbl Wheat Husk LCM pill of 2.5 PPB @ 436m. Thereafter observed loss rate reduced to 6 - 8 bbl/hr. Lost 35 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Losses during 24 hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 90 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Fluid Loss till date: 5755 BBL
hvjg | gvjgv | vjhv | 24 | 03/06/15 06:00 | 03/07/15 04:00 |  |  | 449 | 518 | [8 empty] | Drilled 24" hole from 449m to 518m. Reamed twice at each connection. Swept hole with 30 bbl HV pill @ 482m & 517m. Observed partial losses during drilling from 449m to 503m @ 20 - 25 bbl/hr. Lost 346 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/07/15 04:00 | 03/07/15 05:00 | [12 empty] | P/back to 507m. Conducted Dev Survey on slick line. Recorded 0.75 degree @ 507m. | Productive
hvjg | gvjgv | vjhv | 24 | 03/07/15 05:00 | 03/07/15 06:00 |  |  | 518 | 519 | [8 empty] | RIH to bottom. Drilled 24" hole from 518m to 519m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 346 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Added Rice Husk & Wheat Husk LCM in system during drilling. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6101 BBL
hvjg | gvjgv | vjhv | 24 | 03/07/15 06:00 | 03/07/15 14:30 |  |  | 519 | 528 | [8 empty] | Drilled 24" hole from 519m to 528m (20" CSG TD). | Productive
hvjg | gvjgv | vjhv | 0 | 03/07/15 14:30 | 03/07/15 15:30 | [12 empty] | Circ / swept hole with 40 bbl HV pill.
hvjg | gvjgv | vjhv | 0 | 03/07/15 15:30 | 03/07/15 23:00 | [12 empty] | POOH to surface. R/back BHA & L/down Jar + Shock Sub + Bit.
hvjg | gvjgv | vjhv | 0 | 03/07/15 23:00 | 03/08/15 01:00 | [12 empty] | M/up & RIH 24" bit (RR1) with Packed BHA to 96m & tagged compression.
hvjg | gvjgv | vjhv | 0 | 03/08/15 01:00 | 03/08/15 06:00 | [12 empty] | M/up TDS & Reamed down to 171m with 4 - 5 ton WOB. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6101 BBL
hvjg | gvjgv | vjhv | 0 | 03/08/15 06:00 | 03/08/15 15:30 | [12 empty] | Reamed down from 171m to 528m with 4 - 5 ton WOB. While Reaming @ 308m Observed complete loss. Pumped 105bbl LCM pill of 2.5 PPB Wheat Husk. Returns surfaced after pumping 50bbl LCM. Lost total 166 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/08/15 15:30 | 03/08/15 17:30 | [12 empty] | Circ / swept hole with 40 bbl HV pill till shakers clean.
hvjg | gvjgv | vjhv | 0 | 03/08/15 17:30 | 03/09/15 02:30 | [12 empty] | POOH to surface. L/Down BHA for inspection while POOH. | Non Productive
hvjg | gvjgv | vjhv | 0 | 03/09/15 02:30 | 03/09/15 04:30 | [12 empty] | Held PJSM. R/Up Well Serve Casing Running Gears. Changed TDS Links to 20' & prepared Rig floor to RIH 20" CSG. | Productive
hvjg | gvjgv | vjhv | 0 | 03/09/15 04:30 | 03/09/15 06:00 | [12 empty] | RIH 02 Joints of 20" casing with F/Shoe & Stab-in F/Collar installed on 1st & 2nd joints respectively. Checked integrity of floats & thread locked/torqued up the same. Tack welding float shoe & float collar is in progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 166 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6267 BBL
hvjg | gvjgv | vjhv | 0 | 03/09/15 06:00 | 03/09/15 18:30 | [12 empty] | Tack welded F/Shoe & F/Collar. RIH 20" casing to 129m & observed compression. M/Up circulating head & RIH 20" casing with circulation & reciprocation to 141m. L/down circulating head & RIH casing from 141m to 165m & thereafter observed comression again @ 165m. M/Up circulating head & RIH 20" casing to 176m with circulation & reciprocation. Meanwhile added 2% diesel in mud system. Observed casing stuck @ 176m. Worked & released casing with 40 ton overpull. | Productive
hvjg | gvjgv | vjhv | 0 | 03/09/15 18:30 | 03/10/15 01:00 | [12 empty] | POOH 20" casing to surface & L/down casing joints single by single. While POOH observed 03 nos. Centralizers & 01 no. Stop Collar Left in Hole.
hvjg | gvjgv | vjhv | 0 | 03/10/15 01:00 | 03/10/15 03:00 | [12 empty] | R/Down Well Serve casing running gears & changed TDS links.
hvjg | gvjgv | vjhv | 0 | 03/10/15 03:00 | 03/10/15 06:00 | [12 empty] | M/up & RIH 24" tricone bit (RR2) with 02 Stabs to 66m. While RIH, P/Up & added Inspected DCs single by single.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6267 BBL
hvjg | gvjgv | vjhv | 0 | 03/10/15 06:00 | 03/10/15 19:00 | [12 empty] | RIH 24" tricone bit (RR2) with 02 Stabs from 66m to 122m. Reamed down at high RPM from 122m to bottom. Meanwhile added KCl / Polymer in mud & changed mud system to Modified Spud Mud. While reaming observed complete loss @ 308m. Pumped 83 bbl LCM pill of 2.5 PPB Wheat Husk. Returns surfaced after pumping 60 bbl LCM. Lost total 123 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/10/15 19:00 | 03/10/15 21:00 | [12 empty] | Circ / cleaned hole till shakers clean.
hvjg | gvjgv | vjhv | 0 | 03/10/15 21:00 | 03/11/15 01:00 | [12 empty] | POOH 24" bit with 02 Stabs to surface.
hvjg | gvjgv | vjhv | 0 | 03/11/15 01:00 | 03/11/15 06:00 | [12 empty] | M/up & RIH 24" bit (RR3) with 04 Stabs to 110m. Observed compression @ 110m. M/up TDS & Reamed / washed down to 120m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 123 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/11/15 06:00 | 03/11/15 12:30 | [12 empty] | Reamed / Washed down from 120m to 210m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/11/15 12:30 | 03/12/15 06:00 | [12 empty] | Observed TDS rotation stopped - Checked & Found TDS VFD malfunctioned. Attempted to rectify fault in VFD - No success. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/12/15 06:00 | 03/12/15 06:00 | [12 empty] | Attempted to rectify fault in TDS VFD - No success. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Inspected Mast & Sub-Structure Pins / Safety Pins - All in place.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/13/15 06:00 | 03/13/15 06:00 | [12 empty] | Attempted to rectify fault in TDS VFD - No success. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/14/15 06:00 | 03/14/15 06:00 | [12 empty] | Attempted to rectify fault in TDS VFD - No success. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/15/15 06:00 | 03/15/15 06:00 | [12 empty] | Attempted to rectify fault in TDS VFD - No success. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/16/15 06:00 | 03/16/15 06:00 | [12 empty] | Attempted to rectify fault in TDS VFD. Replaced DC Precharge Relay Board & attempted to operate TDS - One TDS VFD Inverter & Chopper Board went out of order. Meanwhile circ. & reciprocated string.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/17/15 06:00 | 03/17/15 19:00 | [12 empty] | Attempted to rectify fault in TDS VFD. Meanwhile circ. & reciprocated string (03 cycles at high rate to condition mud) and removed Casing Joints & Racks to clear area.
hvjg | gvjgv | vjhv | 0 | 03/17/15 19:00 | 03/18/15 00:30 | [12 empty] | Break out TDS connection with DPs & POOH 24" Bit with 04 Stabs to surface (Hole Free). R/Back BHA & L/Down Bit + Shock Sub + 03 Stabs. | Non Productive
hvjg | gvjgv | vjhv | 0 | 03/18/15 00:30 | 03/18/15 06:00 | [12 empty] | Preparing to L/Down TDS & P/Up Kelly.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 6390 BBL
hvjg | gvjgv | vjhv | 0 | 03/18/15 06:00 | 03/18/15 11:00 | [12 empty] | Made preparations to L/Down TDS & P/Up Kelly. Meanwhile attempted to rectify TDS VFD fault.
hvjg | gvjgv | vjhv | 0 | 03/18/15 11:00 | 03/18/15 12:00 | [12 empty] | Observed TDS VFD fault rectified & rotation resumed. Function tested TDS - OK.
hvjg | gvjgv | vjhv | 0 | 03/18/15 12:00 | 03/19/15 01:00 | [12 empty] | M/Up & RIH 24" bit (RR4) with 04 Stabs to 209m. Observed compression - Reamed down from 209m to 308m. Observed complete loss while reaming @ 308m. Pumped 300 bbl conventional LCM of 20 PPB & 100 bbl LCM of 80 PPB - Meanwhile Reamed down to 409m with partial returns. Lost total 683 bbl mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/19/15 01:00 | 03/19/15 02:00 | [12 empty] | P/Back to 308m. Spotted 60 bbl LCM pill of 80 PPB & displaced LCM with 17 bbl mud. Lost total 77 bbl mud.
hvjg | gvjgv | vjhv | 0 | 03/19/15 02:00 | 03/19/15 03:00 | [12 empty] | P/Back to 238m & allowed Soaking Time to LCM pill.
hvjg | gvjgv | vjhv | 0 | 03/19/15 03:00 | 03/19/15 05:30 | [12 empty] | Filled up hole with 35 bbl mud. Washed down from 238m to 409m. Observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/19/15 05:30 | 03/19/15 06:00 | [12 empty] | Reamed down from 409m to 460m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 335 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 460 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 7185 BBL
hvjg | gvjgv | vjhv | 0 | 03/19/15 06:00 | 03/19/15 11:00 | [12 empty] | Reamed down from 460m to 505m. Observed complete loss while reaming @ 505m. Pumped 58 bbls LCM pill of 25 PPB. Meanwhile Reamed down to 528m with partial returns. Mud loss 346 bbl. | Productive
hvjg | gvjgv | vjhv | 0 | 03/19/15 11:00 | 03/19/15 15:00 | [12 empty] | POOH to surface (Hole Free).
hvjg | gvjgv | vjhv | 0 | 03/19/15 15:00 | 03/19/15 18:00 | [12 empty] | RIH to 306m.
hvjg | gvjgv | vjhv | 0 | 03/19/15 18:00 | 03/19/15 20:00 | [12 empty] | Circulated & conditioned mud. Received lumps of LCM at shale shakers. | Productive
hvjg | gvjgv | vjhv | 0 | 03/19/15 20:00 | 03/19/15 21:00 | [12 empty] | Continued RIH to 528m.
hvjg | gvjgv | vjhv | 0 | 03/19/15 21:00 | 03/20/15 01:00 | [12 empty] | Circulated & conditioned mud till shaker clean. | Productive
hvjg | gvjgv | vjhv | 0 | 03/20/15 01:00 | 03/20/15 06:00 | [12 empty] | POOH to surface (Hole free).
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 346 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 131 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 7662 BBL
hvjg | gvjgv | vjhv | 0 | 03/20/15 06:00 | 03/20/15 07:00 | [12 empty] | L/D Bit, Shock Sub & Stabs. Changed TDS Links.
hvjg | gvjgv | vjhv | 0 | 03/20/15 07:00 | 03/20/15 08:00 | [12 empty] | R/U CRG to run 20"casing.
hvjg | gvjgv | vjhv | 0 | 03/20/15 08:00 | 03/20/15 15:30 | [12 empty] | Held PJSM, P/U track shoe & RIH on 20"casing down to 205m. Observed tight spots @ 127m, 192m, 195m & 205m, worked on string to clear the same. M/U circulation head & washed down from 204m to 210m, observed no return.
hvjg | gvjgv | vjhv | 0 | 03/20/15 15:30 | 03/20/15 21:30 | [12 empty] | RIH 20" casing from 210m to 519m.
hvjg | gvjgv | vjhv | 0 | 03/20/15 21:30 | 03/20/15 22:00 | [12 empty] | Dropped 1.75" Ball & made circulation, observed no return.
hvjg | gvjgv | vjhv | 0 | 03/20/15 22:00 | 03/20/15 23:00 | [12 empty] | P/U 2 x 20" casing Pup joints & RIH to 527m.
hvjg | gvjgv | vjhv | 0 | 03/20/15 23:00 | 03/21/15 00:00 | [12 empty] | R/D casing running gears.
hvjg | gvjgv | vjhv | 0 | 03/21/15 00:00 | 03/21/15 04:00 | [12 empty] | M/U 4-1/2 IF Stinger & RIH on 5" DPs, tagged F/C @ 514.38m with 5 Ton weight.
hvjg | gvjgv | vjhv | 0 | 03/21/15 04:00 | 03/21/15 04:30 | [12 empty] | Worked on mud pumps. | Productive
hvjg | gvjgv | vjhv | 0 | 03/21/15 04:30 | 03/21/15 06:00 | [12 empty] | Filled DPs annulus to observe seals integrity, OK. M/U circulation head & pumped 100 bbls of mud, observed no return. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 596 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: Nil
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 8258 BBL
hvjg | gvjgv | vjhv | 0 | 03/21/15 06:00 | 03/21/15 08:30 | [12 empty] | R/U SLB Dowell meanwhile preparing mixing water.
hvjg | gvjgv | vjhv | 0 | 03/21/15 08:30 | 03/21/15 09:00 | [12 empty] | Held PJSM, pressure tested cementing lines @ 3000 Psi for 10 mins, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/21/15 09:00 | 03/21/15 11:30 | [12 empty] | Pumped 80 bbls of spacer Mud Push II from rig pumps. Switched to cementing unit & pumped 388 bbls of 12.5 ppg Lead Slurry followed by 96 bbls of 15.8 ppg Tail Slurry @ 5 bpm. Displaced slurry with 28 bbls of mud (1 bbl under displace), observed no returns however partial return of 4 bbl received after pumping 210 bbls lead slurry. Bleed off pressure & checked for back flow, no flow. | Productive
hvjg | gvjgv | vjhv | 0 | 03/21/15 11:30 | 03/21/15 12:30 | [12 empty] | POOH 2 x 5" DPs stands,L/D Pup joint & circulated out string volume. | Productive
hvjg | gvjgv | vjhv | 0 | 03/21/15 12:30 | 03/21/15 15:30 | [12 empty] | POOH 5" DPs to surface.
hvjg | gvjgv | vjhv | 0 | 03/21/15 15:30 | 03/22/15 01:00 | [12 empty] | WOC, meanwhile N/D bell nipple & disconnected diverter lines. Cut windows in conductor for Top Job.
hvjg | gvjgv | vjhv | 0 | 03/22/15 01:00 | 03/22/15 02:00 | [12 empty] | R/U SLB Dowell for Top Job meanwhile preparing mixing water.
hvjg | gvjgv | vjhv | 0 | 03/22/15 02:00 | 03/22/15 02:30 | [12 empty] | Held PJSM & pmped 10 bbls of 15.8 ppg slurry, cement surfaced.
hvjg | gvjgv | vjhv | 0 | 03/22/15 02:30 | 03/22/15 06:00 | [12 empty] | WOC
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Fluid Loss: 598 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 8856 BBL
hvjg | gvjgv | vjhv | 0 | 03/22/15 06:00 | 03/22/15 13:00 | [12 empty] | WOC meanwhile cut 30" conductor pipe from cellar base.
hvjg | gvjgv | vjhv | 0 | 03/22/15 13:00 | 03/22/15 16:30 | [12 empty] | R/U SLB Dowell for Top Job & RIH Macroni tubes down to + 24m. Pumped 64 bbls of 15.8 ppg slurry in stages & allowed cement to settle down by gravity. | Productive
hvjg | gvjgv | vjhv | 0 | 03/22/15 16:30 | 03/22/15 20:30 | [12 empty] | WOC.
hvjg | gvjgv | vjhv | 0 | 03/22/15 20:30 | 03/22/15 21:00 | [12 empty] | Checked cement level @ + 5m from cellar base. Filled top with Dry cement.
hvjg | gvjgv | vjhv | 0 | 03/22/15 21:00 | 03/23/15 00:00 | [12 empty] | WOC meanwhile L/D 2 x 8" DC, Jar & Pup joint. P/U 3 x 8" DC & racked back the same.
hvjg | gvjgv | vjhv | 0 | 03/23/15 00:00 | 03/23/15 06:00 | [12 empty] | WOC meanwhile assembled Spacer spool on DSAF, Mud cross on DSAF, HCR & Kill line on Mud Cross.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Fluid Loss: 64 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss till date: 8920 BBL
hvjg | gvjgv | vjhv | 0 | 03/23/15 06:00 | 03/23/15 16:00 | [12 empty] | WOC.
hvjg | gvjgv | vjhv | 0 | 03/23/15 16:00 | 03/23/15 16:30 | [12 empty] | Checked cement, found hard.
hvjg | gvjgv | vjhv | 0 | 03/23/15 16:30 | 03/23/15 19:00 | [12 empty] | Rough cut 20" casing, P/U 20" casing Pup joints & L/D single by single.
hvjg | gvjgv | vjhv | 0 | 03/23/15 19:00 | 03/23/15 22:00 | [12 empty] | N/D Diverter assembly & Bell nipple.
hvjg | gvjgv | vjhv | 0 | 03/23/15 22:00 | 03/23/15 23:30 | [12 empty] | Final cut 20" casing @ .95m from cellar base & dress the stub.
hvjg | gvjgv | vjhv | 0 | 03/23/15 23:30 | 03/24/15 05:00 | [12 empty] | N/U 21-1/4" 5K CHH on 20" casing & welded it.
hvjg | gvjgv | vjhv | 0 | 03/24/15 05:00 | 03/24/15 06:00 | [12 empty] | Waiting for CHH to cool down.
hvjg | gvjgv | vjhv | 0 | 03/24/15 06:00 | 03/24/15 07:30 | [12 empty] | Waiting for CHH to cool down.
hvjg | gvjgv | vjhv | 0 | 03/24/15 07:30 | 03/24/15 08:00 | [12 empty] | Pressure tested CHH @ 500 Psi, found leakage inside welding. | Productive
hvjg | gvjgv | vjhv | 0 | 03/24/15 08:00 | 03/24/15 10:00 | [12 empty] | Re-welded CHH.
hvjg | gvjgv | vjhv | 0 | 03/24/15 10:00 | 03/24/15 12:00 | [12 empty] | Waiting for CHH to cool down.
hvjg | gvjgv | vjhv | 0 | 03/24/15 12:00 | 03/24/15 12:30 | [12 empty] | Pressure tested CHH @ 500 Psi, found OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/24/15 12:30 | 03/25/15 03:00 | [12 empty] | N/U 21-1/4" 5K BOP Stack, installed Bell Nipple & Flow Line[ Adapter Spool & Rizer are of 3k rating]
hvjg | gvjgv | vjhv | 0 | 03/25/15 03:00 | 03/25/15 04:00 | [12 empty] | P/U mouse hole & installed the same.
hvjg | gvjgv | vjhv | 0 | 03/25/15 04:00 | 03/25/15 04:30 | [12 empty] | Function tested BOP, OK.
hvjg | gvjgv | vjhv | 0 | 03/25/15 04:30 | 03/25/15 06:00 | [12 empty] | P/U & M/U test plug assembly, RIH & made preparations to pressure test BOP. | Productive
hvjg | gvjgv | vjhv | 0 | 03/25/15 06:00 | 03/25/15 09:30 | [12 empty] | Pressure tested Pipe Ram, Annular BOP, Kill Line, Choke Line & HCR valve @ 500 Psi low & 3000 Psi high, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/25/15 09:30 | 03/25/15 10:00 | [12 empty] | Tested Komi unit, found OK.
hvjg | gvjgv | vjhv | 0 | 03/25/15 10:00 | 03/25/15 10:30 | [12 empty] | L/D test plug assembly.
hvjg | gvjgv | vjhv | 0 | 03/25/15 10:30 | 03/25/15 12:30 | [12 empty] | Cut & Slip 96 ft Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | 03/25/15 12:30 | 03/25/15 18:00 | [12 empty] | P/U & M/U 17-1/2" Tricone Bit (used) & RIH down to 489m on Slick BHA.
hvjg | gvjgv | vjhv | 0 | 03/25/15 18:00 | 03/25/15 19:00 | [12 empty] | Washed down from 489m to 513.50m, tagged cement @ 513.50m.
hvjg | gvjgv | vjhv | 0 | 03/25/15 19:00 | 03/25/15 20:30 | [12 empty] | Made circulation to homogenise mud.
hvjg | gvjgv | vjhv | 0 | 03/25/15 20:30 | 03/25/15 21:00 | [12 empty] | Pressure tested 20" casing @ 500 Psi, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/25/15 21:00 | 03/25/15 23:30 |  |  | 513.5 | 524 | [8 empty] | Drilled out F/Collar & COC from 513.50m to 524m. F/Collar @ 514.38m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/25/15 23:30 | 03/26/15 00:00 | [12 empty] | Circulate to bottom up. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 00:00 | 03/26/15 00:30 | [12 empty] | Pressure tested 20" casing @ 500 Psi, OK. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/26/15 00:30 | 03/26/15 05:00 |  |  | 528 | 531 | [8 empty] | COC, drilled out F/Shoe @ 527m & continued drilling 17-1/2" Hole from 528m to 531m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 05:00 | 03/26/15 06:00 | [12 empty] | Circulate to bottom up meanwhile worked on junk sub. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 06:00 | 03/26/15 07:30 | [12 empty] | Displaced 1.03 SG Modified Spud Mud with newly prepared KCl PHPA Polymer mud of 1.1 SG weight. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 07:30 | 03/26/15 09:30 | [12 empty] | R/U SLB Dowell for FIT, pressure tested lines to 3000 Psi, OK. Attempted to perform FIT, formation fractured at 215 Psi surface pressure EMW = 1.38 SG. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 09:30 | 03/26/15 10:30 | [12 empty] | Started circulation, observed no returns.
hvjg | gvjgv | vjhv | 0 | 03/26/15 10:30 | 03/26/15 12:30 | [12 empty] | Prepared & pumped 50 bbls of 110 PPB LCM. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 12:30 | 03/26/15 13:30 | [12 empty] | Soaking time for LCM.
hvjg | gvjgv | vjhv | 0 | 03/26/15 13:30 | 03/26/15 14:30 | [12 empty] | Filled annulus through trip tank, no returns.
hvjg | gvjgv | vjhv | 0 | 03/26/15 14:30 | 03/26/15 16:30 | [12 empty] | Prepared & pumped 50 bbls of 300 PPB LCM, returns surfaced after 40 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 03/26/15 16:30 | 03/26/15 17:30 | [12 empty] | Monitered Well through Trip Tank, observed no static loss.
hvjg | gvjgv | vjhv | 0 | 03/26/15 17:30 | 03/26/15 23:30 | [12 empty] | Started circulation, got returns. Circulated hole by gradually increasing SPM at 30, 40, 50, 60 & 70 by both pumps, observed no loss. Meanwhile reduced MW from 1.08 SG to 1.04 SG. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/26/15 23:30 | 03/27/15 01:30 |  |  | 531 | 535 | [8 empty] | Drilled 17-1/2" hole from 531m to 535m. Observed partial dynamic losses. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 01:30 | 03/27/15 02:30 | [12 empty] | Prepared & pumped 25 bbls of 150 PPB LCM. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 02:30 | 03/27/15 03:30 | [12 empty] | POOH inside 20" casing & allowed soaking time for LCM.
hvjg | gvjgv | vjhv | 0 | 03/27/15 03:30 | 03/27/15 05:00 | [12 empty] | Circulated hole by gradually increasing SPM at 30, 40, 50 & 60 by both pumps, observed no loss. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/27/15 05:00 | 03/27/15 06:00 |  |  | 535 | 540 | [8 empty] | Drilled 17-1/2" hole from 535m to 540m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 358 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 115 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 473 BBL
hvjg | gvjgv | vjhv | 17.5 | 03/27/15 06:00 | 03/27/15 07:30 |  |  | 540 | 544 | [8 empty] | Drilled 17-1/2" hole from 540m to 544m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 07:30 | 03/27/15 08:30 | [12 empty] | Reamed once at connection. Took SCR & serviced TDS. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/27/15 08:30 | 03/27/15 15:00 |  |  | 544 | 574 | [8 empty] | Drilled 17-1/2" hole from 544m to 574m, observed Dynamic losses. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 15:00 | 03/27/15 15:30 | [12 empty] | Prepared & pumped 25 bbls of 255 PPB LCM. Displaced with 22 bbls of mud. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/27/15 15:30 | 03/27/15 17:30 |  |  | 574 | 582 | [8 empty] | Drilled 17-1/2" hole from 574m to 582m. Observed complete loss @ 582m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 17:30 | 03/27/15 18:30 | [12 empty] | Prepared & pumped 50 bbls of 300 PPB LCM. Displaced with 25 bbls of mud. Returns surfaced after pumping 44 bbls LCM. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 18:30 | 03/27/15 19:00 | [12 empty] | POOH from 582m to 545m, observed O/pull of max. 7 tons at 566m & 559m.
hvjg | gvjgv | vjhv | 0 | 03/27/15 19:00 | 03/27/15 20:30 | [12 empty] | Monitered Well through Trip Tank, observed 1.5 bbl static loss.
hvjg | gvjgv | vjhv | 0 | 03/27/15 20:30 | 03/27/15 23:00 | [12 empty] | Circulated hole by gradually increasing SPM at 30, 40, 50, 60 & 70 by both pumps, observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/27/15 23:00 | 03/27/15 23:30 | [12 empty] | RIH & reamed down from 545m to 582m. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/27/15 23:30 | 03/28/15 06:00 |  |  | 582 | 600 | [8 empty] | Drilled 17-1/2" hole from 582m to 600m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 377 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 69 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 919 BBL
hvjg | gvjgv | vjhv | 17.5 | 03/28/15 06:00 | 03/28/15 08:00 |  |  | 600 | 602 | [8 empty] | Drilled 17-1/2" hole from 600m to 602m. Reamed connection twice & L/D single for Totco survey. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 08:00 | 03/28/15 08:30 | [12 empty] | Conducted Totco Deviation survey, 0.75 deg @ 590m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 08:30 | 03/28/15 09:00 | [12 empty] | Reamed & washed down from 592m to 602m, observed Hi off-bottom torque (max. 15 ft-Klbs). | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/28/15 09:00 | 03/28/15 10:30 |  |  | 602 | 603 | [8 empty] | Drilled 17-1/2" hole from 602m to 603m, torque abnormal. Prepared & pumped 25 bbls Hi-Vis. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 10:30 | 03/28/15 11:30 | [12 empty] | POOH from 602m to 516m. Checked TDS, found OK. Reamed down from 516m to 546m, observed complete loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 11:30 | 03/28/15 12:30 | [12 empty] | Prepared & pumped 25 bbls of 300 PPB LCM, observed no return. POOH from 546m to 488m. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 12:30 | 03/28/15 14:30 | [12 empty] | Started circulation, observed partial loss. Soaking time for LCM meanwhile monitored well through Trip Tank for static loss.
hvjg | gvjgv | vjhv | 0 | 03/28/15 14:30 | 03/28/15 16:00 | [12 empty] | RIH from 488m to 545m, pumped 300 PPB LCM & got returns after 18 bbls. Displaced LCM with 23 bbls of mud. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 16:00 | 03/28/15 17:00 | [12 empty] | POOH to 516m inside 20"casing. Soaking time for LCM meanwhile monitored well through Trip Tank, observed static loss.
hvjg | gvjgv | vjhv | 0 | 03/28/15 17:00 | 03/28/15 20:00 | [12 empty] | RIH to 603m, pumped 50 bbls of 300 PPB LCM, got returns after 16 bbls. Displaced LCM & POOH to 516m inside 20" casing. Soaking time for LCM meanwhile monitored well through Trip Tank, no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/28/15 20:00 | 03/28/15 22:00 | [12 empty] | Resumed circulation, observed bit nozzles jet plugged. Worked to open the nozzle jets but no success.
hvjg | gvjgv | vjhv | 0 | 03/28/15 22:00 | 03/28/15 23:30 | [12 empty] | POOH from 516m to TOP of BHA @ 298m & RIH down to 401m. Worked to open jets with circulation, no success.
hvjg | gvjgv | vjhv | 0 | 03/28/15 23:30 | 03/29/15 02:00 | [12 empty] | POOH from 401m to surface. L/D Jar & Junk Sub.
hvjg | gvjgv | vjhv | 0 | 03/29/15 02:00 | 03/29/15 03:00 | [12 empty] | Broke Bit & Junk Sub, found 2 x Jets plugged. Received 1.25 Kg Metal pieces of centralizers & snap rings from Junk Sub.
hvjg | gvjgv | vjhv | 0 | 03/29/15 03:00 | 03/29/15 06:00 | [12 empty] | RR 17-1/2" Tricone Bit with Pendulum BHA down to 236m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 218 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 59 BBL, Hi-Vis: 25 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 0 | 03/29/15 06:00 | 03/29/15 07:00 | [12 empty] | RIH from 236m to 519m, filled String.
hvjg | gvjgv | vjhv | 0 | 03/29/15 07:00 | 03/29/15 17:00 | [12 empty] | Reamed & washed down from 519m to 603m, observed compression of 5 tons at 538m. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/29/15 17:00 | 03/30/15 06:00 |  |  | 603 | 634 | [8 empty] | Drilled 17-1/2" hole from 603m to 634m. Reamed at connection twice. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 17.5 | 03/30/15 06:00 | 03/30/15 15:00 |  |  | 634 | 647 | [8 empty] | Drilled 17-1/2" hole from 634m to 647m, observed Hi-torque of max. 5 K ft-lbs. Work on string to reduce torque but no success. | Productive
hvjg | gvjgv | vjhv | 0 | 03/30/15 15:00 | 03/30/15 16:00 | [12 empty] | Flow checked, OK. POOH from 647m to 510m inside 20" casing.
hvjg | gvjgv | vjhv | 0 | 03/30/15 16:00 | 03/30/15 19:30 | [12 empty] | Flow checked, OK. POOH from 510m to surface, L/D Jar & S.Stabs. Observed errosion on Bit & one S.Stab due to hard formation.
hvjg | gvjgv | vjhv | 0 | 03/30/15 19:30 | 03/31/15 03:30 | [12 empty] | P/U & M/U New 17-1/2" Tricone Bit & RIH down to 634m on same BHA.
hvjg | gvjgv | vjhv | 0 | 03/31/15 03:30 | 03/31/15 04:00 | [12 empty] | Reamed & washed down from 634m to 647m. | Productive
hvjg | gvjgv | vjhv | 17.5 | 03/31/15 04:00 | 03/31/15 06:00 |  |  | 647 | 656 | [8 empty] | Resumed Drilling 17-1/2" hole from 647m to 656m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 17.5 | 03/31/15 06:00 | 03/31/15 13:30 |  |  | 656 | 691 | [8 empty] | Drilled 17-1/2" hole from 656m to 691m, reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 03/31/15 13:30 | 03/31/15 14:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 03/31/15 14:00 | 04/01/15 06:00 |  |  | 691 | 756 | [8 empty] | Drilled 17-1/2" hole from 691m to 756m, reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/01/15 06:00 | 04/01/15 10:30 |  |  | 756 | 777 | [8 empty] | Drilled 17-1/2" hole from 756m to 777m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/01/15 10:30 | 04/01/15 11:30 | [12 empty] | Circulated hole till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 04/01/15 11:30 | 04/01/15 12:30 | [12 empty] | Conducted Totco Deviation survey, 0.50 deg @ 767m. | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/01/15 12:30 | 04/02/15 06:00 |  |  | 777 | 841 | [8 empty] | Drilled 17-1/2" hole from 777m to 841m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/02/15 06:00 | 04/02/15 13:00 |  |  | 841 | 862 | [8 empty] | Drilled 17-1/2" hole from 841m to 862m & pumped 30 bbls Hi-Vis pill. | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/02/15 13:00 | 04/03/15 00:30 |  |  | 862 | 890 | [8 empty] | Drilled 17-1/2" hole from 862m to 890m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 00:30 | 04/03/15 03:00 | [12 empty] | Pumped 25 bbls Hi-Vis pill & circulated hole till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 03:00 | 04/03/15 04:00 | [12 empty] | POOH from 890m to 745m, observed O/pull of max. 10 ton @ 745m & 709m.
hvjg | gvjgv | vjhv | 0 | 04/03/15 04:00 | 04/03/15 05:00 | [12 empty] | Pumped out from 745m to 660m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 05:00 | 04/03/15 06:00 | [12 empty] | POOH from 660m to 488m (in progress).
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1221 BBL
hvjg | gvjgv | vjhv | 0 | 04/03/15 06:00 | 04/03/15 07:00 | [12 empty] | Continued POOH from 488m to 293m (Top of BHA).
hvjg | gvjgv | vjhv | 0 | 04/03/15 07:00 | 04/03/15 07:30 | [12 empty] | Flow checked @ BHA Top, observed static loss.
hvjg | gvjgv | vjhv | 0 | 04/03/15 07:30 | 04/03/15 11:00 | [12 empty] | POOH from 293m to Surface. L/D Jar, S.Stab & Bit.
hvjg | gvjgv | vjhv | 0 | 04/03/15 11:00 | 04/03/15 11:30 | [12 empty] | Serviced TDS, meanwhile filled hole with mud pumps. | Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 11:30 | 04/03/15 14:30 | [12 empty] | P/U & M/U 17-1/2" Tricone bit & RIH with 9-5/8" mud motor. Performed shallow function test of mud motor @ 650 GPM & 320 Psi SPP, OK. RIH PBL Sub & performed function test by activating & deactivating through sequence of 2-1/2" & 1-3/4" balls at 400 Psi & 2600 Psi respectivily, found OK.
hvjg | gvjgv | vjhv | 0 | 04/03/15 14:30 | 04/03/15 15:30 | [12 empty] | P/B assembly back to surface, break 17-1/2" Tricone bit. | Non Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 15:30 | 04/03/15 20:30 | [12 empty] | P/U & M/U 17-1/2" PDC bit & RIH with mud motor down to 332m. Flow checked, observed static loss. Filled the hole & got returns after 35 bbls of mud. RIH down to 558m.
hvjg | gvjgv | vjhv | 0 | 04/03/15 20:30 | 04/03/15 23:00 | [12 empty] | Pumped 50 bbls of 300 PPB LCM & displaced with 22 bbls of mud, observed no returns. POOH three stands & allowed soaking time for LCM, meanwhile filled hole through kill line & got returns after 37 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 04/03/15 23:00 | 04/04/15 01:00 | [12 empty] | RIH from 445m to 550m, activated PBL Sub, pumped 50 bbls of 300 PPB LCM & displaced with 22 bbls of mud. POOH from 550m to 445m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/04/15 01:00 | 04/04/15 05:30 | [12 empty] | Allowed soaking time for LCM. Filled hole from kill line & observed static loss. Prepared 100 bbls of 300 PPB LCM, very slow mixing of LCM due to unavailibilty of crane & disorderness of mixing hopers (mixing with hands). | Productive
hvjg | gvjgv | vjhv | 0 | 04/04/15 05:30 | 04/04/15 06:00 | [12 empty] | Preparing to spott LCM pill.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 512 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 100 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 1833 BBL
hvjg | gvjgv | vjhv | 0 | 04/04/15 06:00 | 04/04/15 09:00 | [12 empty] | Pumped 50 bbls of 300 PPB LCM & displaced with 22 bbls of mud. POOH three stands & allowed soaking time for LCM, meanwhile monitored well for static losses. | Productive
hvjg | gvjgv | vjhv | 0 | 04/04/15 09:00 | 04/04/15 09:30 | [12 empty] | POOH from 463m to 445m, started circulation & got return after 24 bbls, observed dynamic losses.
hvjg | gvjgv | vjhv | 0 | 04/04/15 09:30 | 04/04/15 13:00 | [12 empty] | RIH from 445m to 531m, pumped 50 bbls of 300 PPB LCM & displaced with 22 bbls of mud, got returns after 10 bbls. POOH from 531m to 445m & allowed soaking time for LCM, filled hole twice & observed no return. | Productive
hvjg | gvjgv | vjhv | 0 | 04/04/15 13:00 | 04/04/15 18:30 | [12 empty] | POOH from 445m to 217m. Deactivated PBL Sub @ 217m & continued POOH to surface. L/D Jar, S.Stab & R/B PBL Sub, Mud Motor & Bit.
hvjg | gvjgv | vjhv | 0 | 04/04/15 18:30 | 04/04/15 21:00 | [12 empty] | P/U & M/U Mule shoe & run in hole on 5" DPs to 580m.
hvjg | gvjgv | vjhv | 0 | 04/04/15 21:00 | 04/05/15 00:00 | [12 empty] | Reciprocated String meanwhile prepared 70 bbls of 100 sec Hi-Vis Pill. | Productive
hvjg | gvjgv | vjhv | 0 | 04/05/15 00:00 | 04/05/15 01:30 | [12 empty] | RIH down to 620m, pumped 70 bbls Hi-Vis pill & displaced with 36 bbls of mud, got returns after 34 bbls. | Productive
hvjg | gvjgv | vjhv | 0 | 04/05/15 01:30 | 04/05/15 05:00 | [12 empty] | POOH from 620m to 550m, R/U Dowell cement unit. Prepared MUD PUSH II spacer & mixing water for Balanced Cement Plug job. | Productive
hvjg | gvjgv | vjhv | 0 | 04/05/15 05:00 | 04/05/15 06:00 | [12 empty] | Held PJSM, Flushed cement lines & pressure tested the same @ 3000 Psi, OK. Balanced Cement Plug job is in progress. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | HSE Officer not available at location
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 90 BBL, Hi-Vis: 70 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 100 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2093 BBL
hvjg | gvjgv | vjhv | 0 | 04/05/15 06:00 | 04/05/15 07:30 | [12 empty] | Pumped 50 bbls of 13 ppg spacer (MUD PUSH II) ahead followed by 68 bbls of 15.8 ppg cement slurry @ 5 bpm & 2.80 bbls spacer behind. Displaced the slurry with 24 bbls of mud, observed returns of 27 bbls mud. | Productive
hvjg | gvjgv | vjhv | 0 | 04/05/15 07:30 | 04/05/15 08:00 | [12 empty] | POOH from 551m to 430m, pumped string volume, observed no returns. | Productive
hvjg | gvjgv | vjhv | 0 | 04/05/15 08:00 | 04/05/15 09:30 | [12 empty] | POOH from 430m to surface, L/D Mule Shoe.
hvjg | gvjgv | vjhv | 0 | 04/05/15 09:30 | 04/05/15 10:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 04/05/15 10:00 | 04/05/15 19:00 | [12 empty] | WOC, meanwhile monitor well for losses. Filled hole with 16 bbls @ 1200 Hrs & 34 bbls @ 1600 Hrs.
hvjg | gvjgv | vjhv | 0 | 04/05/15 19:00 | 04/05/15 22:30 | [12 empty] | P/U & M/U 17-1/2" Tricone Bit (used), Bit Sub with 8" DCs & RIH to 517m.
hvjg | gvjgv | vjhv | 0 | 04/05/15 22:30 | 04/05/15 23:00 | [12 empty] | Washed down from 517m to 600m, observed no cement in hole.
hvjg | gvjgv | vjhv | 0 | 04/05/15 23:00 | 04/06/15 01:00 | [12 empty] | POOH from 600m to 517m. Circulated hole to observe dynamic losses, observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 01:00 | 04/06/15 01:30 | [12 empty] | Flow checked for static loss, minor level drop from flow line.
hvjg | gvjgv | vjhv | 0 | 04/06/15 01:30 | 04/06/15 04:30 | [12 empty] | RIH from 517m to 650m. Circulated hole to bottom up, observed Hi-Vis pill surfaced. Continued circulation to observe dynamic loss, observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 04:30 | 04/06/15 06:00 | [12 empty] | POOH from 650m to 203m (in progress).
hvjg | gvjgv | vjhv | 0 | [14 empty] | Fork Lifter is Down
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 100 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 121 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2314 BBL
hvjg | gvjgv | vjhv | 0 | 04/06/15 06:00 | 04/06/15 08:00 | [12 empty] | POOH from 203m to surface, breake 17-1/2" Tricone bit. | Non Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 08:00 | 04/06/15 11:00 | [12 empty] | M/U 9-5/8" Mud Motor, PBL Sub & Tricone Bit, conducted Shallow test Mud Motor test @ 650 GPM & 350 Psi pressure, OK. L/D Tricone bit, P/U 17-1/2" PDC bit & RIH to 25m. Decided to POOH for Cement Plug Job.
hvjg | gvjgv | vjhv | 0 | 04/06/15 11:00 | 04/06/15 13:00 | [12 empty] | P/U & M/U Mule shoe & RIH on 5" DPs to 656m.
hvjg | gvjgv | vjhv | 0 | 04/06/15 13:00 | 04/06/15 15:00 | [12 empty] | Circulated hole to observe dynamic loss, observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 15:00 | 04/06/15 16:00 | [12 empty] | Pumped 78 bbls of 138 sec Hi-Vis pill & displaced with 38 bbls of mud. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 16:00 | 04/06/15 17:30 | [12 empty] | Circulated hole to observe dynamic loss, observed no loss. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 17:30 | 04/06/15 18:30 | [12 empty] | R/U Dowell for cement job.
hvjg | gvjgv | vjhv | 0 | 04/06/15 18:30 | 04/06/15 20:30 | [12 empty] | Pressure tested cement lines, pumped 60 bbls of spacer followed by 23 bbls of 15.8 PPG. Due to malfunctioning of fly mixer, unable to raise density of cement above 14.2 PPG. Waited for 30 mins, no success. | Productive
hvjg | gvjgv | vjhv | 0 | 04/06/15 20:30 | 04/07/15 03:30 | [12 empty] | Circulated out spacer & dumped cement with rig pumps. Meanwhile worked on Dowell unit. | Productive
hvjg | gvjgv | vjhv | 0 | 04/07/15 03:30 | 04/07/15 04:30 | [12 empty] | Held PJSM, Pumped 60 bbls of water ahead followed by 110 bbls of 15.8 ppg cement slurry @ 5 bpm & 3.50 bbls water behind. Displaced the slurry with 24.5 bbls of mud, observed returns of 153 bbls mud. | Productive
hvjg | gvjgv | vjhv | 0 | 04/07/15 04:30 | 04/07/15 05:30 | [12 empty] | POOH from 600m to 400m.
hvjg | gvjgv | vjhv | 0 | 04/07/15 05:30 | 04/07/15 06:00 | [12 empty] | Reverse circulated out string volume. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 45 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/07/15 06:00 | 04/07/15 07:00 | [12 empty] | POOH 5" OEDPS from 400m to surface. L/down Mule Shoe.
hvjg | gvjgv | vjhv | 0 | 04/07/15 07:00 | 04/07/15 07:30 | [12 empty] | WOC. Worked on TDS.
hvjg | gvjgv | vjhv | 0 | 04/07/15 07:30 | 04/07/15 21:00 | [12 empty] | WOC. Meanwhile monitored well thru Trip Tank - Observed No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | 04/07/15 21:00 | 04/08/15 04:00 | [12 empty] | WOC. P/Up & M/Up Test Plug Assy. Retrieved Wear Bushing & set Test Plug inside CHH. Flushed BOP Stack & Choke Manifold with water. Press Tested Annular BOP + 5" Pipe Rams + HCRs + Kill Line + Choke Line / Manifold + Rotary Hose + Standpipe / Manifold + TDS IBOP + Pump Manifold + Blind Rams @ 500 psi Low & 2700 psi High for 1/4 hr each - Ok. Retrieved Test Plug & set Wear Bushing inside CHH. L/down Test Plug Assy. | Productive
hvjg | gvjgv | vjhv | 0 | 04/08/15 04:00 | 04/08/15 06:00 | [12 empty] | M/Up 9-5/8" Sperry Mud Motor with Sleeve Stab + PBL Sub & Tricone Bit. Shallow Tested Mud Motor test @ 650 GPM & 330 psi - Ok. L/Down Tricone bit & M/Up 17-1/2" PDC bit.
hvjg | gvjgv | vjhv | 0 | [14 empty] | NOTE: NO HSE OFFICER IS PRESENT AT WELL SITE.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/08/15 06:00 | 04/08/15 10:30 | [12 empty] | M/Up & RIH with Performance BHA to 440m.
hvjg | gvjgv | vjhv | 0 | 04/08/15 10:30 | 04/08/15 11:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 04/08/15 11:00 | 04/08/15 14:00 | [12 empty] | Found TDS Saver Sub Threads Galled. Replaced TDS Saver Sub with New one. Found New Saver Sub Over Sized and incompatible with Torque Plates. Re-Installed Old Saver Sub.
hvjg | gvjgv | vjhv | 0 | 04/08/15 14:00 | 04/08/15 16:00 | [12 empty] | RIH down to 560.5m & tagged top of cement plug with 5 Tons Wt.
hvjg | gvjgv | vjhv | 0 | 04/08/15 16:00 | 04/08/15 16:30 | [12 empty] | COC / Dressed cement to 562m with Zero WOB.
hvjg | gvjgv | vjhv | 0 | 04/08/15 16:30 | 04/08/15 17:30 | [12 empty] | Circ - Homogenized Mud Column. Found cement cuttings at shakers on bottom up.
hvjg | gvjgv | vjhv | 0 | 04/08/15 17:30 | 04/08/15 18:30 | [12 empty] | P/Back to 522m. Held PJSM. R/Up SLB Dowel for FIT. Press tested lines to 1000 psi - Ok. Attempted to perform FIT - Pumped 0.2 bbl mud & observed press increased to 75 psi due to Mud Motor. R/Down SLB Lines. | Productive
hvjg | gvjgv | vjhv | 0 | 04/08/15 18:30 | 04/08/15 21:30 | [12 empty] | Made preparations & R/Up SLB Dowel lines on Kill line. Attempted to perform FIT - Observed Formation Intake @ 1.10 S.G EMW (45 psi surface press). R/Down SLB Lines.
hvjg | gvjgv | vjhv | 0 | 04/08/15 21:30 | 04/09/15 06:00 | [12 empty] | RIH down to 562m. Reamed / Washed Down from 562m to 816m with Zero to 4 Ton WOB. Found Cement Contaminated Mud on shakers till 650m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/09/15 06:00 | 04/09/15 09:30 | [12 empty] | Reamed / Washed Down from 816m to 890m with Zero to 2 Ton WOB. Swept hole with 40 BBL Hi-Vis Pill while Reaming. | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/09/15 09:30 | 04/09/15 21:30 |  |  | 890 | 958 | [8 empty] | Recorded SCR. Resumed Drilling & Drilled 17-1/2" hole from 890m to 958m. Reamed twice at each connection & swept hole with 20 BBL Hi-Vis Pill at 952m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/09/15 21:30 | 04/09/15 22:30 | [12 empty] | P/Back to 949m. Recorded Totco Deviation Survey on Slickline (0.75 deg @ 935m). | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/09/15 22:30 | 04/10/15 06:00 |  |  | 958 | 1014 | [8 empty] | RIH to BTM. Resumed Drilling & Drilled 17-1/2" hole from 958m to 1014m. Reamed twice at connection & Recorded SCR @ 987m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/10/15 06:00 | 04/10/15 13:00 |  |  | 1014 | 1063 | [8 empty] | Drilled 17-1/2" hole from 1014m to 1063m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/10/15 13:00 | 04/10/15 14:30 | [12 empty] | Circ / Swept hole with 30 bbl Hi-Vis pill. Flow checked - Ok.
hvjg | gvjgv | vjhv | 0 | 04/10/15 14:30 | 04/10/15 16:00 | [12 empty] | Conducted Short Trip from 1063m to 845m - Hole Slick.
hvjg | gvjgv | vjhv | 17.5 | 04/10/15 16:00 | 04/11/15 06:00 |  |  | 1063 | 1158 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1063m to 1158m. Reamed twice at each connection & Swept hole with 30 bbl Hi-Vis Pill @ 1155m prior to conduct Deviation Survey on Slickline. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/11/15 06:00 | 04/11/15 07:30 | [12 empty] | Reamed / Circ. out Hi-Vis Pill. Flow checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 04/11/15 07:30 | 04/11/15 08:30 | [12 empty] | P/Back to 1130m. Recorded Totco Deviation Survey on Slickline (0.80° @ 1115m). | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/11/15 08:30 | 04/11/15 12:00 |  |  | 1158 | 1186 | [8 empty] | RIH to BTM. Resumed Drilling & Drilled 17-1/2" hole from 1158m to 1186m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/11/15 12:00 | 04/11/15 12:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/11/15 12:30 | 04/12/15 06:00 |  |  | 1186 | 1308 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1186m to 1308m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/12/15 06:00 | 04/12/15 11:30 |  |  | 1308 | 1345 | [8 empty] | Drilled 17-1/2" Hole from 1308m to 1345m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/12/15 11:30 | 04/12/15 13:30 | [12 empty] | Circ / Swept hole with 40 bbl Hi-Vis pill till shakers clean. Flow checked - OK.
hvjg | gvjgv | vjhv | 0 | 04/12/15 13:30 | 04/13/15 03:30 | [12 empty] | POOH from 1308m to surface. While POOH Flow Checked at BHA & L/Down BHA for inspection. Drained Mud Motor & Checked Motor Bearing Gap. L/Down PDC Bit & M/Up Tricone Bit. Shallow Tested Mud Motor @ 650 GPM & 315 psi. Meanwhile Inspected BHA. | Non Productive
hvjg | gvjgv | vjhv | 0 | 04/13/15 03:30 | 04/13/15 05:00 | [12 empty] | Replaced TDS Saver Sub.
hvjg | gvjgv | vjhv | 0 | 04/13/15 05:00 | 04/13/15 06:00 | [12 empty] | L/Down Ticone Bit & M/Up 17-1/2" PDC Bit (RR) with Mud Motor. RIH to 14m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/13/15 06:00 | 04/13/15 18:30 | [12 empty] | RIH 17-1/2" PDC Bit (RR) with Mud Motor & PBL Sub from 14m to BTM. Reamed / Washed Down Last Stand. While RIH Observed compression at 582m & 617m - Washed Down & cleared it. | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/13/15 18:30 | 04/14/15 06:00 |  |  | 1345 | 1424 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1345m to 1424m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted BOP Drill while Tripping @ 370m (Response Time: 01 min). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/14/15 06:00 | 04/14/15 08:30 |  |  | 1424 | 1443 | [8 empty] | Drilled 17-1/2" hole from 1424m to 1443m. Pumped 30 bbl Hi-Vis Pill @ 1434m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/14/15 08:30 | 04/14/15 09:30 | [12 empty] | Reamed / Circ. Out Hi-Vis Pill. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 04/14/15 09:30 | 04/14/15 10:30 | [12 empty] | P/Back to 1415m. Recorded Totco Deviation Survey on Slickline (0.90° @ 1400m). | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/14/15 10:30 | 04/15/15 06:00 |  |  | 1443 | 1549 | [8 empty] | RIH to BTM. Resumed Drilling & Drilled 17-1/2" hole from 1443m to 1549m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/15/15 06:00 | 04/15/15 17:30 |  |  | 1549 | 1614 | [8 empty] | Drilled 17-1/2" hole from 1549m to 1614m. Reamed twice at each connection. Pumped 40 bbl Hi-Vis Pill @ 1611m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/15/15 17:30 | 04/15/15 18:30 | [12 empty] | Reamed / Circ. Out Hi-Vis Pill. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 04/15/15 18:30 | 04/15/15 21:30 | [12 empty] | Conducted Short Trip from 1614m to 1329m - Hole Slick.
hvjg | gvjgv | vjhv | 0 | 04/15/15 21:30 | 04/15/15 22:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/15/15 22:00 | 04/16/15 06:00 |  |  | 1614 | 1666 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1614m to 1666m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/16/15 06:00 | 04/17/15 03:00 |  |  | 1666 | 1785 | [8 empty] | Drilled 17-1/2" hole from 1666m to 1785m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/17/15 03:00 | 04/17/15 03:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/17/15 03:30 | 04/17/15 06:00 |  |  | 1785 | 1801 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1785m to 1801m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/17/15 06:00 | 04/17/15 08:00 |  |  | 1801 | 1813 | [8 empty] | Drilled 17-1/2" hole from 1801m to 1813m. Swept 40 bbl Hi-Vis Pill while Drilling @ 1805m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/17/15 08:00 | 04/17/15 08:30 | [12 empty] | Circulated / Cleaned hole prior to Deviation Survey. | Productive
hvjg | gvjgv | vjhv | 0 | 04/17/15 08:30 | 04/17/15 09:30 | [12 empty] | P/Back to 1785m. Recorded Totco Deviation Survey on Slickline (1.0° @ 1768m). | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/17/15 09:30 | 04/18/15 00:00 |  |  | 1813 | 1899 | [8 empty] | RIH to BTM. Resumed Drilling & Drilled 17-1/2" hole from 1813m to 1899m. Reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/18/15 00:00 | 04/18/15 00:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/18/15 00:30 | 04/18/15 06:00 |  |  | 1899 | 1927 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 1899m to 1927m. Pumped 40 bbl Hi-Vis Pill @ 1918m while Drilling. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | CMT: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole : 2359 BBL
hvjg | gvjgv | vjhv | 0 | 04/18/15 06:00 | 04/18/15 08:00 | [12 empty] | Stopped Drilling. Circ. / Cleaned hole prior to POOH to 20" Casing Shoe for TDS VFD Repair. | Productive
hvjg | gvjgv | vjhv | 0 | 04/18/15 08:00 | 04/18/15 09:30 | [12 empty] | Flow Checked - Well Static. POOH to 1500m.
hvjg | gvjgv | vjhv | 0 | 04/18/15 09:30 | 04/18/15 13:30 | [12 empty] | Continued POOH from 1500m to 503m (Inside 20" Casing Shoe).
hvjg | gvjgv | vjhv | 0 | 04/18/15 13:30 | 04/18/15 18:00 | [12 empty] | Repair work @ TDS VFD. Replaced TDS Service Loop. Replaced DB Chopper & Inverter at VFD. Found Inverter not responding properly. Removed Chopper. Meanwhile Monitored Well thru Trip Tank - Found Static Loss @ 2 bbl/hr. Lost 9 bbl Mud. | Non Productive
hvjg | gvjgv | vjhv | 0 | 04/18/15 18:00 | 04/18/15 22:00 | [12 empty] | RIH from 503m to 1500m.
hvjg | gvjgv | vjhv | 0 | 04/18/15 22:00 | 04/19/15 00:30 | [12 empty] | Continued RIH from 1500m to BTM. Reamed / Washed Down Last Stand & Pumped 35 bbl Fine LCM Pill of 40 PPB. | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/19/15 00:30 | 04/19/15 06:00 |  |  | 1927 | 1956 | [8 empty] | Resumed Drilling & Drilled 17-1/2" Hole From 1927m to 1956m. Reamed twice at connection. Meanwhile Precautionary added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [5 empty] | 19 | [8 empty] | NOTE: Obsvd Drilling Break while Drilling @ 1952m & ROP increased to 19 m/hr. Stopped Drilling & Flow Checked - Well Static. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 9 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2368 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/19/15 06:00 | 04/20/15 03:30 |  |  | 1956 | 2070 | [8 empty] | Drilled 17-1/2" Hole From 1956m to 2070m. Reamed twice at each connection. Obsvd Dynamic Losses @ 2 - 3 bbl/hr. Added Fine/Medium LCM in Active System. Lost Total 50 BBL. | Productive
hvjg | gvjgv | vjhv | 0 | 04/20/15 03:30 | 04/20/15 04:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/20/15 04:00 | 04/20/15 06:00 |  |  | 2070 | 2081 | [8 empty] | Resumed Drilling & Drilled 17-1/2" Hole From 2070m to 2081m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 50 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2418 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/20/15 06:00 | 04/20/15 10:00 |  |  | 2081 | 2099 | [8 empty] | Drilled 17-1/2" hole from 2081m to 2099m. Pumped 40 bbls HV Pill @ 2095 during Drilling. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/20/15 10:00 | 04/20/15 11:00 | [12 empty] | Circ. / Cleaned hole. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 04/20/15 11:00 | 04/20/15 12:00 | [12 empty] | P/Back to 2070m. Recorded Totco Deviation Survey on Slickline - Found Miss Run. | Productive
hvjg | gvjgv | vjhv | 0 | 04/20/15 12:00 | 04/20/15 13:30 | [12 empty] | Conducted Wiper Trip to 1900m. Hole Condition - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 04/20/15 13:30 | 04/20/15 14:30 | [12 empty] | Recorded Totco Deviation Survey on Slickline @ 2070m Bit Depth (0.75° @ 2055m). | Productive
hvjg | gvjgv | vjhv | 17.5 | 04/20/15 14:30 | 04/21/15 02:00 |  |  | 2099 | 2156 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 2099m to 2156m. Reamed twice at each connection.Obsvd Dynamic Losses @ 4 - 5 bbl/hr. Added Fine/Medium LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | 04/21/15 02:00 | 04/21/15 02:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/21/15 02:30 | 04/21/15 06:00 |  |  | 2156 | 2180 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 2156m to 2180m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 131 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2549 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/21/15 06:00 | 04/21/15 18:30 |  |  | 2180 | 2235 | [8 empty] | Drilled 17-1/2" hole from 2180m to 2235m. Reamed twice at each connection. Obsvd Dynamic Losses @ 8 - 10 bbl/hr. Pumped 44 bbl LCM Pill of 40 PPB @ 2211m during Drilling & Added Fine / Medium LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | 04/21/15 18:30 | 04/21/15 20:30 | [12 empty] | Circ. / Bottom Up for Geological Sample.
hvjg | gvjgv | vjhv | 17.5 | 04/21/15 20:30 | 04/21/15 22:00 |  |  | 2235 | 2242 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 2235m to 2242m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 04/21/15 22:00 | 04/21/15 22:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 17.5 | 04/21/15 22:30 | 04/22/15 01:00 |  |  | 2242 | 2251 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 2242m to 2251m. | Productive
hvjg | gvjgv | vjhv | 0 | 04/22/15 01:00 | 04/22/15 02:00 | [12 empty] | Circ. / Bottom Up for Geological Sample.
hvjg | gvjgv | vjhv | 17.5 | 04/22/15 02:00 | 04/22/15 06:00 |  |  | 2251 | 2267 | [8 empty] | Resumed Drilling & Drilled 17-1/2" hole from 2251m to 2267m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 200 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2749 BBL
hvjg | gvjgv | vjhv | 17.5 | 04/22/15 06:00 | 04/22/15 12:00 |  |  | 2267 | 2285 | [8 empty] | Drilled 17-1/2" hole from 2267m to 2285m. Obsvd Dynamic Losses @ 8 - 10 bbl/hr. Pumped 35 bbl LCM Pill of 40 PPB @ 2279m during Drilling & Added Fine / Medium LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | 04/22/15 12:00 | 04/22/15 16:00 | [12 empty] | Circ / Bottom Up for Geological Sample & Confirmed Section TD (2285m). Cleaned Hole till shakers clean. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 04/22/15 16:00 | 04/23/15 05:00 | [12 empty] | POOH 17-1/2" PDC Bit with Performance BHA from 2285m to Surface. Drained Mud Motor. Removed Sleeve Stab & Installed Blank Sleeve.L/Down PBL Sub + Mud Motor + Bit. During POOH Monitored Well thru Trip Tank - Lost 25 bbl Mud.
hvjg | gvjgv | vjhv | 0 | 04/23/15 05:00 | 04/23/15 06:00 | [12 empty] | M/Up 17-1/2" Tricone Bit (RR) with S/Stabs & 11" DCs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 125 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2874 BBL
hvjg | gvjgv | vjhv | 0 | 04/23/15 06:00 | 04/23/15 16:00 | [12 empty] | RIH with 17-1/2" Tricone Bit (RR) down to 2259m. Meanwhile Monitored well thru Trip Tank - Lost 22 bbl mud.
hvjg | gvjgv | vjhv | 0 | 04/23/15 16:00 | 04/23/15 16:30 | [12 empty] | Washed down from 2259 m to 2285m.
hvjg | gvjgv | vjhv | 0 | 04/23/15 16:30 | 04/23/15 20:00 | [12 empty] | Pumped 50 bbl Hi-Vis LCM Pill of 60 PPB concentration. Circ / Cleaned hole prior to POOH for Logging. Lost 16 bbl during Circulation. Flow checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 04/23/15 20:00 | 04/24/15 06:00 | [12 empty] | POOH from 2285m to Surface. While POOH Flow Checked at BHA - Ok. L/Down Jar + 01 S/Stab + Bit Sub + Bit & R/Back BHA. Meanwhile Monitored well thru Trip Tank - Lost 11 bbl mud.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 49 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2923 BBL
hvjg | gvjgv | vjhv | 0 | 04/24/15 06:00 | 04/24/15 14:00 | [12 empty] | Held Pre-Job Safety Meeting. R/Up SLB W/Line Gears. M/Up & RIH SLB W/Line Tools & Recorded W/Line Logs as per Program. R/Down SLB W/Line Gears. Meanwhile Monitored Well thru Trip Tank - Lost 4 bbl Mud. | Productive
hvjg | gvjgv | vjhv | 0 | 04/24/15 14:00 | 04/24/15 17:00 | [12 empty] | M/Up & RIH 17-1/2" Tricone Bit (RR) with Packed Hole BHA to 518m.
hvjg | gvjgv | vjhv | 0 | 04/24/15 17:00 | 04/24/15 18:30 | [12 empty] | Slipped & Cut 32m Drilling Line. | Productive
hvjg | gvjgv | vjhv | 0 | 04/24/15 18:30 | 04/25/15 02:00 | [12 empty] | RIH from 518m to Bottom. Reamed / Washed Down Last Stand. While RIH Tagged Compression at 718m - 720m, 2257m - 2259m. Reamed / Washed Down & Cleared the same. Lost 17 bbl Mud during Trip. No Fill observed at bottom. | Productive
hvjg | gvjgv | vjhv | 0 | 04/25/15 02:00 | 04/25/15 06:00 | [12 empty] | Circ / Swept Hole with 40 bbl Hi-Vis Pill till shakers clean. Lost 16 bbl Mud.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 37 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2960 BBL
hvjg | gvjgv | vjhv | 0 | 04/25/15 06:00 | 04/25/15 06:30 | [12 empty] | Flow Checked - Ok. Dropped Totco.
hvjg | gvjgv | vjhv | 0 | 04/25/15 06:30 | 04/25/15 17:30 | [12 empty] | POOH 17-1/2" Bit with Packed BHA to surface. Recovered Totco (Dev: 0.50° @ 2278m). L/Down Jar + 1 x 9.5" DC + 2 x 11" DCs + 3 x Stabs + 17.5" Bit. Lost 11 bbl Mud during POOH.
hvjg | gvjgv | vjhv | 0 | 04/25/15 17:30 | 04/25/15 18:00 | [12 empty] | Retrieved Wear Bushing.
hvjg | gvjgv | vjhv | 0 | 04/25/15 18:00 | 04/25/15 21:30 | [12 empty] | Changed 5" Pipe Rams to 13-3/8" Casing Rams. Time Lost as Bonnet Bolts Not Seating Properly.
hvjg | gvjgv | vjhv | 0 | 04/25/15 21:30 | 04/25/15 22:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 04/25/15 22:00 | 04/25/15 23:00 | [12 empty] | M/Up Test Plug Assy & Set inside 21-1/4" Casing Head Housing & Press Tested BOP Bonnet Seals @ 1000 psi - Ok. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 04/25/15 23:00 | 04/26/15 00:00 | [12 empty] | R/Up Wellserve Casing Running Gears. Changed TDS Links & Prepared Rig Floor to RIH 13-3/8" Casing. | Productive
hvjg | gvjgv | vjhv | 0 | 04/26/15 00:00 | 04/26/15 06:00 | [12 empty] | Held Pre-Job Safety Meeting. RIH 13-3/8" Casing [72 ppf, P-110, Vam Top] to 241m. Installed F/Shoe + F/Collar + Baffle Collar + Centralizers & Filled Up Casing as per Tally. M/Up Circ. Head, Dropped 1.75" OD Ball & Converted Autofill Valves to NRVs @ 500 psi after RIH 8 Joints (98m). Lost 4 bbl Mud while RIH Casing. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 20 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2980 BBL
hvjg | gvjgv | vjhv | 0 | 04/26/15 06:00 | 04/26/15 06:00 | [12 empty] | RIH 13-3/8" Casing from 241m to 2265m. Tagged Compression at 2265m - Washed Down from 2265m to 2284m. While RIH Installed ICP + 2 Stage DV Tool + Centralizers & Filled Up Casing as per Tally. Lost 7 bbl Mud During RIH Casing.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 7 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2987 BBL
hvjg | gvjgv | vjhv | 0 | 04/27/15 06:00 | 04/27/15 15:00 | [12 empty] | Circ / Conditioned Mud. Meanwhile R/Down Wellserve Casing Running Gears, R/Up SLB Cementing Head (Pre-Loaded with 1st Stage Shut-Off Plug) and Prepared Spacer & Mix Fluid for 1st Stage Cementing. | Productive
hvjg | gvjgv | vjhv | 0 | 04/27/15 15:00 | 04/27/15 23:00 | [12 empty] | Held PJSM. Press Tested SLB Lines to 3000 psi - Ok. Pumped 100 BBL Mud Push II (Spacer) of 11.5 PPG thru Rig Pump. Opened Cementing Head and Dropped 1st Stage Bypass Plug. Switched Over to SLB Unit. Fly Mixed & Pumped 990 BBL Lead Slurry of 12.5 PPG followed by 100 BBL Batch Mixed Tail Slurry of 15.8 PPG. Dropped 1st Stage Shut-Off Plug. Pumped 20 BBL Water thru SLB Unit. Switched Over to Rig Pump & Displaced Cement Slurry initially by 700 BBL Mud of 1.32 S.G & 377.5 BBL Mud of 1.065 S.G (Total Displacement = 1097.5 BBL) and Bumped Plug at 1400 psi. Switched Over to SLB Unit & Increased Press to 2000 psi to Inflate "ICP". Bled Off Press - No Back Flow. Received Full Returns During Cement Job & Dumped 37 BBL Spacer. | Productive
hvjg | gvjgv | vjhv | 0 | 04/27/15 23:00 | 04/28/15 02:30 | [12 empty] | Opened Cementing Head & Dropped Opening Bomb - Waited for 15 min & then applied Press thru SLB Unit. Obsvd Stage Collar Ports Opened at 800 psi & Mud Returns on Shakers.Resumed Circ thru Rig Pump Dumped 50 BBL Spacer + 230 BBL Neat Cement + 70 BBL Contaminated Spacer / Cement / Mud. Cont'd Circ - Meanwhile Prepared Spacer & Mix Fluid for 2nd Stage Cement Job. | Productive
hvjg | gvjgv | vjhv | 0 | 04/28/15 02:30 | 04/28/15 05:00 | [12 empty] | Pumped 80 BBL Mud Push II (Spacer) of 11.5 PPG thru Rig Pump. Switched to SLB Unit and Pumped 100 BBL Cement Slurry of 13.5 PPG. Dropped Closing Plug and Pumped 20 BBL Water thru SLB Unit. Switched Over to Rig Pump & Displaced Cement Slurry with 220 BBL Mud of 1.065 S.G. Switched Over to SLB Unit - Pumped 8.5 BBL Mud & Bumped Plug at 1700 psi (Total Displacement = 248.5 BBL). Held Press for 10 min. Bled Off Press - No Back Flow. R/Down SLB Lines. | Productive
hvjg | gvjgv | vjhv | 0 | 04/28/15 05:00 | 04/28/15 06:00 | [12 empty] | Preparing to Lift BOP Stack for Setting Casing Hanger.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2987 BBL
hvjg | gvjgv | vjhv | 0 | 04/28/15 06:00 | 04/28/15 21:00 | [12 empty] | WOC. Worked on well head. R/Down Choke Lines & Kill Lines to minimise BOP stack Weight. Failed to hoist complete BOP stack with hoisting system, Broke loose Spacer spool from Pipe rams. Failed to hoist Pipe Rams & Annular BOP together. Made alternate arrangements to hang BOP. Hanged Annular with BOP hoisting winch (Total BOP stack weight = 50 Tons). | Non Productive
hvjg | gvjgv | vjhv | 0 | 04/28/15 21:00 | [13 empty] | Hanged Pipe Ram BOP+Mud Cross+ Spacer spool. Set 13-3/8" casing slips & set back Pipe ram Stack.
hvjg | gvjgv | vjhv | 0 |  | 04/28/15 05:00 | [12 empty] | R/Down cement head- X-Over- & Casing spider. Rough cut & L/Down extra csg pipe, Rig down annular Bop; Pipe Ram Bop; Mud cross & spacer spool.
hvjg | gvjgv | vjhv | 0 | 04/28/15 05:00 | 04/28/15 06:00 | [12 empty] | Final cut 13-3/8" casing in progress.
hvjg | gvjgv | vjhv | 17.5 | [14 empty] | Total Downhole Fluid Loss in 17-1/2" Hole: 2987 BBL
hvjg | gvjgv | vjhv | 0 | 04/29/15 06:00 | 04/29/15 10:00 | [12 empty] | Final cut 13-3/8" casing & N/UP 21-1/4" 5k x 13-5/8" 10k Casing Head Spool. Pressure tested Cavity, bottom seal @ 2400 psi & top seal @ 2300 psi for 10 minutes, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 04/29/15 10:00 | 04/29/15 13:00 | [12 empty] | N/Up 13-5/8" 10k Spacer spool & BOP Stack, hoisted with BOP trollies, OK.
hvjg | gvjgv | vjhv | 0 | 04/29/15 13:00 | 04/30/15 01:00 | [12 empty] | P/U Bell Nipple & tried to install it, Bell Nipple not adjusted to BOP Stack height. L/D & performed fabrication work on the same.
hvjg | gvjgv | vjhv | 0 | 04/30/15 01:00 | 04/30/15 05:30 | [12 empty] | Fabrication work on Bell Nipple meanwhile R/Up BOP Hydraulic hoses. Function tested Rams, Annular, Kill & Choke HCR, OK.
hvjg | gvjgv | vjhv | 0 | 04/30/15 05:30 | 04/30/15 06:00 | [12 empty] | P/U & installed Bell Nipple, placed Flowline (in progress).
hvjg | gvjgv | vjhv | 0 | 04/30/15 06:00 | 04/30/15 08:00 | [12 empty] | Installed Bell Nipple, connected Flowline & Trip tank fill up line.
hvjg | gvjgv | vjhv | 0 | 04/30/15 08:00 | 04/30/15 09:00 | [12 empty] | P/U & M/U 13-5/8" Test Plug Assembly.
hvjg | gvjgv | vjhv | 0 | 04/30/15 09:00 | 04/30/15 11:00 | [12 empty] | Attempted to RIH Test Plug Assembly, observed obstruction through 13-5/8" Annular BOP. Open/close Annular several times but no success. RIH 5" HWDP stand below Test Plug Assembly & pushes it through Annular BOP.
hvjg | gvjgv | vjhv | 0 | 04/30/15 11:00 | 04/30/15 18:00 | [12 empty] | Pressure tested Annular @ 200 Psi low & 3000 Psi high, OK. Pressure tested Pipe Rams, Kill Line, Choke Line, Choke Manifold & IBOP @ 300 Psi low & 7000 Psi high, OK. Pressure tested Stand pipe Manifold @ 4000 Psi, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 04/30/15 18:00 | 04/30/15 19:30 | [12 empty] | M/U 13-3/8" Cup Tester on 5" HWDP & pressure tested Well Head @ 2000 Psi, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 04/30/15 19:30 | 04/30/15 21:30 | [12 empty] | L/D Test Plug Assembly & installed wear bushing.
hvjg | gvjgv | vjhv | 0 | 04/30/15 21:30 | 05/01/15 05:00 | [12 empty] | RIH & POOH BHA single by single, L/D for inspection. | Non Productive
hvjg | gvjgv | vjhv | 0 | 05/01/15 05:00 | 05/01/15 06:00 | [12 empty] | P/U & M/U 12-1/4" Tricone Bit (used) & RIH to 37m on Slick BHA (in progress).
hvjg | gvjgv | vjhv | 0 | 05/01/15 06:00 | 05/01/15 11:00 | [12 empty] | Continued RIH 12-1/4" Bit from 37m to 489m.
hvjg | gvjgv | vjhv | 0 | 05/01/15 11:00 | 05/01/15 13:00 |  |  | 503.36 | 504 | [8 empty] | M/U TDS, washed down & COC from 489m to top of Stage Collar @ 503.36m. Drilled out Stage Collar from 503.36m to 504m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/01/15 13:00 | 05/02/15 00:30 | [12 empty] | RIH from 504m to 829m, P/U & RIH 5" DPs single by single from 829m to 1828m. Continued RIH & tagged top of cement @ 2218m with 10 ton WOB.
hvjg | gvjgv | vjhv | 0 | 05/02/15 00:30 | 05/02/15 04:00 | [12 empty] | Circulated two & half cycles to homogenize mud. | Productive
hvjg | gvjgv | vjhv | 0 | 05/02/15 04:00 | 05/02/15 04:30 | [12 empty] | Pressure tested casing @ 2000 Psi for 10 min, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 05/02/15 04:30 | 05/02/15 06:00 | [12 empty] | COC from 2218m to 2241m.
hvjg | gvjgv | vjhv | 0 | 05/02/15 06:00 | 05/02/15 09:30 |  |  | 2241 | 2254 | [8 empty] | COC from 2241m to 2254m & Drilled out Baffle Collar from 2243.3m to 2244.1m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/02/15 09:30 | 05/02/15 10:00 | [12 empty] | Circ / Conditioned Mud to 1.25 S.G.
hvjg | gvjgv | vjhv | 0 | 05/02/15 10:00 | 05/02/15 10:30 | [12 empty] | Press Tested 13-3/8" Casing @ 2000 Psi for 10 min - OK.
hvjg | gvjgv | vjhv | 0 | 05/02/15 10:30 | 05/02/15 13:00 |  |  | 2254 | 2278 | [8 empty] | COC from 2254m to 2278m & Drilled out F/Collar from 2256.3m to 2257.1m. Observed pH increased to 13.5 & Mud Hydrolysed - Mud Wt. dropped from 1.25 S.G to 1.18 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | 05/02/15 13:00 | 05/03/15 06:00 | [12 empty] | Circ / Conditioned Mud & Increased Mud Wt. from 1.18 S.G to 1.26 S.G.
hvjg | gvjgv | vjhv | 0 | [14 empty] | NOTE: Conducted Kick Drill @ 1205 hrs - Observed No Response from Rig Crew. | Productive
hvjg | gvjgv | vjhv | 0 | 05/03/15 06:00 | 05/03/15 12:30 | [12 empty] | Circ / Conditioned Mud & Increased Mud Wt. from 1.26 S.G to 1.31 S.G.
hvjg | gvjgv | vjhv | 0 | 05/03/15 12:30 | 05/03/15 13:00 | [12 empty] | Press Tested 13-3/8" Casing @ 2000 Psi for 10 min - OK.
hvjg | gvjgv | vjhv | 0 | 05/03/15 13:00 | 05/03/15 15:00 |  |  | 2278 | 2285 | [8 empty] | COC from 2278m to 2285m. Drilled out F/Shoe at 2284m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/03/15 15:00 | 05/03/15 16:30 |  |  | 2285 | 2288 | [8 empty] | Commenced 3rd Stage Drilling & Drilled 12-1/4" hole from 2285m to 2288m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/03/15 16:30 | 05/03/15 18:00 | [12 empty] | Circ / Cleaned Hole & Balanced Mud Column. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 05/03/15 18:00 | 05/03/15 19:30 | [12 empty] | P/Back inside Casing Shoe. Held PJSM. R/Up & Press Tested SLB Lines to 2500 PSI. Conducted FIT to 1.60 S.G EMW (Surface Press = 940 PSI). R/Down SLB Lines.
hvjg | gvjgv | vjhv | 12.25 | 05/03/15 19:30 | 05/04/15 06:00 |  |  | 2288 | 2313 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 2288m to 2313m. Meanwhile Conditioned Mud & Increased Mud Wt. to 1.35 S.G. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/04/15 06:00 | 05/04/15 14:00 |  |  | 2313 | 2330 | [8 empty] | Drilled 12-1/4" hole from 2313m to 2330m. Reamed twice at connection. Observed Partial Losses while Drilling @ 2327m. Lost 18 BBL Mud. | Productive
hvjg | gvjgv | vjhv | 0 | 05/04/15 14:00 | 05/04/15 16:00 | [12 empty] | Circ / Cleaned Hole. Flow Checked - Ok. Pumped Slug. | Productive
hvjg | gvjgv | vjhv | 0 | 05/04/15 16:00 | 05/04/15 23:30 | [12 empty] | POOH 12-1/4" Bit to Surface. L/Down Jar + Bit Sub + Junk Sub + Bit. Received 0.5 kg Metallic Junk. While POOH Flow Checked at 1000m & BHA. Lost 7 BBL Mud During Trip.
hvjg | gvjgv | vjhv | 0 | 05/04/15 23:30 | 05/05/15 00:00 | [12 empty] | Fuction Tested BOP Koomey Unit as per API RP 53 - Found Ok.
hvjg | gvjgv | vjhv | 0 | 05/05/15 00:00 | 05/05/15 00:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 05/05/15 00:30 | 05/05/15 02:00 | [12 empty] | L/Down 6 x 9-1/2" DCs from Racks.
hvjg | gvjgv | vjhv | 0 | 05/05/15 02:00 | 05/05/15 05:30 | [12 empty] | P/Up & M/Up 8" Sperry Mud Motor + PBL Sub + S/Stab with 12-1/4" Tricone Bit. Checked Mud Motor Bearing Gap. Shallow Tested Mud Motor @ 600 GPM & 870 PSI and Operated PBL Sub by activating & deactivating through sequence of 2-1/2" & 2 x 1-3/4" balls at 750 PSI & 2200 PSI Respectively. P/Back to Surface. L/Down Tricone Bit & Recovered dropped balls from PBL Sub.
hvjg | gvjgv | vjhv | 0 | 05/05/15 05:30 | 05/05/15 06:00 | [12 empty] | M/Up New 12-1/4" PDC Bit with Performance BHA & RIH to 12m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | NOTE: Conducted Kick Drill @ 1130 hrs - Observed No Response from Rig Crew. Conducted Fire Drill @ 1440 hrs - Complete Failure. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 25 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 25 BBL
hvjg | gvjgv | vjhv | 0 | 05/05/15 06:00 | 05/05/15 14:30 | [12 empty] | RIH 12-1/4" PDC Bit with Performance BHA from 12m to 2269m. While RIH F/Up String after every 10 Stands & Lost 15 BBL Mud.
hvjg | gvjgv | vjhv | 0 | 05/05/15 14:30 | 05/05/15 15:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 05/05/15 15:00 | 05/05/15 18:00 | [12 empty] | Repaired Drawworks for Height Positioning. | Non Productive
hvjg | gvjgv | vjhv | 0 | 05/05/15 18:00 | 05/05/15 20:30 | [12 empty] | RIH to bottom & Reamed / Wash Down Last Stand. Observed Well Flowing & M.W Out : 1.31 S.G. Circ / BTM Up & Homogenized Mud Column - Returns Surfaced in Batches from 1.31 S.G to 1.36 S.G. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/05/15 20:30 | 05/06/15 06:00 |  |  | 2330 | 2387 | [8 empty] | Recorded SCR. Resume Drilling & Drilled 12-1/4" Hole from 2330m to 2387m. Reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 15 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/06/15 06:00 | 05/06/15 16:00 |  |  | 2387 | 2467 | [8 empty] | Drilled 12-1/4" Hole from 2387m to 2467m. Reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | 05/06/15 16:00 | 05/06/15 17:30 | [12 empty] | Circ / Cleaned Hole. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 05/06/15 17:30 | 05/06/15 18:30 | [12 empty] | Recorded Totco Deviation Survey on Slickline (0.5° @ 2445m). | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/06/15 18:30 | 05/07/15 06:00 | [12 empty] | Resumed Drilling & Drilled 12-1/4" Hole from 2467m to 2554.m. Reamed twice at each connection & Swept 20 BBL Hi-Vis Pill @ 2527m. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/07/15 06:00 | 05/08/15 01:00 |  |  | 2554 | 2707 | [8 empty] | Drilled 12-1/4" Hole from 2554m to 2707m. Reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | 05/08/15 01:00 | 05/08/15 02:30 | [12 empty] | Circ / Swept Hole with 25 BBL Hi-Vis Pill. Flow Checked - Ok. P/Back to 2696m.
hvjg | gvjgv | vjhv | 0 | 05/08/15 02:30 | 05/08/15 03:30 | [12 empty] | Recorded Totco Deviation Survey on Slickline (1.5° @ 2682m). | Productive
hvjg | gvjgv | vjhv | 0 | 05/08/15 03:30 | 05/08/15 06:00 | [12 empty] | POOH from 2696m to 2269m (Inside 13-3/8" CSG Shoe). While POOH Observed Tight Spots @ 2626m, 2620m, 2595m, 2545m & 2459m - Cleared the same with Reciprocation. RIH to 2411m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/08/15 06:00 | 05/08/15 08:00 | [12 empty] | RIH from 2411m to BTM @ 2707m. Reamed / Washed Down Last Stand. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/08/15 08:00 | 05/09/15 06:00 |  |  | 2707 | 2841 | [8 empty] | Drilled 12-1/4" Hole from 2707m to 2841m. Reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/09/15 06:00 | 05/09/15 06:00 |  |  | 2841 | 2954 | [8 empty] | Drilled 12-1/4" Hole from 2841m to 2954m, reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/10/15 06:00 | 05/10/15 11:30 |  |  | 2954 | 2982 | [8 empty] | Drilled 12-1/4" Hole from 2954m to 2982m. Pumped 20 bbls Hi-Vis pill & circulated out. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/10/15 11:30 | 05/11/15 06:00 |  |  | 2982 | 3068 | [8 empty] | Resumed Drilling 12-1/4" Hole from 2982m to 3068m, reamed twice at each connection. Meanwhile added Fine LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/11/15 06:00 | 05/11/15 18:30 |  |  | 3068 | 3125 | [8 empty] | Drilled 12-1/4" Hole from 3068m to 3125m, reamed twice at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | 05/11/15 18:30 | 05/11/15 20:30 | [12 empty] | Pumped 25 bbls Hi-Vis pill & circulated out till surfaced. | Productive
hvjg | gvjgv | vjhv | 0 | 05/11/15 20:30 | 05/11/15 22:00 | [12 empty] | P/Back one single & disconnected TDS. Conducted Totco Deviation Survey & recorded 4.0 degree @ 3100m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/11/15 22:00 | 05/11/15 22:30 | [12 empty] | Pumped 25 bbls slug prior to wiper trip. | Productive
hvjg | gvjgv | vjhv | 0 | 05/11/15 22:30 | 05/12/15 04:00 | [12 empty] | POOH from 3115m to 2961m, observed tight spots @ 2963m, 2961m & 2960m. RIH to 2978m & pumped out of Hole from 2978m to 2668m, back reamed from 2978m to 2953m & 2923m to 2896m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/12/15 04:00 | 05/12/15 06:00 | [12 empty] | RIH from 2668m to 3067m hole free, filled string, reamed & washed down second last stand from 3067m to 3096m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/12/15 06:00 | 05/12/15 09:00 | [12 empty] | Reamed & washed down last stand from 3096m to 3125m, observed obstructions & hole packing @ 3102m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/12/15 09:00 | 05/12/15 09:30 | [12 empty] | Pumped 25 bbls Hi-Vis pill at bottom, observed mechanical cavings continuously at shakers. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/12/15 09:30 | 05/13/15 06:00 |  |  | 3125 | 3186 | [8 empty] | Drilled 12-1/4" Hole from 3125m to 3186m, reamed twice at each connection. Meanwhile increased MW from 1.35 SG to 1.40 SG. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/13/15 06:00 | 05/13/15 13:30 |  |  | 3186 | 3210 | [8 empty] | Drilled 12-1/4" Hole from 3186m to 3210m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/13/15 13:30 | 05/13/15 16:30 | [12 empty] | Pumped 30 bbls Hi-Vis pill & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 05/13/15 16:30 | 05/13/15 18:30 | [12 empty] | P/Back one single & disconnected TDS. RIH Totco on Slick line, Slick line jumped out of sheave @ 3068m. Installed clamp & P/U Slick line to place inside sheave. Recorded deviation 4.0 degree @ 3068m.
hvjg | gvjgv | vjhv | 0 | 05/13/15 18:30 | 05/13/15 23:00 | [12 empty] | Flow checked, Well static. POOH from 3201m to 2637m, observed tight spots @ 3072m, 3042m, 3031m, 3010m, 2881m & 2681m with max. O/Pull of 6-10 Tons.
hvjg | gvjgv | vjhv | 0 | 05/13/15 23:00 | 05/14/15 04:30 | [12 empty] | POOH from 2629m, observed obstruction. Worked on string by reciprocation but no success. Connected TDS & pumped out of hole from 2629m to 2269m inside 13-3/8" casing shoe. Back reamed from 2629m to 2525m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/14/15 04:30 | 05/14/15 05:00 | [12 empty] | Flow checked @ 13-3/8" casing shoe, Well static. Pumped 25 bbls slug. | Productive
hvjg | gvjgv | vjhv | 0 | 05/14/15 05:00 | 05/14/15 06:00 | [12 empty] | Continued POOH from 2269m to 1870m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/14/15 06:00 | 05/14/15 13:00 | [12 empty] | POOH from 1870m to top of BHA @ 245m. Flow checked, Well static. Continued POOH from 245m to surface.
hvjg | gvjgv | vjhv | 0 | 05/14/15 13:00 | 05/14/15 14:00 | [12 empty] | B/U Bit, Mud Motor & PBL Sub, checked bearings gap for Mud Motor, found OK.
hvjg | gvjgv | vjhv | 0 | 05/14/15 14:00 | 05/14/15 14:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 05/14/15 14:30 | 05/14/15 20:00 | [12 empty] | P/U & M/U 13-5/8" Test Plug Assembly. Attempted to RIH Test Plug Assembly, observed obstruction through 13-5/8" Annular BOP. RIH 5" HWDP stand below Test Plug Assembly & attempted several times, no success. Pushed it through Annular BOP & retrieved wear bushing.
hvjg | gvjgv | vjhv | 0 | 05/14/15 20:00 | 05/14/15 22:00 | [12 empty] | Pressure tested Annular @ 300 Psi low & 3500 Psi high, OK. Pressure tested Pipe Rams, Blind Rams, Kill Line, Choke Line, Choke Manifold & IBOP @ 300 Psi low & 7000 Psi high, OK. Pressure tested Stand pipe Manifold @ 4000 Psi, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 05/14/15 22:00 | 05/15/15 00:00 | [12 empty] | L/D Test Plug Assembly & installed wear bushing.
hvjg | gvjgv | vjhv | 0 | 05/15/15 00:00 | 05/15/15 05:00 | [12 empty] | P/U & M/U 8" HLB Mud Motor on 12-1/4" Tri-cone Bit (used), set adjustable Bend Housing to 1.15 degree. P/U & M/U 8" Hange -Off Collar (HOC) & inserted MWD tool inside it, took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 600 GPM & 890 Psi, OK.
hvjg | gvjgv | vjhv | 0 | 05/15/15 05:00 | 05/15/15 06:00 | [12 empty] | P/U & M/U 12-1/4" PDC Bit (new) & RIH to 106m on Directional BHA (in progress).
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/15/15 06:00 | 05/15/15 14:00 | [12 empty] | RIH 12-1/4" Bit from 106m to 1879m with Directional BHA, Rig Power shut down intermittently for two hours.
hvjg | gvjgv | vjhv | 0 | 05/15/15 14:00 | 05/15/15 18:00 | [12 empty] | Observed Draw works "B" Motor malfunctioned, worked on Draw works.
hvjg | gvjgv | vjhv | 0 | 05/15/15 18:00 | 05/16/15 04:30 | [12 empty] | P/U 5" DPs from Catwalk single by single & M/U 40 stands through Mouse hole, racked back the same. Meanwhile made circulatin through circulation head & increased MW from 1.40 SG to 1.50 SG.
hvjg | gvjgv | vjhv | 0 | 05/16/15 04:30 | 05/16/15 06:00 | [12 empty] | Cut & Slip 108 ft of Drill Line (in progress). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/16/15 06:00 | 05/16/15 07:00 | [12 empty] | Cut & Slip 108 ft of Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | 05/16/15 07:00 | 05/16/15 08:30 | [12 empty] | Worked on Draw works, observed toggle valve leaking air, replaced with new one. Function tested Draw works, OK. | Non Productive
hvjg | gvjgv | vjhv | 0 | 05/16/15 08:30 | 05/16/15 09:00 | [12 empty] | MWD Engineer installed Depth encoder sensor on Draw works.
hvjg | gvjgv | vjhv | 0 | 05/16/15 09:00 | 05/16/15 18:00 | [12 empty] | Resumed RIH from 1879m to 2245m, tested MWD inside 13-3/8"casing - 1 degree inc. RIH from 2245m to 3104m, connected TDS & took MWD surveys after every three stands. | Productive
hvjg | gvjgv | vjhv | 0 | 05/16/15 18:00 | 05/17/15 00:00 | [12 empty] | RIH from 3104m to 3158m, observed obstruction @ 3158m. Reamed & washed down from 3158m to 3188m, observed obstruction, Hi-torque & Rotary stalled @ 3188m. Pumped 25 bbls Hi-Vis pill & circulated out, meanwhile reamed & washed down to 3189m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/17/15 00:00 | 05/17/15 06:00 | [12 empty] | Reamed & washed down from 3189m to Bottom @ 3210m. Observed Hi-torque, Hole Packed-Off & Rotary stalled @ 3200m, 3204m & 3208m (max trq 3 - 13 Kft-lbs). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/17/15 06:00 | 05/17/15 07:00 | [12 empty] | Took MWD survey & recorded SCR. Pumped 45 bbls Hi-Vis pill & circulated out. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/17/15 07:00 | 05/17/15 13:30 |  |  | 3210 | 3214 | [8 empty] | Tried to break the bit at low parameters, no progress. Applied WOB to 16 Tons, observed no differential pressure. Drilled 12-1/4" Hole from 3210m to 3214m in the process, pumped 72 bbls detergent pill, no progress. | Productive
hvjg | gvjgv | vjhv | 0 | 05/17/15 13:30 | 05/17/15 18:30 | [12 empty] | POOH from 3214m to 2275m inside 13-3/8" casing shoe. Observed tight spots @ 3135m, 3030m & 2821m, cleared by reciprocation.
hvjg | gvjgv | vjhv | 0 | 05/17/15 18:30 | 05/17/15 19:00 | [12 empty] | Flow checked, Well static. Pumped 25 bls slug. | Productive
hvjg | gvjgv | vjhv | 0 | 05/17/15 19:00 | 05/18/15 00:00 | [12 empty] | POOH from 2275m to 254m @ Top of BHA.
hvjg | gvjgv | vjhv | 0 | 05/18/15 00:00 | 05/18/15 00:30 | [12 empty] | Flow checked @ Top of BHA, Well static.
hvjg | gvjgv | vjhv | 0 | 05/18/15 00:30 | 05/18/15 02:00 | [12 empty] | POOH from 254m to surface, L/D Jar & PBL sub.
hvjg | gvjgv | vjhv | 0 | 05/18/15 02:00 | 05/18/15 04:30 | [12 empty] | Drained Mud Motor & broke out PDC Bit. P/U & M/U Tri-con Bit, performed Shallow Mud Motor test @ 600 GPM & 990 Psi pressure. P/U Mud Motor with bit in Bell Nipple, observed bit rotating @ 100 GPM. Adjusted Bend Housing to 0 degree & broke out Sleeve Stab. Checked Mud Motor thrust bearing play 5.7mm, L/D Mud Motor.
hvjg | gvjgv | vjhv | 0 | 05/18/15 04:30 | 05/18/15 06:00 | [12 empty] | P/U & M/U 12-1/4" PDC Bit RR on Pendulum Assembly & RIH down to 41m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/18/15 06:00 | 05/18/15 18:00 | [12 empty] | Continued RIH from 41m to 3179m, observed compression of max. 5 tons @ 2855m.
hvjg | gvjgv | vjhv | 0 | 05/18/15 18:00 | 05/18/15 20:00 | [12 empty] | Reamed & washed down last two stands from 3179m to 3214m, observed compression of max. 10 tons @ 3206m. Pumped 50 bbls Detergent pill prior to tag bottom @ 3214m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/18/15 20:00 | 05/19/15 06:00 |  |  | 3214 | 3224 | [8 empty] | Drilled 12-1/4" Hole from 3214m to 3224m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/19/15 06:00 | 05/19/15 13:00 |  |  | 3224 | 3237 | [8 empty] | Drilled 12-1/4" Hole from 3224m to 3237m. Reamed before connection, observed Hi-torque & tight hole @ 3225m, 3217m (max. O/pull 8 tons). Conducted MWD survey @ 3235m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/19/15 13:00 | 05/19/15 13:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 12.25 | 05/19/15 13:30 | 05/20/15 06:00 |  |  | 3237 | 3266 | [8 empty] | Drilled 12-1/4" Hole from 3237m to 3266m. Reamed before connection & conducted MWD survey @ 3265m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/20/15 06:00 | 05/20/15 21:00 |  |  | 3266 | 3294 | [8 empty] | Drilled 12-1/4" Hole from 3266m to 3294m. Reamed & conducted MWD survey @ 3293m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/20/15 21:00 | 05/20/15 23:00 | [12 empty] | Pumped 55 bbls Hi-Vis pill & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 05/20/15 23:00 | 05/20/15 23:30 | [12 empty] | Flow checked, Well static.
hvjg | gvjgv | vjhv | 0 | 05/20/15 23:30 | 05/21/15 00:00 | [12 empty] | POOH from 3293m to 3180m, obsevred tight spots @ 3276m, 3271m, 3263m & 3261m (max. O/pull 6-9 tons).
hvjg | gvjgv | vjhv | 0 | 05/21/15 00:00 | 05/21/15 01:00 | [12 empty] | Observed swabbing effect in the hole @ 3180m, run back to bottom.
hvjg | gvjgv | vjhv | 0 | 05/21/15 01:00 | 05/21/15 02:30 | [12 empty] | Circulated hole for bottom up, observed MW in/out 1.50 S.G. Flow checked, Well static. | Productive
hvjg | gvjgv | vjhv | 0 | 05/21/15 02:30 | 05/21/15 06:00 | [12 empty] | POOH from 3263m to 2790m, observed tight spots @ 3261m, 3244m, 3241m & 3087m (max. O/pull 6-9 tons). Pumped out of hole from 3263m to 3237m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Kamlial Formation has been marked @ 3270m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/21/15 06:00 | 05/21/15 08:00 | [12 empty] | POOH from 2790m to 2257m inside 13-3/8" casing shoe.
hvjg | gvjgv | vjhv | 0 | 05/21/15 08:00 | 05/21/15 08:30 | [12 empty] | Flow checked, Well static.
hvjg | gvjgv | vjhv | 0 | 05/21/15 08:30 | 05/21/15 13:00 | [12 empty] | Continued POOH from 2257m to top of BHA @ 240m.
hvjg | gvjgv | vjhv | 0 | 05/21/15 13:00 | 05/21/15 13:30 | [12 empty] | Flow checked, Well static.
hvjg | gvjgv | vjhv | 0 | 05/21/15 13:30 | 05/21/15 17:30 | [12 empty] | Continued POOH from 240m to surface. L/D BHA single by single for inspection, broke bit & HOC, L/D the same. | Non Productive
hvjg | gvjgv | vjhv | 0 | 05/21/15 17:30 | 05/21/15 20:30 | [12 empty] | P/U & M/U 8" HLB Mud Motor on 12-1/4" Tri-cone Bit (used), set adjustable Bend Housing to 1.15 degree. P/U & M/U 8" Hange -Off Collar (HOC) & inserted MWD tool inside it, took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 600 GPM & 1080 Psi, OK.
hvjg | gvjgv | vjhv | 0 | 05/21/15 20:30 | 05/21/15 23:00 | [12 empty] | Tried to M/U New 12-1/4" PDC bit, observed manufacturing fault in Bit Breaker, repaired the same. | Non Productive
hvjg | gvjgv | vjhv | 0 | 05/21/15 23:00 | 05/22/15 06:00 | [12 empty] | P/U & M/U 12-1/4" PDC Bit (new) & RIH to 1135m on Directional BHA by picking up 8" DCs single by single. Filled the string @ BHA & after 15 DP stands, RIH in progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/22/15 06:00 | 05/22/15 14:00 | [12 empty] | Continued RIH from 1135m to 3247m, observed obstruction @ 3233m, 3242m & 3248m (max. compression 10-16 tons).
hvjg | gvjgv | vjhv | 0 | 05/22/15 14:00 | 05/22/15 15:30 | [12 empty] | Washed & reamed down from 3247m to 3294m, obsevred tight spot @ 3284m (max. compression 10 tons). Pumped 50 bbls Hi-Vis pill. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/22/15 15:30 | 05/22/15 18:30 |  |  | 3294 | 3303 | [8 empty] | Drilled 12-1/4" Hole from 3294m to 3303m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/22/15 18:30 | 05/22/15 19:30 | [12 empty] | Reamed before connection to clear the tight spots. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/22/15 19:30 | 05/23/15 06:00 |  |  | 3303 | 3332 | [8 empty] | Drilled 12-1/4" Hole from 3303m to 3332m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/23/15 06:00 | 05/23/15 07:00 | [12 empty] | Reamed before connection & took MWD survey @ 3330m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/23/15 07:00 | 05/23/15 16:30 |  |  | 3332 | 3361 | [8 empty] | Drilled 12-1/4" Hole from 3332m to 3361m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/23/15 16:30 | 05/23/15 17:00 | [12 empty] | Reamed before connection & took MWD survey @ 3360m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/23/15 17:00 | 05/24/15 00:30 |  |  | 3361 | 3389 | [8 empty] | Drilled 12-1/4" Hole from 3361m to 3389m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/24/15 00:30 | 05/24/15 02:00 | [12 empty] | Pumped 50 bbls Hi-Vis pill @ 3387m & string out. Reamed before connection & observed tight spots @ 3386m, 3380m & 3375m, cleared the same, circulated till Hi-Vis surfaced. Took MWD survey @ 3389m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/24/15 02:00 | 05/24/15 06:00 |  |  | 3389 | 3398 | [8 empty] | Drilled 12-1/4" Hole from 3389m to 3398m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/24/15 06:00 | 05/24/15 12:00 |  |  | 3398 | 3417 | [8 empty] | Drilled 12-1/4" Hole from 3398m to 3417m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/24/15 12:00 | 05/24/15 13:30 | [12 empty] | Reamed before connection & took MWD survey @ 3416m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/24/15 13:30 | 05/24/15 20:00 |  |  | 3417 | 3446 | [8 empty] | Drilled 12-1/4" Hole from 3417m to 3446m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/24/15 20:00 | 05/24/15 21:30 | [12 empty] | Reamed before connection, pumped 50 bbls Hi-Vis pill & circulated out. Took MWD survey @ 3444m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/24/15 21:30 | 05/25/15 03:30 |  |  | 3446 | 3475 | [8 empty] | Drilled 12-1/4" Hole from 3446m to 3475m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/25/15 03:30 | 05/25/15 05:30 | [12 empty] | Reamed before connection & observed tight spots @ 3474m, 3468m, 3458m & 3453m (max. O/pull 6-12 tons), cleared the same. Took MWD survey @ 3473m & recorded SCR. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/25/15 05:30 | 05/25/15 06:00 |  |  | 3475 | 3478 | [8 empty] | Drilled 12-1/4" Hole from 3475m to 3478m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/25/15 06:00 | 05/25/15 12:00 |  |  | 3478 | 3503 | [8 empty] | Drilled 12-1/4" Hole from 3478m to 3503m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/25/15 12:00 | 05/25/15 13:00 | [12 empty] | Reamed before connection, observed tight spot @ 3494m & 3502m, cleared the same. Took MWD survey @ 3502m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/25/15 13:00 | 05/25/15 17:30 |  |  | 3503 | 3532 | [8 empty] | Drilled 12-1/4" Hole from 3503m to 3532m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/25/15 17:30 | 05/25/15 18:30 | [12 empty] | Reamed before connection, observed tight spot @ 3517m, 3515m, 3512m & 3505m, cleared the same. Took MWD survey @ 3530m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/25/15 18:30 | 05/26/15 01:00 |  |  | 3532 | 3560 | [8 empty] | Drilled 12-1/4" Hole from 3532m to 3560m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/26/15 01:00 | 05/26/15 02:30 | [12 empty] | Reamed before connection & observed tight spots @ 3556m & 3536m (max. O/pull 6-9 tons), cleared the same. Took MWD survey @ 3558m & recorded SCR. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/26/15 02:30 | 05/26/15 06:00 |  |  | 3560 | 3582 | [8 empty] | Drilled 12-1/4" Hole from 3560m to 3582m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Murree Formation has been marked @ 3563m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/26/15 06:00 | 05/26/15 08:00 |  |  | 3582 | 3589 | [8 empty] | Drilled 12-1/4" Hole from 3582m to 3589m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/26/15 08:00 | 05/26/15 09:30 | [12 empty] | Reamed before connection, observed tight spot @ 3574m & 3564m, cleared the same. Took MWD survey @ 3587m. | Productive
hvjg | gvjgv | vjhv | 0 | 05/26/15 09:30 | 05/26/15 12:00 | [12 empty] | Pumped 50 bbls Hi-Vis pill & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 05/26/15 12:00 | 05/26/15 13:30 | [12 empty] | Flow checked, Well static. POOH from 3589m to 3389m, observed tight spots @ 3553m, 3550m, 3519m, 3505m, 3427m & 3383m.
hvjg | gvjgv | vjhv | 0 | 05/26/15 13:30 | 05/26/15 21:00 | [12 empty] | Pumped out of Hole from 3389m to 3103m. Resumed POOH from 3103m to 2275m (inside 13-3/8" casing shoe). | Productive
hvjg | gvjgv | vjhv | 0 | 05/26/15 21:00 | 05/26/15 22:00 | [12 empty] | Serviced TDS. Flow checked, Well static.
hvjg | gvjgv | vjhv | 0 | 05/26/15 22:00 | 05/27/15 00:30 | [12 empty] | RIH from 2275m to 2933m hole free.
hvjg | gvjgv | vjhv | 0 | 05/27/15 00:30 | 05/27/15 01:00 | [12 empty] | Replaced Draw works Guide Roller line meanwhile made circulation.
hvjg | gvjgv | vjhv | 0 | 05/27/15 01:00 | 05/27/15 06:00 | [12 empty] | RIH from 2933m to 3368m. Observed obstruction @ 3368m, washed down to clear the obstruction, compression 5-9 tons. Washed & Reamed down from 3374m to 3378m, Rotary stalled @ 3378m, max. Trq 6-13 Kft-lbs, compression 5-7 tons. Washed & Reamed down to 3390m (RIH in progress). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 05/27/15 06:00 | 05/27/15 07:30 | [12 empty] | Continued RIH from 3390m to 3560m hole free.
hvjg | gvjgv | vjhv | 0 | 05/27/15 07:30 | 05/27/15 09:00 | [12 empty] | Washed & Reamed down last stand from 3560m to 3589m. Pumped 45 bbls Hi-Vis pill & String out. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/27/15 09:00 | 05/27/15 16:00 |  |  | 3589 | 3617 | [8 empty] | Drilled 12-1/4" Hole from 3589m to 3617m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/27/15 16:00 | 05/27/15 17:00 | [12 empty] | Reamed twice at connection & took MWD survey @ 3615m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/27/15 17:00 | 05/27/15 23:00 |  |  | 3617 | 3645 | [8 empty] | Drilled 12-1/4" Hole from 3617m to 3645m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/27/15 23:00 | 05/28/15 00:00 | [12 empty] | Reamed twice at connection & took MWD survey @ 3644m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/28/15 00:00 | 05/28/15 06:00 |  |  | 3645 | 3674 | [8 empty] | Drilled 12-1/4" Hole from 3645m to 3674m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/28/15 06:00 | 05/28/15 13:30 |  |  | 3674 | 3703 | [8 empty] | Drilled 12-1/4" Hole from 3674m to 3703m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/28/15 13:30 | 05/28/15 14:00 | [12 empty] | Circulated & Coducted MWD survey @ 3683m. Recorded 4.93 degrees inclination. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/28/15 14:00 | 05/28/15 15:30 |  |  | 3703 | 3709 | [8 empty] | Drilled 12-1/4" Hole from 3703m to 3709m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/28/15 15:30 | 05/28/15 18:00 |  |  | 3709 | 3711 | [8 empty] | Drilled 12-1/4" Hole from 3709m to 3711m in Slide mode, to drop well angle. Stopped slide as frequent Hang Off observed. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/28/15 18:00 | 05/29/15 02:00 |  |  | 3711 | 3731 | [8 empty] | Drilled 12-1/4" Hole from 3711m to 3731m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/29/15 02:00 | 05/29/15 03:00 | [12 empty] | Reamed before connection & took MWD survey @ 3713m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/29/15 03:00 | 05/29/15 06:00 |  |  | 3731 | 3742 | [8 empty] | Drilled 12-1/4" Hole from 3731m to 3742m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/29/15 06:00 | 05/29/15 08:00 |  |  | 3742 | 3747 | [8 empty] | Drilled 12-1/4" Hole from 3742m to 3747m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/29/15 08:00 | 05/29/15 12:30 |  |  | 3747 | 3752 | [8 empty] | Drilled 12-1/4" Hole from 3747m to 3752m in Slide mode, to drop well angle. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/29/15 12:30 | 05/29/15 14:30 |  |  | 3752 | 3760 | [8 empty] | Drilled 12-1/4" Hole from 3752m to 3760m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/29/15 14:30 | 05/29/15 15:30 | [12 empty] | Reamed before connection & conducted MWD survey @ 3740m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/29/15 15:30 | 05/30/15 06:00 |  |  | 3760 | 3787 | [8 empty] | Drilled 12-1/4" Hole from 3760m to 3787m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/30/15 06:00 | 05/30/15 07:00 |  |  | 3787 | 3788 | [8 empty] | Drilled 12-1/4" Hole from 3787m to 3788m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/30/15 07:00 | 05/30/15 08:30 | [12 empty] | Reamed before connection & conducted MWD survey @ 3770m. Inclination recorded 4.43 degrees. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/30/15 08:30 | 05/31/15 00:00 |  |  | 3788 | 3817 | [8 empty] | Drilled 12-1/4" Hole from 3788m to 3817m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/31/15 00:00 | 05/31/15 01:00 | [12 empty] | Reamed before connection & took MWD survey @ 3795m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/31/15 01:00 | 05/31/15 06:00 |  |  | 3817 | 3829 | [8 empty] | Pumped 50 bbls Hi-Vis pill & string out. Drilled 12-1/4" Hole from 3817m to 3829m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 05/31/15 06:00 | 05/31/15 15:30 |  |  | 3829 | 3845 | [8 empty] | Drilled 12-1/4" Hole from 3829m to 3845m in Rotary & Slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/31/15 15:30 | 05/31/15 16:30 | [12 empty] | Reamed before connection & took MWD survey @ 3825m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/31/15 16:30 | 05/31/15 18:00 |  |  | 3845 | 3850 | [8 empty] | Drilled 12-1/4" Hole from 3845m to 3850m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 05/31/15 18:00 | 05/31/15 18:30 | [12 empty] | Observed Drilling Break @ 3850m. Flow checked, Well Static. | Productive
hvjg | gvjgv | vjhv | 12.25 | 05/31/15 18:30 | 06/01/15 06:00 |  |  | 3850 | 3874 | [8 empty] | Drilled 12-1/4" Hole from 3850m to 3874m in Rotary & Slide mode. While P/U String, observed tight spots @ 3855m, 3862m, 3863m & 3865m (max Trq 5-12 Kft-Lbs) in slide sections. Back reamed to clear the tight spots, checked string free with / without rotation. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/01/15 06:00 | 06/01/15 14:00 |  |  | 3874 | 3903 | [8 empty] | Drilled 12-1/4" Hole from 3874m to 3903 m in Rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 06/01/15 14:00 | 06/01/15 15:30 | [12 empty] | Reamed before connection & conducted MWD survey @ 3899 m.Dev 1.34 deg. Reamed several times from 3884 m to 3900 m prior to survey. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/01/15 15:30 | 06/01/15 20:00 |  |  | 3903 | 3915 | [8 empty] | Drilled 12-1/4" Hole from 3903 m to 3915 m in Rotary mode. During drilling incresed Mud Sp.Gr from 1.61 to 1.63. | Productive
hvjg | gvjgv | vjhv | 0 | 06/01/15 20:00 | 06/02/15 00:00 | [12 empty] | Pumped & Circulated out 50 bbls HV pill prior to POOH for BHA | Productive
hvjg | gvjgv | vjhv | 0 | 06/02/15 00:00 | 06/02/15 00:30 | [12 empty] | Recorded MWD survey & SCR | Productive
hvjg | gvjgv | vjhv | 0 | 06/02/15 00:30 | 06/02/15 06:00 | [12 empty] | Flow checked. Well Statick. Resumed POOH.Observed tigh hole.POHfrom 3902 m to 3646m with circulation & back reaming | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | nm
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/02/15 06:00 | 06/02/15 15:00 | [12 empty] | POOH from 3646m to 2961m. Back Reamed from 3646m to 3333m & Pumped Out up to 3184m - then free onwards. | Productive
hvjg | gvjgv | vjhv | 0 | 06/02/15 15:00 | 06/03/15 06:00 | [12 empty] | Rectifying Draw works fault. R/Up Safety Valve & Circulating Head on Drill String and Circ. at Low GPM. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | At 1515 hrs, During POOH (after racking back DP stand, Driller was lowering TDS) Complete Power Out occurred - Engines Shut Off. Restarted Engines. No power at Draw works. TDS at 26m. Rectifying Draw works Fault . | Productive
hvjg | gvjgv | vjhv | 0 | 06/03/15 06:00 | 06/03/15 06:00 | [12 empty] | Attempted to rectify Draw works fault - Meanwhile Circ. at low GPM.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/04/15 06:00 | 06/04/15 12:00 | [12 empty] | Attempted to rectify Draw works fault. Uploaded Parameters - Fault rectified. Function tested D/Works & Rotary Table - OK. Meanwhile Circ.
hvjg | gvjgv | vjhv | 0 | 06/04/15 12:00 | 06/04/15 15:00 | [12 empty] | Flow Checked. Pumped Slug & POOH to 2070m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/04/15 15:00 | 06/04/15 16:30 | [12 empty] | During POOH at 2070 Complete Power Shut Down occurred - Engines were Shut Off. Started Engines & restored Electric Supply. Found D/Works not working. Worked on D/Works & rectified fault again.
hvjg | gvjgv | vjhv | 0 | 06/04/15 16:30 | 06/05/15 02:30 | [12 empty] | Resumed POOH from 2070m to Surface. While POOH Flow Checked at BHA & L/Down 12 x 5" HWDPs + 12 x 8" DCs for Inspection. Also L/Down Jar + PBL Sub + MWD Tool + Mud Motor + Bit. | Non Productive
hvjg | gvjgv | vjhv | 0 | 06/05/15 02:30 | 06/05/15 06:00 | [12 empty] | P/Up & M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside CHS. Flushed BOP Stack with water. Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 500 psi Low & 4000 psi - OK. Press Tested Upper Pipe Rams + IBOP + HCR Valves @ 500 psi Low - Ok. Observed Test Pump Bleed-Off Valve Leaking while Press Testing Upper Pipe Rams @ 7000 psi. Repairing Bleed-Off Valve. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/05/15 06:00 | 06/05/15 10:30 | [12 empty] | Repaired Test Pump - Changed Bleed-Off & Suction Valves. Press Tested Upper Pipe Rams + Lower pipe Ram + Blind Shear Rams + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 500 psi Low & 7000 psi High Press - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 06/05/15 10:30 | 06/05/15 11:30 | [12 empty] | L/Down Test Plug Assy & Set Wear Bushing inside CHS.
hvjg | gvjgv | vjhv | 0 | 06/05/15 11:30 | 06/05/15 13:30 | [12 empty] | M/Up 12-1/4" PDC Bit + New Mud Motor (Zero bend) with 12-1/8" Sleeve Stab + 12-1/8" S. Stab + NMDC + New Hang Off Sub & RIH to 22m. Found MWD tool not seating properly inside Hang Off sub.
hvjg | gvjgv | vjhv | 0 | 06/05/15 13:30 | 06/05/15 15:00 | [12 empty] | L/Down NMDC & HOS. RIH Used Hang Off Collar & new PBL Sub. Shallow Tested Motor & MWD @ 535 GPM & 1100 psi - OK.
hvjg | gvjgv | vjhv | 0 | 06/05/15 15:00 | 06/05/15 16:00 | [12 empty] | Function Tested PBL Sub by Activating & De-Activating @ 250 psi & 2600 psi respectively - Found OK. Recovered balls from PBL Sub.
hvjg | gvjgv | vjhv | 0 | 06/05/15 16:00 | 06/06/15 02:00 | [12 empty] | RIH to 2251m. While RIH P/Up new BHA from Cat Walk single by single.
hvjg | gvjgv | vjhv | 0 | 06/06/15 02:00 | 06/06/15 03:00 | [12 empty] | Slipped & Cut 88 ft Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | 06/06/15 03:00 | 06/06/15 04:00 | [12 empty] | Serviced TDS. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors.
hvjg | gvjgv | vjhv | 0 | 06/06/15 04:00 | 06/06/15 06:00 | [12 empty] | Resumed RIH from 2251m to 2736m. While RIH Tagged Compression & Reamed Down from 2506m to 2508m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/06/15 06:00 | 06/06/15 08:00 | [12 empty] | RIH from 2736m to 3306m.
hvjg | gvjgv | vjhv | 0 | 06/06/15 08:00 | 06/07/15 06:00 | [12 empty] | Tagged Compression & Reamed Down from 3306m to 3658m. Very Slow Reaming after 3500m - Observed High Erratic Torque & Rotaty Stalled Intermittently. Meanwhile Increased M.W to 1.70 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/07/15 06:00 | 06/07/15 06:00 | [12 empty] | Continued reaming from 3658m to 3851m - Observed Frequent Pack Off & M. Motor Stalling. Swept 30 BBL Hi-Vis Pills @ 3693 & 3826m. Recorded MWD Check-Shot Surveys at connections. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/08/15 06:00 | 06/08/15 11:30 | [12 empty] | Cont. Reaming from 3851m to 3878m - Observed String Packed Off - SPP shoot up to 4000 psi. No Rotation / Movement. Shut off one pump. | Productive
hvjg | gvjgv | vjhv | 0 | 06/08/15 11:30 | 06/08/15 12:00 | [12 empty] | Worked on String - Circ. with one pump & released String Torque. Applied Max 50 Ton O/Pull. Activated jar - String got free after Jarring. Switched on 2nd pump - Normal circ pressure. | Productive
hvjg | gvjgv | vjhv | 0 | 06/08/15 12:00 | 06/08/15 21:30 | [12 empty] | Resumed Reaming & Reamed down to 3915m. Pumped 40 BBL Hi-Vis Pill @ 3878m & 3904m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/08/15 21:30 | 06/09/15 06:00 |  |  | 3915 | 3926 | [8 empty] | Recorded SCR & resumed Drilling after Bit Breaking. Drilled 12-1/4" hole from 3915m to 3926m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/09/15 06:00 | 06/09/15 06:00 |  |  | 3926 | 3959 | [8 empty] | Cont'd Drilling & Drilled 12-1/4" hole from 3926m to 3959m. Reamed twice & Recorded MWD Survey at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/10/15 06:00 | 06/10/15 09:00 |  |  | 3959 | 3962 | [8 empty] | Cont'd Drilling & Drilled 12-1/4" hole from 3959m to 3962m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/10/15 09:00 | 06/10/15 12:30 | [12 empty] | Reamed drilled section. Circ. out 40 bbl Hi-Vis Pill. Observed no Cavings / Cuttings on Bottom up. Recorded MWD Survey. | Productive
hvjg | gvjgv | vjhv | 0 | 06/10/15 12:30 | 06/10/15 13:30 | [12 empty] | Spotted 100 bbl of 2% concentration Lube Pill at Bottom. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 06/10/15 13:30 | 06/11/15 05:00 | [12 empty] | POOH to Surface. While POOH Flow Checked @ 13-3/8" Casing Shoe & BHA. L/Down Jar + S/Stabs + PBL Sub + MWD + Mud Motor + Bit.
hvjg | gvjgv | vjhv | 0 | 06/11/15 05:00 | 06/11/15 06:00 | [12 empty] | M/Up & RIH New 12-1/4" PDC Bit with New HOC (MWD Tool) to 18m. Now Preparing to Fucntion Test MWD.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/11/15 06:00 | 06/11/15 06:30 | [12 empty] | Function Tested MWD Tool - OK - 600 psi @ 510 GPM.
hvjg | gvjgv | vjhv | 0 | 06/11/15 06:30 | 06/11/15 23:30 | [12 empty] | Resumed RIH with new PDC bit + MWD+ PBL Sub down to 3838m. Tagged Compression & Reamed / Washed Down from 3838m to Bottom. Filled String after every 10 Stands while RIH. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/11/15 23:30 | 06/12/15 06:00 |  |  | 3962 | 3967 | [8 empty] | Recorded SCR. Resumed Drilling & Drilled 12-1/4" hole from 3962m to 3967m. Adjusted Parameters to increase ROP - No Success. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/12/15 06:00 | 06/12/15 06:00 |  |  | 3967 | 4001 | [8 empty] | Drilled 12-1/4" hole from 3967m to 4001m. Reamed twice at connection & Recorded MWD Survey @ 3972m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/13/15 06:00 | 06/13/15 20:00 |  |  | 4001 | 4049 | [8 empty] | Drilled 12-1/4" hole from 4001m to 4049m. Reamed twice at connection & Recorded MWD Survey @ 4013m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | High Drilling Torque Observed @ 4001m, 4005m - 4006m, 4014m, 4029m & 4031m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | High Reaming Torque Observed @ 4001m, 4010m, 4013m, 4036m, 4038m & 4048m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/14/15 06:00 | 06/14/15 17:00 |  |  | 4049 | 4105 | [8 empty] | Drilled 12-1/4" hole from 4049m to 4105m. P/Up for Reaming - TDS Controls tripped at VFD. | Productive
hvjg | gvjgv | vjhv | 0 | 06/14/15 17:00 | 06/14/15 17:30 | [12 empty] | Worked on TDS / VFD.
hvjg | gvjgv | vjhv | 12.25 | 06/14/15 17:30 | 06/15/15 06:00 |  |  | 4105 | 4155 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 4105 m to 4155m. Reamed twice & Recorded MWD Survey at each conection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/15/15 06:00 | 06/15/15 15:00 |  |  | 4155 | 4191 | [8 empty] | Drilled 12-1/4" hole from 4155m to 4191m. Meanwhile Increased M.W to 1.72 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | 06/15/15 15:00 | 06/15/15 16:00 | [12 empty] | Reamed drilled stand. | Productive
hvjg | gvjgv | vjhv | 0 | 06/15/15 16:00 | 06/15/15 18:30 | [12 empty] | Pumped 30 bbl of Hi-Vis Pill & Circulated out. Recorded MWD Survey. | Productive
hvjg | gvjgv | vjhv | 0 | 06/15/15 18:30 | 06/15/15 19:30 | [12 empty] | Soptted 100 bbl 2% Lube Concentration Pill at Bottom. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 06/15/15 19:30 | 06/16/15 02:00 | [12 empty] | POOH from 4191m to 3791m for Wiper Trip - Observed Tight Hole. Reamed Back from 4191m to 3848m & P/Out from 3848m to 3819m. Obsvd Mechanical Cavings on Shakers at Bottom Up. Meanwhile Increased M.W. | Productive
hvjg | gvjgv | vjhv | 0 | 06/16/15 02:00 | 06/16/15 06:00 | [12 empty] | RIH from 3791m to 4134m. Reamed / Washed Down from 3906m - 3934m & 3959m - 4077m and Cleared Tight Spots. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tight Hole Observed during POOH - Unable to POOH even with Pump Out. Maximum Over Pull applied 25 Tons. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/16/15 06:00 | 06/16/15 07:30 | [12 empty] | RIH free from 4134m to 4180m & Reamed Down from 4180m to 4191m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/16/15 07:30 | 06/17/15 06:00 |  |  |  | 4222 | [8 empty] | M/Up New Connection & resumed Drilling. Drilled 12-1/4" hole from 4191m down to 4222m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Kick Drill while Drilling @ 4219m - Secured Well in 01 min. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/17/15 06:00 | 06/17/15 20:00 |  |  | 4222 | 4236 | [8 empty] | Drilled 12-1/4" hole from 4222m to 4236m. Recorded MWD Survey @ 4212m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/17/15 20:00 | 06/17/15 21:00 | [12 empty] | Circ / Cleaned hole prior to Short Trip. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 06/17/15 21:00 | 06/17/15 22:00 | [12 empty] | Conducted Short Trip from 4236m to 4162m - Observed Tight Spots @ 4213m, 4183m & 4180m - Cleared with Reciprocation.
hvjg | gvjgv | vjhv | 12.25 | 06/17/15 22:00 | 06/18/15 06:00 |  |  | 4236 | 4245 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 4236m to 4245m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/18/15 06:00 | 06/19/15 05:00 |  |  | 4245 | 4281 | [8 empty] | Drilled 12-1/4" hole from 4245m to 4281m. Reamed twice at each Connection. Recorded MWD Survey @ 4244m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/19/15 05:00 | 06/19/15 06:00 | [12 empty] | Stopped Drilling. Pumped 40 bbl Hi-Vis Pill & Circulating it out. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/19/15 06:00 | 06/19/15 07:30 | [12 empty] | Circ / Cleaned Hole. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 06/19/15 07:30 | 06/19/15 08:30 | [12 empty] | Recorded MWD Survey. Spotted 100 bbl Lube Pill at bottom - Under displaced by 04 bbl. | Productive
hvjg | gvjgv | vjhv | 0 | 06/19/15 08:30 | 06/20/15 04:00 | [12 empty] | Resumed POOH from 4281 m to Surface. While POOH Flow Checked at BHA & L/Down 12 x 5" HWDPs + 13 x 8" DCs for Inspection. Also L/Down Jar + PBL Sub + MWD Tool. Observed Bit Breaker Broken/Cracked while Breaking Out Bit - L/Down together Bit + Bit Sub. | Non Productive
hvjg | gvjgv | vjhv | 0 | 06/20/15 04:00 | 06/20/15 06:00 | [12 empty] | P/Up & M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside CHS. Press Test Annular BOP is in Progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Observed Swabbing at 4113m & 4048m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Pumped Out from 4113m to 4092m & 4048m to 4020m to avoid Swabbing. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/20/15 06:00 | 06/20/15 10:00 | [12 empty] | Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + Lower Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 7000 psi High Press - OK. Function Tested Blind Rams. Retrieved Test Plug & Set Wear Bushing inside CHS. Meanwhile Repaired Cracked Bit Breaker. | Non Productive
hvjg | gvjgv | vjhv | 0 | 06/20/15 10:00 | 06/20/15 10:30 | [12 empty] | Repaired Cracked Bit Breaker. | Non Productive
hvjg | gvjgv | vjhv | 0 | 06/20/15 10:30 | 06/20/15 14:00 | [12 empty] | M/Up 12-1/4" PDC Bit (12 RR) + B.Sub + HOC + New PBL Sub + 1 x 8" DC. Attempted to Break loose Bit from Bit Sub - No Success - PDC Bit Shank slipped inside PDC Breaker Plate. L/Down PDC Bit (12 RR) along with Bit Sub. | Non Productive
hvjg | gvjgv | vjhv | 0 | 06/20/15 14:00 | 06/20/15 16:00 | [12 empty] | M/Up New 12-1/4" PDC Bit + B.Sub + F.Valve + New HOC/MWD + NewPBL Sub + 1 x 8" DC. Function tested MWD - 780 psi @ 550 GPM - OK. Function Tested PBL Sub - Found Leakage from Ports with Pumps Off. L/Down PBL Sub. | Productive
hvjg | gvjgv | vjhv | 0 | 06/20/15 16:00 | 06/21/15 06:00 | [12 empty] | RIH with New 12-1/4" PDC Bit to 2934m. While RIH P/Up New Inspected BHA single by single from Cat Walk & Filled Up String after every 10 Stands
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/21/15 06:00 | 06/21/15 07:30 | [12 empty] | Continue RIH from 2934m to 3274m. While RIH Filled Up String after every 10 Stands.
hvjg | gvjgv | vjhv | 0 | 06/21/15 07:30 | 06/21/15 09:00 | [12 empty] | Worked on TDS - Changed Gear Oil Filters. Meanwhile Circulated during Repair Work. | Productive
hvjg | gvjgv | vjhv | 0 | 06/21/15 09:00 | 06/21/15 13:00 | [12 empty] | Resumed RIH from 3274m to 4242m. While RIH Filled Up String after every 10 Stands.
hvjg | gvjgv | vjhv | 0 | 06/21/15 13:00 | 06/21/15 15:00 | [12 empty] | M/Up TDS. Washed Down from 4242m to 4262m & Reamed Down from 4262m to 4281m (Hard Reaming from 4267m to 4281m). | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/21/15 15:00 | 06/22/15 06:00 |  |  | 4281 | 4305 | [8 empty] | Reasumed Drilling after Bit Breaking & Drilled 12-1/4" hole from 4281m to 4305m. Reamed Twice at connection & Recorded MWD Survey @ 4293m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/22/15 06:00 | 06/22/15 06:00 |  |  | 4305 | 4334 | [8 empty] | Continued Drilling & Drilled 12-1/4" hole from 4305m to 4334m. Reamed Twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/23/15 06:00 | 06/23/15 06:00 |  |  | 4334 | 4372 | [8 empty] | Continued Drilling & Drilled 12-1/4" hole from 4334m to 4372m. Reamed Twice at connection & Recorded MWD Survey @ 4324m & 4355m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/24/15 06:00 | 06/24/15 06:00 |  |  | 4372 | 4406 | [8 empty] | Continued Drilling & Drilled 12-1/4" hole from 4372m to 4406m. Reamed Twice at connection & Recorded MWD Survey @ 4381m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tentative Top Of Sakesar Formation @ 4401m MD / 4398.5m TVD
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/25/15 06:00 | 06/25/15 13:30 |  |  | 4406 | 4416 | [8 empty] | Continued Drilling & Drilled 12-1/4" hole from 4406m to 4416m. Reamed Twice & Recorded MWD Survey @ 4405m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/25/15 13:30 | 06/25/15 16:30 | [12 empty] | Circ / Swept hole with 40 bbl Hi-Vis Pill till Shakers clean. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 06/25/15 16:30 | 06/26/15 02:00 | [12 empty] | POOH from 4416m to 2276m (inside 13-3/8" Casing Shoe). While POOH Observed Tight Spot @ 4043m - Back Reamed from 4043m to 4040m & Cleared Tight Spot. | Productive
hvjg | gvjgv | vjhv | 0 | 06/26/15 02:00 | 06/26/15 05:00 | [12 empty] | Worked on TDS - Changed TDS Gear Oil. Meanwhile monitored Well thru Trip Tank.
hvjg | gvjgv | vjhv | 0 | 06/26/15 05:00 | 06/26/15 06:00 | [12 empty] | Slipped & Cut 96' Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 0 | 06/26/15 06:00 | 06/26/15 14:30 | [12 empty] | RIH from 2276m (13-3/8" Casing Shoe) to bottom (4416m). Reamed / Washed Down Last Stand - No Fill at bottom. While RIH Filled Up String after every 10 Stands. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/26/15 14:30 | 06/27/15 06:00 |  |  | 4416 | 4440 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 4416m to 4440m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/27/15 06:00 | 06/27/15 06:00 |  |  | 4440 | 4484 | [8 empty] | Cont' Drilling & Drilled 12-1/4" Hole from 4440m to 4484m. Reamed Twice & Recorded MWD Survey at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tentative Top Of Nammal Formation @ 4455m MD / 4452.54m TVD
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/28/15 06:00 | 06/28/15 10:30 |  |  | 4484 | 4494 | [8 empty] | Cont' Drilling & Drilled 12-1/4" Hole from 4484m to 4494m. | Productive
hvjg | gvjgv | vjhv | 0 | 06/28/15 10:30 | 06/28/15 15:30 | [12 empty] | NPT. Observed leakage in TDS Wash Pipe. POOH from 4494m to 4357m. Installed Circ Head & Circ @ 1000 psi & Rotated String @ 10 RPM. Replaced TDS Wash Pipe & Press Tested the same @ 4000 psi - OK. Reamed down from 4357m to 4494m. | Productive
hvjg | gvjgv | vjhv | 12.25 | 06/28/15 15:30 | 06/29/15 06:00 |  |  | 4494 | 4521 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 4494 m to 4521m. Reamed Twice & Recorded MWD Survey at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/29/15 06:00 | 06/29/15 06:00 |  |  | 4521 | 4577 | [8 empty] | Cont' Drilling & Drilled 12-1/4" hole from 4521m to 4577m. Reamed Twice & Recorded MWD Survey at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 06/30/15 06:00 | 06/30/15 06:00 |  |  | 4577 | 4622 | [8 empty] | Cont' Drilling & Drilled 12-1/4" hole from 4577m to 4622m. Reamed Twice & Recorded MWD Survey at each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 07/01/15 06:00 | 07/01/15 06:00 |  |  | 4622 | 4658 | [8 empty] | Cont' Drilling & Drilled 12-1/4" hole from 4622m to 4658m. Reamed Twice & Recorded MWD Survey at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Kick Drill while Drilling @ 4636m. Secured well in 01.15 Minutes | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tentative Top Of Patala Formation @ 4622m MD / 4619.53m TVD
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 07/02/15 06:00 | 07/02/15 06:00 |  |  | 4658 | 4699 | [8 empty] | Cont' Drilling & Drilled 12-1/4" hole from 4658m to 4699m. Reamed Twice & Recorded MWD Survey at connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducteded Fire Drill while Drilling @ 4666 m. Fire Controlled in 02.15 Minutes | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 40 BBL
hvjg | gvjgv | vjhv | 12.25 | 07/03/15 06:00 | 07/03/15 07:00 |  |  | 4699 | 4699.7 | [8 empty] | Cont' Drilling & Drilled 12-1/4" hole from 4699m to 4699.7m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/03/15 07:00 | 07/03/15 09:30 | [12 empty] | Observed Partial Losses - Stopped Drilling. P/Up String & reduced GPM. Thereafter observed Complete Loss & Level Out of Sight - Lost 51 bbl Mud. Prepared 115 bbl LCM Pill of 100 PPB (40 PPB CaCO3 (F) + 10 PPB Chek Loss + 10 PPB Kwik Seal (F) + 20 PPB Mica (F) + 20 PPB Mica (M)) - Meanwhile attempted to fill hole with 43 bbl Pit Water thru Trip Tank. Pumped 115 bbl LCM & Displaced with 267 bbl Mud. Observed Returns Surfaced during Displacement after Pumping 84 bbl Mud. Flow Checked - Ok. Total Loss 293 bbl. | Productive
hvjg | gvjgv | vjhv | 0 | 07/03/15 09:30 | 07/03/15 19:00 | [12 empty] | POOH to 13-3/8" Casing Shoe - Lost 60 bbl Mud.
hvjg | gvjgv | vjhv | 0 | 07/03/15 19:00 | 07/03/15 23:30 | [12 empty] | Circ / Btm Up at low GPM to check for losses - No Loss. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 07/03/15 23:30 | 07/04/15 06:00 | [12 empty] | POOH from 13-3/8" Casing Shoe to 140m. While POOH Flow Checked at BHA & L/Down 12 x 5" HWDPs Single by Single for Inspection. | Non Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 195 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 115 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 43 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total: 353 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 393 BBL
hvjg | gvjgv | vjhv | 0 | 07/04/15 06:00 | 07/04/15 09:30 | [12 empty] | Cont' POOH from 140m to Surface & L/Down Bit (Bit Condition Green. One Nozzle partially Plugged). While POOH L/Down All DCs + Bit Sub + S.Stabs for Inspection & also L/Down Jar + MWD Tool. Hole Static. | Non Productive
hvjg | gvjgv | vjhv | 0 | 07/04/15 09:30 | 07/04/15 10:30 | [12 empty] | Serviced TDS. Meanwhile Inspected Bit Sub + S. Stab.
hvjg | gvjgv | vjhv | 0 | 07/04/15 10:30 | 07/05/15 06:00 | [12 empty] | M/Up & RIH Same PDC Bit (13RR1) with F/Valve to 4330m. While RIH P/Up Inspected BHA from Pipe Racks & added New Jar. Filled Up String after every 10 Stands. Lost 22 bbl Mud during Trip.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 22 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total: 22 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 415 BBL
hvjg | gvjgv | vjhv | 0 | 07/05/15 06:00 | 07/05/15 09:00 | [12 empty] | Cont' RIH from 4330m to Bottom. Reamed / Washed Down Last Stand - Observed 1.5m Hole Fill. Circ @ Bottom for 30 Min - No Loss. Meanwhile added 20 PPB LCM in Active System. | Productive
hvjg | gvjgv | vjhv | 12.25 | 07/05/15 09:00 | 07/05/15 11:00 |  |  | 4699.77 | 4702 | [8 empty] | Resumed Drilling & Drilled 12-1/4" hole from 4699.77m to 4702m - Observed Partial Lossed during Drilling - Lost 86 bbl Mud. | Productive
hvjg | gvjgv | vjhv | 12.25 | 07/05/15 11:00 | 07/05/15 23:30 |  |  | 4702 | 4713 | [8 empty] | Swept 30 bbl LCM Pill of 70 PPB. Meanwhile Cont' Drilling & Drilled 12-1/4" hole from 4702m to 4713m - Observed No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | 07/05/15 23:30 | 07/06/15 05:00 | [12 empty] | Stopped Drilling. Pumped 40 bbl Hi-Vis Pill & Circ / BTM Up for Geological Sample - No Loss during Circ. Declared Casing TD @ 4713m (MD). Spotted 8 bbl 100 PPB LCM @ Bottom. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 07/06/15 05:00 | 07/06/15 06:00 | [12 empty] | POOH from 4713m to 4586m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tentative Top Of Lockhart Formation @ 4708m MD / 4705.53m TVD
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 86 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total: 86 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/06/15 06:00 | 07/06/15 22:00 | [12 empty] | Cont' POOH from 4586m to Surface. L/Down Jar + Bit (02 Nozzles Partially Plugged) & R/Back BHA.
hvjg | gvjgv | vjhv | 0 | 07/06/15 22:00 | 07/07/15 06:00 | [12 empty] | Held Pre-Job Safety Meeting. R/Up SLB W/Line Gears. Installed & Press Tested Shooting Nipple + W/Line BOP @ 500 psi - Ok. M/Up & RIH (Run # 1) SLB W/Line Tools to Bottom. Recorded HRLA (Cal-GR-SP) Logs from Bottom to 4400m, Cal Log from Bottom to 2550m & in Progress. Meanwhile Monitored Well thru Trip Tank - No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Water: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/07/15 06:00 | 07/07/15 17:00 | [12 empty] | Recorded Caliper Log from 2550m to 13-3/8" Casing Shoe. POOH Logging Tools to Surface & L/Down the same. M/Up & RIH W/Line Tools (Run # 2) and Recorded MCFL-TDL-CNL Logs as per program & POOH W/Line Tools to Surface - During RIH & POOH Observed Tight Spots at Several Depths. L/Down SLB Logging Tools + W/Line Gears + W/Line BOP + Shooting Nipple. Monitored Well thru Trip Tank during Logging - No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | 07/07/15 17:00 | 07/08/15 06:00 | [12 empty] | M/Up & RIH with same PDC Bit (13 RR2) & BHA to 3702m for Condition Trip before Run # 3 of W/Line Logging (as per SLB W/Line Engg. Requirement) - Filled String after every 10 Stands while RIH. Found No Obstruction during RIH & No Loss during Trip. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/08/15 06:00 | 07/08/15 09:30 | [12 empty] | Cont' RIH from 3702m to Bottom @ 4713m. Precautionary Wash Down Last Stand - No Fill.
hvjg | gvjgv | vjhv | 0 | 07/08/15 09:30 | 07/08/15 14:00 | [12 empty] | Circ / Swept Hole with 40 bbl Hi-Vis. Meanwhile Reciprocated and Rotated String. Flow Checked & Spotted 8 bbl 100 PPB LCM Pill @ Bottom.
hvjg | gvjgv | vjhv | 0 | 07/08/15 14:00 | 07/09/15 03:00 | [12 empty] | POOH to Surface - Hole Slick. L/Down Jar + Bit & R/Back BHA. While POOH Flow Checked at 13-3/8" Casing Shoe & BHA.
hvjg | gvjgv | vjhv | 0 | 07/09/15 03:00 | 07/09/15 06:00 | [12 empty] | Held Pre-Job Safety Meeting. R/Up SLB W/Line Gears. Installed Shooting Nipple + W/Line BOP. M/Up & RIH (Run # 3) FMI-DSI-GR-CALI Tools to 1380m. Meanwhile Monitored Well thru Trip Tank. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/09/15 06:00 | 07/09/15 19:00 | [12 empty] | RIH FMI-DSI-GR-CALI Tools from 1380m to Bottom (Run # 3) & Recorded W/Line Logs as per Program. POOH W/Line to Surface & L/Down SLB Logging Tools + W/Line Gears + W/Line BOP + Shooting Nipple. Monitored Well thru Trip Tank during Logging - No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | 07/09/15 19:00 | 07/10/15 00:00 | [12 empty] | RIH 5" OEDPs with Mule Shoe to 13-3/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 07/10/15 00:00 | 07/10/15 02:00 | [12 empty] | Slipped & Cut 120' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 07/10/15 02:00 | 07/10/15 03:30 | [12 empty] | M/Up TDS & Circ / BTM Up to Condition Mud.
hvjg | gvjgv | vjhv | 0 | 07/10/15 03:30 | 07/10/15 06:00 | [12 empty] | Cont' RIH from 13-3/8" Casing Shoe to 3337m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/10/15 06:00 | 07/10/15 11:00 | [12 empty] | Cont' RIH from 3337m to Bottom. While RIH Broke Circ @ 3500m & P/Up 25 x 5" DPs from Pipe Raks.
hvjg | gvjgv | vjhv | 0 | 07/10/15 11:00 | 07/10/15 22:00 | [12 empty] | M/Up TDS & Circ / Conditioned Mud. Meanwhile Prepared Spacer (MUDPUSH-II) in Mud Tanks. | Productive
hvjg | gvjgv | vjhv | 0 | 07/10/15 22:00 | 07/11/15 00:30 | [12 empty] | Held Pre-Job Safety Meeting. R/Up & Press Tested SLB Cementing Lines to 4000 psi - Ok. Prepared 50 bbl 15.8 ppg (1.90 S.G) Class "G" Cement Slurry in Batch Mixer. Pumped 50 bbl 15.2 ppg (1.82 S.G) Spacer as Pre-Flush from Rig Pump. Switched Over to SLB Unit & Pumped 50 bbl Batch Mixed Cement Slurry of 15.8 ppg (1.90 S.G). Displaced Cement Slurry with 6 bbl Spacer (Post- Flush) & 262 bbl Mud - Underdisplaced by 6 bbl. R/Down SLB Cement Lines. No Loss during Cement Plug Job. | Productive
hvjg | gvjgv | vjhv | 0 | 07/11/15 00:30 | 07/11/15 06:00 | [12 empty] | POOH from 4713m to 2723m. While POOH Flushed DPs with 20 bbl Mud @ 4560m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/11/15 06:00 | 07/11/15 07:30 | [12 empty] | Cont' POOH 5" OEDPs from 2723m to 2277m (inside 13-3/8" Casing Shoe).
hvjg | gvjgv | vjhv | 0 | 07/11/15 07:30 | 07/11/15 09:00 | [12 empty] | Circ / BTM up - No Loss. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 07/11/15 09:00 | 07/11/15 14:00 | [12 empty] | Cont' POOH 5" OEDPs to Surface. L/Down Mule Shoe.
hvjg | gvjgv | vjhv | 0 | 07/11/15 14:00 | 07/11/15 21:30 | [12 empty] | M/Up & RIH with same PDC Bit (13 RR3) & BHA to 13-3/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 07/11/15 21:30 | 07/11/15 22:30 | [12 empty] | Circ / BTM up - No Loss. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 07/11/15 22:30 | 07/12/15 06:00 | [12 empty] | Resumed RIH from 13-3/8" Casing Shoe to 4044m. Tagged 10 Ton Compression. Attempted to Wash Down - No Success. Reamed Down from 4044m to 4058m. Observed Rotary Stalled while Reaming @ 4057m. While RIH Broke Circ @ 3500m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/12/15 06:00 | 07/12/15 12:00 | [12 empty] | RIH from 4058m & Reamed / Washed Down Tight Spots. Tagged Cement Top @ 4635m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/12/15 12:00 | 07/12/15 20:00 | [12 empty] | COC / Dressed Cement from 4635m to 4712m - Observed Mud System Contaminated with Cement.
hvjg | gvjgv | vjhv | 0 | 07/12/15 20:00 | 07/13/15 06:00 | [12 empty] | Circ / Conditioned Mud in Progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/13/15 06:00 | 07/13/15 07:00 | [12 empty] | Cont' Circ / Conditioned Mud.
hvjg | gvjgv | vjhv | 0 | 07/13/15 07:00 | 07/13/15 12:30 | [12 empty] | Flow Checked & Conducted Wiper Trip up to 4000m. Observed Tight Spot @ 4044m - Cleared with Reciprocation. | Productive
hvjg | gvjgv | vjhv | 0 | 07/13/15 12:30 | 07/13/15 16:00 | [12 empty] | Circ / Spotted 4 PPB Lubra Beads Mud in Open Hole & 40 bbl Lubra Beads Hi-Vis Pill @ Bottom (Total 1400 bbl). Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 07/13/15 16:00 | 07/14/15 06:00 | [12 empty] | POOH to 20m. While POOH Soft Broke BHA & L/Down Jar + 2 x S.Stabs. Flow Checked @ 13-3/8" Casing Shoe & BHA. POOH in Progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/14/15 06:00 | 07/14/15 07:00 | [12 empty] | POOH from 20m to Surface. L/Down Bit + Bit Sub.
hvjg | gvjgv | vjhv | 0 | 07/14/15 07:00 | 07/14/15 10:00 | [12 empty] | Retrieved Wear Bushing. Changed 5" Pipe Rams to 9-5/8" Casing Rams. M/Up Test Plug Assy & Set inside 13-5/8" Casing Head Spool & Press Tested BOP Bonnet Seals @ 1000 psi - Ok. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 07/14/15 10:00 | 07/14/15 12:00 | [12 empty] | R/Up Wellserve Casing Running Gears. Changed TDS Links & Prepared Rig Floor to RIH 9-5/8" Casing. | Productive
hvjg | gvjgv | vjhv | 0 | 07/14/15 12:00 | 07/15/15 06:00 | [12 empty] | Sacrificed Two Goats & Prayed to ALLAH ALMIGHTY. Held Pre-Job Safety Meeting. RIH 9-5/8" Casing [53.5 ppf, TN-110HC, TSH Blue] to 996m. Installed R/Shoe + F/Collar + Baffle Collar + Centralizers + PipTag & Filled Up Casing as per Tally. M/Up Circ. Head, Dropped 1.75" OD Ball & Converted Autofill Valves to NRVs @ 700 psi & 300 psi (after Several Attempts) after RIH 4 Joints (48m). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/15/15 06:00 | 07/15/15 17:00 | [12 empty] | Cont' RIH 9-5/8" Casing from 996m to 2278m. Filled Up Casing & Installed Centralizers as per Program.
hvjg | gvjgv | vjhv | 0 | 07/15/15 17:00 | 07/15/15 18:00 | [12 empty] | Circ / Cond. Mud.
hvjg | gvjgv | vjhv | 0 | 07/15/15 18:00 | 07/16/15 12:00 | [12 empty] | Resumed RIH 9-5/8" Casing from 2278m to 3539m. Filled Up Casing & Installed Centralizers + ICP + DV Tool as per Tally.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/16/15 06:00 | 07/16/15 15:30 | [12 empty] | Cont' RIH 9-5/8" Casing from 3539m to 4710m (Bottom). Filled Up Casing + Installed Centralizers + Broke Circ. as per Program.
hvjg | gvjgv | vjhv | 0 | 07/16/15 15:30 | 07/16/15 16:30 | [12 empty] | R/Down WellServe Casing Running Gears.
hvjg | gvjgv | vjhv | 0 | 07/16/15 16:30 | 07/16/15 21:30 | [12 empty] | Circ / Conditioned Mud. Meanwhile Prepared Spacer and Mix Fluid for 1st Stage Lead & Tail Slurries. | Productive
hvjg | gvjgv | vjhv | 0 | 07/16/15 21:30 | 07/17/15 06:00 | [12 empty] | Held PJSM. R/Up SLB Cementing Head & Press Tested SLB Lines to 4000 psi - Ok. Pumped 100 BBL Mud Push II (Spacer) of 15.4 PPG thru Rig Pump. Opened Cementing Head and Dropped 1st Stage Bypass Plug. Switched Over to SLB Unit. Fly Mixed & Pumped 800 BBL Lead Slurry of 16.2 PPG followed by 100 BBL Batch Mixed Tail Slurry of 16.2 PPG @ 3.5 - 5 BPM. Dropped 1st Stage Shut-Off Plug. Pumped 20 BBL Water thru SLB Unit. Switched Over to Rig Pump & Displaced Cement Slurry by 1050 BBL Mud of 1.75 S.G. Switched again to SLB Unit & Dispaced with 15 bbl Water and Bumped Plug at 1500 psi (Total Displacement = 1085 BBL). Increased Press to 2600 psi in increments to Inflate "ICP". Bled Off Press - No Back Flow. No Loss Observed During Cement Job. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | After Pumping 430 bbl Lead Slurry - Observed Leakage in 01 Pump of SLB Cementing Unit. Reduced Pumping Rate to 3 - 4 BPM. During Final 15 bbl Displacement Found 2nd Pump also Leaking. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 12.25 | [14 empty] | Total Downhole Fluid Loss in 12-1/4" Hole: 501 BBL
hvjg | gvjgv | vjhv | 0 | 07/17/15 06:00 | 07/17/15 12:00 | [12 empty] | Opened Cementing Head & Dropped Free Fall Opening Device - Waited for 40 min & then applied Press thru Rig Pump. Obsvd Stage Collar Ports Opened at 1600 psi & Mud Returns on Shakers. Resumed Circ thru Rig Pump. Dumped 130 BBL Contaminated Spacer / Cement / Mud & 110 BBL Neat Cement. Cont'd Circ - Meanwhile Prepared Spacer & Mix Fluid for 2nd Stage Cement Job. | Productive
hvjg | gvjgv | vjhv | 0 | 07/17/15 12:00 | 07/17/15 16:30 | [12 empty] | Pumped 80 BBL Water & 50 BBL Mud Push II (Spacer) of 15.0 PPG thru Rig Pump. Switched to SLB Unit and Pumped 250 BBL Cement Slurry of 15.2 PPG @ 4 - 5 BPM. Dropped Closing Plug and Pumped 20 BBL Water thru SLB Unit. Switched Over to Rig Pump & Displaced Cement Slurry with 480 BBL Mud of 1.75 S.G. Switched Over to SLB Unit - Pumped 24 BBL Mud & Bumped Plug at 1600 psi (Total Displacement = 524 BBL). Held Press for 10 min to Close Stage Collar Ports. Bled Off Press - No Back Flow. R/Down SLB Lines. | Productive
hvjg | gvjgv | vjhv | 0 | 07/17/15 16:30 | 07/17/15 22:00 | [12 empty] | WOC. Removed Flow Line & Fill Up Lines. Made arrangements & Lifted BOP Stack.
hvjg | gvjgv | vjhv | 0 | 07/17/15 22:00 | 07/18/15 06:00 | [12 empty] | Set Casing Hanger. Rough Cut 9-5/8" Casing & L/Down 2 x 9-5/8" Pup Joints. Opened & Removed Spacer Spool. Final Cut 9-5/8" Casing @ 4.75" & Dressed / Grinded Stub. Installed Primary Seal Assy + Energizing Ring + DRCMS (Metal Seal). Installation of 13-5/8" - 10k x 11" - 10k Tubing Head Spool is in Progress.
hvjg | gvjgv | vjhv | 0 | 07/18/15 06:00 | 07/18/15 10:00 | [12 empty] | Installated of 13-5/8" - 10k x 11" - 10k Tubing Head Spool & Attempted to Press Test the same - Observed Leakage from Flange. Slacked BOP Weight & Re-Tightened Stud Bolts. Press Tested FS Seals + Metal Seal + Flange @ 500 PSI Low & 5000 PSI High - Ok. | Non Productive
hvjg | gvjgv | vjhv | 0 | 07/18/15 10:00 | 07/18/15 22:00 | [12 empty] | N/Up 13-5/8" - 10k BOP Stack. Opened Telescopic Bell Nipple & Installed Flow Line + Fill Up Line. Meanwhile Worked on TDS.
hvjg | gvjgv | vjhv | 0 | 07/18/15 22:00 | 07/19/15 00:30 | [12 empty] | Replaced TDS Saver Sub & Changed TDS Links.
hvjg | gvjgv | vjhv | 0 | 07/19/15 00:30 | 07/19/15 06:00 | [12 empty] | M/Up Test Plug Assy & Set Test Plug inside THS. Filled BOP Stack with Water. Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + Lower Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 7500 psi High Press - OK. Press Testing Blind Rams in Progress.
hvjg | gvjgv | vjhv | 0 | 07/19/15 06:00 | 07/19/15 10:00 | [12 empty] | Press Tested Blind Rams @ 300 psi Low & 7500 psi High Press - OK. Set Wear Bushing inside THS & L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 07/19/15 10:00 | 07/19/15 12:30 | [12 empty] | L/Down 14 x 8" DCs single by single.
hvjg | gvjgv | vjhv | 0 | 07/19/15 12:30 | 07/19/15 16:30 | [12 empty] | P/Up & M/Up 5 Stands of 6-1/2" DCs.
hvjg | gvjgv | vjhv | 0 | 07/19/15 16:30 | 07/20/15 00:30 | [12 empty] | M/Up & RIH 8-1/2" Tricone Bit (RR) with Slick BHA & Tagged Stage Collar / Plugs @ 2178.63m. During RIH F/Up String after every 10 Stands.
hvjg | gvjgv | vjhv | 0 | 07/20/15 00:30 | 07/20/15 01:00 | [12 empty] | Broke Circ. Closed Pipe Rams & Press Tested 9-5/8" Casing to 500 psi - OK.
hvjg | gvjgv | vjhv | 0 | 07/20/15 01:00 | 07/20/15 03:00 |  |  | 2178.63 | 2184 | [8 empty] | Drilled Out Stage Collar / Plugs from 2178.63m to 2184m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/20/15 03:00 | 07/20/15 06:00 | [12 empty] | Cont' RIH to 3285m. During RIH F/Up String after every 10 Stands.
hvjg | gvjgv | vjhv | 0 | 07/20/15 06:00 | 07/20/15 11:30 | [12 empty] | Cont' RIH from 3285m to 4669m & Tagged Plugs / Baffle Collar.
hvjg | gvjgv | vjhv | 0 | 07/20/15 11:30 | 07/20/15 14:00 |  |  | 4669 | 4674 | [8 empty] | Drilled Out Baffle Collar / Plugs from 4669m to 4674m & Cont' COC to 4684.5m (Top of F/Collar). | Productive
hvjg | gvjgv | vjhv | 0 | 07/20/15 14:00 | 07/20/15 14:15 | [12 empty] | Closed Pipe Rams & Press Tested 9-5/8" Casing to 500 psi - OK.
hvjg | gvjgv | vjhv | 0 | 07/20/15 14:15 | 07/20/15 17:30 |  |  | 4684.5 | 4689 | [8 empty] | Drilled Out Float Collar / Plugs from 4684.5m to 4689m & Cont' COC to 4707m (Above R/Shoe). | Productive
hvjg | gvjgv | vjhv | 0 | 07/20/15 17:30 | 07/20/15 17:45 | [12 empty] | Closed Pipe Rams & Press Tested 9-5/8" Casing to 500 psi - OK.
hvjg | gvjgv | vjhv | 0 | 07/20/15 17:45 | 07/20/15 20:00 | [12 empty] | Circ / Swept 30 BBL Hi-Vis Pill & Displaced Mud System to 1.10 S.G KCl Polymer Low Damaging Mud.
hvjg | gvjgv | vjhv | 0 | 07/20/15 20:00 | 07/20/15 21:30 | [12 empty] | Dumped / Cleaned Possum Belly & Sand Trap.
hvjg | gvjgv | vjhv | 0 | 07/20/15 21:30 | 07/21/15 00:00 |  |  | 4710 | 4713 | [8 empty] | Cont' COC from 4707m & Drilled Out R/Shoe @ 4710m. Drilled Rat Hole from 4710m to 4713m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/21/15 00:00 | 07/21/15 01:00 |  |  | 4713 | 4714 | [8 empty] | Commenced Next Stage Drilling & Drilled 8-1/2" hole from 4713m to 4714m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/21/15 01:00 | 07/21/15 04:00 | [12 empty] | Circ / Swept 30 BBL Hi-Vis Pill till Shakers Clean & Homogenized Mud Column.
hvjg | gvjgv | vjhv | 0 | 07/21/15 04:00 | 07/21/15 05:30 | [12 empty] | Held Pre-Job Safety Meeting. R/Up & Press Tested SLB Lines to 2500 psi. Conducted F.I.T to 1.30 S.G EMW (1540 PSI Surface Pressure with 1.07 S.G Mud). R/Down SLB Lines. | Productive
hvjg | gvjgv | vjhv | 0 | 07/21/15 05:30 | 07/21/15 06:00 | [12 empty] | M/Up TDS & Broke Circ. Flow Checked - Ok. POOH to 4680m.
hvjg | gvjgv | vjhv | 0 | 07/21/15 06:00 | 07/21/15 19:30 | [12 empty] | Cont' POOH from 4680m to Surface. While POOH Flow Checked at BHA. L/Down Jar + Bit.
hvjg | gvjgv | vjhv | 0 | 07/21/15 19:30 | 07/21/15 22:30 | [12 empty] | M/Up & RIH with Tricone Bit (15RR) & 9-5/8" Casing Scrapper to 405m.
hvjg | gvjgv | vjhv | 0 | 07/21/15 22:30 | 07/22/15 00:30 | [12 empty] | Slipped & Cut 112' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 07/22/15 00:30 | 07/22/15 06:00 | [12 empty] | Cont' RIH from 405m to 2484m.
hvjg | gvjgv | vjhv | 0 | 07/22/15 06:00 | 07/22/15 12:00 | [12 empty] | Cont' RIH from 2484m to 4708m & Scrapped 9-5/8" Casing.
hvjg | gvjgv | vjhv | 0 | 07/22/15 12:00 | 07/22/15 14:00 | [12 empty] | Circ. / Cleaned Hole & Shakers - Meanwhile Reciprocated String. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 07/22/15 14:00 | 07/23/15 01:00 | [12 empty] | POOH 9-5/8" Scrapper Assy to Surface. While POOH Flow Checked at BHA. L/Down Jar + Scrapper + Bit.
hvjg | gvjgv | vjhv | 0 | 07/23/15 01:00 | 07/23/15 06:00 | [12 empty] | Held Pre-Job Safety Meeting. R/Up SLB W/Line Gears. M/Up & RIH SLB "CBL-VDL-CCL-GR" Tools to bottom. Recorded Logs up to 4200m & in Progress. | Productive
hvjg | gvjgv | vjhv | 0 | 07/23/15 06:00 | 07/23/15 09:00 | [12 empty] | After logging CBL, VDL, CCL, GR, Gears down SLB W/Line ( Meanwhile moniter well on Trip tank.)
hvjg | gvjgv | vjhv | 0 | 07/23/15 09:00 | 07/23/15 22:00 | [12 empty] | Installed Mouse hole, M/U New PDC Bit # 16 MDSI616 & RIH with Pendulum BHA down to 3684m (Filled String after 10 stands each).
hvjg | gvjgv | vjhv | 0 | 07/23/15 22:00 | 07/23/15 22:30 | [12 empty] | Worked on TDS Pipe Handler.
hvjg | gvjgv | vjhv | 0 | 07/23/15 22:30 | 07/24/15 01:30 | [12 empty] | Resumed RIH from 3684m to 4712m, washed down last stand.
hvjg | gvjgv | vjhv | 0 | 07/24/15 01:30 | 07/24/15 02:30 | [12 empty] | Pumped 25 bbls Hi-Vis pill & stringed out meanwhile reciprocated the string. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/24/15 02:30 | 07/24/15 06:00 |  |  | 4714 | 4717.6 | [8 empty] | Tagged bottom @ 4714m & broke-in the bit. Drilled 8-1/2" Hole from 4714m to 4717.60m with controlled parameters. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Obsereved 1.67% Trip Gas at Bottom Up.
hvjg | gvjgv | vjhv | 8.5 | 07/24/15 06:00 | 07/24/15 17:30 |  |  | 4717 | 4740 | [8 empty] | Drilled 8-1/2" Hole from 4717m to 4740m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/24/15 17:30 | 07/24/15 20:00 | [12 empty] | P/u String, observed Hi-Trq & rotary stalled @ 4737m, String stuck. Worked on String, Jarred up (max. 35 Ton) several times, string released. | Non Productive
hvjg | gvjgv | vjhv | 0 | 07/24/15 20:00 | 07/24/15 21:00 | [12 empty] | Pumped 56 bbls Lube pill & stringed out meanwhile reciprocated string. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/24/15 21:00 | 07/25/15 00:30 |  |  | 4740 | 4747 | [8 empty] | Drilled 8-1/2" Hole from 4740m to 4747m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/25/15 00:30 | 07/25/15 01:00 | [12 empty] | P/U String for Flow Check, observed Hi-Trq & rotary stalled @ 4744m, String stuck. Worked on String, Jarred up (max. 35 Ton), string released. Flow Checked, found Well Static. | Non Productive
hvjg | gvjgv | vjhv | 8.5 | 07/25/15 01:00 | 07/25/15 06:00 |  |  | 4747 | 4753 | [8 empty] | Resumed Drilling 8-1/2" Hole from 4747m to 4753m. Reamed twice before connection, observed Hi-trq @ 4748m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/25/15 06:00 | 07/25/15 06:30 |  |  | 4753 | 4754 | [8 empty] | Drilled 8-1/2" Hole from 4753m to 4754m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/25/15 06:30 | 07/25/15 10:00 | [12 empty] | Stopped drilling, circulated & increased mud weight, screened out coarse LCM from mud system prior to core job. | Productive
hvjg | gvjgv | vjhv | 0 | 07/25/15 10:00 | 07/25/15 12:00 | [12 empty] | Performed check trip to csg shoe @ 4710m & continued circulation to conditioned mud.
hvjg | gvjgv | vjhv | 8.5 | 07/25/15 12:00 | 07/25/15 18:30 |  |  | 4754 | 4767 | [8 empty] | Drilled 8-1/2" Hole from 4754m to 4767m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/25/15 18:30 | 07/25/15 19:30 | [12 empty] | POOH from 4767m to csg shoe @ 4710m.
hvjg | gvjgv | vjhv | 0 | 07/25/15 19:30 | 07/25/15 21:00 | [12 empty] | Installed Inverter in TDS VFD room meanwhile circulation.
hvjg | gvjgv | vjhv | 0 | 07/25/15 21:00 | 07/25/15 22:00 | [12 empty] | RIH down to 4767m & pumped 20 bbls LCM pill. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/25/15 22:00 | 07/26/15 06:00 |  |  | 4767 | 4791 | [8 empty] | Drilled 8-1/2" Hole from 4767m to 4791m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 8.5 | 07/26/15 06:00 | 07/26/15 08:00 |  |  | 4791 | 4797 | [8 empty] | Drilled 8-1/2" Hole from 4791m to 4797m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/26/15 08:00 | 07/26/15 09:00 | [12 empty] | Reamed before connection, observed Hi-Trq & rotary stalled @ 4771m, 4780m & 4783m, clear the same. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/26/15 09:00 | 07/26/15 22:30 |  |  | 4797 | 4825 | [8 empty] | Drilled 8-1/2" Hole from 4797m to 4825m. | Productive
hvjg | gvjgv | vjhv | 0 | 07/26/15 22:30 | 07/26/15 23:30 | [12 empty] | Reamed before connection, observed Hi-Trq & rotary stalled @ 4824m, clear the same. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/26/15 23:30 | 07/27/15 06:00 |  |  | 4825 | 4852 | [8 empty] | Drilled 8-1/2" Hole from 4825m to 4852m. Meanwhile increased MW from 1.10 SG to 1.12 SG. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Hangu Formation has been marked @ 4792m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Lumshiwal Formation has been marked @ 4809m
hvjg | gvjgv | vjhv | 8.5 | 07/27/15 06:00 | 07/27/15 10:00 |  |  | 4852 | 4865 | [8 empty] | Drilled 8-1/2" Hole from 4852m to 4865m. Observed rain water causing wash outs under Generator foundation, stopped drilling. | Productive
hvjg | gvjgv | vjhv | 0 | 07/27/15 10:00 | 07/27/15 11:00 | [12 empty] | POOH to csg shoe, Hole Slick (155 DP stands in hole).
hvjg | gvjgv | vjhv | 0 | 07/27/15 11:00 | 07/27/15 11:30 | [12 empty] | M/up Safety Valve & connected TDS. Spaced out & Shut in well (Upper Pipe ram), Choke line HCR open. Monitoring well.
hvjg | gvjgv | vjhv | 0 | 07/27/15 11:30 | 07/28/15 06:00 | [12 empty] | Observed big crater under Generator foundation caused by rain water. Shut Down Rig Generators, disconnected VFD-1 & VFD-2 from Generators. Rig down all auxilary electrical connections from VFDs & made preparations to shift VFDs / generators & repaire / rebuild Generator foundation. | Non Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | SIDPP = Zero & SICP = Zero
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Hangu Formation has been marked @ 4792m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Lumshiwal Formation has been marked @ 4809m
hvjg | gvjgv | vjhv | 0 | 07/28/15 06:00 | 07/28/15 08:00 | [12 empty] | Continued filling barite bags into crater to temporarily secure the VFD plateform base (Total bags used = 175).
hvjg | gvjgv | vjhv | 0 | 07/28/15 08:00 | 07/28/15 20:00 | [12 empty] | Made preparations & shifted VFD-1, VFD-2 & three Rig Generators 6m towards Well center at secure location.
hvjg | gvjgv | vjhv | 0 | 07/28/15 20:00 | 07/28/15 21:00 | [12 empty] | Meanwhile Hook up DWS unit, resumed circulation with mud through standpipe manifold & returns through choke manifold into DWS unit tank. Received returns after 3 bbls, 550 Psi circulation pressure @ 5 bpm.
hvjg | gvjgv | vjhv | 0 | 07/28/15 21:00 | 07/29/15 06:00 | [12 empty] | Shifted Fourth Rig Generator to its position, Rig-up of electrical & mechanical connections is in progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | SIDPP = Zero & SICP = Zero
hvjg | gvjgv | vjhv | 0 | 07/29/15 06:00 | 07/29/15 15:00 | [12 empty] | Commissioned Generators / VFDs & all Electrical / Mechanical connections. Checked integrity of all electrical connections, found OK.
hvjg | gvjgv | vjhv | 0 | 07/29/15 15:00 | 07/29/15 16:00 | [12 empty] | Started Rig Generators, energised system. Function tested, found OK.
hvjg | gvjgv | vjhv | 0 | 07/29/15 16:00 | 07/29/15 18:00 | [12 empty] | SICP & SIDPP = zero, openned BOP. Resumed circulation for bottom up.
hvjg | gvjgv | vjhv | 0 | 07/29/15 18:00 | 07/29/15 19:00 | [12 empty] | POOH 10 stands up to 4403m to test hoisting system, found OK.
hvjg | gvjgv | vjhv | 0 | 07/29/15 19:00 | 07/29/15 22:00 | [12 empty] | RIH from 4403m to 4820m on elevators. Washed down from 4820m to bottom @ 4865m.
hvjg | gvjgv | vjhv | 8.5 | 07/29/15 22:00 | 07/30/15 06:00 |  |  | 4865 | 4893 | [8 empty] | Drilled 8-1/2" Hole from 4865m to 4893m, reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 8.5 | 07/30/15 06:00 | 07/30/15 06:00 |  |  | 4893 | 4949 | [8 empty] | Drilled 8-1/2" Hole from 4893m to 4949m, reamed before each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Chichali Formation has been marked @ 4851m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Samanasuk Formation has been marked @ 4896m
hvjg | gvjgv | vjhv | 8.5 | 07/31/15 06:00 | 07/31/15 06:00 |  |  | 4949 | 4995 | [8 empty] | Drilled 8-1/2" Hole from 4949m to 4995m, reamed before each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Shinwari Formation has been marked @ 4950 m
hvjg | gvjgv | vjhv | 8.5 | 08/01/15 06:00 | 08/01/15 06:00 |  |  | 4995 | 5033 | [8 empty] | Drilled 8-1/2" Hole from 4995m to 5033m, reamed before each connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Datta Formation has been marked @ 5006m
hvjg | gvjgv | vjhv | 8.5 | 08/02/15 06:00 | 08/02/15 08:00 |  |  | 5033 | 5035 | [8 empty] | Drilled 8-1/2" Hole from 5033m to 5035m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/02/15 08:00 | 08/02/15 10:00 | [12 empty] | Pumped & circulated out 20 bbls Hi-vis pill prior to Wiper Trip. | Productive
hvjg | gvjgv | vjhv | 0 | 08/02/15 10:00 | 08/02/15 13:30 | [12 empty] | POOH up to 4684m inside 9-5/8" csg shoe. Back reamed tight spots from 4907m to 4880m & pumped out from 4880m to 4850m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/02/15 13:30 | 08/02/15 14:00 | [12 empty] | Serviced TDS & repaired auxillary connection for TRQ & RPM at TDS-VFD. | Non Productive
hvjg | gvjgv | vjhv | 0 | 08/02/15 14:00 | 08/02/15 15:00 | [12 empty] | RIH suspended due to RAIN water accomulated behind Generators foundation. Excavated drainage channel to drain rain water.
hvjg | gvjgv | vjhv | 0 | 08/02/15 15:00 | 08/02/15 16:30 | [12 empty] | RIH down to bottom @ 5035m. Washed down last stand, no resistance observed during RIH.
hvjg | gvjgv | vjhv | 8.5 | 08/02/15 16:30 | 08/03/15 06:00 |  |  | 5035 | 5059 | [8 empty] | Resumed drilling & Drilled 8.5" Hole from 5035m to 5059m. Reamed before connection twice & cleared the tight spot @ 5049m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 20 bbls LCM pill after every four (04) Hrs.
hvjg | gvjgv | vjhv | 8.5 | 08/03/15 06:00 | 08/03/15 12:00 |  |  | 5059 | 5072 | [8 empty] | Drilled 8-1/2" Hole from 5059m to 5072m. Stopped drilling as Rain water inundated entire rig area, observed one wash out occurred at Mud Chemical area & a huge crater at Camp-Rig enterance near Muster Point-B. | Productive
hvjg | gvjgv | vjhv | 0 | 08/03/15 12:00 | 08/03/15 14:00 | [12 empty] | POOH up to 4684m inside 9-5/8" csg shoe, back reamed tight spots from 5054m to 5026m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/03/15 14:00 | 08/03/15 14:30 | [12 empty] | Shut in well at Upper Pipe Ram BOP.
hvjg | gvjgv | vjhv | 0 | 08/03/15 14:30 | 08/04/15 06:00 | [12 empty] | Monitored well through choke & circulated hole intermitently. | Productive
hvjg | gvjgv | vjhv | 0 | 08/04/15 06:00 | 08/04/15 06:00 | [12 empty] | Monitored well through choke & circulated hole intermitently. | Productive
hvjg | gvjgv | vjhv | 0 | 08/05/15 06:00 | 08/05/15 06:00 | [12 empty] | Monitored well through choke & circulated hole intermitently. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 06:00 | 08/06/15 07:00 | [12 empty] | Monitored Well through Choke & Circulated Hole Intermittently. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 07:00 | 08/06/15 09:00 | [12 empty] | Circ. / BTM Up prior to RIH to check Hole Condition.
hvjg | gvjgv | vjhv | 0 | 08/06/15 09:00 | 08/06/15 13:00 | [12 empty] | B/Out TDS. L/Down Safety Valve. Found TDS Rotation Lock engaged automatically - Unable to Rotate TDS. Worked on TDS & Rectified Problem.
hvjg | gvjgv | vjhv | 0 | 08/06/15 13:00 | 08/06/15 15:00 | [12 empty] | RIH down to 5072m. Reamed tight spots from 4888 m to 4911m while RIH. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 15:00 | 08/06/15 18:00 | [12 empty] | Circ. / Cond. Mud prior to Wiper Trip. Recorded Max. 0.40% Total Gas & Min 1.04 S.G M. WT at Bottom & PIT GAIN OF 5 BBLS OBSERVED. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 18:00 | 08/06/15 21:30 | [12 empty] | Conducted Wiper Trip to 9-5/8" Casing Shoe - Hole Condition Good. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 21:30 | 08/07/15 01:00 | [12 empty] | Swept 20 BBL HV Pill & Increased M.WT from 1.15 S.G to 1.16+ S.G. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 08/07/15 01:00 | 08/07/15 01:30 | [12 empty] | Dropped Totco & Allowed Time to Record Deviation.
hvjg | gvjgv | vjhv | 0 | 08/07/15 01:30 | 08/07/15 06:00 | [12 empty] | POOH to 3800m. Pumped Slug at Casing Shoe. | Productive
hvjg | gvjgv | vjhv | 0 | 08/07/15 06:00 | 08/07/15 18:30 | [12 empty] | Cont'd POOH from 3800m to Surface & Recovered Totco (Dev: 2.75⁰ @ 5069m). While POOH Flow Checked at 1400m & BHA and L/Down BHA for Inspection. | Non Productive
hvjg | gvjgv | vjhv | 0 | 08/07/15 18:30 | 08/08/15 00:00 | [12 empty] | M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Filled BOP Stack with Water. Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + Lower Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 8000 psi High Press - OK. Function Tested Blind Rams. Set Wear Bushing inside THS & L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 08/08/15 00:00 | 08/08/15 06:00 | [12 empty] | M/Up & RIH New 8-1/2" PDC Bit to 1090m. While RIH P/Up Inspected BHA from Racks.
hvjg | gvjgv | vjhv | 0 | 08/08/15 06:00 | 08/08/15 17:30 | [12 empty] | RIH from 1090m to 4683m (Inside 9-5/8" Casing Shoe). After RIH G-105 DPs, P/Up 30 x 5" S-135 DPs Single by Single from Cat Walk.
hvjg | gvjgv | vjhv | 0 | 08/08/15 17:30 | 08/08/15 19:00 | [12 empty] | Slipped & Cut 95' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 08/08/15 19:00 | 08/08/15 22:30 | [12 empty] | Resumed RIH from 4683m to 5065m. While RIH Observed Tight Spots & Reamed Down from 4770m - 4797m, 4851m - 4855m, 4857m - 4884m, 4986m - 4996m & 5027m - 5065m. Observed Hole Fill @ 5065m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/08/15 22:30 | 08/09/15 00:00 | [12 empty] | Circ / Bottom Up. Observed Max. 0.18% Gas & Min. 1.02 S.G Mud WT. @ Bottom Up.
hvjg | gvjgv | vjhv | 0 | 08/09/15 00:00 | 08/09/15 01:00 | [12 empty] | Reamed Down from 5065m to 5072m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/09/15 01:00 | 08/09/15 06:00 |  |  | 5072 | 5089 | [8 empty] | Drilled 8-1/2" Hole from 5072m to 5089m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Kick drill during RIH @ 4400 m (Inside Casing). Time Lapsed is 1.75 minutes…Set Slips, Released Elevator--Installed & Closed Safety valve: 45 seconds. Closed Pipe Rams: 62 seconds. Closed Choke: 105 seconds. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/09/15 06:00 | 08/09/15 06:00 |  |  | 5089 | 5130 | [8 empty] | Drilled 8-1/2" Hole from 5089m to 5130m. Observed Rotary Stalled & String Stuck while Reaming before Connection @ 5114m. Worked & Released String. Meanwhile Gradually Increased M.WT to 1.20 S.G during Drilling. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/10/15 06:00 | 08/10/15 22:00 |  |  | 5130 | 5148 | [8 empty] | Drilled 8-1/2" Hole from 5130m to 5148m. Reamed Twice at Connection. Observed Frequent Rotary Stalled (18 kft-lb) & String Stuck while Drilling @ 5146m - 5148m. Worked & Released String. | Productive
hvjg | gvjgv | vjhv | 0 | 08/10/15 22:00 | 08/11/15 01:30 | [12 empty] | Circ / Increased M. WT from 1.21 S.G to 1.23 S.G.
hvjg | gvjgv | vjhv | 8.5 | 08/11/15 01:30 | 08/11/15 06:00 |  |  | 5148 | 5153 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5148m to 5153m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/11/15 06:00 | 08/11/15 11:00 |  |  | 5153 | 5155 | [8 empty] | Drilled 8-1/2" Hole from 5153m to 5155m. Stopped Drilling & Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 08/11/15 11:00 | 08/11/15 13:00 | [12 empty] | POOH to 9-5/8" Casing Shoe for Wiper Trip - Hole Condition Very Good. | Productive
hvjg | gvjgv | vjhv | 0 | 08/11/15 13:00 | 08/11/15 13:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 08/11/15 13:30 | 08/11/15 15:30 | [12 empty] | RIH down to Bottom.
hvjg | gvjgv | vjhv | 8.5 | 08/11/15 15:30 | 08/12/15 01:30 |  |  | 5155 | 5164 | [8 empty] | Drilled 8-1/2" Hole from 5155m to 5164m. Observed Drilling Break & ROP Increased to 17 m/hr. | Productive
hvjg | gvjgv | vjhv | 0 | 08/12/15 01:30 | 08/12/15 02:00 | [12 empty] | Stopped Drilling & Flow Checked - Found Ok. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/12/15 02:00 | 08/12/15 02:30 |  |  | 5164 | 5165 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5164m to 5165m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/12/15 02:30 | 08/12/15 03:00 | [12 empty] | Stopped Drilling & Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 08/12/15 03:00 | 08/12/15 05:00 | [12 empty] | Circ / Bottom Up. Observed Max. 0.17% Gas but No Wt. Cut Mud @ Bottom Up.
hvjg | gvjgv | vjhv | 8.5 | 08/12/15 05:00 | 08/12/15 06:00 |  |  | 5165 | 5167 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5165m to 5167m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/12/15 06:00 | 08/12/15 06:00 |  |  | 5167 | 5196 | [8 empty] | Drilled 8-1/2" Hole from 5167m to 5196m. Reamed Twice at Connection. Observed Rotary Stalled while Drilling @ 5181m, 5184m & 5192m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | 7/8
hvjg | gvjgv | vjhv | 8.5 | 08/13/15 06:00 | 08/13/15 09:00 |  |  | 5196 | 5201 | [8 empty] | Drilled 8-1/2" Hole from 5196m to 5201m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/13/15 09:00 | 08/13/15 10:30 | [12 empty] | Circ / Bottom Up prior to Wiper Trip. | Productive
hvjg | gvjgv | vjhv | 0 | 08/13/15 10:30 | 08/13/15 11:30 | [12 empty] | Conducted Wiper Trip to 5116m - Hole Condition OK. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/13/15 11:30 | 08/14/15 06:00 |  |  | 5201 | 5220 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5201m to 5220m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/14/15 06:00 | 08/14/15 11:00 |  |  | 5220 | 5221 | [8 empty] | Drilled 8-1/2" Hole from 5220m to 5221m. Stopped Drilling due to Very Slow ROP. | Productive
hvjg | gvjgv | vjhv | 0 | 08/14/15 11:00 | 08/14/15 12:00 | [12 empty] | Circ / Bottom Up prior to Wiper Trip. | Productive
hvjg | gvjgv | vjhv | 0 | 08/14/15 12:00 | 08/14/15 15:00 | [12 empty] | Conducted Wiper Trip to Casing Shoe - Hole Condition OK. | Productive
hvjg | gvjgv | vjhv | 0 | 08/14/15 15:00 | 08/14/15 17:00 | [12 empty] | Circ / Bottom Up & Dropped Totco. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 08/14/15 17:00 | 08/15/15 06:00 | [12 empty] | POOH to 179m. Slugged DPs at Casing Shoe and Flow Checked @ Casing Shoe & BHA.
hvjg | gvjgv | vjhv | 0 | 08/15/15 06:00 | 08/15/15 07:30 | [12 empty] | POOH from 179m to Surface. L/Down Jar + Bit & Recovered Totco (Dev: 6⁰ @ 5213m).
hvjg | gvjgv | vjhv | 0 | 08/15/15 07:30 | 08/16/15 01:30 | [12 empty] | M/Up & RIH New 8-1/2" Tricone Bit with Junk Sub & New Jar to 5106m.
hvjg | gvjgv | vjhv | 0 | 08/16/15 01:30 | 08/16/15 03:00 | [12 empty] | Circ / Bottom Up. Observed Max. 0.45% Gas & Min. 1.21 S.G M. WT @ Bottom Up.
hvjg | gvjgv | vjhv | 0 | 08/16/15 03:00 | 08/16/15 06:00 | [12 empty] | Reamed / Washed Down from 5106m to 5200m. Reamed Down from 5200m to 5216m with Cont' WOB. | Productive
hvjg | gvjgv | vjhv | 0 | 08/16/15 06:00 | 08/16/15 09:00 | [12 empty] | Reamed Down from 5216m to 5221m. Worked on Junk Sub & Pumped 30 BBL Hi-Vis Pill. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/16/15 09:00 | 08/16/15 21:30 |  |  | 5221 | 5226 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5221m to 5226m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/16/15 21:30 | 08/17/15 01:00 | [12 empty] | Stopped Drilling. Worked on Junk Sub & Swept Hole with 15 BBL Hi-Vis Pill. Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 08/17/15 01:00 | 08/17/15 06:00 | [12 empty] | POOH to 3035m. Flow Checked & Pumped Slug at 9-5/8" Casing Shoe. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Resumed drilling with 460 GPM, then decreased discharge to 385 GPM after drilling 0.5 meter. | Productive
hvjg | gvjgv | vjhv | 0 | 08/17/15 06:00 | 08/17/15 13:30 | [12 empty] | POOH to Surface. L/Down Bit + Junk Sub + 02 S.Stabs + 01 DC. Recovered 103 Grams Metallic Junk from Junk Sub.
hvjg | gvjgv | vjhv | 0 | 08/17/15 13:30 | 08/18/15 03:00 | [12 empty] | M/Up New 8-1/2" PDC. Added 01 NMDC above bit 02 New 8-3/8" S.Stabs in BHA & RIH Down to 9-5/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 08/18/15 03:00 | 08/18/15 04:00 | [12 empty] | Cut & Slipped 72' Drilling Line. | Productive
hvjg | gvjgv | vjhv | 0 | 08/18/15 04:00 | 08/18/15 06:00 | [12 empty] | RIH from 9-5/8" Casing Shoe to 4886m. While RIH Observed Obstruction & Reamed / Washed Down from 4772m - 4803m & 4836m - 4886m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/18/15 06:00 | 08/18/15 22:30 | [12 empty] | Reamed Down from 4886m to Bottom (5226m) & Pumped 15 BBL Hi-Vis Pill. Observed Hi-Torque Intermittently during Reaming. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/18/15 22:30 | 08/19/15 03:00 |  |  | 5226 | 5236 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5226m to 5236m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 0 | 08/19/15 03:00 | 08/19/15 04:30 | [12 empty] | Circ / Bottom Up Till Shakers Clean. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 08/19/15 04:30 | 08/19/15 06:00 | [12 empty] | POOH to 4850m for Wiper Trip to 9-5/8" Casing Shoe prior to Record Multishot Survey. | Productive
hvjg | gvjgv | vjhv | 0 | 08/19/15 06:00 | 08/19/15 08:30 | [12 empty] | POOH to 9-5/8" Casing Shoe & RIH to Bottom - Hole Condition Good.
hvjg | gvjgv | vjhv | 0 | 08/19/15 08:30 | 08/19/15 10:00 | [12 empty] | Circ / Bottom Up. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 08/19/15 10:00 | 08/19/15 10:30 | [12 empty] | Dropped Multi-Shot Survey Tool inside String & Allowed Time to Reach Bottom - Meanwhile Reciprocated String. | Productive
hvjg | gvjgv | vjhv | 0 | 08/19/15 10:30 | 08/19/15 12:30 | [12 empty] | POOH to 9-5/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 08/19/15 12:30 | 08/19/15 16:00 | [12 empty] | R/Up Safety Valve & Recovered EMS tool on Slick Line - Meanwhile Monitored Well thru Trip Tank.
hvjg | gvjgv | vjhv | 0 | 08/19/15 16:00 | 08/19/15 18:00 | [12 empty] | RIH to Bottom.
hvjg | gvjgv | vjhv | 8.5 | 08/19/15 18:00 | 08/19/15 20:00 |  |  | 5236 | 5239 | [8 empty] | Drilled 8-1/2" Hole from 5236m to 5239m. Observed Increase in Mud Return. | Productive
hvjg | gvjgv | vjhv | 0 | 08/19/15 20:00 | 08/19/15 21:00 | [12 empty] | Stopped Drilling & Flow Checked - Observed M. WT. Out 1.17 S.G (Aerated Mud). Circ / Balanced Mud Column. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/19/15 21:00 | 08/20/15 06:00 |  |  | 5239 | 5254 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5239m to 5254m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/20/15 06:00 | 08/20/15 06:00 |  |  | 5254 | 5278 | [8 empty] | Cont' Drilling & Drilled 8-1/2" Hole from 5254m to 5278m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/21/15 06:00 | 08/21/15 06:00 |  |  | 5278 | 5299 | [8 empty] | Cont' Drilling & Drilled 8-1/2" Hole from 5278m to 5299m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/22/15 06:00 | 08/22/15 19:00 |  |  | 5299 | 5311 | [8 empty] | Cont' Drilling & Drilled 8-1/2" Hole from 5299m to 5311m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/22/15 19:00 | 08/22/15 19:30 | [12 empty] | Observed Increase in Mud Returns. Stopped Drilling & Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 08/22/15 19:30 | 08/22/15 21:30 | [12 empty] | Circ / Bottom Up. Observed Max. 0.30% Gas & Min. 1.22 S.G M. WT @ Bottom Up.
hvjg | gvjgv | vjhv | 8.5 | 08/22/15 21:30 | 08/23/15 06:00 |  |  | 5311 | 5319 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5311m to 5319m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/23/15 06:00 | 08/23/15 15:00 |  |  | 5319 | 5328 | [8 empty] | Drilled 8-1/2" Hole from 5319m to 5328m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/23/15 15:00 | 08/23/15 16:30 | [12 empty] | Circ / Bottom Up. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 08/23/15 16:30 | 08/23/15 17:30 | [12 empty] | Conducted Wiper Trip to 5200m - Hole Condition OK. | Productive
hvjg | gvjgv | vjhv | 0 | 08/23/15 17:30 | 08/23/15 20:00 | [12 empty] | Circ / Swept 20 BBL Hi-Vis Pill. Dropped Totco & Allowed Time to Reach Bottom - Meanwhile Cont'd Circ.
hvjg | gvjgv | vjhv | 0 | 08/23/15 20:00 | 08/24/15 06:00 | [12 empty] | Flow Checked - Well Static. POOH to 1487m. While POOH Flow Checked & Pumped Slug at 9-5/8" Casing Shoe. | Productive
hvjg | gvjgv | vjhv | 0 | 08/24/15 06:00 | 08/24/15 08:30 | [12 empty] | POOH from 1487m to 297m.
hvjg | gvjgv | vjhv | 0 | 08/24/15 08:30 | 08/24/15 09:30 | [12 empty] | Worked on TDS.
hvjg | gvjgv | vjhv | 0 | 08/24/15 09:30 | 08/24/15 14:00 | [12 empty] | Cont'd POOH from 297m to Surface & Recovered Totco (Dev: 4 Deg @ 5326m). While POOH Flow Checked at BHA & L/Down Bit + Complete BHA for Inspection. | Non Productive
hvjg | gvjgv | vjhv | 0 | 08/24/15 14:00 | 08/24/15 21:00 | [12 empty] | M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + Lower Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 8000 psi High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 08/24/15 21:00 | 08/25/15 06:00 | [12 empty] | P/Up & M/Up New 8-1/2" PDC Bit with Directional BHA. Shallow Tested & Downlinked 'PD' to Power V Mode. M/Up & Shallow Tested MWD @ 400 GPM & 1150 PSI. M/Up & Function Tested PBL Sub. Observed PBL Ports Opened @ 30 - 40 psi Only & Closing Balls Not Seating Properly. L/Down PBL Sub. Cont'd RIH to 193m & P/Up Inpected BHA from Racks.
hvjg | gvjgv | vjhv | 0 | 08/25/15 06:00 | 08/25/15 21:30 | [12 empty] | Con't RIH from 193m to 4883m. While RIH P/Up BHA Single by Single from Racks & Filled Up String / Broke Circ. After every 15 Stands. & Observed Obstruction @ 4883m.
hvjg | gvjgv | vjhv | 0 | 08/25/15 21:30 | 08/26/15 06:00 | [12 empty] | Reamed Down from 4883m to 5307m & Recorded MWD Surveys @ 5238m, 5267m & 5296m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Fire Drill & Kick Drill | Productive
hvjg | gvjgv | vjhv | 0 | 08/26/15 06:00 | 08/26/15 08:00 | [12 empty] | Reamed Down from 5307m to Bottom & Recorded MWD Survey. Downlinked SLB 'PD' to 'Absolute Command' (180⁰ Toolface & 75% Steering Ratio) & Pumped 20 BBL Hi-Vis Pill. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/26/15 08:00 | 08/26/15 20:30 |  |  | 5328 | 5339 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5328m to 5339m in 'Absolute Command'. Downlinked SLB 'PD' to 'Power V' Mode & Drilled 8-1/2" Hole from 5339m to 5356m in 'Power V' Mode. Reamed Twice at Connection & Recorded MWD Surveys @ 5316m, 5327m & 5341m. Observed Well Inclination Not Controlled by SLB 'PD' & Increased to 8.69 Deg. | Productive
hvjg | gvjgv | vjhv | 0 | 08/26/15 20:30 | 08/26/15 23:00 | [12 empty] | Stopped Drilling & Swept 20 BBL Hi-Vis Pill. Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 08/26/15 23:00 | 08/27/15 06:00 | [12 empty] | POOH to 3910m. Obsvd Tight Spots & Pumped Out from 5333m - 5307m, 5277m - 5250m and Cleared Tight Spots with Reciprocation @ 5229m, 5162m, 4869m & 4858m. While POOH Recorded MWD Surveys @ 4814m, 4756m & 4727m & Flow Checked at Casing Shoe. | Productive
hvjg | gvjgv | vjhv | 0 | 08/27/15 06:00 | 08/27/15 16:30 | [12 empty] | NPT SLB, POOH from 3910m to Surface. L/Down Bit + PD + Float Sub & R/Back BHA. While POOH Flow Checked at BHA.
hvjg | gvjgv | vjhv | 0 | 08/27/15 16:30 | 08/27/15 20:30 | [12 empty] | NPT SLB, Programmed SLB 'Xceed' at Surface (180⁰ Toolface & 50% Steering Ratio).
hvjg | gvjgv | vjhv | 0 | 08/27/15 20:30 | 08/28/15 06:00 | [12 empty] | NPT SLB, P/Up & M/Up 8-1/2" PDC Bit (RR) with 'Xceed' Directional BHA. Shallow Tested MWD Tool @ 424 GPM & 450 PSI and RIH down to 2108m. Filled Up String after every 10 Stands While RIH.
hvjg | gvjgv | vjhv | 0 | 08/28/15 06:00 | 08/28/15 14:00 | [12 empty] | Cont'd RIH from 2108m to 9-5/8" Casing Shoe. Filled Up String after every 10 Stands While RIH.
hvjg | gvjgv | vjhv | 0 | 08/28/15 14:00 | 08/28/15 15:30 | [12 empty] | Slipped & Cut 78' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors & Serviced TDS. Meanwhile Monitored Well thru Trip Tank. | Productive
hvjg | gvjgv | vjhv | 0 | 08/28/15 15:30 | 08/28/15 19:00 | [12 empty] | RIH from 9-5/8" Casing Shoe to 5338m. Filled Up String after every 10 Stands. While RIH Observed Tight Spot & Reamed Down from 4855m to 4882m. | Productive
hvjg | gvjgv | vjhv | 0 | 08/28/15 19:00 | 08/28/15 20:30 | [12 empty] | Downlinked 'Xceed'. RIH to Bottom - Pumped & Displaced 20 BBL Hi-Vis Pill Out of String. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/28/15 20:30 | 08/29/15 06:00 |  |  | 5356 | 5371 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5356m to 5371m. Observed Max. 0.558% Gas & Min. 1.20 S.G M. WT @ Bottom Up of Hi-Vis Pill. Reamed Twice at Connection & Recorded MWD Survey @ 5357m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/29/15 06:00 | 08/30/15 00:30 |  |  | 5371 | 5396 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5371m to 5396m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (7.05 Deg @ 5385m). | Productive
hvjg | gvjgv | vjhv | 0 | 08/30/15 00:30 | 08/30/15 01:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 8.5 | 08/30/15 01:00 | 08/30/15 06:00 |  |  | 5396 | 5405 | [8 empty] | Drilled 8-1/2" Hole from 5396m to 5405m with SLB 'Xceed' | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/30/15 06:00 | 08/30/15 06:00 |  |  | 5405 | 5443 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5405m to 5443m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (4.35 Deg @ 5412m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/31/15 06:00 | 08/31/15 06:00 |  |  | 5443 | 5474 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5443m to 5474m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (2.28 Deg @ 5440m). Recorded 0.21% Connection Gas. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/01/15 06:00 | 09/01/15 17:30 |  |  | 5474 | 5491 | [8 empty] | Drilled 8-1/2" Hole from 5474m to 5491m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (0.28 Deg @ 5468m). | Productive
hvjg | gvjgv | vjhv | 0 | 09/01/15 17:30 | 09/01/15 22:00 |  |  |  | 5395 | [8 empty] | Observed TDS Washpipe Leaked. Stopped Drilling & P/Back to 5395m. Repaired TDS Washpipe - Meanwhile Circ. & Rotated String. RIH to Bottom. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/01/15 22:00 | 09/02/15 00:00 |  |  | 5491 | 5493 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5491m to 5493m. Observed Increase in Mud Return. | Productive
hvjg | gvjgv | vjhv | 0 | 09/02/15 00:00 | 09/02/15 01:00 | [12 empty] | Stopped Drilling & Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/02/15 01:00 | 09/02/15 06:00 |  |  | 5493 | 5498 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5493m to 5498m with SLB 'Xceed'. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/02/15 06:00 | 09/02/15 09:00 |  |  | 5498 | 5500 | [8 empty] | Drilled 8-1/2" Hole from 5498m to 5500m with SLB 'Xceed' & Recorded MWD Survey (2.50 Deg @ 5487m). | Productive
hvjg | gvjgv | vjhv | 0 | 09/02/15 09:00 | 09/02/15 11:30 | [12 empty] | Circ / Swept Hole with 20 BBL Hi-Vis Pill prior to Wiper Trip. Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 09/02/15 11:30 | 09/02/15 15:30 | [12 empty] | POOH to 9-5/8" Casing Shoe for Wiper Trip - Hole Condition Good. | Productive
hvjg | gvjgv | vjhv | 0 | 09/02/15 15:30 | 09/02/15 16:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 09/02/15 16:00 | 09/02/15 19:30 | [12 empty] | RIH to Bottom. While RIH Filled Up String & Reamed / Washed Down Last Stand. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/02/15 19:30 | 09/03/15 06:00 |  |  | 5500 | 5511 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5500m to 5511m with SLB 'Xceed'. Recorded Max. 0.45% Trip Gas & Min. 1.21 S.G M. WT @ Bottom Up. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Kick Drill @ 1500 Hrs | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Tredian Formation Marked @ 5430m (MD)
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Mianwali Formation Marked @ 5496m (MD)
hvjg | gvjgv | vjhv | 8.5 | 09/03/15 06:00 | 09/03/15 06:00 |  |  | 5511 | 5553 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5511m to 5553m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connections. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/04/15 06:00 | 09/04/15 06:00 |  |  | 5553 | 5591 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5553m to 5591m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (3.15 Deg @ 5556m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/05/15 06:00 | 09/05/15 06:00 |  |  | 5591 | 5621 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5591m to 5621m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (0.07 Deg @ 5585m). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Top of Chhidru Formation Marked @ 5532m (MD)
hvjg | gvjgv | vjhv | 8.5 | 09/06/15 06:00 | 09/06/15 09:30 |  |  | 5621 | 5624 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5621m to 5624m with SLB 'Xceed'. | Productive
hvjg | gvjgv | vjhv | 0 | 09/06/15 09:30 | 09/06/15 14:00 |  |  |  | 5481 | [8 empty] | Observed TDS Washpipe Leaked. Stopped Drilling & P/Back to 5481m. Replaced TDS Washpipe with New One - Meanwhile Installed Circ Head and Circ / Rotated String. RIH to Bottom. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/06/15 14:00 | 09/07/15 06:00 |  |  | 5624 | 5646 | [8 empty] | Resumed Drilling & Drilled 8-1/2" Hole from 5624m to 5646m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (0.08 Deg @ 5613m). Recorded Max. 0.13% Gas @ Bottom Up. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/07/15 06:00 | 09/07/15 06:00 |  |  | 5646 | 5667 | [8 empty] | Downlinked SLB 'Xceed' to Neutral Mode & Drilled 8-1/2" Hole from 5646m to 5667m. Reamed Twice & Recorded MWD Survey at Connection (0.23 Deg @ 5642m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/08/15 06:00 | 09/08/15 09:30 |  |  | 5667 | 5669 | [8 empty] | Drilled 8-1/2" Hole from 5667m to 5669m. | Productive
hvjg | gvjgv | vjhv | 0 | 09/08/15 09:30 | 09/08/15 12:30 | [12 empty] | Recorded MWD survey (0.05⁰ @ 5655m). Pumped Hi-vis pill & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 09/08/15 12:30 | 09/08/15 17:30 | [12 empty] | POOH from 5669m to 4706m, observed tight spots at 5643m & 5638m, clear the same while pumped out of hole. | Productive
hvjg | gvjgv | vjhv | 0 | 09/08/15 17:30 | 09/08/15 18:00 | [12 empty] | Flow checked @ casing shoe, well static.
hvjg | gvjgv | vjhv | 0 | 09/08/15 18:00 | 09/09/15 02:30 | [12 empty] | POOH from 4706m to 2082m, L/D 17 stds of S-135 DPs single by single.
hvjg | gvjgv | vjhv | 0 | 09/09/15 02:30 | 09/09/15 06:00 | [12 empty] | RIH 16 stds of S-135 DPs from 2082m to 2534m, POOH & L/D the same single by single from 2534m to 2130m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Kick Drill @ 1730 Hrs | Productive
hvjg | gvjgv | vjhv | 0 | 09/09/15 06:00 | 09/09/15 10:30 | [12 empty] | POOH from 2130m to 287m.
hvjg | gvjgv | vjhv | 0 | 09/09/15 10:30 | 09/09/15 11:00 | [12 empty] | Flow checked @ Top of BHA, well static.
hvjg | gvjgv | vjhv | 0 | 09/09/15 11:00 | 09/09/15 15:00 | [12 empty] | POOH BHA to surface & L/D for inspection. L/D Bit, Exeed & D. Jar. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/09/15 15:00 | 09/09/15 21:00 | [12 empty] | M/Up Test Plug Assy & Set Test Plug inside THS. Filled BOP Stack with Water. Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + Lower Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 7500 psi High Press - OK. Installed Wear Bushing & L/D Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 09/09/15 21:00 | 09/10/15 02:00 | [12 empty] | P/U & M/U 8-3/4" SLB Mud Motor on 8-1/2" PDC Bit (used), set adjustable Bend Housing to 1.15 degree. P/U & M/U 6-3/4" SPSA & inserted MWD tool inside it, took Tool Face Correction (TFC). Performed Shallow Pulse test @ 400 GPM & 550 Psi, OK.
hvjg | gvjgv | vjhv | 0 | 09/10/15 02:00 | 09/10/15 06:00 | [12 empty] | M/U PDC Bit (New) & RIH on Directional BHA single by single down to 435m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Note: PBL surface test failed. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/10/15 06:00 | 09/10/15 11:00 | [12 empty] | RIH from 435m to 2091m.
hvjg | gvjgv | vjhv | 0 | 09/10/15 11:00 | [13 empty] | Re-positioned / replaced 5" S-135 DP's (Rig Mari-1) & brought New One's on the top. P/U 102 Joints of 5" S-135 DP's from Cat-Walk single by single & RIH from 2091m to 3075m.
hvjg | gvjgv | vjhv | 0 |  | 09/10/15 06:00 | [12 empty] | RIH 5" DP's Stds from 3075m to 4702m inside 9-5/8" Csg Shoe & break circulation. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/11/15 06:00 | 09/11/15 07:00 | [12 empty] | RIH from 4702m to 4965m on elevators.
hvjg | gvjgv | vjhv | 0 | 09/11/15 07:00 | 09/11/15 10:00 | [12 empty] | Reamed down from 4965m to 4987m, RIH from 4987m to 5111m on elevators. Recorded max. 0.295% Gas & min. 1.23 SG M.W at bottom up. | Productive
hvjg | gvjgv | vjhv | 0 | 09/11/15 10:00 | 09/11/15 19:00 | [12 empty] | Hard reaming from 5111m to 5185m, observed rotary stalled at several depths. String stuck @ 5151m & 5159m, released by jarring. | Productive
hvjg | gvjgv | vjhv | 0 | 09/11/15 19:00 | 09/11/15 22:00 | [12 empty] | Washed down from 5185m to 5216m, observed obstruction & string stuck @ 5216m. Worked on string, jarred up (max. 40 Tons) several times but no success. Spotted 30 bbls of Lube + Detergent pill & worked on string by jarring, string got released. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/11/15 22:00 | 09/11/15 23:30 | [12 empty] | 500 Psi pressure drop during circulation. Observed MWD signals not receiving at surface. Replaced MWD SPP sensor & tried to rectify the problem, no success. Decided to POOH.
hvjg | gvjgv | vjhv | 0 | 09/11/15 23:30 | 09/12/15 06:00 | [12 empty] | POOH from 5216m to 3016m, Flow checked @ casing shoe, well static.
hvjg | gvjgv | vjhv | 0 | 09/12/15 06:00 | 09/12/15 14:00 | [12 empty] | POOH from 3062m to surface, found 6-1/4" X/Over twisted-off from pin & left in hole 88.36m BHA assembly. Total Fish in hole = PDC Bit + Mud Motor + SPSA + NMDC + 6 x 6-1/2" DC's (88.36m).
hvjg | gvjgv | vjhv | 0 | 09/12/15 14:00 | 09/12/15 22:00 | [12 empty] | Changed Upper Pipe Ram to 5-1/2" Rams. M/Up Test Plug Assy & Set Test Plug inside THS. Pressure Tested Upper Pipe Ram + Bonnet seals @ 500 psi Low & 7500 psi High - OK. Installed Wear Bushing & L/D Test Plug Assy. | Productive
hvjg | gvjgv | vjhv | 0 | 09/12/15 22:00 | 09/13/15 06:00 | [12 empty] | RIH 64 stds of 5" G-105 & 6 stds of 5" S-135 down to 1998m. L/D 74 singles from 1998m to 1329m (in progress).
hvjg | gvjgv | vjhv | 0 | 09/13/15 06:00 | 09/13/15 13:00 | [12 empty] | L/D 140 joints of 5" DP's single by single from 1329m to surface.
hvjg | gvjgv | vjhv | 0 | 09/13/15 13:00 | 09/13/15 14:30 | [12 empty] | Slipped & Cut 91' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 09/13/15 14:30 | [13 empty] | M/U 8-1/8" Over Shot (FS) & RIH on Fishing Assembly down to 3160m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Break circulation & flow checked, well static. | Non Productive
hvjg | gvjgv | vjhv | 0 |  | 09/13/15 02:30 | [12 empty] | Changed TDS Saver-sub to 5-1/2" FH & function tested, OK.
hvjg | gvjgv | vjhv | 0 | 09/13/15 02:30 | 09/13/15 06:00 | [12 empty] | P/u 30 joints of 5-1/2" S-135 from Cat-Walk & RIH single by single from 3160m to 3446m.
hvjg | gvjgv | vjhv | 0 | 09/14/15 06:00 | 09/14/15 09:00 | [12 empty] | P/U 60 joints of 5-1/2" S-135 DP's from Cat-Walk & RIH single by single from 3464m to 3721m.
hvjg | gvjgv | vjhv | 0 | 09/14/15 09:00 | 09/14/15 11:00 | [12 empty] | POOH & racked back 20 stds of 5-1/2" S-135 DP's from 3721m to 3159m.
hvjg | gvjgv | vjhv | 0 | 09/14/15 11:00 | 09/14/15 21:00 | [12 empty] | P/U 150 joints of 5-1/2" S-135 DP's from Cat-Walk & RIH single by single from 3159m to 4592m.
hvjg | gvjgv | vjhv | 0 | 09/14/15 21:00 | [13 empty] | RIH from 4592m to 5107m on elevators, Hole Slick. Recorded String weight 207 Tons Upward / 200 Tons Downward (without circulation) & 205 Tons Upward / 199 Tons Downward (with circulation). Washed down from 5107m to 5126.42m @ Top of Fish.
hvjg | gvjgv | vjhv | 0 |  | 09/14/15 02:00 | [12 empty] | Tagged Top of Fish with circulation (150 GPM) & 2-3 tons compression. Made several attempts to engage fish with compression (max. 40 Tons) & rotation (10 RPM), pressure increased from 600 Psi to 1200 Psi & observed surface indications of Fish insertion in Over Shot. P/U string, observed no change in weight indicator (Fish slipped from grapple).
hvjg | gvjgv | vjhv | 0 | 09/14/15 02:00 | 09/14/15 03:00 | [12 empty] | Circulated for bottom up. Recorded max. 0.39% Gas & min. 1.22 SG M.W at bottom up. | Productive
hvjg | gvjgv | vjhv | 0 | 09/14/15 03:00 | 09/14/15 06:00 | [12 empty] | POOH from 5127m to 4564m on elevators. Flow checked @ 9-5/8" casing shoe, well static.
hvjg | gvjgv | vjhv | 0 | 09/15/15 06:00 | 09/15/15 20:30 | [12 empty] | POOH from 4564m to surface. Flow checked @ Top of BHA, well static. L/D intensifier & 6-1/2" DC single, break-out Over Shot. Inspected Over Shot thoroughly, found fish marks on Over Shot Bowl (out-side), no scratches on Grapples. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/15/15 20:30 | 09/15/15 23:00 | [12 empty] | Made preparations for Fishing BHA, slightly bent 5" G-105 DP. Dressed Over Shot with 6-1/2" Grapples.
hvjg | gvjgv | vjhv | 0 | 09/15/15 23:00 | 09/16/15 06:00 | [12 empty] | P/U & M/U 8-1/8" Over Shot with bent DP & RIH with Fishing BHA down to 1997m.
hvjg | gvjgv | vjhv | 0 | 09/16/15 06:00 | 09/16/15 15:00 | [12 empty] | RIH from 1997m to 4830m, broke circulation @ 4710m inside 9-5/8" casing shoe.
hvjg | gvjgv | vjhv | 0 | 09/16/15 15:00 | 09/16/15 18:30 | [12 empty] | Washed down from 4830m to Top of Fish @ 5126.42m, observed obstruction at different depths, cleared the same with rotation. Recorded String weight 207 Tons Upward / 200 Tons Downward (without circulation) & 205 Tons Upward / 199 Tons Downward (with circulation).
hvjg | gvjgv | vjhv | 0 | 09/16/15 18:30 | [13 empty] | Tagged Top of Fish with circulation (150 GPM) & 2-5 tons compression. Made several attempts to engage fish with compression (max. 5 Tons) & rotation (15 RPM), observed no change in SPP & weight indicator. Decided to POOH.
hvjg | gvjgv | vjhv | 0 |  | 09/16/15 06:00 | [12 empty] | Started POOH to 4710m, flow checked @ 9-5/8" casing shoe, well static. POOH from 4710m to 3741m.
hvjg | gvjgv | vjhv | 0 | 09/17/15 06:00 | 09/17/15 17:30 | [12 empty] | POOH from 3741m to surface. Flow checked @ Top of BHA, well static. L/D intensifier & 6-1/2" DC single, break-out Over Shot. Inspected Over Shot thoroughly, found fish marks on Over Shot Bowl & Lip-Guide (out-side). L/D 8-1/8" Over Shot & 5" bent DP. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/17/15 17:30 | 09/18/15 06:00 | [12 empty] | P/U & M/U 8-1/2" RR PDC Bit & RIH down to 4256m. Circulated for 5 min after every 30 stands. | Productive
hvjg | gvjgv | vjhv | 0 | 09/18/15 06:00 | 09/18/15 07:00 | [12 empty] | Continued RIH from 4256m to 4685m.
hvjg | gvjgv | vjhv | 0 | 09/18/15 07:00 | 09/18/15 09:00 | [12 empty] | Slipped & Cut 95' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 09/18/15 09:00 | 09/18/15 13:30 | [12 empty] | Resumed RIH from 4685m to 5116m on elevators. Washed down last stand from 5116m to Top of Fish & confirmed Top of Fish @ 5125m. Recorded max. 0.60% Gas at bottom up.
hvjg | gvjgv | vjhv | 0 | 09/18/15 13:30 | 09/18/15 15:30 | [12 empty] | POOH from 5125m to 4675m. Flow checked @ 9-5/8"casing shoe, well static.
hvjg | gvjgv | vjhv | 0 | 09/18/15 15:30 | 09/19/15 04:30 | [12 empty] | POOH from 4675m to surface. L/D Intensifier, Fishing Jar & 8-1/2" PDC Bit.
hvjg | gvjgv | vjhv | 0 | 09/19/15 04:30 | 09/19/15 06:00 | [12 empty] | Made preparations for Fishing BHA, P/U & M/U 8-1/8" Wall Hook Guide with Over Shot (SH) & RIH down to 71m.
hvjg | gvjgv | vjhv | 0 | 09/19/15 06:00 | 09/19/15 18:00 | [12 empty] | RIH from 71m to 4687m, broke circulation inside 9-5/8" casing shoe.
hvjg | gvjgv | vjhv | 0 | 09/19/15 18:00 | 09/19/15 18:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 09/19/15 18:30 | 09/19/15 20:30 | [12 empty] | Continued RIH from 4687m to 5091m on elevators. Washed down last stand from 5091m to Top of Fish @ 5125m. Recorded String weight 207 Tons Upward / 200 Tons Downward (without circulation) & 205 Tons Upward / 199 Tons Downward (with circulation). Recorded max. 0.52% Gas & min. 1.24 SG MW on bottom up.
hvjg | gvjgv | vjhv | 0 | 09/19/15 20:30 | 09/19/15 23:00 | [12 empty] | Tagged Top of Fish with circulation (210 GPM) & 2-5 tons compression. Made several attempts to engage fish with compression (max. 20 Tons) & rotation (10 RPM), observed no change in SPP & weight indicator.
hvjg | gvjgv | vjhv | 0 | 09/19/15 23:00 | 09/20/15 00:00 | [12 empty] | Pumped & spotted 30 bbls Lube pill & allowed soaking time. | Productive
hvjg | gvjgv | vjhv | 0 | 09/20/15 00:00 | 09/20/15 03:00 | [12 empty] | Continued work on fish with different parameters, no success. Decided to POOH.
hvjg | gvjgv | vjhv | 0 | 09/20/15 03:00 | 09/20/15 06:00 | [12 empty] | POOH from 5125m to 4401m. Flow checked @ 9-5/8"casing shoe, well static.
hvjg | gvjgv | vjhv | 0 | 09/20/15 06:00 | 09/20/15 18:00 | [12 empty] | Continued POOH from 4401m to surface. Flow checked @ Top of BHA, well static, L/D Fishing BHA. Inspected Over Shot thoroughly, found fish marks on Over Shot Bowl (out-side), no scratches on Grapples.
hvjg | gvjgv | vjhv | 0 | 09/20/15 18:00 | 09/20/15 21:00 | [12 empty] | P/U & M/U 3-1/2" Mule Shoe & RIH with 3-1/2" DP's single by single down to 211m.
hvjg | gvjgv | vjhv | 0 | 09/20/15 21:00 | 09/21/15 06:00 | [12 empty] | RIH 105 Stds of 5" S-135 DP's & 5-1/2" S-135 DP's Stds down to 4021m.
hvjg | gvjgv | vjhv | 0 | 09/21/15 06:00 | 09/21/15 09:00 | [12 empty] | Continued RIH 5-1/2" DP Stds from 4021m to 5111m.
hvjg | gvjgv | vjhv | 0 | 09/21/15 09:00 | 09/21/15 10:30 | [12 empty] | Washed down from 5111m to 5125m. Circulated to bottom up, Recorded max. 0.42% Gas & min. 1.20 SG M.W. | Productive
hvjg | gvjgv | vjhv | 0 | 09/21/15 10:30 | 09/21/15 14:00 | [12 empty] | Spotted 30 bbls Hi-Vis pill @ 5125m & POOH to 5110m. Conditioned mud prior to Balanced Cement Plug job meanwhile R/U Dowell Cementing Unit & prepared mix fluid. | Productive
hvjg | gvjgv | vjhv | 0 | 09/21/15 14:00 | 09/21/15 17:00 | [12 empty] | Held PJSM, pressure tested cement lines to 3000 Psi & holds for 10 min, OK. Pumped 60 bbls of 13 PPG MUDPUSH II spacer ahead of 40 bbls 17.5 PPG Dura STONE slurry & 20 bbls of 13 PPG MUDPUSH II spacer behind @ 5-6 BPM. Displaced with 274 bbls of mud @ 5-6 BPM. | Productive
hvjg | gvjgv | vjhv | 0 | 09/21/15 17:00 | 09/21/15 19:00 | [12 empty] | POOH from 5110m to 4795m, reverse circulated bottom up. Discarded 15 bbls spacer contaminated mud (1.30-1.33 SG MW). | Productive
hvjg | gvjgv | vjhv | 0 | 09/21/15 19:00 | 09/22/15 06:00 | [12 empty] | POOH from 4795m to 732m.
hvjg | gvjgv | vjhv | 0 | 09/22/15 06:00 | 09/22/15 10:00 | [12 empty] | Continued POOH from 732m to surface. L/D CMT Stinger & 22 joints of 3-1/2" DP's single by single.
hvjg | gvjgv | vjhv | 0 | 09/22/15 10:00 | 09/22/15 13:00 | [12 empty] | P/U & M/U 6-3/4" HLB Mud Motor on 8-1/2" Tri-cone Bit (New), set adjustable Bend Housing to 1.83 degree. P/U & M/U 6-3/4" Hange -Off Collar (HOC) & Placed MWD tool inside it, took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 420 GPM.SSP recorded 750 psi- 930 Psi, OK.
hvjg | gvjgv | vjhv | 0 | 09/22/15 13:00 | 09/22/15 16:00 | [12 empty] | RIH 8-1/2" Tri-cone Bit with Directional BHA down to 454m.
hvjg | gvjgv | vjhv | 0 | 09/22/15 16:00 | 09/22/15 17:30 | [12 empty] | Slipped & Cut 101' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 09/22/15 17:30 | 09/23/15 06:00 | [12 empty] | Resumed RIH & from 450m to 4710m inside 9-5/8" casing shoe. Filled up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 09/23/15 06:00 | 09/23/15 07:00 | [12 empty] | RIH 8-1/2" Tri-cone Bit with Directional BHA down to 4864m on elevators.
hvjg | gvjgv | vjhv | 0 | 09/23/15 07:00 | 09/23/15 08:00 | [12 empty] | RIH with circulation from 4864m to 4913m. Tagged compression at 4913m.
hvjg | gvjgv | vjhv | 0 | 09/23/15 08:00 | 09/23/15 10:00 | [12 empty] | Reamed / Cleaned from 4913m to 4975m. | Productive
hvjg | gvjgv | vjhv | 0 | 09/23/15 10:00 | 09/23/15 11:30 | [12 empty] | Circulated bottom up @ 4975m, Found DuraStone at bottom up but no cement cuttings. | Productive
hvjg | gvjgv | vjhv | 0 | 09/23/15 11:30 | 09/23/15 14:00 | [12 empty] | Reamed / cleaned down from 4975m to Top of Cement @ 4987m, tagged TOC with 5 Tons compression. | Productive
hvjg | gvjgv | vjhv | 0 | 09/23/15 14:00 | 09/23/15 15:30 |  |  | 4987 | 5040 | [8 empty] | Drilled Cmt Plug from 4987m to 5040m with 3-4 Tons WOB, 300 GPM & surface RPM @ 30. | Productive
hvjg | gvjgv | vjhv | 0 | 09/23/15 15:30 | 09/23/15 16:30 | [12 empty] | Pumped 20 bbls Hi-Vis pill & String out. | Productive
hvjg | gvjgv | vjhv | 0 | 09/23/15 16:30 | 09/24/15 06:00 |  |  | 5040 | 5045.62 | [8 empty] | Resumed TIME Drilling 1"/5min from 5040m to 5045.62m to KICK OFF from 5050m. Observed weight hanging & 20 Tons O/pull while P/U String, increased TIME Drilling rate to 1"/2min. Received traces of formation & 90% soft to firm Cmt cuttings at surface. | Productive
hvjg | gvjgv | vjhv | 0 | 09/24/15 06:00 | 09/24/15 08:00 |  |  | 5045.62 | 5046.54 | [8 empty] | Continued TIME Drilling 1"/4min from 5045.62m to 5046.54 m. Observed partial dynamic losses, Stoped drilling. Observed O/pull while P/U String, String released at 30 Tons O/pull. | Productive
hvjg | gvjgv | vjhv | 0 | 09/24/15 08:00 | 09/24/15 13:00 | [12 empty] | Stopped pump. Flow checked, found no static loss. Swept 30 bbl tendem Fine LCM pills of 30 PPB concentration. Circulated at 295 GPM & reciprocated string. Reduced M.W from 1.27 to 1.24 S.G by dilution & running centrifuge. Added checkLoss to system. | Productive
hvjg | gvjgv | vjhv | 0 | 09/24/15 13:00 | 09/24/15 21:00 |  |  | 5046.54 | 5050 | [8 empty] | Recorded SCR & resumed TIME Drilling 1"/4min from 5046.54m to 5050m (KOP). Received 60% Formation & 40% Cmt cuttings @ 5050m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/24/15 21:00 | 09/25/15 02:30 |  |  | 5050 | 5054.85 | [8 empty] | Drilled 8-1/2" Hole from 5050m to 5054.85m in Sliding Mode with 10-12 Tons WOB. Received 100% Formation cuttings @ 5052m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/25/15 02:30 | 09/25/15 06:00 |  |  | 5054.85 | 5058 | [8 empty] | Observed partial dynamic losses @ 5054.82m, reduced SPM to 40/40. Swept 30 bbls LCM pill (Check Loss F + C) of 30 PPB in fly, found volumes static. Continued drilling 8-1/2" Hole from 5054.85m to 5058m in Sliding Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 15 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 120 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:130 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 250 BBL
hvjg | gvjgv | vjhv | 8.5 | 09/25/15 06:00 | 09/25/15 11:30 |  |  | 5058 | 5062 | [8 empty] | Drilled 8-1/2" Hole from 5058m to 5062m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 09/25/15 11:30 | 09/25/15 12:00 | [12 empty] | Worked on Pump # 1 meanwhile resumed circulation. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/25/15 12:00 | 09/25/15 13:30 |  |  | 5062 | 5063 | [8 empty] | Drilled 8-1/2" Hole from 5062m to 5063m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/25/15 13:30 | 09/25/15 20:30 |  |  | 5063 | 5068 | [8 empty] | Drilled 8-1/2" Hole from 5063m to 5068m in Sliding Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/25/15 20:30 | 09/25/15 22:30 |  |  | 5068 | 5070 | [8 empty] | Drilled 8-1/2" Hole from 5068m to 5070m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 09/25/15 22:30 | 09/26/15 01:00 | [12 empty] | Recorded MWD Survey @ 5054m. Bottom up & circulated till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 09/26/15 01:00 | 09/26/15 04:30 | [12 empty] | Flow checked, Well static. POOH from 5070m to 4571m.
hvjg | gvjgv | vjhv | 0 | 09/26/15 04:30 | 09/26/15 06:00 | [12 empty] | Flow checked @ 9-5/8" csg shoe, Well static. Pumped 25 bbls slug & POOH from 4571m to 4315m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 15 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 15 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 265 BBL
hvjg | gvjgv | vjhv | 0 | 09/26/15 06:00 | 09/26/15 20:00 | [12 empty] | Continued POOH from 4315m to surface. Retrieved MWD tool & reset ABH @ 1.5 degree, R/B Mud Motor & HOC. L/Down Drilling Jar & bit. | Productive
hvjg | gvjgv | vjhv | 0 | 09/26/15 20:00 | 09/26/15 23:30 | [12 empty] | Held PJSM, M/Up Test Plug Assy & Set Test Plug inside THS. Filled BOP Stack with Water. P/U 5-1/2" DP & Press Tested Annular BOP + Kelly Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines @ 300 psi Low & 8000 psi High Press - OK.
hvjg | gvjgv | vjhv | 0 | 09/26/15 23:30 | 09/27/15 03:30 | [12 empty] | P/U 5" DP & Press Tested Lower Pipe Rams + Blind Rams + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 8000 psi High Press - OK. Installed Wear Bushing & L/D Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 09/27/15 03:30 | 09/27/15 06:00 | [12 empty] | P/U & M/U 8-1/2" PDC Bit (New) on 6-3/4" HLB Mud Motor & added 8-1/4" S.Stab. Inserted MWD tool inside HOC & took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 425 GPM & 650 Psi, OK.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 265 BBL
hvjg | gvjgv | vjhv | 0 | 09/27/15 06:00 | 09/27/15 22:00 | [12 empty] | RIH 8-1/2" PDC bit with Directional BHA down to 4993m. Filled Up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 09/27/15 22:00 | 09/28/15 00:00 | [12 empty] | Found obstruction @ 4993m, Reamed & Washed down from 4993m to 5070m. Recorded max. 0.79% Gas & min. 1.18 SG Cut M.W at bottom up. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 00:00 | 09/28/15 02:30 |  |  | 5070 | 5075 | [8 empty] | Broke the bit & Drilled 8-1/2" Hole from 5070m to 5075m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 02:30 | 09/28/15 05:00 |  |  | 5075 | 5078 | [8 empty] | Drilled 8-1/2" Hole from 5075m to 5078m in Slide Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 05:00 | 09/28/15 06:00 |  |  | 5078 | 5080 | [8 empty] | Drilled 8-1/2" Hole from 5078m to 5080m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 265 BBL
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 06:00 | 09/28/15 10:00 |  |  | 5080 | 5091 | [8 empty] | Drilled 8-1/2" Hole from 5080m to 5091m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 09/28/15 10:00 | 09/28/15 10:30 | [12 empty] | Reamed at connection. Recorded MWD Survey @ 5073m & took SCR. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 10:30 | 09/28/15 14:30 |  |  | 5091 | 5102 | [8 empty] | Drilled 8-1/2" Hole from 5091m to 5102m in Rotary Mode. Observed Partial dynamic loss @ 5102m, stopped drilling. | Productive
hvjg | gvjgv | vjhv | 0 | 09/28/15 14:30 | 09/28/15 15:00 | [12 empty] | Reduced pump discharge. P/Up string & stopped Pump, Flow checked, found well static. | Productive
hvjg | gvjgv | vjhv | 0 | 09/28/15 15:00 | 09/28/15 16:00 | [12 empty] | Pumped 20 bbl & 15 bbl Tandem LCM pills (check Loss C + F) of 30 PPB concentration & Resumed drilling. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/28/15 16:00 | 09/29/15 01:30 |  |  | 5102 | 5125 | [8 empty] | Drilled 8-1/2" Hole from 5102m to 5125m in Rotary Mode. Recorded MWD Survey @ 5101m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 01:30 | 09/29/15 04:00 |  |  | 5125 | 5127 | [8 empty] | Drilled 8-1/2" Hole from 5125m to 5127m in Slide Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 04:00 | 09/29/15 06:00 |  |  | 5127 | 5131 | [8 empty] | Drilled 8-1/2" Hole from 5127m to 5131m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 10 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 20 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 285 BBL
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 06:00 | 09/29/15 13:30 |  |  | 5131 | 5148 | [8 empty] | Drilled 8-1/2" Hole from 5131m to 5148m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 09/29/15 13:30 | 09/29/15 14:00 | [12 empty] | Reamed before connection. Recorded MWD Survey @ 5130m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 14:00 | 09/29/15 20:00 |  |  | 5148 | 5159 | [8 empty] | Drilled 8-1/2" Hole from 5148m to 5159m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 20:00 | 09/29/15 23:30 |  |  | 5159 | 5164 | [8 empty] | Drilled 8-1/2" Hole from 5159m to 5164m in Slide Mode. P/U String, observed tight spot & Hi-Trq @ 5160m. Clear the same with Back reaming. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/29/15 23:30 | 09/30/15 06:00 |  |  | 5164 | 5177 | [8 empty] | Drilled 8-1/2" Hole from 5164m to 5177m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Fire Drill @ 16:00 Hrs | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 10 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM:0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 285 BBL
hvjg | gvjgv | vjhv | 0 | 09/30/15 06:00 | 09/30/15 07:00 | [12 empty] | Reamed before connection. Recorded MWD Survey @ 5158m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/30/15 07:00 | 09/30/15 11:00 |  |  | 5177 | 5184 | [8 empty] | Drilled 8-1/2" Hole from 5177m to 5184m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/30/15 11:00 | 09/30/15 13:30 |  |  | 5184 | 5186.7 | [8 empty] | Drilled 8-1/2" Hole from 5184m to 5186.7m in Slide Mode. Observed partial dynamic losses. | Productive
hvjg | gvjgv | vjhv | 0 | 09/30/15 13:30 | 09/30/15 14:00 | [12 empty] | Stopped drilling. Stopped pump. Observed well & found static loss @ 20 bbls/ hr . | Productive
hvjg | gvjgv | vjhv | 0 | 09/30/15 14:00 | 09/30/15 15:30 | [12 empty] | Pumped 40 bbls of 30 PPB concentration M/F LCM pill & sopotted at bottom. Pulled Back to 5150m. | Productive
hvjg | gvjgv | vjhv | 0 | 09/30/15 15:30 | 09/30/15 17:00 | [12 empty] | Allowed soaking time to pill & Monitored well at trip tank. Static loss gradually decreased to zero bbls/ hr (Lost 11 bbls).
hvjg | gvjgv | vjhv | 8.5 | 09/30/15 17:00 | 09/30/15 17:30 | [12 empty] | Ran back to bottom. Pumped 20 bbls of 30 ppb LCM pill in string & resumed drilling 8-1/2" Hole @ reduced flow rate (350 GPM). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/30/15 17:30 | 10/01/15 06:00 |  |  | 5186.7 | 5204 | [8 empty] | Drilled 8-1/2" Hole from 5186.7m to 5204m in Rotary Mode. Meanwhile observed 6 bbls/hr dynamic partial losses, continued mixing LCM (CaCO3 M + Check Loss F & C) in active mud system. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 10 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 138 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 92 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 515 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/01/15 06:00 | 10/01/15 08:00 |  |  | 5204 | 5205 | [8 empty] | Drilled 8-1/2" Hole from 5204m to 5205m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 10/01/15 08:00 | 10/01/15 08:30 | [12 empty] | Reamed before connection. Recorded MWD Survey @ 5187m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/01/15 08:30 | 10/02/15 06:00 |  |  | 5205 | 5226 | [8 empty] | Drilled 8-1/2" Hole from 5205m to 5226m in Rotary Mode meanwhile continued mixing LCM (CaCO3 M + Check Loss F & C) in active mud system. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 10 bbls LCM pill after every four (04) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 25 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/02/15 06:00 | 10/02/15 08:00 | [12 empty] | Circulated clean hole prior to wiper trip. Recorded MWD Survey @ 5224m bit depth. | Productive
hvjg | gvjgv | vjhv | 0 | 10/02/15 08:00 | 10/02/15 10:30 | [12 empty] | POOH up to 5048m, Back reamed with circulation tight hole section from 5084m to 5050m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/02/15 10:30 | 10/02/15 11:00 | [12 empty] | Made several Bit Passes through KOP @ 5050m with different Tool Face positons to insure smooth entry through KOP.
hvjg | gvjgv | vjhv | 0 | 10/02/15 11:00 | 10/02/15 13:30 | [12 empty] | RIH down to 5206m. Reamed from 5061m to 5111m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/02/15 13:30 | 10/02/15 14:00 | [12 empty] | Pumped 15 bbls of LCM pill & Washed down from 5206m to 5226m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/02/15 14:00 | 10/03/15 02:00 |  |  | 5226 | 5234 | [8 empty] | Resumed drilling & Drilled 8-1/2" Hole from 5226m to 5234m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 10/03/15 02:00 | 10/03/15 02:30 | [12 empty] | Reamed before connection. Recorded MWD Survey @ 5215m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/03/15 02:30 | 10/03/15 06:00 |  |  | 5234 | 5237 | [8 empty] | Drilled 8-1/2" Hole from 5234m to 5237m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Swept out 10 bbls LCM pill after every Six (06) Hrs
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/03/15 06:00 | 10/03/15 08:00 |  |  | 5237 | 5238.8 | [8 empty] | Drilled 8-1/2" Hole from 5237m to 5238.80m in Rotary Mode. Observed high Erratic torque (10-17 Kf-lb) during drilling & (8-9Kf-lb) Off bottom. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/03/15 08:00 | 10/03/15 12:00 |  |  | 5238.8 | 5241 | [8 empty] | Resumed drilling 8-1/2" Hole from 5238.80m to 5241m with different drilling parameters but High erratic torque persisted. Stopped drilling. | Productive
hvjg | gvjgv | vjhv | 0 | 10/03/15 12:00 | 10/03/15 14:00 | [12 empty] | Circulated to clean hole prior to POOH. Flow Checked, Well static. | Productive
hvjg | gvjgv | vjhv | 0 | 10/03/15 14:00 | 10/03/15 17:00 | [12 empty] | POOH from 5241m to 4689m, clear KOP @ 5050m. Observed tight spot @ 4884m with max. 10-15 Tons, clear the same with reciprocation.
hvjg | gvjgv | vjhv | 0 | 10/03/15 17:00 | 10/04/15 03:30 | [12 empty] | Flow checked @ 9-5/8" csg shoe, Well static. Pumped 22 bbls slug & POOH from 4689m to 223m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/04/15 03:30 | 10/04/15 04:00 | [12 empty] | Flow checked @ Top of BHA, Well static. RIH three stands of 5" HWDP's from 223m to 308m.
hvjg | gvjgv | vjhv | 0 | 10/04/15 04:00 | 10/04/15 06:00 | [12 empty] | POOH BHA from 308m to 107m & L/D single by single.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/04/15 06:00 | 10/04/15 08:00 | [12 empty] | POOH up to surface. Bit condition GOOD. Suspect High Erratic torque due to Mud Motor.
hvjg | gvjgv | vjhv | 0 | 10/04/15 08:00 | 10/04/15 09:30 | [12 empty] | Handled Dir BHA at rig floor. L/Down MWD, HOC, 8-1/4" S.Stab, Motor sleeve Stab & Mud Motor.
hvjg | gvjgv | vjhv | 0 | 10/04/15 09:30 | 10/04/15 12:00 | [12 empty] | Slipped & Cut 95' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 10/04/15 12:00 | 10/04/15 14:00 | [12 empty] | P/U & M/U 6-3/4" HLB Mud Motor on 8-1/2" PDC Bit (New), set adjustable Bend Housing to 1.15 degree. P/U & M/U 6-3/4" Hange -Off Collar (HOC) & Placed MWD tool inside it, took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 350 GPM, SPP 550-670 Psi, OK.
hvjg | gvjgv | vjhv | 0 | 10/04/15 14:00 | 10/04/15 18:30 | [12 empty] | P/Up inspected BHA single by single from Cat Walk & RIH 8-1/2" PDC bit with Directional BHA down to 229m. Flushed BHA with mud by pumping Twice BHA capcity. | Productive
hvjg | gvjgv | vjhv | 0 | 10/04/15 18:30 | 10/05/15 06:00 | [12 empty] | Resumed RIH from 229m to 4467m. Filled up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/05/15 06:00 | 10/05/15 09:00 | [12 empty] | Continued RIH from 4467m to 5103m & Tagged compression @ 5103m.
hvjg | gvjgv | vjhv | 0 | 10/05/15 09:00 | 10/05/15 14:30 | [12 empty] | M/Up TDS. Reamed from 5101m to 5126m, Hard reaming observed from 5101m to 5118m. Motor / TDS stalled several times (Trq limit 17000 ft-lb). | Productive
hvjg | gvjgv | vjhv | 0 | 10/05/15 14:30 | 10/05/15 17:00 | [12 empty] | Washed / Reamed from 5126m down to bottom @ 5241m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/05/15 17:00 | 10/06/15 06:00 |  |  | 5241 | 5264 | [8 empty] | Drilled 8-1/2" Hole from 5241m to 5264m. Recorded SCR @ 5258m & adjusted MP # 1 SPM to maintain SPP. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/06/15 06:00 | 10/07/15 00:00 |  |  | 5264 | 5297 | [8 empty] | Cont'd drilling 8 1/2'' hole from 5264 m to 5297 m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/07/15 00:00 | 10/07/15 00:30 | [12 empty] | Reamed before connection. Recorded MWD survey @ 5278 m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/07/15 00:30 | 10/07/15 06:00 |  |  | 5297 | 5304 | [8 empty] | Resumed drilling 8 1/2'' hole from 5297 m to 5304 m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/07/15 06:00 | 10/07/15 10:30 |  |  | 5304 | 5310 | [8 empty] | Cont'd drilling 8 1/2'' hole from 5304 m to 5310 m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/07/15 10:30 | 10/07/15 12:30 | [12 empty] | Circulated to clean hole prior to wiper trip. Flow checked. Well static | Productive
hvjg | gvjgv | vjhv | 0 | 10/07/15 12:30 | 10/07/15 15:00 | [12 empty] | Made wiper trip up to 5068 m. Hole condition GOOD. | Productive
hvjg | gvjgv | vjhv | 0 | 10/07/15 15:00 | 10/08/15 06:00 |  |  | 5310 | 5333 | [8 empty] | Resumed drilling 8 1/2'' hole from 5310 m to 5333 m. (Reamed before connection. Recorded MWD survey @ 5307 m.) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 0 | 10/08/15 06:00 | 10/08/15 16:30 |  |  | 5333 | 5348 | [8 empty] | Cont'd drilling 8 1/2'' hole from 5333 m to 5348 m in rotary mode. Conducted check shot survey @ 5329 m, found inclination increased from 0.95 degree to 1.13 degrees. Stopped drilling in rotary mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/08/15 16:30 | 10/08/15 23:30 |  |  | 5348 | 5353.5 | [8 empty] | Drilled 8.5" hole from 5348 m to 5353.5 m in slide mode. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/08/15 23:30 | 10/09/15 06:00 |  |  | 5353.5 | 5362 | [8 empty] | Drilled 8.5" hole from 5353.5 m to 5362 m in rotary mode. (Reamed before connection, recorded MWD survey @ 5336 m.) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/09/15 06:00 | 10/09/15 06:00 |  |  | 5362 | 5387 | [8 empty] | Drilled 8.5" hole from 5362 m to 5387 m in rotary mode. (Reamed before connection, recorded MWD survey @ 5365 m) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 540 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/10/15 06:00 | 10/10/15 13:30 |  |  | 5387 | 5394 | [8 empty] | Drilled 8.5" hole from 5387 m to 5394m in rotary mode. Observed 200 psi drop in SPP. | Productive
hvjg | gvjgv | vjhv | 0 | 10/10/15 13:30 | 10/10/15 14:00 | [12 empty] | Checked Pumps. All OK. Recorded Check shot @ 5375 m . Found weak pulse from MWD tool. Pressure dropped due to weak poppet pulses. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/10/15 14:00 | 10/11/15 02:00 |  |  | 5394 | 5400 | [8 empty] | Drilled 8.5" hole from 5394 m to 5400 m in slide mode. | Productive
hvjg | gvjgv | vjhv | 0 | 10/11/15 02:00 | 10/11/15 06:00 |  |  | 5400 | 5405 | [8 empty] | Resumed drilling 8 1/2'' hole from 5400 m to 5405 m in rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 40 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | LCM: 0 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Fluid Loss: 580 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/11/15 06:00 | 10/11/15 07:00 |  |  | 5405 | 5406 | [8 empty] | Drilled 8.5" hole from 5405 m to 5406 m in rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | 10/11/15 07:00 | 10/11/15 09:00 | [12 empty] | Circulated to clean hole prior to wiper trip. Flow checked. Well static. | Productive
hvjg | gvjgv | vjhv | 0 | 10/11/15 09:00 | 10/11/15 10:00 | [12 empty] | POOH up to 5212 m. Tight spot observed at 5296 m. Cleared with reciprocating the string. Rest of the hole condition OK.
hvjg | gvjgv | vjhv | 0 | 10/11/15 10:00 | 10/11/15 11:00 | [12 empty] | Ran back to 5374 m. Washed down to 5406 m
hvjg | gvjgv | vjhv | 0 | 10/11/15 11:00 | 10/12/15 06:00 |  |  | 5406 | 5423 | [8 empty] | Resumed drilling 8 1/2'' hole from 5406 m to 5423 m in rotary mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 24 BBL / LCM: 0 BBL--Total Downhole Fluid Loss: 604 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | NOTE: At 1600 hrs during survey prior to connection at 5410 m, found no signals // communication from MWD tool. Failed to get survey from MWD. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/12/15 06:00 | 10/12/15 06:00 |  |  | 5423 | 5453 | [8 empty] | Cont'd drilling 8.5" hole from 5423 m to 5453 m in rotary mode. (Reamed before connection) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 8 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 612 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/13/15 06:00 | 10/13/15 06:00 |  |  | 5453 | 5478 | [8 empty] | Cont'd drilling 8.5" hole from 5453 m to 5478 m in rotary mode. (Reamed before connection) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 30 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 642 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/14/15 06:00 | 10/14/15 06:00 |  |  | 5478 | 5502 | [8 empty] | Cont'd drilling 8.5" hole from 5478 m to 5502 m in rotary mode. (Reamed before connection) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 43 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 685 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/15/15 06:00 | 10/16/15 05:00 |  |  | 5478 | 5530 | [8 empty] | Cont'd drilling 8.5" hole from 5478 m to 5530 m in rotary mode. (Reamed before connection) | Productive
hvjg | gvjgv | vjhv | 0 | 10/16/15 05:00 | 10/16/15 06:00 | [12 empty] | Circulation for bottom up for formation sample to confirm Lithology.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 30 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 642 BBL
hvjg | gvjgv | vjhv | 0 | 10/16/15 06:00 | 10/16/15 07:00 | [12 empty] | Circulaed to clean hole
hvjg | gvjgv | vjhv | 0 | 10/16/15 07:00 | 10/16/15 11:30 | [12 empty] | Flow checked, Well static. POOH up to 9 5/5'' casing shoe
hvjg | gvjgv | vjhv | 0 | 10/16/15 11:30 | 10/16/15 13:30 | [12 empty] | Slipped/ cut 165 m D. Line. Reset ACS & CrownoMatic
hvjg | gvjgv | vjhv | 0 | 10/16/15 13:30 | 10/16/15 17:30 | [12 empty] | RIH down to 5498 m & washed down to bottom @ 5530 m. Hole condition, Good
hvjg | gvjgv | vjhv | 0 | 10/16/15 17:30 | 10/16/15 21:00 | [12 empty] | Circulaed to clean hole. Pumped 30 bbl Hi-Vis and circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 10/16/15 21:00 | 10/17/15 01:00 | [12 empty] | POOH from 5530 m to 4695 m (inside 9 5/8'' csg shoe). Flow checked. Well static.
hvjg | gvjgv | vjhv | 0 | 10/17/15 01:00 | 10/17/15 06:00 | [12 empty] | Pumped slug. POOH from 4695 m to 2980 m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/17/15 06:00 | 10/17/15 15:30 | [12 empty] | POOH to surface. L/down all BHA for inspection. Observed well, found static. | Non Productive
hvjg | gvjgv | vjhv | 0 | 10/17/15 15:30 | 10/17/15 17:00 | [12 empty] | Retrieved MWD. L/down HOC. Set Mud motor ABH to '0'. L/down PDC bit and motor.
hvjg | gvjgv | vjhv | 0 | 10/17/15 17:00 | 10/17/15 19:00 | [12 empty] | Held PJSM. R/up Shooting Nipple, W/L BOP and anchored same. Closed Annular BOP & pressure tested W/L BOP @ 400 psi. Found no leakage. R/up SLB remaining gears. | Productive
hvjg | gvjgv | vjhv | 0 | 10/17/15 19:00 | 10/18/15 06:00 | [12 empty] | Performed SLB W/L log, Run # 1 (HRLA-SP-CALI-GR) as per program.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/18/15 06:00 | 10/18/15 07:15 | [12 empty] | R/down Slb W/l Logging gears.
hvjg | gvjgv | vjhv | 0 | 10/18/15 07:15 | 10/18/15 11:00 | [12 empty] | Held PJSM, M/Up Test Plug Assy & Set Test Plug inside THS. Filled BOP Stack with Water. P/U 5" DP & Press Tested Annular BOP + TDS Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi High - OK. Press Tested Lower Pipe Rams + IBOP + Coflex hose at @ 300 psi Low & 8000 psi High Press - OK.
hvjg | gvjgv | vjhv | 0 | 10/18/15 11:00 | 10/18/15 14:00 | [12 empty] | P/up 5 1/2'' test assy and pressure tested Upper Pipe Ram, Safety valve, both HCR @ 300 psi Low & 8000 psi High. OK. Pressure tested manual Kill line+ HCR manual valve @ 500 psi Low & 8000 psi High. OK. Installed wear bushing and L/down test assy. | Productive
hvjg | gvjgv | vjhv | 0 | 10/18/15 14:00 | 10/19/15 06:00 | [12 empty] | P/up and M/up 8 1/2'' RR PDC bit + new BHA single by single and RIH to 4700 m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/19/15 06:00 | 10/19/15 08:30 | [12 empty] | Circulated at 4700 m to condition mud. Min sp.gr of 0.85 received due to air cut mud. | Productive
hvjg | gvjgv | vjhv | 0 | 10/19/15 08:30 | 10/19/15 10:30 | [12 empty] | RIH. Tagged compression at 5052.5 m.
hvjg | gvjgv | vjhv | 0 | 10/19/15 10:30 | 10/20/15 06:00 | [12 empty] | M/Up TDS and reamed down from 5052.5 m to 5450 m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Tight spots = 5086m, 5096m, 5099m, 5119m, 5131m, 5203m, 5236m, 5240m, 5243m, 5295m, 5358m, 5361m
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/20/15 06:00 | 10/20/15 11:00 | [12 empty] | Reamed down from 5450m to bottom @ 5530m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/20/15 11:00 | 10/20/15 13:00 | [12 empty] | Pumped 25 bbls of HV pill & circulated till shakers clean. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 10/20/15 13:00 | 10/20/15 14:30 | [12 empty] | POOH up to 5387m. Tight hole / Swabbing observed from 5501 m to 5415m. Free from 5415 m to 5387m.
hvjg | gvjgv | vjhv | 0 | 10/20/15 14:30 | 10/20/15 16:00 | [12 empty] | RIH & reamed from 5415m down to 5530m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/20/15 16:00 | 10/20/15 17:30 | [12 empty] | Circulated to clean hole prior to POOH. Flow Checked - Ok. | Productive
hvjg | gvjgv | vjhv | 0 | 10/20/15 17:30 | 10/21/15 06:00 | [12 empty] | POOH to 710m. (Pumped Out from 5530m to 5414m.) | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/21/15 06:00 | 10/21/15 09:00 | [12 empty] | POOH from 710m to Surface. Racked back BHA. L/Down Jar & Bit.
hvjg | gvjgv | vjhv | 0 | 10/21/15 09:00 | 10/22/15 06:00 | [12 empty] | Held PJSM. Installed Shooting Nipple & R/Up SLB W/L Gears. M/Up & RIH SLB W/L Tools (Run # 2) & Recorded "HNGS-FMI" Logs from Bottom to 9-5/8" Casing Shoe - POOH & L/Down W/L Tools. M/Up & RIH SLB W/L Tools (Run # 3) & Recorded "DSI-GR" Logs from Bottom & 9-5/8" Casing Shoe - POOH to Surface & L/Down W/L Tools is in Progress. Monitored Well thru Trip Tank during W/L Logging.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/22/15 06:00 | 10/22/15 07:00 | [12 empty] | L/Down W/L Tools & R/Down SLB W/L Gear.
hvjg | gvjgv | vjhv | 0 | 10/22/15 07:00 | 10/22/15 20:30 | [12 empty] | M/Up & RIH with 8-1/2" PDC Bit (23RR2) to 9-5/8" Casing Shoe. While RIH Filled Up String with Mud after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 10/22/15 20:30 | 10/22/15 21:00 | [12 empty] | Serviced TDS. Meanwhile Filled Up String.
hvjg | gvjgv | vjhv | 0 | 10/22/15 21:00 | 10/23/15 06:00 | [12 empty] | Cont'd RIH from 9-5/8" Casing Shoe to 5472m. While RIH Observed Obstruction & Reamed Down from 5140m - 5157m & 5177m - 5300m. Washed Down from 5300m - 5472m. Meanwhile Gradually Increasing M.WT. to 1.27 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/23/15 06:00 | 10/23/15 07:00 | [12 empty] | Reamed Down from 5472m to Bottom (5530m). | Productive
hvjg | gvjgv | vjhv | 0 | 10/23/15 07:00 | 10/23/15 13:00 | [12 empty] | Circ / Increased M.WT. to 1.27 S.G & Swept Hole with 30 BBL Hi-Vis Pill till shakers clean. Flow Checked - Ok.
hvjg | gvjgv | vjhv | 0 | 10/23/15 13:00 | 10/24/15 03:00 | [12 empty] | POOH to Surface - Observed Tight Spot & Pumped Out from 5530m to 5385m. Racked back BHA. L/Down Jar & Bit. While POOH Flow Checked at BHA. | Productive
hvjg | gvjgv | vjhv | 0 | 10/24/15 03:00 | 10/24/15 06:00 | [12 empty] | Held PJSM. R/Up SLB W/L Gear & Installed Shooting Nipple. M/Up & RIH SLB W/L Tools for "PEX-GR" Log to 2500m (Run # 4).
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/24/15 06:00 | 10/24/15 13:00 | [12 empty] | RIH SLB "PEX-GR" Tools from 2500m to Bottom & Recorded W/L Logs (Run # 4). POOH to Surface & L/Down W/L Tools & R/Down SLB W/L Gear. Monitored Well thru Trip Tank during W/L Logging.
hvjg | gvjgv | vjhv | 0 | 10/24/15 13:00 | 10/25/15 00:00 | [12 empty] | M/Up & RIH with 8-1/2" PDC Bit (23RR3) & 02 x S.Stabs to 9-5/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 10/25/15 00:00 | 10/25/15 01:00 | [12 empty] | Cut & Slipped 100ft Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | 10/25/15 01:00 | 10/25/15 06:00 | [12 empty] | Cont'd RIH from 9-5/8" Casing Shoe to 5375m. Observed Obstruction & Reamed / Washed Down from 5375m to 5446m & is in Progress. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 0 | 10/25/15 06:00 | 10/25/15 12:00 | [12 empty] | Washed Down from 5446m to 5462m and Reamed Down from 5462m to Bottom (5530m). Pumped 30 BBL Hi-Vis Pill. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/25/15 12:00 | 10/26/15 02:00 |  |  | 5530 | 5545 | [8 empty] | Drilled 8-1/2" Hole from 5530m to 5545m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/26/15 02:00 | 10/26/15 02:30 | [12 empty] | P/Up Off-Bottom to check Hole Condition - Observed Hi Off-Bottom Torque. Reamed & Cleared the same. | Productive
hvjg | gvjgv | vjhv | 8.5 | 10/26/15 02:30 | 10/26/15 06:00 |  |  | 5545 | 5549 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5545m to 5549m. Meanwhile Increasing M.WT. to 1.28 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 698 BBL
hvjg | gvjgv | vjhv | 8.5 | 10/26/15 06:00 | 10/26/15 19:30 |  |  | 5549 | 5560 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5549m to 5560m (Section TD). Reamed Twice at Connection @ 5559m. | Productive
hvjg | gvjgv | vjhv | 0 | 10/26/15 19:30 | 10/26/15 21:30 | [12 empty] | Observed Rotary Stalled & String Stuck @ 5559m While P/Up for Reaming After Drilling to TD. Also Observed Mud Losses & Lost 150 BBL Mud - Swept 25 BBL LCM Pill of 100 PPB. Worked & Released String with Upward Jarring. | Productive
hvjg | gvjgv | vjhv | 0 | 10/26/15 21:30 | 10/26/15 23:30 | [12 empty] | Reamed Back / Pumped Out to 5474m. Lost 75 BBL Mud. | Productive
hvjg | gvjgv | vjhv | 0 | 10/26/15 23:30 | 10/27/15 00:30 | [12 empty] | Spotted 25 BBL LCM of 100 PPB.
hvjg | gvjgv | vjhv | 0 | 10/27/15 00:30 | 10/27/15 04:30 | [12 empty] | POOH from 5474m to 9-5/8" Casing Shoe.
hvjg | gvjgv | vjhv | 0 | 10/27/15 04:30 | 10/27/15 05:30 | [12 empty] | Flow Checked - Ok. Circ. to Check for Dynamic Losses - No Loss. | Productive
hvjg | gvjgv | vjhv | 0 | 10/27/15 05:30 | 10/27/15 06:00 | [12 empty] | RIH from 9-5/8" Casing Shoe to 4871m & in Progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 225 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 923 BBL
hvjg | gvjgv | vjhv | 0 | 10/27/15 06:00 | 10/27/15 09:30 | [12 empty] | RIH from 4871m to 5540m.
hvjg | gvjgv | vjhv | 0 | 10/27/15 09:30 | 10/27/15 13:30 | [12 empty] | Hard Reamed with 2 Tons WOB from 5540m to Bottom (5560m). | Productive
hvjg | gvjgv | vjhv | 0 | 10/27/15 13:30 | 10/27/15 16:30 | [12 empty] | Swept 30 BBL LCM Pill of 30 PPB followed by 25 BBL Hi-Vis Pill till Shakers Clean & Spotted 30 BBL Hi-Vis Pill at Bottom. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 10/27/15 16:30 | 10/28/15 06:00 | [12 empty] | POOH from Bottom (5560m) to 87m - Hole Condition Good. While POOH Flow Checked at 9-5/8" Casing Shoe & BHA.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 923 BBL
hvjg | gvjgv | vjhv | 0 | 10/28/15 06:00 | 10/28/15 07:00 | [12 empty] | POOH Bit from 87m to Surface. R/Back BHA & L/Down Jar + Bit.
hvjg | gvjgv | vjhv | 0 | 10/28/15 07:00 | 10/28/15 08:00 | [12 empty] | R/Up Wellserve Casing Running Gear & Prepared Rig Floor to RIH 7" Liner. | Productive
hvjg | gvjgv | vjhv | 0 | 10/28/15 08:00 | 10/28/15 16:00 | [12 empty] | Held Pre-Job Safety Meeting. RIH 7" Liner [32 ppf, P-110, Vam Top] to 939m. Installed Reamer Shoe + Float Collar + Landing Collar + Centralizers + PipTag & Filled Up Liner as per Tally. Checked Integrity of Reamer Shoe + Float Collar While RIH. | Productive
hvjg | gvjgv | vjhv | 0 | 10/28/15 16:00 | 10/28/15 17:30 | [12 empty] | P/Up & M/Up 7" W.F Liner Hanger Assembly with "HNG" Setting Tool. Installed Liner Wiper Plug on Pick-Up sub with appropriate Shear Screws. Adjusted Shear Screws of Liner Hanger & Packer. Circ. one Liner Volume. Filled Up Liner Hanger PBR with Water & Checked Integrity of Pack Off Bushing - OK. Recorded Up and Down Liner Weight. R/Down Wellserve Casing Running Gear.
hvjg | gvjgv | vjhv | 0 | 10/28/15 17:30 | 10/29/15 06:00 | [12 empty] | Cont'd RIH 7" Liner on 5" DPs to 4129m. While RIH Filled Up DPs with Mud as per Program.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 923 BBL
hvjg | gvjgv | vjhv | 0 | 10/29/15 06:00 | 10/29/15 08:00 | [12 empty] | RIH 7" Liner on 5" x 5-1/2" DPs from 4129m to 9-5/8" Casing Shoe. While RIH Filled Up DPs with Mud as per Program.
hvjg | gvjgv | vjhv | 0 | 10/29/15 08:00 | 10/29/15 09:00 | [12 empty] | M/Up TDS & Circ. / Cond. Mud.
hvjg | gvjgv | vjhv | 0 | 10/29/15 09:00 | 10/29/15 14:00 | [12 empty] | Cont'd RIH 7" Liner on 5" x 5-1/2" DPs from 9-5/8" Casing Shoe & Tagged Bottom @ 5560m. Washed Down Last 02 Stands & Reamed Down from 5555m to 5560m. Meanwhile Prepared MUDPUSH II (Spacer) in Mud Tanks. | Productive
hvjg | gvjgv | vjhv | 0 | 10/29/15 14:00 | 10/29/15 16:00 | [12 empty] | Circ. / Bottom Up & Conditioned Mud.
hvjg | gvjgv | vjhv | 0 | 10/29/15 16:00 | 10/29/15 19:00 | [12 empty] | Stopped Circ. & Installed W.F Plug Dropping Head (Pre-Loaded with DP Dart). Dropped Liner Hanger Setting Ball & Chased the same with Mud. Observed Ball Seated & Press Increased - Set Liner Hanger @ 2000 psi / Released Setting Tool @ 2200 psi with 55 Ton Compression / Sheared Ball Seat @ 2800 psi.
hvjg | gvjgv | vjhv | 0 | 10/29/15 19:00 | 10/29/15 20:00 | [12 empty] | Resumed Circ. & Conditioned Mud.
hvjg | gvjgv | vjhv | 0 | 10/29/15 20:00 | 10/29/15 20:30 | [12 empty] | Stopped Circ. R/Up & Press Tested SLB Cement Lines & 5000 psi - Ok.
hvjg | gvjgv | vjhv | 0 | 10/29/15 20:30 | 10/29/15 23:30 | [12 empty] | Resumed Circ. & Conditioned Mud. Meanwhile Prepared 150 BBL Batch Mixed Cement Slurry of 15.8 PPG (1.90 S.G). | Productive
hvjg | gvjgv | vjhv | 0 | 10/29/15 23:30 | 10/30/15 02:30 | [12 empty] | Held Pre-Job Safety Meeting. Pumped 30 BBL CW-100 (Chemical Wash) thru Cement Unit & 80 BBL Spacer thru Rig Pump @ 5 BPM. Switch Back to Cement Unit & Pumped 150 BBL Cement Slurry @ 5 BPM. Dropped Drill Pipe Dart. Displaced Cement Slurry with 10 BBL Spacer + 80 BBL Mud + 20 BBL Water + 20 BBL Spacer + 250 BBL Mud (Total Displacement = 380 BBL) @ 5 BPM thru Cement Unit. Observed Plugs Bumped / Increased Press to 3200 psi & Held for 10 Min. Bled Off Press - 03 BBL Returns & No Back Flow. No Loss During Cement Job. | Productive
hvjg | gvjgv | vjhv | 0 | 10/30/15 02:30 | 10/30/15 05:30 | [12 empty] | R/Down Cement Lines. P/Up String after Several Attempts with Overpull & Set Packer with 35 Ton Compression. P/Back to 4556m / Rig Down Plug Dropping Head & Reverse Circ. 02 String Volumes. Dumped 15 BBL Contaminated Mud / Spacer + 15 BBL Neat Cement + 40 BBL Contaminated Cement / Spacer / Mud @ Bottom Up.
hvjg | gvjgv | vjhv | 0 | 10/30/15 05:30 | 10/30/15 06:00 | [12 empty] | POOH from 4556 to 4351m.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses during 24 hrs:
hvjg | gvjgv | vjhv | 0 | [14 empty] | Mud: 0 BBL / LCM: 0 BBL --Total Downhole Fluid Loss: 923 BBL
hvjg | gvjgv | vjhv | 0 | 10/30/15 06:00 | 10/30/15 18:00 | [12 empty] | POOH from 4351m to Surface & L/Down Liner Hanger Setting Tool.
hvjg | gvjgv | vjhv | 0 | 10/30/15 18:00 | 10/31/15 05:00 | [12 empty] | M/Up & RIH 8-1/2" Bit (23RR4) with Slick Rotary BHA to 4468m.
hvjg | gvjgv | vjhv | 0 | 10/31/15 05:00 | 10/31/15 06:00 | [12 empty] | Washed Down Precautionary from 4468m to 4553m & in Progress (To Tag Top of 7" Liner @ ± 4613m).
hvjg | gvjgv | vjhv | 0 | 10/31/15 06:00 | 10/31/15 07:00 | [12 empty] | Cont'd Washed Down from 4553m & Tagged Top of 7" Liner @ 4613m.
hvjg | gvjgv | vjhv | 0 | 10/31/15 07:00 | 10/31/15 09:00 | [12 empty] | Circ. / Cleaned Hole - Observed LCM (CemNet) @ Shakers.
hvjg | gvjgv | vjhv | 0 | 10/31/15 09:00 | 10/31/15 14:30 | [12 empty] | POOH from 4613m to 3771m & L/Down 29 x 5-1/2" DP Stands (87 Singles) While POOH.
hvjg | gvjgv | vjhv | 0 | 10/31/15 14:30 | 10/31/15 16:30 | [12 empty] | RIH 24 x 5-1/2" DP Stands from Derrick from 3771m to 4471m.
hvjg | gvjgv | vjhv | 0 | 10/31/15 16:30 | 10/31/15 20:30 | [12 empty] | POOH from 4471m to 3771 & L/Down 24 x 5-1/2" DP Stands (72 Singles) While POOH.
hvjg | gvjgv | vjhv | 0 | 10/31/15 20:30 | 10/31/15 21:30 | [12 empty] | RIH 13 x 5-1/2" DP Stands from Derrick from 3771m to 4471m.
hvjg | gvjgv | vjhv | 0 | 10/31/15 21:30 | 11/01/15 00:30 | [12 empty] | Found Draw Works Stuffing Box Seal Leaked & Gear Oil Mixed with Water - Changed Draw Works Gear Oil. | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/01/15 00:30 | 11/01/15 06:00 | [12 empty] | RIH Remaining 4 x 5-1/2" DP Stands from 4154m to 4262m & POOH from 4262m to 2975m. L/Down 17 x 5-1/2" DP (51 Sgls) Stands While POOH.
hvjg | gvjgv | vjhv | 0 | 11/01/15 06:00 | 11/01/15 15:00 | [12 empty] | Cont'd POOH from 2975m to Surface. L/Down Complete BHA + Jar + Bit While POOH.
hvjg | gvjgv | vjhv | 0 | 11/01/15 15:00 | 11/01/15 16:30 | [12 empty] | Changed TDS Saver Sub & Dies to 4-1/2 IF.
hvjg | gvjgv | vjhv | 0 | 11/01/15 16:30 | 11/01/15 18:30 | [12 empty] | Changed BOP Upper Pipe Rams from 5-1/2" to Variable Pipe Rams (2-7/8" - 5" Range).
hvjg | gvjgv | vjhv | 0 | 11/01/15 18:30 | 11/02/15 02:00 | [12 empty] | Held PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Variable Pipe Rams (With Both 5" DP & 3-1/2" DP) + Lower Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 8000 psi High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 11/02/15 02:00 | 11/02/15 03:00 | [12 empty] | Attempted to M/Up 6" Tricone Bit (25RR) with Bit Sub. Found Bit Breaker Not Compatible with Bit - Dressed / Grinded Bit Breaker. | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/02/15 03:00 | 11/02/15 06:00 | [12 empty] | P/Up New BHA Single by Single from Pipe Racks & RIH 6" Tricone Bit to 211m (Torqued Up - Break Out & Re-Torqued New BHA). | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/02/15 06:00 | 11/02/15 06:30 | [12 empty] | Cont'd RIH from 211m to 240m with New BHA.
hvjg | gvjgv | vjhv | 0 | 11/02/15 06:30 | 11/02/15 08:00 | [12 empty] | Cut & Slipped 108' Drill Line. | Productive
hvjg | gvjgv | vjhv | 0 | 11/02/15 08:00 | 11/03/15 06:00 | [12 empty] | Cont'd RIH with 6" Bit (RR) from 240m to 3779m. While RIH P/Up 117 x G-105 3-1/2" DPs (New) + 63 x G-105 5" DPs + 48 x S-135 5" DPs Single by Single from Pipe Racks - (Torqued Up - Break Out & Re-Torqued New DPs). | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/03/15 06:00 | 11/03/15 11:30 | [12 empty] | Cont'd RIH from 3779m & Tagged Compression @ 5404m.
hvjg | gvjgv | vjhv | 0 | 11/03/15 11:30 | 11/03/15 14:00 | [12 empty] | Washed Down from 5404m to 5418m / Reamed Down from 5418m & Tagged Plugs / Landing Collar @ 5521m. Observed LCM (CemNet) & Cement Traces on Shakers. | Productive
hvjg | gvjgv | vjhv | 0 | 11/03/15 14:00 | 11/04/15 00:30 |  |  |  | 5555 | [8 empty] | Drilled Out Plugs / Landing Collar & COC. Tagged Float Collar @ 5534m & COC to 5555m (4m above R/Shoe). | Productive
hvjg | gvjgv | vjhv | 0 | 11/04/15 00:30 | 11/04/15 03:30 | [12 empty] | Circ. / Swept 20 BBL Hi-Vis Pill till Shakers Clean.
hvjg | gvjgv | vjhv | 0 | 11/04/15 03:30 | 11/04/15 06:00 | [12 empty] | POOH from 5555m to 4548m.
hvjg | gvjgv | vjhv | 0 | 11/04/15 06:00 | 11/04/15 19:30 | [12 empty] | Cont'd POOH 6" Bit from 4548m to Surface. While POOH L/Down BHA for Inspection. | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/04/15 19:30 | 11/05/15 06:00 | [12 empty] | Held PJSM. R/Up SLB W/Line Gear. M/Up & RIH SLB Junk Basket to 5555m & POOH to Surface - No Junk Found. M/Up & RIH "CBL-VDL-CCL-GR" Tools to 5555m & Recorded Logs from 5555m to 4613m (Top of 7" Liner). POOH W/Line to 960m. Meanwhile Inspected Complete BHA - Found OK.
hvjg | gvjgv | vjhv | 0 | 11/05/15 06:00 | 11/05/15 07:30 | [12 empty] | Cont'd POOH W/Line from 960m to Surface. R/Down W/Line Tools & SLB W/Line Gear.
hvjg | gvjgv | vjhv | 0 | 11/05/15 07:30 | 11/05/15 11:00 | [12 empty] | M/Up New 6" PDC Bit & RIH with MWD & PBL Sub. Performed Shallow Function Test of MWD @ 260 GPM & 600 PSI SPP. Function Test PBL Sub by Activating & Deactivating through sequence of 1-1/2" & 1-3/8" Balls at 150 PSI & 1470 PSI Respectively.
hvjg | gvjgv | vjhv | 0 | 11/05/15 11:00 | 11/06/15 01:30 | [12 empty] | P/Up Inspected BHA from Pipe Racks & RIH 6" PDC Bit to 4600m (Above TOL). While RIH Filled Up String with Mud.
hvjg | gvjgv | vjhv | 0 | 11/06/15 01:30 | 11/06/15 02:30 | [12 empty] | M/Up TDS. Broke Circ. & Press Tested 7" Liner to 3500 PSI in Increments & Held Final Press for 10 Mins - OK.
hvjg | gvjgv | vjhv | 0 | 11/06/15 02:30 | 11/06/15 06:00 | [12 empty] | Cont'd RIH from 4600m to 5535m. Washed Down from 5535m & Tagged Cement @ 5555m.
hvjg | gvjgv | vjhv | 0 | 11/06/15 06:00 | 11/06/15 08:30 | [12 empty] | COC from 5555m & Drilled Out Reamer Shoe @ 5560m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/06/15 08:30 | 11/06/15 12:00 |  |  | 5560 | 5565 | [8 empty] | Commenced 6" Hole Drilling & Drilled Formation from 5560m to 5565m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/06/15 12:00 | 11/06/15 14:00 | [12 empty] | Circ. / Cleaned Hole & Homogenized Mud Column Prior to FIT.
hvjg | gvjgv | vjhv | 0 | 11/06/15 14:00 | 11/06/15 15:30 | [12 empty] | Held PJSM. R/Up & Press Tested SLB Cement Lines to 2500 PSI. Conducted FIT to 1.40 S.G EMW (950 PSI Surface Press) - OK. R/Down SLB Lines.
hvjg | gvjgv | vjhv | 6 | 11/06/15 15:30 | 11/07/15 06:00 |  |  | 5565 | 5588 | [8 empty] | Cont'd Drilling & Drilled 6" Hole from 5565m to 5588m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/07/15 06:00 | 11/07/15 06:00 |  |  | 5588 | 5609 | [8 empty] | Drilled 6" Hole from 5588m to 5609m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 6 | 11/08/15 06:00 | 11/08/15 06:00 |  |  | 5609 | 5629 | [8 empty] | Drilled 6" Hole from 5609m to 5629m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 6 | 11/09/15 06:00 | 11/09/15 06:00 |  |  | 5629 | 5650 | [8 empty] | Drilled 6" Hole from 5629m to 5650m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 6 | 11/10/15 06:00 | 11/10/15 06:00 |  |  | 5650 | 5665 | [8 empty] | Drilled 6" Hole from 5650m to 5665m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/11/15 06:00 | 11/11/15 09:00 |  |  | 5665 | 5667 | [8 empty] | Drilled 6" Hole from 5665m to 5667m. Stopped Drilling & Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 11/11/15 09:00 | 11/11/15 10:00 | [12 empty] | POOH from 5667m to 5535m (Inside 7" Liner Shoe) for Wiper Trip. | Productive
hvjg | gvjgv | vjhv | 0 | 11/11/15 10:00 | 11/11/15 10:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 11/11/15 10:30 | 11/11/15 12:30 | [12 empty] | RIH from 5535m to 5659m & Observed Compression. Reamed Down from 5659m to 5667m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/11/15 12:30 | 11/12/15 06:00 |  |  | 5667 | 5678 | [8 empty] | Resumed Drilling & Drilled 6" Hole from 5667m to 5678m. Now Reaming before Connection. | Productive
hvjg | gvjgv | vjhv | 0 | 11/12/15 06:00 | 11/12/15 07:30 | [12 empty] | Reamed Twice at Connection - Observed Hi-Torque & Rotary Stalled Frequently. | Productive
hvjg | gvjgv | vjhv | 6 | 11/12/15 07:30 | 11/12/15 15:00 |  |  | 5678 | 5682 | [8 empty] | Drilled 6" Hole from 5678m to 5682m. Meanwhile Increased M.WT. to 1.30 S.G. Stopped Drilling. | Productive
hvjg | gvjgv | vjhv | 0 | 11/12/15 15:00 | 11/12/15 16:00 | [12 empty] | Circ. / Cleaned Hole. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 11/12/15 16:00 | 11/13/15 06:00 | [12 empty] | POOH from 5678m to 558m for Bit Trip.
hvjg | gvjgv | vjhv | 0 | 11/13/15 06:00 | 11/13/15 11:00 | [12 empty] | POOH Bit from 558m to Surface & L/Down Complete BHA for Inspection While POOH. | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/13/15 11:00 | 11/13/15 11:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 11/13/15 11:30 | 11/13/15 20:00 | [12 empty] | Held PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 500 psi Low & 4500 psi - OK. Press Tested Upper Variable Pipe Rams (With Both 5" DP & 3-1/2" DP) + Lower Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 500 psi Low & 8000 psi High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy. Meanwhile Inspected (MPI) Complete BHA.
hvjg | gvjgv | vjhv | 0 | 11/13/15 20:00 | 11/14/15 06:00 | [12 empty] | M/Up New 6" PDC Bit & RIH with MWD & PBL Sub. Performed Shallow Function Test of MWD @ 260 GPM & 520 PSI SPP. P/Up Inspected BHA from Pipe Racks & RIH to 2096m. While RIH Filled Up String with Mud after every 15 Stds.
hvjg | gvjgv | vjhv | 0 | 11/14/15 06:00 | 11/14/15 15:30 | [12 empty] | Cont'd RIH New 6" PDC Bit with MWD from 2096m to 5510m.
hvjg | gvjgv | vjhv | 0 | 11/14/15 15:30 | 11/14/15 17:00 | [12 empty] | Cut and Slipped 100' Drilling Line. | Productive
hvjg | gvjgv | vjhv | 0 | 11/14/15 17:00 | 11/14/15 20:30 | [12 empty] | RIH from 5510m to 5601m & Observed Compression. Reamed Down from 5601m to Bottom (WOB = 2 Ton + RPM = 60 + GPM = 260). Recorded MWD Surveys at each Stand While RIH Below 7" Liner Shoe. | Productive
hvjg | gvjgv | vjhv | 6 | 11/14/15 20:30 | 11/15/15 06:00 |  |  | 5682 | 5700 | [8 empty] | Resumed Drilling & Drilled 6" Hole from 5682m to 5700m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/15/15 06:00 | 11/15/15 06:00 |  |  | 5700 | 5735 | [8 empty] | Drilled 6" Hole from 5700m to 5735m. Reamed Twice at Connection. Recorded MWD Survey at Connection & Checkshot at 5711m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/16/15 06:00 | 11/16/15 06:00 |  |  | 5735 | 5761 | [8 empty] | Drilled 6" Hole from 5735m to 5761m. Reamed Twice at Connection. Recorded MWD Survey at 5725m & 5740m. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | "Tentative Top of WARGAL Formation Marked @ 5758m (MD)"
hvjg | gvjgv | vjhv | 6 | 11/17/15 06:00 | 11/17/15 06:00 |  |  | 5761 | 5777 | [8 empty] | Drilled 6" Hole from 5761m to 5777m. Reamed Twice at Connection. Recorded MWD Survey at 5754m & 5767m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/18/15 06:00 | 11/18/15 11:00 |  |  | 5777 | 5779 | [8 empty] | Drilled 6" Hole from 5777m to 5779m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/18/15 11:00 | 11/18/15 12:30 | [12 empty] | Circulated hole prior to POOH. Recorded MWD Checkshot @ 5770m (5.75 / 66.08 deg). | Productive
hvjg | gvjgv | vjhv | 0 | 11/18/15 12:30 | 11/19/15 05:00 | [12 empty] | Flow checked, found Well Static. POOH from 5779m to Top of BHA @ 247m. Flow checked @ Top of BHA, found Well Static. POOH from 247m to Surface, L/D BHA single by single for inspection. Retrieved MWD tool, L/D HOC & Bit. | Non Productive
hvjg | gvjgv | vjhv | 0 | 11/19/15 05:00 | 11/19/15 06:00 | [12 empty] | P/U New 6" PDC Bit & M/U with 4-3/4" M.Motor. Installed HOC & placed MWD tool iside, set Adjusted Bend Housing (ABH) to 1.5 deg.
hvjg | gvjgv | vjhv | 0 | 11/19/15 06:00 | 11/19/15 08:00 | [12 empty] | P/U & M/U 4-3/4" HOC, inserted MWD tool inside HOC & took Rig Floor Off-Set (RFO). Performed Shallow Pulse test @ 215 GPM & 950 Psi, OK. M/Up & Function Tested PBL Sub. Observed PBL Ports Opened @ 100 psi & Closed @ 2400 psi, OK.
hvjg | gvjgv | vjhv | 0 | 11/19/15 08:00 | 11/20/15 01:30 | [12 empty] | P/U Inspected BHA from CatWalk & RIH 6" PDC Bit with Directional BHA down to 5565m. Filled Up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 11/20/15 01:30 | 11/20/15 02:00 | [12 empty] | Broke circulation & checked MWD Signals, OK.
hvjg | gvjgv | vjhv | 0 | 11/20/15 02:00 | 11/20/15 04:30 | [12 empty] | RIH from 5565m to 5576m, observed 5 Tons compression @ 5576m. Reamed & Washed down from 5565m to Bottom @ 5779m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 04:30 | 11/20/15 06:00 |  |  | 5779 | 5782 | [8 empty] | Broke Bit & Drilled 6" Hole from 5779m to 5782m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Conducted Fire Drill @ 16:00 Hrs, Poor Response | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 06:00 | 11/20/15 10:30 |  |  | 5782 | 5788 | [8 empty] | Drilled 6" Hole from 5782m to 5788m in Slide Mode. | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 10:30 | 11/20/15 16:00 |  |  | 5788 | 5798 | [8 empty] | Drilled 6" Hole from 5788m to 5798m in Rotary Mode. Reamed before connection & Recorded MWD Survey @ 5780m (5.80 deg / 66.75 Azm). | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 16:00 | 11/20/15 19:00 |  |  | 5798 | 5804 | [8 empty] | Drilled 6" Hole from 5798m to 5804m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 19:00 | 11/20/15 20:00 |  |  | 5804 | 5807 | [8 empty] | Drilled 6" Hole from 5804m to 5807m in Slide Mode. | Productive
hvjg | gvjgv | vjhv | 6 | 11/20/15 20:00 | 11/21/15 06:00 |  |  | 5807 | 5825 | [8 empty] | Drilled 6" Hole from 5807m to 5825m in Rotary Mode. Recorded MWD Checkshot @ 5802m (3.91 deg / 66.29 Azm). | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Rig Power Shut-Down for 15 min @ 15:30 Hrs
hvjg | gvjgv | vjhv | 6 | 11/21/15 06:00 | 11/21/15 07:00 |  |  | 5825 | 5826 | [8 empty] | Drilled 6" Hole from 5825m to 5826m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 11/21/15 07:00 | 11/21/15 07:30 | [12 empty] | Reamed before connection & Recorded MWD Survey @ 5809m (3.30 deg / 55.18 Azm). | Productive
hvjg | gvjgv | vjhv | 6 | 11/21/15 07:30 | 11/22/15 05:30 |  |  | 5826 | 5855 | [8 empty] | Drilled 6" Hole from 5826m to 5855m in Rotary Mode. | Productive
hvjg | gvjgv | vjhv | 0 | 11/22/15 05:30 | 11/22/15 06:00 | [12 empty] | Reamed before connection & Recorded MWD Survey @ 5837m (3.10 deg / 48.40 Azm). | Productive
hvjg | gvjgv | vjhv | 6 | 11/22/15 06:00 | 11/22/15 06:00 |  |  | 5855 | 5883 | [8 empty] | Drilled 6" Hole from 5855m to 5883m in Rotary Mode. Recorded MWD Checkshot @ 5847m (3.11 deg / 44.3 Azm). | Productive
hvjg | gvjgv | vjhv | 0 | 11/23/15 06:00 | 11/23/15 07:00 | [12 empty] | Reamed before connection & Recorded MWD Survey @ 5866m (3.56 deg / 37.70 Azm). | Productive
hvjg | gvjgv | vjhv | 6 | 11/23/15 07:00 | 11/23/15 17:00 |  |  | 5883 | 5900 | [8 empty] | Drilled 6" Hole from 5883m to 5900m in Rotary Mode. Marked Well TD. | Productive
hvjg | gvjgv | vjhv | 0 | 11/23/15 17:00 | 11/23/15 20:00 | [12 empty] | Recorded MWD Survey @ 5882m (3.70 deg / 37.53 Azm). Circulated to clean hole. | Productive
hvjg | gvjgv | vjhv | 0 | 11/23/15 20:00 | 11/24/15 04:00 | [12 empty] | Flow checked, Well Static. Conducted Wiper Trip up to 7" Liner shoe @ 5560m (Observed tight spots @ 5849m & 5793m, max. O/pull 10 Tons. Back Reamed from 5849m to 5826m). Flow checked, Well Static. RIH from 5560m to 5604m, observed obstruction @ 5604m. Reamed / Washed down from 5604m to Bottom @ 5900m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 04:00 | 11/24/15 06:00 | [12 empty] | Pumped 30 bbls Hi-Vis pill & circulated out meanwhile conditioned mud is in progress. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 06:00 | 11/24/15 08:00 | [12 empty] | Conditioned mud & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 08:00 | 11/24/15 11:30 | [12 empty] | Flow checked, Well Static. POOH from 5900m to 5541m inside 7" Liner shoe. Observed tight spots @ 5883m, 5826m, 5811m, 5717m & 5670m. Pumped out of hole from 5883m to 5683m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 11:30 | 11/24/15 12:00 | [12 empty] | Flow checked, Well Static. Performed Kick Drill. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 12:00 | 11/24/15 14:00 | [12 empty] | Worked on TDS.
hvjg | gvjgv | vjhv | 0 | 11/24/15 14:00 | 11/24/15 16:00 | [12 empty] | RIH from 5541m to Bottom @ 5900m. Reamed / Washed down last stand. | Productive
hvjg | gvjgv | vjhv | 0 | 11/24/15 16:00 | 11/25/15 02:30 | [12 empty] | Circulated hole to increase MW from 1.30 S.G to 1.35 S.G. | Productive
hvjg | gvjgv | vjhv | 0 | 11/25/15 02:30 | 11/25/15 04:30 | [12 empty] | Flow checked, Well Static. POOH from 5900m to 5541m inside 7" Liner shoe, Hole condition is GOOD.
hvjg | gvjgv | vjhv | 0 | 11/25/15 04:30 | 11/25/15 05:00 | [12 empty] | Flow checked, Well Static.
hvjg | gvjgv | vjhv | 0 | 11/25/15 05:00 | 11/25/15 06:00 | [12 empty] | POOH from 5541m to 5199m (in progress).
hvjg | gvjgv | vjhv | 0 | 11/25/15 06:00 | 11/25/15 20:30 | [12 empty] | Continued POOH from 5199m to Top of BHA @ 223m. Flow checked, Well Static. POOH from 223m to Surface, racked back BHA. Retrieved MWD Tool & L/D Bit, Mud Motor, HOC & PBL Sub.
hvjg | gvjgv | vjhv | 0 | 11/25/15 20:30 | 11/25/15 22:00 | [12 empty] | R/U SLB W/L Gears & installed Shooting Nipple.
hvjg | gvjgv | vjhv | 0 | 11/25/15 22:00 | 11/26/15 04:00 | [12 empty] | Held PJSM, Pressure tested W/L BOP @ 300 Psi, OK. M/U & RIH SLB W/L Tools, Run # 1 (SP-HRLA-CAL-GR) Logs to 5700m. Observed obstruction @ 5700m, Tools could not pass below 5700m despite of several attempts. Conduct W/L Logging to 5700m & POOH to Surface, L/D SLB W/L Tools. | Productive
hvjg | gvjgv | vjhv | 0 | 11/26/15 04:00 | 11/26/15 05:00 | [12 empty] | R/D SLB W/L Gears & L/D Shooting Nipple.
hvjg | gvjgv | vjhv | 0 | 11/26/15 05:00 | 11/26/15 06:00 | [12 empty] | P/U & M/U RR 6" PDC Bit & RIH down to 79m on Pendulum BHA.
hvjg | gvjgv | vjhv | 0 | 11/26/15 06:00 | 11/26/15 21:00 | [12 empty] | RIH from 79m to 7" Liner Shoe @ 5560m. Filled up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 11/26/15 21:00 | 11/26/15 22:00 | [12 empty] | Cut & Slipped 92' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 11/26/15 22:00 | 11/27/15 06:00 | [12 empty] | Resumed RIH from 5560m to 5604m, observed tight spot @ 5604m (max. 10 Tons Compression). Reamed / Washed down from 5604m to 5855m, Hard Reaming from 5855m to 5865m (in progress). | Productive
hvjg | gvjgv | vjhv | 0 | 11/27/15 06:00 | 11/27/15 10:00 | [12 empty] | Continued Hard Reaming from 5865m to Bottom @ 5900m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/27/15 10:00 | 11/27/15 13:00 | [12 empty] | Pumped 30 bbls Hi-Vis pill & circulated out till shakers clean. | Productive
hvjg | gvjgv | vjhv | 0 | 11/27/15 13:00 | 11/27/15 23:30 | [12 empty] | Flow checked, Well Static. POOH from 5900m to 5560m @ 7" Liner shoe (observed O/pull of max. 8 Tons @ 5882m. Pumped out of Hole from 5882m to 5855m). RIH from 5560m to Bottom @ 5900m (observed Compression of max. 10 Tons @ 5665m. Reamed / Washed down from 5665m to 5684m). | Productive
hvjg | gvjgv | vjhv | 0 | 11/27/15 23:30 | 11/28/15 05:00 | [12 empty] | Circulated Hole to condition / homogenise mud. | Productive
hvjg | gvjgv | vjhv | 0 | 11/28/15 05:00 | 11/28/15 06:00 | [12 empty] | Flow checked, Well Static. POOH from 5900m to 5656m, Hole Slick.
hvjg | gvjgv | vjhv | 0 | 11/28/15 06:00 | 11/28/15 21:00 | [12 empty] | POOH from 5656m to Surface, L/D 6" Bit & Jar (Meanwhile Inspected 3-1/2" Tubing, performed VTI & Drifted all Joints).
hvjg | gvjgv | vjhv | 0 | 11/28/15 21:00 | 11/28/15 23:00 | [12 empty] | Made preparations & R/U ITS TRS Gears.
hvjg | gvjgv | vjhv | 0 | 11/28/15 23:00 | 11/29/15 06:00 | [12 empty] | Held PJSM, P/U & M/U 4-3/4" Mule Shoe + Landing Ring & RIH down to 874m on 3-1/2" Tubing. Broke circulation @ 479m.
hvjg | gvjgv | vjhv | 0 | 11/29/15 06:00 | 11/29/15 09:00 | [12 empty] | RIH 3-1/2" Tubing from 479m to 1351m single by single.
hvjg | gvjgv | vjhv | 0 | 11/29/15 09:00 | 11/29/15 10:00 | [12 empty] | Circulated @ 1351m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/29/15 10:00 | 11/29/15 11:00 | [12 empty] | RIH 2 x 5" DP Stands from 1351m to 1407m meanwhile R/Down ITS.
hvjg | gvjgv | vjhv | 0 | 11/29/15 11:00 | 11/29/15 13:30 | [12 empty] | R/Up Weatherford W/L Gears for CDO Dummy Run. RIH Weatherford CDO Tools to 1407m, Released & Re-Lached again. POOH to Surface, found Tools left in String. L/D Weatherford W/L Gears.
hvjg | gvjgv | vjhv | 0 | 11/29/15 13:30 | 11/29/15 20:30 | [12 empty] | POOH from 1407m to Surface. Retrieved Tools from Landing Ring.
hvjg | gvjgv | vjhv | 0 | 11/29/15 20:30 | 11/30/15 06:00 | [12 empty] | R/Up ITS, RIH 4-3/4" Mule Shoe + Landing Ring on 3-1/2" Tubing & 5" DP Stands down to 3707m.
hvjg | gvjgv | vjhv | 0 | 11/30/15 06:00 | 11/30/15 12:30 | [12 empty] | Continued RIH 4-3/4" Mule Shoe + Landing Ring on 5" DPs from 3707m to 5875m. Washed down from 5875m to Bottom @ 5900m.
hvjg | gvjgv | vjhv | 0 | 11/30/15 12:30 | 11/30/15 15:30 | [12 empty] | Circulated to condition hole. | Productive
hvjg | gvjgv | vjhv | 0 | 11/30/15 15:30 | 11/30/15 17:00 | [12 empty] | Spaced out for W/L Tools & POOH 2 x 5" DP Stands from 5900m to 5847m, racked back the same. Changed TDS Links meanwhile circulated hole. | Productive
hvjg | gvjgv | vjhv | 0 | 11/30/15 17:00 | 12/01/15 02:00 | [12 empty] | R/Up Weatherford W/L Gears for CDO Logging Run # 1. P/U W/L Tools Run # 1 (HRAL-SONIC-GR-SP) & RIH down to 5847m. Released Tools & POOH to Surface.
hvjg | gvjgv | vjhv | 0 | 12/01/15 02:00 | 12/01/15 02:30 | [12 empty] | R/Down W/L Gears & Changed TDS Links.
hvjg | gvjgv | vjhv | 0 | 12/01/15 02:30 | 12/01/15 05:30 | [12 empty] | Conduct Logging from 5884.90m to 5428m inside 7" Liner.
hvjg | gvjgv | vjhv | 0 | 12/01/15 05:30 | 12/01/15 06:00 | [12 empty] | R/Up Weatherford W/L Gears to retrieve W/L Tools.
hvjg | gvjgv | vjhv | 0 | 12/01/15 06:00 | 12/01/15 12:30 | [12 empty] | RIH Weatherford W/L to 5428m & Retrived W/L Tools Run # 1 to Surface. L/D Weatherford W/L Tools.
hvjg | gvjgv | vjhv | 0 | 12/01/15 12:30 | 12/01/15 13:30 | [12 empty] | RIH from 5428m to 5875m. Washed down from 5875m to 5900m.
hvjg | gvjgv | vjhv | 0 | 12/01/15 13:30 | 12/01/15 18:00 | [12 empty] | Pumped 30 bbls Hi-Vis pill & Circulated out to homogenize Mud. | Productive
hvjg | gvjgv | vjhv | 0 | 12/01/15 18:00 | 12/01/15 19:00 | [12 empty] | Spaced out for W/L Tools & POOH to 5866m. Changed TDS Links.
hvjg | gvjgv | vjhv | 0 | 12/01/15 19:00 | 12/02/15 04:00 | [12 empty] | R/Up Weatherford W/L Gears for CDO Logging Run # 2. P/U W/L Tools Run # 2 (MPD-MDN-SGR-CALI) & RIH down to 5866m. Released Tools & POOH to Surface.
hvjg | gvjgv | vjhv | 0 | 12/02/15 04:00 | 12/02/15 04:30 | [12 empty] | R/Down W/L Gears & Changed TDS Links.
hvjg | gvjgv | vjhv | 0 | 12/02/15 04:30 | 12/02/15 06:00 | [12 empty] | Conduct Logging from 5891.83m to 5676m.
hvjg | gvjgv | vjhv | 0 | 12/02/15 06:00 | 12/02/15 07:00 | [12 empty] | Continued Logging from 5676m to 5477.51m inside 7" Liner.
hvjg | gvjgv | vjhv | 0 | 12/02/15 07:00 | 12/02/15 13:30 | [12 empty] | R/U Weatherford W/L & RIH down to 5477m. Retrieved W/L Tools Run # 2 to Surface. L/D Weatherford W/L Tools & R/D W/L.
hvjg | gvjgv | vjhv | 0 | 12/02/15 13:30 | 12/03/15 03:00 | [12 empty] | POOH from 5477.51m to 1354m. R/U ITS Gears, resumed POOH 3-1/2" Tubing from 1354m to Surface. L/D 4-3/4" Mule Shoe + 4-3/4" Landing Ring & R/D ITS Gears.
hvjg | gvjgv | vjhv | 0 | 12/03/15 03:00 | 12/03/15 06:00 | [12 empty] | P/U & M/U R3 6" PDC Bit & RIH down to 934m for Condition Trip. Filled Up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 12/03/15 06:00 | 12/03/15 19:00 | [12 empty] | RIH 6" PDC Bit from 934m to 5539m. Filled Up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 12/03/15 19:00 | 12/03/15 20:00 | [12 empty] | Cut & Slipped 98' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 12/03/15 20:00 | 12/03/15 22:00 | [12 empty] | Resumed RIH from 5539m to Bottom @ 5900m on elevators. Observed tight spots @ 5665m, 5690m & 5791m (max. Compression 3-4 Tons), cleared the same with reciprocation. Washed down last Stand. Hole condition is GOOD.
hvjg | gvjgv | vjhv | 0 | 12/03/15 22:00 | 12/04/15 02:00 | [12 empty] | Circulated to Condition Mud. | Productive
hvjg | gvjgv | vjhv | 0 | 12/04/15 02:00 | 12/04/15 06:00 | [12 empty] | Flow Checked, Well Static. POOH from 5900m to 4571m.
hvjg | gvjgv | vjhv | 0 | 12/04/15 06:00 | 12/04/15 17:00 | [12 empty] | POOH from 4571m to Surface. L/D 6" Bit & S. Stabs.
hvjg | gvjgv | vjhv | 0 | 12/04/15 17:00 | 12/04/15 21:00 | [12 empty] | P/U & M/U Weatherford BHA for CWS Logging Run # 1, placed Logging Tools (CMI-GR) inside it.
hvjg | gvjgv | vjhv | 0 | 12/04/15 21:00 | 12/05/15 00:00 | [12 empty] | P/U 3-1/2" DPs from Catwalk Single by Single & RIH down to 234m.
hvjg | gvjgv | vjhv | 0 | 12/05/15 00:00 | 12/05/15 06:00 | [12 empty] | RIH 42 x 3-1/2" DP + 37 x 5" DP Stands from 234m to 2489m meanwhile Drifted all Stands with 2.125" Drift. Filled Up String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 12/05/15 06:00 | 12/05/15 15:00 | [12 empty] | RIH from 2489m to 5809m. Filled String after every 15 Stands.
hvjg | gvjgv | vjhv | 0 | 12/05/15 15:00 | 12/05/15 18:30 | [12 empty] | Spaced out for Logging Tools & POOH to 5795m. Circulated hole at different pumping rates & noted SPP. Dropped Dart & displaced at 10 SPM, 210 Psi pressure, Dart bumped. Observed pressure spike & pressure dropped to 162 Psi. Gradually increased pumping rate & made confirmation of Logging Tools deployment. | Productive
hvjg | gvjgv | vjhv | 0 | 12/05/15 18:30 | 12/05/15 21:00 | [12 empty] | Conduct logging from 5806m to 5490m inside 7" Liner.
hvjg | gvjgv | vjhv | 0 | 12/05/15 21:00 | 12/05/15 21:30 | [12 empty] | Flow checked, Well Static. Pumped 30 bbls Slug. | Productive
hvjg | gvjgv | vjhv | 0 | 12/05/15 21:30 | 12/06/15 06:00 | [12 empty] | POOH from 5490m to 1316m.
hvjg | gvjgv | vjhv | 0 | 12/06/15 06:00 | 12/06/15 09:30 | [12 empty] | POOH from 1316m to Surface. L/D 21 x 3-1/2" DPs single by single.
hvjg | gvjgv | vjhv | 0 | 12/06/15 09:30 | 12/06/15 11:00 | [12 empty] | Retrieved CWS Tools Run # 1 (CMI-GR) to Surface. L/D Weatherford CWS BHA.
hvjg | gvjgv | vjhv | 0 | 12/06/15 11:00 | 12/06/15 17:00 | [12 empty] | Held PJSM. Conduct BOP Press Test, Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi High Press - OK. Press Tested Upper Variable Pipe Rams (With 5" DP) + Lower Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 7000 psi High Press - OK.
hvjg | gvjgv | vjhv | 0 | 12/06/15 17:00 | 12/07/15 06:00 | [12 empty] | P/U & M/U R4 6" PDC Bit & RIH down to 4800m for Condition Trip (Filled Up String after every 15 Stands).
hvjg | gvjgv | vjhv | 0 | 12/07/15 06:00 | 12/07/15 10:00 | [12 empty] | Con't RIH from 4800m to Bottom @ 5900m, washed down last stand (Filled Up String after every 15 Stands).
hvjg | gvjgv | vjhv | 0 | 12/07/15 10:00 | 12/07/15 14:00 | [12 empty] | Circulated to clean hole. | Productive
hvjg | gvjgv | vjhv | 0 | 12/07/15 14:00 | 12/07/15 17:00 | [12 empty] | Flow checked, Well Static. Performed Wiper Trip to 7" Liner Shoe @ 5560m, Hole Slick. | Productive
hvjg | gvjgv | vjhv | 0 | 12/07/15 17:00 | 12/08/15 01:00 | [12 empty] | Circulated hole to condition mud. | Productive
hvjg | gvjgv | vjhv | 0 | 12/08/15 01:00 | 12/08/15 02:00 | [12 empty] | Flow checked, Well Static. POOH from 5900m to 5523m inside 7" Liner Shoe.
hvjg | gvjgv | vjhv | 0 | 12/08/15 02:00 | 12/08/15 02:30 | [12 empty] | Flow checked - OK, pumped 30 bbls slug. | Productive
hvjg | gvjgv | vjhv | 0 | 12/08/15 02:30 | 12/08/15 06:00 | [12 empty] | POOH from 5523m to 3403m (in progress).
hvjg | gvjgv | vjhv | 0 | 12/08/15 06:00 | 12/08/15 14:00 | [12 empty] | Con't POOH from 3403m to Surface. L/D 6" Bit, S.Stabs & D.Jar. Flow checked @ BHA, Well Static.
hvjg | gvjgv | vjhv | 0 | 12/08/15 14:00 | 12/08/15 15:30 | [12 empty] | Cut & Slipped 98' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 12/08/15 15:30 | 12/08/15 17:00 | [12 empty] | R/U Well Serve Casing Running Gears.
hvjg | gvjgv | vjhv | 0 | 12/08/15 17:00 | 12/08/15 23:00 | [12 empty] | Held PJSM, P/U & M/U 5" Liner (P-110, 18 #, Vam FJL) Shoe Track (R/Shoe + 1 x 5" Liner Jt + F/Collar + 2 x 5" Liner Jts + L/Collar), ensured integrity of Float Equipments & RIH down to 365m. Filled up 5" Liner after every 10 Joints.
hvjg | gvjgv | vjhv | 0 | 12/08/15 23:00 | 12/09/15 00:30 | [12 empty] | P/Up & M/Up 5" Liner Hanger Assembly with "HNG" Setting Tool. Installed Liner Wiper Plug (w/ Ball Seat) on Stinger with appropriate Shear Screws. Adjusted Shear Screws of Hold Down Sub & Liner Hanger. Filled Up PBR with Hi-Vis & Checked Integrity of Pack Off Bushing - OK. Circulated out one Liner Volume. Recorded Up 45 Tons and Down 45 Tons Liner Weight. R/Down Wellserve Casing Running Gears. | Productive
hvjg | gvjgv | vjhv | 0 | 12/09/15 00:30 | 12/09/15 06:00 | [12 empty] | RIH 5" Liner on 3-1/2" & 5" DPs Stands down to 2168m ( 1.5 min/std). Drifted all Stands with 2.125" Drift O.D.
hvjg | gvjgv | vjhv | 0 | 12/09/15 06:00 | 12/09/15 17:30 | [12 empty] | Con't RIH 5" Liner on 5" DP Stands from 2168m to 5548m @ 7" Liner Shoe (Filled Up String after every 05 Stands, Drifted all Stands with 2.125" Drift).
hvjg | gvjgv | vjhv | 0 | 12/09/15 17:30 | 12/09/15 18:00 | [12 empty] | M/U TDS & Broke Circulation.
hvjg | gvjgv | vjhv | 0 | 12/09/15 18:00 | 12/09/15 20:00 | [12 empty] | Cont'd RIH 5" Liner on 5" DP Stands from 5548m & Tagged Bottom @ 5900m. Washed Down Last 02 Stands. Recorded Up 195 Tons & Down 186 Tons Weight.
hvjg | gvjgv | vjhv | 0 | 12/09/15 20:00 | 12/09/15 22:30 | [12 empty] | Circulated hole to Condition Mud @ 30 SPM & 860 Psi (70% of Hanger Setting Press). | Productive
hvjg | gvjgv | vjhv | 0 | 12/09/15 22:30 | 12/10/15 01:30 | [12 empty] | Installed W.F Cement Head (Pre-Loaded with DP Dart). Dropped Liner Hanger Setting Ball & Chased the same with Mud. Observed Ball Seated, Increased Press slowly to 1800 Psi & waited for 5 min. Set Hold Down Sub with 10 Tons O/pull - OK, Attempted to set Liner Hanger but Slided down after 15 Tons Compression. Dropped 5" Liner to Botttom @ 5900m & Released Setting Tool @ 2000 psi with 35 Ton Compression / Sheared Ball Seat @ 3000 psi.
hvjg | gvjgv | vjhv | 0 | 12/10/15 01:30 | 12/10/15 06:00 | [12 empty] | Circulated hole to Condition Mud prior to Cement Job (Observed increase in pressure when started circulation after shearing of ball seat, solved by rotating the string and by circulating at different rates). | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 06:00 | 12/10/15 09:00 | [12 empty] | Circulated hole to Condition Mud prior to Cement Job | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 09:00 | 12/10/15 09:30 | [12 empty] | R/U Dowell Pumping Unit & Pressure tested Cmt Lines @ 5000 Psi for 5 Min, OK. | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 09:30 | 12/10/15 10:30 | [12 empty] | Cont'd Circulation / Condition Mud meanwhile prepared 16.20 PPG "GasBlock" Slurry in Batch Mixer. | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 10:30 | 12/10/15 12:00 | [12 empty] | Held Pre-Job Safety Meeting. Pumped 20 BBL Chemical Wash thru Cement Unit & 40 BBL of MUDPUSH II as Spacer thru Rig Pump @ 5 BPM. Switch Back to Cement Unit & Pumped 40.8 BBL of 16.20 PPG Cement Slurry @ 5.4 BPM. Dropped Drill Pipe Dart. Displaced Cement Slurry with 25 BBL MUDPUSH II followed by 285 BBL Mud (Total Displacement = 310 BBL) @ 5 BPM thru Cement Unit. Observed Plugs Bumped / Increased Press to 2400 psi & Held for 10 Min. Bled Off Pressure, Observed 02 BBL Returns & No Back Flow. No Loss During Cement Job. | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 12:00 | 12/10/15 15:00 | [12 empty] | R/Down Cement Lines. P/Up String & Set Packer with 20 Tons Compression. R/Down Cement Head & P/Back to 5381m. Reverse Circulated 02 String Volumes. Dumped 20 BBL Chemical Wash + 30 BBL Spacer. | Productive
hvjg | gvjgv | vjhv | 0 | 12/10/15 15:00 | 12/11/15 03:30 | [12 empty] | POOH from 5381m to Surface. L/D WFD "HNG" Setting Tool.
hvjg | gvjgv | vjhv | 0 | 12/11/15 03:30 | 12/11/15 06:00 | [12 empty] | P/U & M/U R5 6" PDC Bit & RIH down to 911m (Filled Up String after every 15 Stands).
hvjg | gvjgv | vjhv | 0 | 12/11/15 06:00 | 12/11/15 17:30 | [12 empty] | RIH with 6" PDC Bit from 911m to 5400m (Filled Up String after every 15 Stands).
hvjg | gvjgv | vjhv | 0 | 12/11/15 17:30 | 12/11/15 20:00 | [12 empty] | Washed down from 5400m to 5475m & Tagged Compression @ 5475m. COC from 5475m to 5529m, Tagged & Confirmed TOL @ 5529m with 5 Tons Compression (COC with Sur. RPM 30, 2-3 Tons WOB & 60 SPM).
hvjg | gvjgv | vjhv | 0 | 12/11/15 20:00 | 12/12/15 00:30 | [12 empty] | Pumped 50 BBL Hi-Vis & Circulated out till Shakers Clean. | Productive
hvjg | gvjgv | vjhv | 0 | 12/12/15 00:30 | 12/12/15 06:00 | [12 empty] | Pumped 20 BBL Slug. POOH from 5529m to 2749m (in progress). | Productive
hvjg | gvjgv | vjhv | 0 | 12/12/15 06:00 | 12/12/15 14:00 | [12 empty] | POOH from 2749m to Surface. L/D Bit, Bit Sub, D.Jar & 9 x 3-1/2" HWDP's.
hvjg | gvjgv | vjhv | 0 | 12/12/15 14:00 | 12/12/15 22:30 | [12 empty] | P/U & M/U 4-1/8" Mill Bit, P/U 30 x 3-1/8" DC's + 12 x 2-7/8" DP's Single by Single & RIH down to 392m (Filled Up / Circulated String Twice). | Productive
hvjg | gvjgv | vjhv | 0 | 12/12/15 22:30 | 12/13/15 06:00 | [12 empty] | RIH 4-1/8" Mill Bit from 392m to 3714m on 3-1/2" & 5" DP's Stands (Filled Up String after every 15 Stands).
hvjg | gvjgv | vjhv | 0 | 12/13/15 06:00 | 12/13/15 10:30 | [12 empty] | RIH 4-1/8" Mill Bit from 3714m to 5512m on 5" DP's Stands (Filled Up String after every 15 Stands). Washed down from 5512m to 5" TOL @ 5529m.
hvjg | gvjgv | vjhv | 0 | 12/13/15 10:30 | 12/14/15 00:00 | [12 empty] | COC from 5529m to 5769m (RPM 30, 0-1 Tons WOB & 150 GPM). Pumped 25 BBL Hi-Vis @ 5743m. | Productive
hvjg | gvjgv | vjhv | 0 | 12/14/15 00:00 | 12/14/15 01:30 | [12 empty] | RIH from 5769m & Tagged Cement Plug / Landing Collar @ 5863.50m.
hvjg | gvjgv | vjhv | 0 | 12/14/15 01:30 | 12/14/15 06:00 |  |  | 5863.5 | 5868 | [8 empty] | Drilled Out Plugs / Landing Collar & COC from 5863.50m to 5868m. | Productive
hvjg | gvjgv | vjhv | 0 | 12/14/15 06:00 | 12/14/15 09:30 | [12 empty] | COC from 5868m to 5884m (02m above F/Collar).
hvjg | gvjgv | vjhv | 0 | 12/14/15 09:30 | 12/14/15 14:00 | [12 empty] | Pumped 25 BBL Hi-Vis & Circulated out till Shakers Clean. | Productive
hvjg | gvjgv | vjhv | 0 | 12/14/15 14:00 | 12/15/15 05:00 | [12 empty] | POOH from 5884m to Surface, R/Back Slim Hole BHA.
hvjg | gvjgv | vjhv | 0 | 12/15/15 05:00 | 12/15/15 06:00 | [12 empty] | Cut & Slipped 98' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 12/15/15 06:00 | 12/15/15 09:00 | [12 empty] | P/U & M/U 5" & 7" Scrappers on 4-1/8" Mill Bit & RIH down to 358m on Slim Hole BHA. L/D 4 x 2-7/8" DP's.
hvjg | gvjgv | vjhv | 0 | 12/15/15 09:00 | 12/16/15 00:00 | [12 empty] | RIH from 358m to 5848m on 3-1/2" & 5" DP Stands (Filled Up String after every 15 Stands). Washed down from 5848m & Tagged Compression @ 5883.50m.
hvjg | gvjgv | vjhv | 0 | 12/16/15 00:00 | 12/16/15 05:00 | [12 empty] | Pumped 20 BBL + 30 BBL Hi-Vis Consecutively & Circulated out till Shakers Clean. | Productive
hvjg | gvjgv | vjhv | 0 | 12/16/15 05:00 | 12/16/15 06:00 | [12 empty] | Pumped Slug & POOH from 5883m to 5700m. | Productive
hvjg | gvjgv | vjhv | 0 | 12/16/15 06:00 | 12/16/15 09:00 | [12 empty] | Cont'd POOH 5" DPs & R/Back 60 x 5" DP Stds (Total 70 x 5" DP Stds in Derrick).
hvjg | gvjgv | vjhv | 0 | 12/16/15 09:00 | 12/17/15 05:30 | [12 empty] | POOH & L/Down 91 x 5" DP Stds (273 Singles) + 42 x 3-1/2" DP Stds (126 Singles) + 7" Scrapper.
hvjg | gvjgv | vjhv | 0 | 12/17/15 05:30 | 12/17/15 06:00 | [12 empty] | POOH to 279m. P/Up 01 x 2-7/8" DP from Pipe Racks & R/Back 3 x 2-7/8" DP Stds.
hvjg | gvjgv | vjhv | 0 | 12/17/15 06:00 | 12/17/15 09:00 | [12 empty] | POOH from 279m to Surface & R/Back 10 x 3-1/8" DC Stds. L/Down 5" Scrapper + Mill Bit.
hvjg | gvjgv | vjhv | 0 | 12/17/15 09:00 | 12/17/15 15:00 | [12 empty] | Held Pre-Job Safety Meeting & R/Up SLB W/L Gear. M/Up & RIH W/L Tools and Recorded CBL - VDL Logs in 5" Liner. POOH and L/D W/L Tools. | Productive
hvjg | gvjgv | vjhv | 0 | 12/17/15 15:00 | 12/18/15 06:00 | [12 empty] | M/Up & RIH SLB VSP Log Tools & Recorded VSP Log from 5885m to Surface.
hvjg | gvjgv | vjhv | 0 | 12/18/15 06:00 | 12/18/15 07:30 | [12 empty] | L/Down SLB VSP Tool & R/Down SLB W/L Gear.
hvjg | gvjgv | vjhv | 0 | 12/18/15 07:30 | 12/18/15 08:30 | [12 empty] | Held PJSM. Closed Blind Ram & Press Tested Casing / 7" Liner / 5" Liner in Increments to 3500 PSI for 15 min - OK.
hvjg | gvjgv | vjhv | 0 | 12/18/15 08:30 | 12/18/15 14:00 | [12 empty] | Held PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Variable Pipe Rams + Lower Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 7000 psi High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 12/18/15 14:00 | 12/19/15 06:00 | [12 empty] | Handed Over Well to Production Dept. for DST. P/Up & M/Up 3 x 4-3/4" DC Stds & R/Back the same. Held PJSM & R/Up Wellserve TRS Equipment. RIH 3-1/2" TBG with Flex Trip BHA to 2050m & Press Tested the same as per Program.
hvjg | gvjgv | vjhv | 0 | 12/19/15 06:00 | 12/19/15 06:00 | [12 empty] | RIH 3-1/2" x 4-1/2" TBG from 2050m to 4703m for Flex Trip & Press Tested TBG as per Program.
hvjg | gvjgv | vjhv | 0 | 12/20/15 06:00 | 12/20/15 06:00 | [12 empty] | Tubing Flex Trip. POOH is in Progress.
hvjg | gvjgv | vjhv | 0 | 12/21/15 06:00 | 12/21/15 19:00 | [12 empty] | POOH TBG to Surface & Perforated 5" Liner with W/Line Guns as per Program.
hvjg | gvjgv | vjhv | 0 | 12/21/15 19:00 | 12/22/15 06:00 | [12 empty] | Obseved Guns Stuck after Perforation. Working to Release Stuck Guns. | Non Productive
hvjg | gvjgv | vjhv | 0 | 12/22/15 06:00 | 12/22/15 19:00 | [12 empty] | Worked to Release Stuck Guns - No Success. Broke W/Line from Weak Point & POOH to Surface. R/Down SLB W/L Gear. | Non Productive
hvjg | gvjgv | vjhv | 0 | 12/22/15 19:00 | 12/22/15 22:00 | [12 empty] | Shifted TBG Stands from Off-Driller Side to Driller Side in Derrick Racks. Meanwhile Shifted & Prepared Tally of 3-1/2" & 5" DPs on Pipe Racks. | Productive
hvjg | gvjgv | vjhv | 0 | 12/22/15 22:00 | 12/23/15 06:00 | [12 empty] | P/UP & M/Up 3-3/4" OD Over Shot (Dressed with 2-1/4" Basket Grapple) with Fishing BHA & RIH to 862m. While RIH P/Up 52 x 3-1/2" DPs from Pipe Racks.
hvjg | gvjgv | vjhv | 0 | 12/23/15 06:00 | 12/24/15 05:30 | [12 empty] | RIH 3-3/4" W.F Over Shot Fishing BHA from 862m to 4610m (Top of 7" Liner). While RIH P/Up 47 x 3-1/2" DPs & 273 x 5" DPs Single by Single from Pipe Racks.
hvjg | gvjgv | vjhv | 0 | 12/24/15 05:30 | 12/24/15 06:00 | [12 empty] | Connected TDS & Broke Circ.
hvjg | gvjgv | vjhv | 0 | 12/24/15 06:00 | 12/24/15 11:30 | [12 empty] | RIH from 4610m to 5800m. Washed Down & Tagged Top of Fish @ 5851m. Worked & Latched Fish. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 12/24/15 11:30 | 12/25/15 06:00 | [12 empty] | POOH Fish from 5851m to 1337m. While POOH R/Back 96 x 5" DP Stands & L/Down 195 x 5" DPs Single by Single.
hvjg | gvjgv | vjhv | 0 | 12/25/15 06:00 | 12/25/15 15:30 | [12 empty] | POOH Fish from 1337m to Surface - Observed all Guns Fired & Complete Fish Recovered. L/Down Fish + Fishing BHA + 99 x 3-1/2" DPs Single by Single While POOH.
hvjg | gvjgv | vjhv | 0 | 12/25/15 15:30 | 12/25/15 17:00 | [12 empty] | Cut & Slipped 88' Drilling Line. | Productive
hvjg | gvjgv | vjhv | 0 | 12/25/15 17:00 | 12/26/15 06:00 | [12 empty] | Held PJSM. M/Up & RIH TCP Guns with 2-7/8" x 3-1/2" TBG to 2206m.
hvjg | gvjgv | vjhv | 0 | 12/26/15 06:00 | 12/26/15 06:00 | [12 empty] | RIH TCP Guns from 2206m to Perforation Depth on 3-1/2" x 4-1/2" TBG. R/Up SLB W/Line Gear & Co-Related Depth with W/Line. R/Up ETS Slickline Gear & Press Test Slickline BOP is in Progress.
hvjg | gvjgv | vjhv | 0 | 12/27/15 06:00 | 12/27/15 06:00 | [12 empty] | RIH Slickline & Attempted to Fire TCP Guns Both Mechanically (2 Times) & Hydraulically (3 Times) - No Success. R/Down Slickline Gear. R/Up & RIH with Sprint CT.
hvjg | gvjgv | vjhv | 0 | 12/28/15 06:00 | 12/28/15 06:00 | [12 empty] | RIH Sprint CT & Circ. / Cleaned Mechanical Firing Head Top. POOH CT to Surface. RIH CT with Mechanical Firing Head Tool.
hvjg | gvjgv | vjhv | 0 | 12/29/15 06:00 | 12/29/15 06:00 | [12 empty] | RIH CT with Mechanical Firing Head Tool & Attempted to Fire TCP Guns. POOH CT to Surface - No Indication / Mark on Firing Tool. R/Down Sprint CT. R/Up & RIH ETS Slickline & Fired TCP Guns. POOH Slickline to Surface & R/ Down the same - Observed Marks on Firing Tool. Circ / Homegenized Mud Column. Flow Check Prior to POOH TCP Guns in Progress.
hvjg | gvjgv | vjhv | 0 | 12/30/15 06:00 | 12/30/15 06:00 | [12 empty] | Attempted to POOH TCP Guns - Observed String Stuck. Worked & Released String with 50 Ton Overpull. POOH TCP Guns to Surface - Observed Guns Not Fired. L/Down TCP Guns in Progress. | Non Productive
hvjg | gvjgv | vjhv | 0 | 12/31/15 06:00 | 12/31/15 09:00 | [12 empty] | POOH & L/Down All TCP Guns.
hvjg | gvjgv | vjhv | 0 | 12/31/15 09:00 | 12/31/15 14:00 | [12 empty] | Held PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 psi Low & 4500 psi - OK. Press Tested Upper Variable Pipe Rams + Lower Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 psi Low & 8000 psi High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 12/31/15 14:00 | 12/31/15 18:00 | [12 empty] | Shifted TBG Stands from Off-Driller Side to Driller Side. Meanwhile Shifted & Prepared Tally of 3-1/2" DPs on Pipe Racks. | Productive
hvjg | gvjgv | vjhv | 0 | 12/31/15 18:00 | 01/01/16 06:00 | [12 empty] | M/Up & RIH New 4-1/8" Mill Bit to 1365m. While RIH P/Up 99 x 3-1/2" DPs + 5 x 5" DPs Single by Single from Pipe Racks.
hvjg | gvjgv | vjhv | 0 | 01/01/16 06:00 | 01/01/16 06:00 | [12 empty] | RIH 4-1/8" Mill Bit from 1365m to 5500m. Reamed / Washed Down from 5500m to 5800m & Observed Compression While Reaming inside 5" Liner. While RIH P/Up 190 x 5" DPs Single by Single from Pipe Racks. Meanwhile Preparing 1.10 S.G CaCl2 Brine in Progress. | Productive
hvjg | gvjgv | vjhv | 0 | 01/02/16 06:00 | 01/02/16 09:00 | [12 empty] | Washed Down from 5800m to 5884m & Observed Compression While Wasing Down. Meanwhile Prepared 1.10 S.G CaCl2 Brine & Cleaned Mud Tanks. | Productive
hvjg | gvjgv | vjhv | 0 | 01/02/16 09:00 | 01/02/16 14:00 | [12 empty] | Circ. / Swept Out 50 BBL Hi-Vis Pill at High Flow Rate. Meanwhile Reciprocated / Rotated String & Prepared Spacers for Displacement with Brine. | Productive
hvjg | gvjgv | vjhv | 0 | 01/02/16 14:00 | 01/02/16 21:00 | [12 empty] | Pumped 60 BBL Transition Pill + 50 BBL High PH Surfactant Pill + 60 BBL Viscosified Push Pill + 40 BBL Clean Water Followed by 1.10 S.G CaCl2 Brine. Cont'd Circ. till Clean Brine on Surface. | Productive
hvjg | gvjgv | vjhv | 0 | 01/02/16 21:00 | 01/03/16 06:00 | [12 empty] | Cleaned Remaining Mud Tanks + Shakers + Mud Ditches. Dumped & Cleaned Sand Trap. Meanwhile Monitored Well.
hvjg | gvjgv | vjhv | 0 | 01/03/16 06:00 | 01/03/16 11:00 | [12 empty] | Circ. to Condition / Homogenise Brine to 1.10 Sp.Gr.
hvjg | gvjgv | vjhv | 0 | 01/03/16 11:00 | 01/03/16 18:00 | [12 empty] | Flow Checked - Well Static. POOH to 3159m & R/Back 96 x 5" DP Stands
hvjg | gvjgv | vjhv | 0 | 01/03/16 18:00 | 01/04/16 06:00 | [12 empty] | Cont'd POOH to 830m & L/Down 195 x 5" DPs + 50 x 3-1/2" DPs Single by Single.
hvjg | gvjgv | vjhv | 0 | 01/04/16 06:00 | 01/04/16 07:00 | [12 empty] | POOH from 830m to 630m & L/Down 21 x 3-1/2" DPs While POOH.
hvjg | gvjgv | vjhv | 0 | 01/04/16 07:00 | 01/04/16 08:00 | [12 empty] | Waited for SLB W/Line.
hvjg | gvjgv | vjhv | 0 | 01/04/16 08:00 | 01/04/16 13:30 | [12 empty] | POOH to Surface. R/Back Slim BHA & L/Down 28 x 3-1/2" DPs + Jar + Mill Bit.
hvjg | gvjgv | vjhv | 0 | 01/04/16 13:30 | 01/04/16 14:30 | [12 empty] | Held PJSM. R/Up / Anchored Shooting Nipple & Hooked Up with Standpipe.
hvjg | gvjgv | vjhv | 0 | 01/04/16 14:30 | 01/04/16 15:30 | [12 empty] | Held PJSM. R/Up W/Line BOP (Arrived with SLB Engineer). Flushed BOP Stack. Closed Blind Ram & Annular BOP. Press Tested W/Line BOP / Shooting Nipple at 400 PSI - OK.
hvjg | gvjgv | vjhv | 0 | 01/04/16 15:30 | 01/05/16 06:00 | [12 empty] | RIH SLB Guns & Carried Out Perforations as Per Program.
hvjg | gvjgv | vjhv | 0 | 01/05/16 06:00 | 01/06/16 00:00 | [12 empty] | Carried Out Perforation Job as Per Program. R/Down Shooting Nipple + SLB W/Line Gear.
hvjg | gvjgv | vjhv | 0 | 01/06/16 00:00 | 01/06/16 06:00 | [12 empty] | Held PJSM & R/Up Wellserve TRS Gear. RIH DST String in Progress.
hvjg | gvjgv | vjhv | 0 | 01/06/16 06:00 | 01/06/16 06:00 | [12 empty] | Continued RIH DST String.
hvjg | gvjgv | vjhv | 0 | 01/07/16 06:00 | 01/07/16 08:00 | [12 empty] | Continued RIH DST String to Packer Setting Depth.
hvjg | gvjgv | vjhv | 0 | 01/07/16 08:00 | 01/08/16 06:00 | [12 empty] | P/Up & M/Up Flow Head. Set Packer at 5508m. Press Tested Hook Up. DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/08/16 06:00 | 01/08/16 06:00 | [12 empty] | Well Under Production Testing - DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/09/16 06:00 | 01/09/16 06:00 | [12 empty] | Well Under Production Testing - DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/10/16 06:00 | 01/10/16 06:00 | [12 empty] | Well Under Production Testing - DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/11/16 06:00 | 01/11/16 12:30 | [12 empty] | Terminated DST # 1. R/Down Sprint CT Injector Head & BOP. H/Up SLB Pumping Line to Annulus & Ruptured both RD Circ. V/Vs @ 3500 PSI - Reverse Circ. Tubing Volume. Open Pipe Rams & Unset PKR. | Productive
hvjg | gvjgv | vjhv | 0 | 01/11/16 12:30 | 01/11/16 20:00 | [12 empty] | Circ. / Homogenised Mud Column to 1.11 S.G. Flow Checked - OK.
hvjg | gvjgv | vjhv | 0 | 01/11/16 20:00 | 01/11/16 21:00 | [12 empty] | Slipped & Cut 90' Drilling Line. Calibrated / Adjusted ACS + Crown-O-Matic + Hook Load Sensors. | Productive
hvjg | gvjgv | vjhv | 0 | 01/11/16 21:00 | 01/12/16 06:00 | [12 empty] | POOH DST # 1 Assy from 5595m to 2518m.
hvjg | gvjgv | vjhv | 0 | 01/12/16 06:00 | 01/12/16 16:00 | [12 empty] | POOH DST # 1 Assy from 2518m to Surface.
hvjg | gvjgv | vjhv | 0 | 01/12/16 16:00 | 01/12/16 21:00 | [12 empty] | Held PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 PSI Low & 4500 PSI - OK. Press Tested Upper Variable Pipe Rams + Blind Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 PSI Low & 8000 PSI High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 01/12/16 21:00 | 01/12/16 23:00 | [12 empty] | RIH 5" DPs Kill String to 428m.
hvjg | gvjgv | vjhv | 0 | 01/12/16 23:00 | 01/13/16 02:00 | [12 empty] | Arranged 5" Bridge Plug W/Line Adapter Kit - Meanwhile Monitored Well thru Trip Tank.
hvjg | gvjgv | vjhv | 0 | 01/13/16 02:00 | 01/13/16 03:30 | [12 empty] | POOH Kill String to Surface.
hvjg | gvjgv | vjhv | 0 | 01/13/16 03:30 | 01/13/16 06:00 | [12 empty] | Held PJSM. R/Up SLB W/L Gear. Installed / Anchored & Press Tested Shooting Nipple with SLB W/Line BOP @ 500 PSI. M/Up 5" Bridge Plug with SLB W/Line in Progress.
hvjg | gvjgv | vjhv | 0 | 01/13/16 06:00 | 01/13/16 14:00 | [12 empty] | RIH & Set 5" Weatherford Bridge Plug @ 5802m by SLB W/Line. POOH W/Line to Surface & R/Down SLB W/Line Gear & Shooting Nipple.
hvjg | gvjgv | vjhv | 0 | 01/13/16 14:00 | 01/13/16 14:30 | [12 empty] | Held PJSM. Closed Blind Rams & Press Tested Bridge Plug with Rig Pump @ 1000 PSI for 15 Min - OK. | Productive
hvjg | gvjgv | vjhv | 0 | 01/13/16 14:30 | 01/14/16 06:00 | [12 empty] | Held PJSM. R/Up Wellserve TRS Gear & RIH 3-1/8" - 6 SPF TCP Guns to 3600m & in Progress.
hvjg | gvjgv | vjhv | 0 | 01/14/16 06:00 | 01/14/16 13:30 | [12 empty] | RIH 3-1/8" - 6 SPF TCP Guns down to 5780m.
hvjg | gvjgv | vjhv | 0 | 01/14/16 13:30 | 01/14/16 17:30 | [12 empty] | PJSM. R/Up SLB wireline .Correlated RA marker. R/down SLB wireline.
hvjg | gvjgv | vjhv | 0 | 01/14/16 17:30 | 01/14/16 19:30 | [12 empty] | PJSM.Added one Pup joint(2.916m) & one joint(9.584m) of 4.5"tubing to the string. R/Up Flow Head. H/Up kill wing with standpipe. Closed Pipe ram BOP & Fired TCP guns with hydraulic fire head by applying 3500 psi surface pressure. Observed clear indication at surface.
hvjg | gvjgv | vjhv | 0 | 01/14/16 19:30 | 01/14/16 20:00 | [12 empty] | Observed well through trip tank. No gain/loss observed.
hvjg | gvjgv | vjhv | 0 | 01/14/16 20:00 | 01/15/16 00:00 | [12 empty] | Direct Circ 1.4 times annulus volume (1260 bbl). Observed Well static. L/D flow head.
hvjg | gvjgv | vjhv | 0 | 01/15/16 00:00 | 01/15/16 06:00 | [12 empty] | POOH to 3485m & in progress.
hvjg | gvjgv | vjhv | 0 | 01/15/16 06:00 | 01/15/16 17:30 | [12 empty] | POOH to surface & L/Down TCP guns.
hvjg | gvjgv | vjhv | 0 | 01/15/16 17:30 | 01/15/16 23:00 | [12 empty] | PJSM. M/Up DST # 2's BHA & 1x3-1/2" Tubing Stand, Filled with water & pressure testes at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/15/16 23:00 | 01/16/16 06:00 | [12 empty] | Continued RIH DST # 2 string with 3-1/2" Tubing to 2235m & in progress . Filled the string every 5th stand & pressure tested every 25th stand at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/16/16 06:00 | 01/16/16 17:30 | [12 empty] | Continued RIH DST # 2 assembly down to 5591.78m.
hvjg | gvjgv | vjhv | 0 | 01/16/16 17:30 | 01/16/16 18:30 | [12 empty] | PJSM. M/Up flow Head.Set 7" DST Packer @ 5504m.
hvjg | gvjgv | vjhv | 0 | 01/16/16 18:30 | 01/16/16 20:30 | [12 empty] | H/U flow line and kill line of flow head. Pressure tested upstream of choke manifold at 8000 psi & line to annulus at 4000 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/16/16 20:30 | 01/17/16 04:00 | [12 empty] | PJSM. Opened well for production testing. Meanwhile R/U of CTU.
hvjg | gvjgv | vjhv | 0 | 01/17/16 04:00 | 01/17/16 06:00 | [12 empty] | RIH CT to 1670m and in progress
hvjg | gvjgv | vjhv | 0 | 01/17/16 06:00 | 01/17/16 06:00 | [12 empty] | Well under production testing.
hvjg | gvjgv | vjhv | 0 | 01/18/16 06:00 | 01/18/16 23:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 01/18/16 23:00 | 01/19/16 02:00 | [12 empty] | PJSM. Terminated DST#2. Filled the tubing with brine. Operated RDs.
hvjg | gvjgv | vjhv | 0 | 01/19/16 02:00 | 01/19/16 04:00 | [12 empty] | Reverse circulated tubing volume. | Productive
hvjg | gvjgv | vjhv | 0 | 01/19/16 04:00 | 01/19/16 05:30 | [12 empty] | Unset 7" DST Packer, flow check. L/D Flow head, 2x4-1/2" tubing Pup joints & 1x4-1/2" tubing joint.
hvjg | gvjgv | vjhv | 0 | 01/19/16 05:30 | 01/19/16 06:00 | [12 empty] | M/U circulating head. Direct Circulation in progress. | Productive
hvjg | gvjgv | vjhv | 0 | 01/19/16 06:00 | 01/19/16 06:30 | [12 empty] | Circulated to condition Brine. Observed 80 bbls loss in half hour. Stopped circulation. | Productive
hvjg | gvjgv | vjhv | 0 | 01/19/16 06:30 | 01/19/16 08:00 | [12 empty] | Observed well for static loss & thoroughly Checked for surface loss. Found surface connections OK. Static loss of 20 bbls / hr.
hvjg | gvjgv | vjhv | 0 | 01/19/16 08:00 | 01/19/16 12:00 | [12 empty] | POOH up to 7" liner top (4601m)
hvjg | gvjgv | vjhv | 0 | 01/19/16 12:00 | 01/19/16 12:30 | [12 empty] | Monitored well. Observed Static loss of 20 bbls / hr.
hvjg | gvjgv | vjhv | 0 | 01/19/16 12:30 | 01/20/16 04:00 | [12 empty] | Resumed POOH. POOH 4-1/2" & 3-1/2" tubing stds. L/D DST tools, 3 x 2-7/8" TB jts & 2x perforated jts & Mule shoe. Observed 13 bbl/hr loss during POOH.
hvjg | gvjgv | vjhv | 0 | 01/20/16 04:00 | 01/20/16 06:00 | [12 empty] | Monitored well. Observed static loss of 14 bbl/hr. R/U Shooting nipple & wireline gears. PJSM. Pressure tested W/L BOP at 500 psi, OK. Arming of W/L detonator in progress. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Losses = 383 BBL
hvjg | gvjgv | vjhv | 0 | 01/20/16 06:00 | 01/20/16 12:30 | [12 empty] | Armed W/L detonator. RIH W/L to setting depth. Correlated depth and set BP at 5660m. POOH W/L. R/D SLB W/L gears. Lost 30 BBL brine till setting of BP.
hvjg | gvjgv | vjhv | 0 | 01/20/16 12:30 | 01/20/16 13:00 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 01/20/16 13:00 | 01/20/16 14:00 | [12 empty] | Slip and cut 80' drilling line. | Productive
hvjg | gvjgv | vjhv | 0 | 01/20/16 14:00 | 01/21/16 06:00 | [12 empty] | Held PJSM. P/U TCP guns and RIH through 3-1/2" & 4-1/2" tubing to 4200m & in progress.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses in 24 hrs = 30 BBL
hvjg | gvjgv | vjhv | 0 | [14 empty] | Accumulated Downhole Losses = 413 BBL
hvjg | gvjgv | vjhv | 0 | 01/21/16 06:00 | 01/21/16 10:00 | [12 empty] | Contd. RIH TCP guns to 5607m.
hvjg | gvjgv | vjhv | 0 | 01/21/16 10:00 | 01/21/16 13:30 | [12 empty] | R/U SLB W/L and correlated the depth. POOH and R/D W/L
hvjg | gvjgv | vjhv | 0 | 01/21/16 13:30 | 01/21/16 16:00 | [12 empty] | Added 1x4-1/2" TB jt. & 2x4-1/2" Pup jts. M/U Flow head. Held PJSM. Fired the TCP guns through hydraulic firing head. Flow checked. No loss/gain observed.(Observed sound indication of gun fired at surface) | Productive
hvjg | gvjgv | vjhv | 0 | 01/21/16 16:00 | 01/22/16 06:00 | [12 empty] | L/D Flow head. POOH TCP guns to 120m & in progress.
hvjg | gvjgv | vjhv | 0 | 01/22/16 06:00 | 01/22/16 08:00 | [12 empty] | POOH to surface. L/D 2 x 2-7/8" jts & TCP guns.
hvjg | gvjgv | vjhv | 0 | 01/22/16 08:00 | 01/22/16 12:00 | [12 empty] | PJSM. M/Up DST # 3 BHA & 1 x 3-1/2" Tubing stand, Filled with water & pressure tested at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/22/16 12:00 | 01/22/16 12:30 | [12 empty] | Serviced TDS.
hvjg | gvjgv | vjhv | 0 | 01/22/16 12:30 | 01/23/16 06:00 | [12 empty] | Continued RIH DST # 3 string with 3-1/2" & 4-1/2" Tubing to 5328m & in progress . Filled the string with water every 5th stand & pressure tested every 25th stand at 7500 psi down to 3121m. | Productive
hvjg | gvjgv | vjhv | 0 | 01/23/16 06:00 | 01/23/16 07:30 | [12 empty] | RIH DST # 3 string to bottom. Added 2x4-1/2" Pup jts. M/U flow head connected with 1x4-1/2" TB jt. Set 7" DST packer.
hvjg | gvjgv | vjhv | 0 | 01/23/16 07:30 | 01/24/16 06:00 | [12 empty] | M/U SWT lines & pressure tested upstream of choke manifold at 7500 psi. Held PJSM. Well under production testing. | Productive
hvjg | gvjgv | vjhv | 0 | 01/24/16 06:00 | 01/24/16 21:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 01/24/16 21:00 | 01/24/16 22:30 | [12 empty] | Held PJSM. Terminated DST-3. Ruptured RDs at 3500 psi. Reverse Circulated out NH4Cl. | Productive
hvjg | gvjgv | vjhv | 0 | 01/24/16 22:30 | 01/24/16 23:30 | [12 empty] | B/O SWT lines. Unset packer. L/D flow head, 1x4-1/2" TB jt & 2x4-1/2" Pup jts. Meanwhile observed the well, found static.
hvjg | gvjgv | vjhv | 0 | 01/24/16 23:30 | 01/25/16 06:00 | [12 empty] | M/U circulating head. Direct circulated to reduce Brine weight from 1.10 SG to 1.05 SG & in progress. | Productive
hvjg | gvjgv | vjhv | 0 | 01/25/16 06:00 | 01/25/16 06:30 | [12 empty] | Direct Circulated brine to homogenize (MWin/out = 1.05 SG) | Productive
hvjg | gvjgv | vjhv | 0 | 01/25/16 06:30 | 01/25/16 23:30 | [12 empty] | B/O Circ. Head, flow checked level static. POOH DST-3 string. L/D DST tools and tail assembly.
hvjg | gvjgv | vjhv | 0 | 01/25/16 23:30 | 01/26/16 05:30 | [12 empty] | R/U shooting nipple and SLB W/L gears. Hold PJSM. Pressure tested W/L BOP at 500 psi. Armed W/L detonator. RIH W/L with BP. Corrleated & set BP at 5565m. | Productive
hvjg | gvjgv | vjhv | 0 | 01/26/16 05:30 | 01/26/16 06:00 | [12 empty] | POOH wireline in progress.
hvjg | gvjgv | vjhv | 0 | 01/26/16 06:00 | 01/26/16 08:00 | [12 empty] | POOH wireline to surface. R/D W/L gears. Pressure tested BP at 3200 psi surface pressure. | Productive
hvjg | gvjgv | vjhv | 0 | 01/26/16 08:00 | 01/26/16 12:00 | [12 empty] | L/D 30 x 3-1/8" DCs & 9 x 2-7/8" DP.
hvjg | gvjgv | vjhv | 0 | 01/26/16 12:00 | 01/26/16 17:00 | [12 empty] | Hold PJSM. M/Up Test Plug Assy & Retrieved Wear Bushing. Set Test Plug inside THS. Flushed & Filled BOP Stack with Water. Press Tested Annular BOP + Rotary Hose + Stand Pipe Manifold @ 300 PSI Low & 4500 PSI high - OK. Press Tested Upper Variable Pipe Rams + IBOP + HCRs / Manual Valves at Choke & Kill Lines + Coflexip & Master Valve at Choke Manifold @ 300 PSI Low & 8000 PSI High Press - OK. Retrieved Test Plug & Set Wear Bushing inside THS. L/Down Test Plug Assy.
hvjg | gvjgv | vjhv | 0 | 01/26/16 17:00 | 01/26/16 18:30 | [12 empty] | Cut and slip 68' drill line. | Productive
hvjg | gvjgv | vjhv | 0 | 01/26/16 18:30 | 01/27/16 06:00 | [12 empty] | Held PJSM. P/U & RIH 4-1/2" 5SPF TCP guns with 3-1/2" tubing to 2443m and in progress.
hvjg | gvjgv | vjhv | 0 | 01/27/16 06:00 | 01/27/16 15:30 | [12 empty] | RIH TCP guns to 5483m.
hvjg | gvjgv | vjhv | 0 | 01/27/16 15:30 | 01/27/16 19:00 | [12 empty] | PJSM. R/U SLB W/L gears. RIH W/L for correlation. Correlated the depth. POOH W/L & R/D W/L gears.
hvjg | gvjgv | vjhv | 0 | 01/27/16 19:00 | 01/27/16 20:00 | [12 empty] | Added 2x4-1/2" Pup joints, M/U flow head connected with 1x4-1/2" TB jt. H/U mud pump with kill side of flow head and pumping unit with annulus. | Productive
hvjg | gvjgv | vjhv | 0 | 01/27/16 20:00 | 01/27/16 21:00 | [12 empty] | PJSM. Fired the guns with hydraulic firing head by applying 3200 psi pressure. Clear indication of firing observed at surface. Flow checked. No gain/loss observed.
hvjg | gvjgv | vjhv | 0 | 01/27/16 21:00 | 01/28/16 06:00 | [12 empty] | L/D flow head & pup joints. POOH TCP guns to 2018m & in progress.
hvjg | gvjgv | vjhv | 0 | 01/28/16 06:00 | 01/28/16 14:00 | [12 empty] | POOH TCP guns from 2018m to surface. L/D Guns.
hvjg | gvjgv | vjhv | 0 | 01/28/16 14:00 | 01/28/16 21:00 | [12 empty] | PJSM. P/U & RIH DST-4 BHA & 1 x 3-1/2" Tubing stand to 291m, Filled with water & pressure tested at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/28/16 21:00 | 01/29/16 06:00 | [12 empty] | Continued RIH DST-4 string with 3-1/2" & 4-1/2" Tubing to 2724m & pressure test is in progress . Filled the string with water every 5th stand & pressure tested at every 28th stand at 7500 psi down to 2724m. | Productive
hvjg | gvjgv | vjhv | 0 | 01/29/16 06:00 | 01/29/16 14:30 | [12 empty] | Continued RIH DST-4 string to 5356m. Added 2x4-1/2" pup jts.
hvjg | gvjgv | vjhv | 0 | 01/29/16 14:30 | 01/29/16 16:30 | [12 empty] | M/U flow head connected with 1x4-1/2" TB jt. Set 7" DST packer. M/U SWT lines & pressure tested upstream of choke manifold at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 01/29/16 16:30 | 01/30/16 06:00 | [12 empty] | Held PJSM. Well opened for production testing.
hvjg | gvjgv | vjhv | 0 | 01/30/16 06:00 | 01/30/16 06:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 01/31/16 06:00 | 02/01/16 01:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/01/16 01:00 | 02/01/16 06:00 | [12 empty] | Well shut in for final build up. Meanwhile POOH CT in progress.
hvjg | gvjgv | vjhv | 0 | 02/01/16 06:00 | 02/01/16 13:30 | [12 empty] | Well remained shut in for final build up. Meanwhile R/D CT injector head and BOP.
hvjg | gvjgv | vjhv | 0 | 02/01/16 13:30 | 02/01/16 16:30 | [12 empty] | Opened the well to flare pit and observed. Terminated the DST-4. Ruptured RD at 3200 psi & reverse circulated out tubing volume. | Productive
hvjg | gvjgv | vjhv | 0 | 02/01/16 16:30 | 02/01/16 21:30 | [12 empty] | B/O SWT and kill lines of flow head. Unset 7" DST packer. Observed the well. No gain/Loss observed. (Pipe handler not operating due to TDS fault). L/U mud pump with kill side of flow head. Direct circulated complete cycle (No dynamic losses observed). Meanwhile rectifying TDS problem. | Productive
hvjg | gvjgv | vjhv | 0 | 02/01/16 21:30 | 02/02/16 06:00 | [12 empty] | TDS troubleshooting in progress. Meanwhile observed the well. Observed static losses @ 12bbl/hr. Filled the hole through trip tank and reciprocated the string intermittently.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Total Downhole Losses in 24 hrs = 97 bbls
hvjg | gvjgv | vjhv | 0 | 02/02/16 06:00 | 02/02/16 19:00 | [12 empty] | Troubleshoot TDS. Resolved the issue temporarily. Function tested TDS links operation.
hvjg | gvjgv | vjhv | 0 | 02/02/16 19:00 | 02/02/16 22:00 | [12 empty] | L/D flow head, 2 x 4-1/2" Pup jts & 1 x 4-1/2" TB jt. Continued POOH DST- 4 string to 4581m (7" DST packer above 7" liner top).
hvjg | gvjgv | vjhv | 0 | 02/02/16 22:00 | 02/03/16 00:00 | [12 empty] | M/U circulating head. Pumped 40bbl Ca2CO3 Fine pill of 88PPB and displaced with brine to string out. Lost 35bbls during pumping. L/D circulating head & continued POOH to 4323m. Observed the well through trip tank. Observed 12bbl/hr static loss. | Productive
hvjg | gvjgv | vjhv | 0 | 02/03/16 00:00 | 02/03/16 06:00 | [12 empty] | M/U circulating head. Pumped 40bbl Ca2CO3 Fine + Medium pill of 132PPB and displaced with brine to string out. Lost 30bbls during pumping. L/D circulating head & continued POOH to 2668m & in progress. Meanwhile Observed the well through trip tank. Observed 12bbl/hr static loss. | Productive
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses in 24 hrs = 317 bbls
hvjg | gvjgv | vjhv | 0 | [14 empty] | Accumulated Downhole Losses = 414 bbls
hvjg | gvjgv | vjhv | 0 | 02/03/16 06:00 | 02/03/16 14:30 | [12 empty] | Continued POOH DST-4 string to surface. L/D DST tools.
hvjg | gvjgv | vjhv | 0 | 02/03/16 14:30 | 02/03/16 17:00 | [12 empty] | R/U shooting nipple & SLB W/L gears. PJSM. Pressure tested W/L BOP at 500 psi. Armed W/L detonator. | Productive
hvjg | gvjgv | vjhv | 0 | 02/03/16 17:00 | 02/03/16 20:30 | [12 empty] | RIH W/L with 7" permanent BP. Correlated the depth. Set BP at 5343m. Observed 10 bbl/hr static losses till BP is set.
hvjg | gvjgv | vjhv | 0 | 02/03/16 20:30 | 02/03/16 23:30 | [12 empty] | POOH W/L to surface. L/U pumping unit & pressure tested BP at 3200 psi. R/D Schlumberger W/L gears. | Productive
hvjg | gvjgv | vjhv | 0 | 02/03/16 23:30 | 02/04/16 06:00 | [12 empty] | Waiting for TDS problem to be resolved.
hvjg | gvjgv | vjhv | 0 | [14 empty] | Downhole Losses in 24 hrs = 112 bbls
hvjg | gvjgv | vjhv | 0 | [14 empty] | Accumulated Downhole Losses = 526 bbls
hvjg | gvjgv | vjhv | 0 | 02/04/16 06:00 | 02/04/16 11:30 | [12 empty] | Waited for TDS problem to be resolved.
hvjg | gvjgv | vjhv | 0 | 02/04/16 11:30 | 02/04/16 12:30 | [12 empty] | RIH 6 stands of 5" DP. Function tested rotary table on different parameters.
hvjg | gvjgv | vjhv | 0 | 02/04/16 12:30 | 02/04/16 17:30 | [12 empty] | Prepared TCP guns and spacers for additional interval provided in Datta formation. | Productive
hvjg | gvjgv | vjhv | 0 | 02/04/16 17:30 | 02/05/16 06:00 | [12 empty] | PJSM. RIH 4-1/2" 5 SPF TCP guns on 3-1/2" tubing to 2419m & in progress.
hvjg | gvjgv | vjhv | 0 | 02/05/16 06:00 | 02/06/16 02:00 | [12 empty] | RIH TCP guns on 3-1/2" & 4-1/2" tubing to bottom.
hvjg | gvjgv | vjhv | 0 | 02/06/16 02:00 | 02/06/16 18:00 | [12 empty] | R/U SLB W/L gears & RIH W/L. Correlated the depth with GR. POOH W/L to surface & R/D W/L gears.
hvjg | gvjgv | vjhv | 0 | 02/06/16 18:00 | 02/06/16 19:30 | [12 empty] | Added 2 x 4-1/2" pup jts and M/U flow head already connected with 4-1/2" TB jt. L/U mud pump with kill side of flow head. | Productive
hvjg | gvjgv | vjhv | 0 | 02/06/16 19:30 | 02/06/16 20:30 | [12 empty] | PJSM. Fired the guns with hydraulic firing head. Observed clear indication of guns fired at surface. Flow Checked, no gain/loss observed.
hvjg | gvjgv | vjhv | 0 | 02/06/16 20:30 | 02/06/16 06:00 | [12 empty] | L/D flow head and 2 x 4-1/2" pup jts. Continued POOH TCP guns to 786m & in progress.
hvjg | gvjgv | vjhv | 0 | 02/06/16 06:00 | 02/06/16 13:00 | [12 empty] | POOH TCP guns from 786m to surface. L/D Guns.
hvjg | gvjgv | vjhv | 0 | 02/06/16 13:00 | 02/06/16 18:00 | [12 empty] | PJSM. P/U & RIH DST-5 BHA & 1 x 3-1/2" Tubing stand to 274m, Filled with water & pressure tested at 7500 psi. | Productive
hvjg | gvjgv | vjhv | 0 | 02/06/16 18:00 | 02/07/16 06:00 | [12 empty] | Continued RIH DST-5 string with 3-1/2" Tubing to 3415m & in progress . Filled the string with water every 5th stand & pressure tested at every 22nd stand at 7500 psi down to 2141m. | Productive
hvjg | gvjgv | vjhv | 0 | 02/07/16 06:00 | 02/07/16 11:00 | [12 empty] | RIH DST-5 string to bottom. Added 2x4-1/2" pup jts.
hvjg | gvjgv | vjhv | 0 | 02/07/16 11:00 | 02/07/16 12:00 | [12 empty] | M/U flow head connected with 1x4-1/2" TB jt. Set 7" DST packer.
hvjg | gvjgv | vjhv | 0 | 02/07/16 12:00 | 02/07/16 14:00 | [12 empty] | M/U SWT lines & pressure tested upstream of choke manifold at 7500 psi. M/U SLB line with annulus & pressure tested. | Productive
hvjg | gvjgv | vjhv | 0 | 02/07/16 14:00 | 02/08/16 06:00 | [12 empty] | Held PJSM. Well opened for production testing.
hvjg | gvjgv | vjhv | 0 | 02/08/16 06:00 | 02/08/16 06:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/09/16 06:00 | 02/09/16 08:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/09/16 08:00 | 02/10/16 06:00 | [12 empty] | Well shut in for intermdiate build up.
hvjg | gvjgv | vjhv | 0 | 02/10/16 06:00 | 02/10/16 10:00 | [12 empty] | Well remained shut in for intermdiate build up.
hvjg | gvjgv | vjhv | 0 | 02/10/16 10:00 | 02/11/16 06:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/11/16 06:00 | 02/11/16 09:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/11/16 09:00 | 02/11/16 13:30 | [12 empty] | Well Shut In. R/U WF PCE (BOP/Lubricator) and W/L gear for PSP, P/T same at 2500 psi.
hvjg | gvjgv | vjhv | 0 | 02/11/16 13:30 | 02/11/16 19:00 | [12 empty] | RIH PSP tools string (Dummy Run) to 5130 m. POOH and L/D PSP tools string.
hvjg | gvjgv | vjhv | 0 | 02/11/16 19:00 | 02/12/16 06:00 | [12 empty] | P/U and function test PSP tools string. P/T same at 2500 pai. RIH and perform PSP operation as per plan.
hvjg | gvjgv | vjhv | 0 | 02/12/16 06:00 | 02/12/16 06:00 | [12 empty] | Perform PSP operation is in progress as per plan.
hvjg | gvjgv | vjhv | 0 | 02/13/16 06:00 | 02/13/16 18:00 | [12 empty] | Performed PSP operation as per plan.
hvjg | gvjgv | vjhv | 0 | 02/13/16 18:00 | 02/14/16 00:00 | [12 empty] | Shut in well from surface. Terminate PSP operation. POOH WF W/L to surface, L/D PSP tools string. R/D W/L Lubricator / BOP.
hvjg | gvjgv | vjhv | 0 | 02/14/16 00:00 | 02/14/16 06:00 | [12 empty] | PVT sampling at 20/64" choke is in progress.
hvjg | gvjgv | vjhv | 0 | 02/14/16 06:00 | 02/14/16 09:30 | [12 empty] | Continue PVT 3rd sampling at 20/64" choke.
hvjg | gvjgv | vjhv | 0 | 02/14/16 09:30 | 02/15/16 06:00 | [12 empty] | Well shut in for final build up at surface and down hole with keeping 500 psi press in the DST string.
hvjg | gvjgv | vjhv | 0 | 02/15/16 06:00 | 02/15/16 06:00 | [12 empty] | Well remained shut in for final build up at surface and down hole with keeping 545 psi press in the DST string.
hvjg | gvjgv | vjhv | 0 | 02/16/16 06:00 | 02/16/16 06:00 | [12 empty] | Well remained shut in for final build up at surface and down hole with keeping 545 psi press in the DST string.
hvjg | gvjgv | vjhv | 0 | 02/17/16 06:00 | 02/17/16 06:00 | [12 empty] | Well remained shut in for final build up at surface and down hole .
hvjg | gvjgv | vjhv | 0 | 02/18/16 06:00 | 02/18/16 15:30 | [12 empty] | Recorded bottom hole parameters & made preparations to terminate DST # 5.
hvjg | gvjgv | vjhv | 0 | 02/18/16 15:30 | 02/18/16 19:30 | [12 empty] | Ruptured RD by applying 3400 psi from tubing annulus.Reversed out Tubing capacity & flared oil at pit. Dumped 50 bbls of contaminated brine. Circulated to homogenize brine to 1.05 Sp.Gr. | Productive
hvjg | gvjgv | vjhv | 0 | 02/18/16 19:30 | 02/18/16 20:00 | [12 empty] | Un set pkr. Confirmed Upward & Downward PKR movement is free..
hvjg | gvjgv | vjhv | 0 | 02/18/16 20:00 | 02/19/16 00:00 | [12 empty] | Resumed direct circulation.Circulated for complete cycle. | Productive
hvjg | gvjgv | vjhv | 0 | 02/19/16 00:00 | 02/19/16 01:00 | [12 empty] | Continued circulation & Circulated for complete cycle. | Productive
hvjg | gvjgv | vjhv | 0 | 02/19/16 01:00 | 02/19/16 06:00 | [12 empty] | Stopped circulation. Observed well. Found static. Resumed POOH & POOH up to 3856m.
hvjg | gvjgv | vjhv | 0 | 02/19/16 06:00 | 02/19/16 17:30 | [12 empty] | POOH. L/Down DST tools.Well static.
hvjg | gvjgv | vjhv | 0 | 02/19/16 17:30 | 02/19/16 19:00 | [12 empty] | PJSM. R/Up Shooting Nipple & Wire Line BOP. Closed Annular BOP at Nipple & Pressure tested against Blind Ram BOP @ 400 psi. OK | Productive
hvjg | gvjgv | vjhv | 0 | 02/19/16 19:00 | [13 empty] | R/Up SCHL for setting One permanent Bridge Plug @ 5009 m & one composit Bridge Plug @4885. Permanent B.Plug failed to pass through Perforations. POOH & L/Down B.Plug. Set composit B.Plu at 4885 m. POOH wire line in progress. | Non Productive
hvjg | gvjgv | vjhv | 0 | 02/20/16 06:00 | 02/20/16 08:00 | [12 empty] | POOH wire line to surface.
hvjg | gvjgv | vjhv | 0 | 02/20/16 08:00 | 02/20/16 08:30 | [12 empty] | PJSM.Pressure tested 7"B.Plug @ 3200. OK. R/Down Schl. | Productive
hvjg | gvjgv | vjhv | 0 | 02/20/16 08:30 | 02/20/16 10:30 | [12 empty] | Repair work on TDS / VFD( By Chinese Engineer). Function tested. OK. | Non Productive
hvjg | gvjgv | vjhv | 0 | 02/20/16 10:30 | 02/20/16 15:00 | [12 empty] | Periodic BOP pressure test. Retrieved Wear bushing. Pressure tested BOP stack & components. Set wear bushing | Productive
hvjg | gvjgv | vjhv | 0 | 02/20/16 15:00 | 02/21/16 06:00 | [12 empty] | PJSM. M/Up 7x4.5"TCP Guns (5SPF) & RIH down to 3897.76m
hvjg | gvjgv | vjhv | 0 | 02/21/16 06:00 | 02/21/16 09:00 | [12 empty] | RIH TCP guns down to 4797 m.
hvjg | gvjgv | vjhv | 0 | 02/21/16 09:00 | 02/21/16 12:00 | [12 empty] | PJSM.R/Up Schl wire line for correlation.Correlated & R/D Schl wire line.
hvjg | gvjgv | vjhv | 0 | 02/21/16 12:00 | 02/21/16 13:00 | [12 empty] | RIH TCP guns down to 4816 m. R/Up Flow head & Spaced out.M/Up surface connections. Flushed string & Closed pipe ram BOP. Activated TCP Guns fire head by applying 3200 psi pressure from Tubing annulus. Observed jerk at Rig Flloor.Confirmed Guns fired.
hvjg | gvjgv | vjhv | 0 | 02/21/16 13:00 | 02/21/16 14:00 | [12 empty] | Opened BOP.Monitored well at trip tank. Well static
hvjg | gvjgv | vjhv | 0 | 02/21/16 14:00 | 02/22/16 03:00 | [12 empty] | L/Down Flow Head & POOH up to surface. L/Down TCP guns. Well static.
hvjg | gvjgv | vjhv | 0 | 02/22/16 03:00 | 02/22/16 06:00 | [12 empty] | M/Up DST # 6 assembly & RIH down to 236 m. filled string with water.Pressure test BHA in progress. | Productive
hvjg | gvjgv | vjhv | 0 | 02/22/16 06:00 | 02/22/16 22:30 | [12 empty] | RIH DST # 6 down to 4730 m.
hvjg | gvjgv | vjhv | 0 | 02/22/16 22:30 | 02/23/16 00:00 | [12 empty] | PJSM. R/Up Flow head. Set Packer @ 4720 m.M/Up surface connections & Pr. tested hook up. OK
hvjg | gvjgv | vjhv | 0 | 02/23/16 00:00 | 02/23/16 03:00 | [12 empty] | PJSM. R/Up CTU.
hvjg | gvjgv | vjhv | 0 | 02/23/16 03:00 | 02/23/16 06:00 | [12 empty] | PJSM. Opened well to PIT. Well flowing to pit for cleanup.DST # 6 as per program.
hvjg | gvjgv | vjhv | 0 | 02/23/16 06:00 | 02/23/16 22:00 | [12 empty] | DST # 6 as per program. (Well flowing to pit for cleaning.After cleaning diverted well to flare pit through Seperator.)
hvjg | gvjgv | vjhv | 0 | 02/23/16 22:00 | 02/24/16 06:00 | [12 empty] | Shut in well at surface for Intermediate Shut In.
hvjg | gvjgv | vjhv | 0 | 02/24/16 06:00 | 02/24/16 11:00 | [12 empty] | Well remained shut at surface for intermediate build up.
hvjg | gvjgv | vjhv | 0 | 02/24/16 11:00 | 02/25/16 06:00 | [12 empty] | Opened well to pit for clean up & after cleaning diverted flow thorgh seperator. Production testing in progress.
hvjg | gvjgv | vjhv | 0 | 02/25/16 06:00 | 02/26/16 02:00 | [12 empty] | Well under production testing.
hvjg | gvjgv | vjhv | 0 | 02/26/16 02:00 | 02/26/16 06:00 | [12 empty] | Well shut in at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/26/16 06:00 | 02/26/16 06:00 | [12 empty] | Well remained shut at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/27/16 06:00 | 02/27/16 06:00 | [12 empty] | Well remained shut at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/28/16 06:00 | 02/28/16 06:00 | [12 empty] | Well remained shut at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/29/16 06:00 | 02/29/16 12:00 | [12 empty] | PJSM.Terminated DST # 6. Bled off string pressure. Filled string with brine.Failled to Bull head at 1000 psi pumping pressure. Ruptured RD & Cariied out reverse circulation. | Productive
hvjg | gvjgv | vjhv | 0 | 02/29/16 12:00 | 02/29/16 13:00 | [12 empty] | PJSM.Un set packer. Confirmed UP & Down movement of paker is free. Monitored well. Well static.
hvjg | gvjgv | vjhv | 0 | 02/29/16 13:00 | 02/29/16 19:00 | [12 empty] | Direct circulated. Observed Crude oil contaminated brine at bottom up.Diverted to Flare Pit & Dumped 350 bbls of brine | Productive
hvjg | gvjgv | vjhv | 0 | 02/29/16 19:00 | 02/29/16 20:00 | [12 empty] | PJSM. L/Down Flow Head. POOH up to 7"liner top.
hvjg | gvjgv | vjhv | 0 | 02/29/16 20:00 | 03/01/16 06:00 | [12 empty] | Monitored well at 7"liner top. Well stattic. POOH up to 236m & in progress.
hvjg | gvjgv | vjhv | 0 | 03/01/16 06:00 | 03/01/16 08:30 | [12 empty] | POOH to surface. L/Down DST tools.
hvjg | gvjgv | vjhv | 0 | 03/01/16 08:30 | 03/01/16 09:00 | [12 empty] | PJSM.R/Up shooting Nipple & Wire Line BOP. Pressure tested.@ 400 psi. OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/16 09:00 | 03/01/16 15:30 | [12 empty] | R/Up Wire Line & set Composite B.Plug @ 4770m. POOH line to surface.
hvjg | gvjgv | vjhv | 0 | 03/01/16 15:30 | 03/01/16 16:30 | [12 empty] | PJSM. Pressure tested B..Plug at 3500 psi surface pr. OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/16 16:30 | 03/01/16 17:00 | [12 empty] | R/Down Wire Line & Shooting Nipple.
hvjg | gvjgv | vjhv | 0 | 03/01/16 17:00 | 03/01/16 18:30 | [12 empty] | Slipped & Cut 66 Ms drill line. Reset Crown-o-Matic & ACS.. | Productive
hvjg | gvjgv | vjhv | 0 | 03/01/16 18:30 | 03/02/16 06:00 | [12 empty] | PJSM. M/Up TCP Guns & RIH down to 2812m. RIH in progress
hvjg | gvjgv | vjhv | 0 | 03/02/16 06:00 | 03/02/16 11:00 | [12 empty] | RIH TCP guns down to 4743.82.
hvjg | gvjgv | vjhv | 0 | 03/02/16 11:00 | 03/02/16 14:30 | [12 empty] | PJSM. R/Up schl wire line for correlation Correlated RA marker& R/Down Schl.
hvjg | gvjgv | vjhv | 0 | 03/02/16 14:30 | 03/02/16 15:30 | [12 empty] | RIH TCP guns down to 4761.R/Up Flow head & Spaced out.
hvjg | gvjgv | vjhv | 0 | 03/02/16 15:30 | 03/02/16 16:30 | [12 empty] | PJSM.Fired TCP guns by activating Hyd Firing head. Closed Pipe Ram BOP.Applied 3200 psi surface pressure from Tubing Annulus with DWS pumping Unit, Observed strong vibration at floor; confirmed guns fiired. | Productive
hvjg | gvjgv | vjhv | 0 | 03/02/16 16:30 | 03/02/16 17:30 | [12 empty] | Monitored well. Found static.
hvjg | gvjgv | vjhv | 0 | 03/02/16 17:30 | 03/03/16 00:00 | [12 empty] | L/Down Flow Head,4.5"pup joint. M/Up one 4.5"tbg jt & resumed POOH.
hvjg | gvjgv | vjhv | 0 |  | 03/03/16 06:00 | [12 empty] | Continued POOH up to surface & L/D all guns.
hvjg | gvjgv | vjhv | 0 | 03/03/16 06:00 | 03/03/16 17:30 | [12 empty] | PJSM. M/Up DST # 7 assembly & RIH down to 1961.295m. Filled string with water during RIH.( water cushion 1929.3m) Pressure tested water cushion at 7500 psi(@265m;@811m;@1386m & @ 1961m) Test OK. | Productive
hvjg | gvjgv | vjhv | 0 | 03/03/16 17:30 | 03/04/16 00:00 | [12 empty] | Continued RIH DST # 7 assembly down to 4268 m.
hvjg | gvjgv | vjhv | 0 | 03/04/16 00:00 | 03/04/16 03:00 | [12 empty] | Continued RIH DST # 7 assembly down to 4683.51m(EOT)PJSM. R/Up Flow head. Set Packer @ 4664 m
hvjg | gvjgv | vjhv | 0 | 03/04/16 03:00 | 03/04/16 04:30 | [12 empty] | M/Up surface connections to flow head & tubing annulus. Pr. tested hook up. OK
hvjg | gvjgv | vjhv | 0 | 03/04/16 04:30 | 03/04/16 06:00 | [12 empty] | DST as per program
hvjg | gvjgv | vjhv | 0 | 03/04/16 06:00 | 03/05/16 00:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/05/16 00:00 | 03/05/16 06:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/05/16 06:00 | 03/06/16 00:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/06/16 00:00 | 03/06/16 06:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit through seperator.
hvjg | gvjgv | vjhv | 0 | 03/06/16 06:00 | 03/07/16 00:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/07/16 00:00 | 03/07/16 06:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit for cleaning after Acid job.
hvjg | gvjgv | vjhv | 0 | 03/07/16 06:00 | 03/08/16 00:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/08/16 00:00 | 03/08/16 06:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit for cleaning after Acid job.
hvjg | gvjgv | vjhv | 0 | 03/08/16 06:00 | 03/09/16 00:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/09/16 00:00 | 03/09/16 06:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit for cleaning after Acid job.
hvjg | gvjgv | vjhv | 0 | 03/09/16 06:00 | 03/09/16 13:00 | [12 empty] | DST # 7 in pprogress. Well open to flare pit.
hvjg | gvjgv | vjhv | 0 | 03/09/16 13:00 | 03/10/16 06:00 | [12 empty] | Well shut in at tool for final buildup.R/Down injector head of CTU & well sut in at surface also.
hvjg | gvjgv | vjhv | 0 | 03/10/16 06:00 | 03/11/16 00:00 | [12 empty] | Well shut in at tool for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/11/16 00:00 | 03/11/16 06:00 | [12 empty] | Well shut in at tool for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/11/16 06:00 | 03/12/16 00:00 | [12 empty] | Well shut in at tool & @ surface for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/12/16 00:00 | 03/12/16 06:00 | [12 empty] | Well shut in at tool & @ surface for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/12/16 06:00 | 03/13/16 00:00 | [12 empty] | Well shut in at tool & @ surface for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/13/16 00:00 | 03/13/16 06:00 | [12 empty] | Well shut in at tool & @ surface for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/13/16 06:00 | 03/13/16 13:00 | [12 empty] | Well remained shut in at tool & @ surface for final buildup.
hvjg | gvjgv | vjhv | 0 | 03/13/16 13:00 | 03/13/16 14:00 | [12 empty] | Opened Tester valve by applying 2200 pr from tubing annulus. Recorded pressure at surface.
hvjg | gvjgv | vjhv | 0 | 03/13/16 14:00 | 03/14/16 00:00 | [12 empty] | Opened well to Flare pit. Well under production testing.
hvjg | gvjgv | vjhv | 0 | 03/14/16 00:00 | 03/14/16 06:00 | [12 empty] | Well under production testing.
hvjg | gvjgv | vjhv | 0 | 03/14/16 06:00 | 03/14/16 08:30 | [12 empty] | Well under production testing.
hvjg | gvjgv | vjhv | 0 | 03/14/16 08:30 | 03/14/16 17:00 | [12 empty] | PJSM.Terminated DST # 7. Bull headed HydroCarbon in string to formation with 170 bbls of Brine @ 3-4 BPM.( DWS pump).Spotted CaCO3 lcm pill against perforations to cure loss. | Productive
hvjg | gvjgv | vjhv | 0 | 03/14/16 17:00 | 03/14/16 19:00 | [12 empty] | Ruptured RD @ 3500 psi & revese circulated tubing volume with rig pump.R/Down ETS testing lines. | Productive
hvjg | gvjgv | vjhv | 0 | 03/14/16 19:00 | 03/14/16 19:30 | [12 empty] | Un seat DST packer.Confirmed Up/Down movement free.
hvjg | gvjgv | vjhv | 0 | 03/14/16 19:30 | 03/15/16 00:30 | [12 empty] | Resumed direct ciirculation with rig pump to homogenise brine. | Productive
hvjg | gvjgv | vjhv | 0 | 03/15/16 00:30 | 03/15/16 01:00 | [12 empty] | Flow checked-OK. L/Down Flow head.
hvjg | gvjgv | vjhv | 0 | 03/15/16 01:00 | 03/15/16 06:00 | [12 empty] | POOH up to 3256m. Racked back 4.5"tubing & laying down 3.5"tubing in progress.
hvjg | gvjgv | vjhv | 0 | 03/15/16 06:00 | 03/16/16 00:00 | [12 empty] | POOH DST assembly up to . L/Down 3-1/2"tubing joint. Observed partial losses @ 7 bbls/hr-average
hvjg | gvjgv | vjhv | 0 | 03/16/16 00:00 | 03/16/16 04:30 | [12 empty] | L/Down all 3.5"tubing & DST tools. Racked back DCs.
hvjg | gvjgv | vjhv | 0 | 03/16/16 04:30 | 03/16/16 06:00 | [12 empty] | PJSM. Retrieved wear bushing.Set test plug & Pressure tested BOP Stack & Its Components in progress. | Productive
hvjg | gvjgv | vjhv | 0 | 03/16/16 06:00 | 03/16/16 09:00 | [12 empty] | Pressure tested BOP Stack. | Productive
hvjg | gvjgv | vjhv | 0 | 03/16/16 09:00 | 03/16/16 10:00 | [12 empty] | Installed wear bushing.
hvjg | gvjgv | vjhv | 0 | 03/16/16 10:00 | 03/16/16 12:00 | [12 empty] | P/U & M/U 5 7/8" Flat Bottom mill with milling/Clean out BHA and RIH to 203m.
hvjg | gvjgv | vjhv | 0 | 03/16/16 12:00 | 03/16/16 18:00 | [12 empty] | Continue P/U 3 1/2" x 81 DP sgl from P/Rack and RIH from 203m to 971m.
hvjg | gvjgv | vjhv | 0 | 03/16/16 18:00 | 03/17/16 06:00 | [12 empty] | Continue P/U 5" x 180 DP sgl from P/Rack and RIH from 971m to 3194m. Drift all DP sgl and Stands. Fill up string every 20 string.