## Sheet1
WellGUID | WellName | WellboreName | WellboreDiameter | StartDate | EndDate | ActivityStartDepthMD | ActivityEndDepthMD | TopDepthMD | BottomDepthMD | TopDepthTVD | BottomDepthTVD | ActivityCodeL1 | ActivityCodeL2 | ActivityCodeL3 | ActivityCodeL4 | ActivityCodeL5 | ActivityCodeL6 | Description | TimeClassification | NPTReason | NPTDetail | UPDATE_DATE
hvjg | gvjgv | vjhv | 24 | 02/20/15 07:00 | 02/20/15 16:00 |  |  | 76 | 96 | [8 empty] | Added 24" S.Stab in BHA & drilled 24" hole from 76m to 96m. Reamed twice at connection. | Productive
hvjg | gvjgv | vjhv | 0 | 08/05/15 06:00 | 08/05/15 06:00 | [12 empty] | Monitored well through choke & circulated hole intermitently. | Productive
hvjg | gvjgv | vjhv | 0 | 08/06/15 06:00 | 08/06/15 07:00 | [12 empty] | Monitored Well through Choke & Circulated Hole Intermittently. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/10/15 06:00 | 08/10/15 22:00 |  |  | 5130 | 5148 | [8 empty] | Drilled 8-1/2" Hole from 5130m to 5148m. Reamed Twice at Connection. Observed Frequent Rotary Stalled (18 kft-lb) & String Stuck while Drilling @ 5146m - 5148m. Worked & Released String. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/21/15 06:00 | 08/21/15 06:00 |  |  | 5278 | 5299 | [8 empty] | Cont' Drilling & Drilled 8-1/2" Hole from 5278m to 5299m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/22/15 06:00 | 08/22/15 19:00 |  |  | 5299 | 5311 | [8 empty] | Cont' Drilling & Drilled 8-1/2" Hole from 5299m to 5311m. | Productive
hvjg | gvjgv | vjhv | 8.5 | 08/31/15 06:00 | 08/31/15 06:00 |  |  | 5443 | 5474 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5443m to 5474m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (2.28 Deg @ 5440m). Recorded 0.21% Connection Gas. | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/01/15 06:00 | 09/01/15 17:30 |  |  | 5474 | 5491 | [8 empty] | Drilled 8-1/2" Hole from 5474m to 5491m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (0.28 Deg @ 5468m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/04/15 06:00 | 09/04/15 06:00 |  |  | 5553 | 5591 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5553m to 5591m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (3.15 Deg @ 5556m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/05/15 06:00 | 09/05/15 06:00 |  |  | 5591 | 5621 | [8 empty] | Cont'd Drilling & Drilled 8-1/2" Hole from 5591m to 5621m with SLB 'Xceed'. Reamed Twice & Recorded MWD Survey at Connection (0.07 Deg @ 5585m). | Productive
hvjg | gvjgv | vjhv | 8.5 | 09/08/15 06:00 | 09/08/15 09:30 |  |  | 5667 | 5669 | [8 empty] | Drilled 8-1/2" Hole from 5667m to 5669m. | Productive
hvjg | gvjgv | vjhv | 0 | 09/11/15 06:00 | 09/11/15 07:00 | [12 empty] | RIH from 4702m to 4965m on elevators.
hvjg | gvjgv | vjhv | 0 | 09/14/15 06:00 | 09/14/15 09:00 | [12 empty] | P/U 60 joints of 5-1/2" S-135 DP's from Cat-Walk & RIH single by single from 3464m to 3721m.
hvjg | gvjgv | vjhv | 0 | 09/15/15 06:00 | 09/15/15 20:30 | [12 empty] | POOH from 4564m to surface. Flow checked @ Top of BHA, well static. L/D intensifier & 6-1/2" DC single, break-out Over Shot. Inspected Over Shot thoroughly, found fish marks on Over Shot Bowl (out-side), no scratches on Grapples. | Non Productive
hvjg | gvjgv | vjhv | 0 | 09/17/15 06:00 | 09/17/15 17:30 | [12 empty] | POOH from 3741m to surface. Flow checked @ Top of BHA, well static. L/D intensifier & 6-1/2" DC single, break-out Over Shot. Inspected Over Shot thoroughly, found fish marks on Over Shot Bowl & Lip-Guide (out-side). L/D 8-1/8" Over Shot & 5" bent DP. | Non Productive
hvjg | gvjgv | vjhv | 6 | 11/08/15 06:00 | 11/08/15 06:00 |  |  | 5609 | 5629 | [8 empty] | Drilled 6" Hole from 5609m to 5629m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 6 | 11/09/15 06:00 | 11/09/15 06:00 |  |  | 5629 | 5650 | [8 empty] | Drilled 6" Hole from 5629m to 5650m. Reamed Twice at Connection. | Productive
hvjg | gvjgv | vjhv | 6 | 11/10/15 06:00 | 11/10/15 06:00 |  |  | 5650 | 5665 | [8 empty] | Drilled 6" Hole from 5650m to 5665m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/11/15 06:00 | 11/11/15 09:00 |  |  | 5665 | 5667 | [8 empty] | Drilled 6" Hole from 5665m to 5667m. Stopped Drilling & Flow Checked - OK. | Productive
hvjg | gvjgv | vjhv | 6 | 11/16/15 06:00 | 11/16/15 06:00 |  |  | 5735 | 5761 | [8 empty] | Drilled 6" Hole from 5735m to 5761m. Reamed Twice at Connection. Recorded MWD Survey at 5725m & 5740m. | Productive
hvjg | gvjgv | vjhv | 6 | 11/18/15 06:00 | 11/18/15 11:00 |  |  | 5777 | 5779 | [8 empty] | Drilled 6" Hole from 5777m to 5779m. | Productive
hvjg | gvjgv | vjhv | 0 | 11/23/15 06:00 | 11/23/15 07:00 | [12 empty] | Reamed before connection & Recorded MWD Survey @ 5866m (3.56 deg / 37.70 Azm). | Productive
hvjg | gvjgv | vjhv | 0 | 12/20/15 06:00 | 12/20/15 06:00 | [12 empty] | Tubing Flex Trip. POOH is in Progress.
hvjg | gvjgv | vjhv | 0 | 12/21/15 06:00 | 12/21/15 19:00 | [12 empty] | POOH TBG to Surface & Perforated 5" Liner with W/Line Guns as per Program.
hvjg | gvjgv | vjhv | 0 | 12/27/15 06:00 | 12/27/15 06:00 | [12 empty] | RIH Slickline & Attempted to Fire TCP Guns Both Mechanically (2 Times) & Hydraulically (3 Times) - No Success. R/Down Slickline Gear. R/Up & RIH with Sprint CT.
hvjg | gvjgv | vjhv | 0 | 12/28/15 06:00 | 12/28/15 06:00 | [12 empty] | RIH Sprint CT & Circ. / Cleaned Mechanical Firing Head Top. POOH CT to Surface. RIH CT with Mechanical Firing Head Tool.
hvjg | gvjgv | vjhv | 0 | 12/29/15 06:00 | 12/29/15 06:00 | [12 empty] | RIH CT with Mechanical Firing Head Tool & Attempted to Fire TCP Guns. POOH CT to Surface - No Indication / Mark on Firing Tool. R/Down Sprint CT. R/Up & RIH ETS Slickline & Fired TCP Guns. POOH Slickline to Surface & R/ Down the same - Observed Marks on Firing Tool. Circ / Homegenized Mud Column. Flow Check Prior to POOH TCP Guns in Progress.
hvjg | gvjgv | vjhv | 0 | 12/30/15 06:00 | 12/30/15 06:00 | [12 empty] | Attempted to POOH TCP Guns - Observed String Stuck. Worked & Released String with 50 Ton Overpull. POOH TCP Guns to Surface - Observed Guns Not Fired. L/Down TCP Guns in Progress. | Non Productive
hvjg | gvjgv | vjhv | 0 | 12/31/15 06:00 | 12/31/15 09:00 | [12 empty] | POOH & L/Down All TCP Guns.
hvjg | gvjgv | vjhv | 0 | 01/02/16 06:00 | 01/02/16 09:00 | [12 empty] | Washed Down from 5800m to 5884m & Observed Compression While Wasing Down. Meanwhile Prepared 1.10 S.G CaCl2 Brine & Cleaned Mud Tanks. | Productive
hvjg | gvjgv | vjhv | 0 | 01/07/16 06:00 | 01/07/16 08:00 | [12 empty] | Continued RIH DST String to Packer Setting Depth.
hvjg | gvjgv | vjhv | 0 | 01/09/16 06:00 | 01/09/16 06:00 | [12 empty] | Well Under Production Testing - DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/10/16 06:00 | 01/10/16 06:00 | [12 empty] | Well Under Production Testing - DST # 1 in Progress.
hvjg | gvjgv | vjhv | 0 | 01/11/16 06:00 | 01/11/16 12:30 | [12 empty] | Terminated DST # 1. R/Down Sprint CT Injector Head & BOP. H/Up SLB Pumping Line to Annulus & Ruptured both RD Circ. V/Vs @ 3500 PSI - Reverse Circ. Tubing Volume. Open Pipe Rams & Unset PKR. | Productive
hvjg | gvjgv | vjhv | 0 | 01/18/16 06:00 | 01/18/16 23:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 01/31/16 06:00 | 02/01/16 01:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/09/16 06:00 | 02/09/16 08:00 | [12 empty] | Well remained under production testing.
hvjg | gvjgv | vjhv | 0 | 02/13/16 06:00 | 02/13/16 18:00 | [12 empty] | Performed PSP operation as per plan.
hvjg | gvjgv | vjhv | 0 | 02/16/16 06:00 | 02/16/16 06:00 | [12 empty] | Well remained shut in for final build up at surface and down hole with keeping 545 psi press in the DST string.
hvjg | gvjgv | vjhv | 0 | 02/17/16 06:00 | 02/17/16 06:00 | [12 empty] | Well remained shut in for final build up at surface and down hole .
hvjg | gvjgv | vjhv | 0 | 02/18/16 06:00 | 02/18/16 15:30 | [12 empty] | Recorded bottom hole parameters & made preparations to terminate DST # 5.
hvjg | gvjgv | vjhv | 0 | 02/27/16 06:00 | 02/27/16 06:00 | [12 empty] | Well remained shut at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/28/16 06:00 | 02/28/16 06:00 | [12 empty] | Well remained shut at tool for final build up.
hvjg | gvjgv | vjhv | 0 | 02/29/16 06:00 | 02/29/16 12:00 | [12 empty] | PJSM.Terminated DST # 6. Bled off string pressure. Filled string with brine.Failled to Bull head at 1000 psi pumping pressure. Ruptured RD & Cariied out reverse circulation. | Productive