## Sheet1
WellGUID | WellName | WellboreName | WellboreDiameter | StartDate | EndDate | ActivityStartDepthMD | ActivityEndDepthMD | TopDepthMD | BottomDepthMD | TopDepthTVD | BottomDepthTVD | ActivityCodeL1 | ActivityCodeL2 | ActivityCodeL3 | ActivityCodeL4 | ActivityCodeL5 | ActivityCodeL6 | Description | TimeClassification | NPTReason | NPTDetail | UPDATE_DATE | Discontinuity
z | z | z |  | 09/20/16 00:00 | 09/20/16 05:00 | [12 empty] | ADJUSTED ROTARY CENTER. CHECKED MUD PUMP EFFICIENCY & ACCEPTED RIG. | Productive |  |  |  | No
z | z | z |  | 09/20/16 05:00 | 09/20/16 09:30 | [12 empty] | P/U & M/U 36" TC BIT, BIT SUB, SHOCK SUB & 11" DC. M/U 1 X 5" HWDP & RACKED BACK. |  |  |  |  | No
z | z | z |  | 09/20/16 09:30 | 09/20/16 10:00 | [12 empty] | CONDUCTED PRE-SPUD SAFETY MEETING, SACRIFICED TWO GOATS IN THE NAME OF ALLAH AND POST PRAYERS, SPUDDED-IN WELL ZARGHUN SOUTH-3 @ 1000 HRS ON SEPTEMBER 20, 2016 WITH BENTONITE SPUD MUD. | Productive |  |  |  | No
z | z | z | 36 | 09/20/16 10:00 | 09/20/16 00:00 |  |  | 14 | 25 | [8 empty] | COMMENCED DRILLING & DRILLED 36" HOLE FROM 14M TO 25M. | Productive |  |  |  | No
z | z | z | 36 | 09/20/16 00:00 | 09/20/16 06:00 |  |  | 25 | 35 | [8 empty] | CONTINUED DRILLING 36" HOLE FROM 25M TO 35M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 36 | 09/21/16 00:00 | 09/21/16 14:45 |  |  | 25 | 41 | [8 empty] | CONTINUED DRILLING 36" HOLE FROM 25M TO 41M. | Productive |  |  |  | No
z | z | z |  | 09/21/16 14:45 | 09/21/16 15:30 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 09/21/16 15:30 | 09/21/16 15:45 | [12 empty] | POOH INSIDE STOVE PIPE. |  |  |  |  | No
z | z | z |  | 09/21/16 15:45 | 09/21/16 16:00 | [12 empty] | RIH TO BOTTOM. |  |  |  |  | No
z | z | z |  | 09/21/16 16:00 | 09/21/16 17:30 | [12 empty] | SWEPT OUT 40 BBL HI-VIS PILL. CIRCULATED OUT TRACER PILL, HOLE WAS IN GAUGE. | Productive |  |  |  | No
z | z | z |  | 09/21/16 17:30 | 09/21/16 18:45 | [12 empty] | DROPPED TOTCO. POOH BHA TO SURFACE. RACK BACK 11" DC STAND AND L/D 36" BIT, BIT SUB, SHOCK SUB & ST. STAB. RETRIEVED TOTCO & RECORDED 0.5 DEG DEVIATION @ 39M. |  |  |  |  | No
z | z | z |  | 09/21/16 18:45 | 09/21/16 19:15 | [12 empty] | R/U WFD TRS GEARS. |  |  |  |  | Yes
z | z | z |  | 09/21/16 19:15 | 09/21/16 22:45 | [12 empty] | P/U & RIH 30" CONDUCTOR ALREADY WELDED WITH FLOAT SHOE DOWN TO 40M. SECURED THE CONDUCTOR ON RIG FLOOR. |  |  |  |  | No
z | z | z |  | 09/21/16 22:45 | 09/22/16 00:00 | [12 empty] | RIH STINGER ON 5" HWDPS & 2 X 5" PUP JTS. STABBED-IN STRINGER, CHECKED INTEGRITY AND SECURED THE STRING ON RIG FLOOR. |  |  |  |  | No
z | z | z |  | 09/22/16 00:00 | 09/22/16 00:45 | [12 empty] | H/U CEMENT LINES AND CIRCULATED TO CONDITION MUD. | Productive |  |  |  | No
z | z | z |  | 09/22/16 00:45 | 09/22/16 01:00 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 09/22/16 01:00 | 09/22/16 01:30 | [12 empty] | FLUSHED CEMENT LINES. PRESSURE TESTED CEMENT LINES AT MIN/MAX 500PSI / 3000PSI, OK. | Productive |  |  |  | No
z | z | z |  | 09/22/16 01:30 | 09/22/16 02:30 | [12 empty] | PUMPED 40 BBL WATER @ 5BPM. FLY MIXED & PUMPED 15.8 PPG CEMENT SLURRY @ 5BPM. OBSERVED MUD WATER CONTAMINATION AFTER 10 BBL OF CEMENT. OBSERVED CONTAMINATED CEMENT AFTER 60 BBL & NEAT CEMENT AFTER 85 BBL (RETURN CEMENT WT. 15.8 PPG) . TOTAL 93 BBL CEMENT WAS PUMPED. CHECKED RETURNS, FLOATS HOLD. STING OUT STINGER AND FLUSHED LINES WITH 1.5 BBL OF MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 09/22/16 02:30 | 09/22/16 03:15 | [12 empty] | WOC, MEANWHILE R/D CEMENT LINES. POOH & L/D 2 X 5" DP PUP JOINTS & 1 X 5" HWDP. RACK BACK 1 X 5" HWDP STAND. |  |  |  |  | No
z | z | z |  | 09/22/16 03:15 | 09/22/16 05:00 | [12 empty] | WOC. |  |  |  |  | No
z | z | z |  | 09/22/16 05:00 | 09/22/16 06:00 | [12 empty] | WOC, MEANWHILE WINDOW CUT 42" STOVE PIPE IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 09/22/16 00:00 | 09/22/16 00:45 | [12 empty] | H/U CEMENT LINES AND CIRCULATED TO CONDITION MUD. | Productive |  |  |  | No
z | z | z |  | 09/22/16 00:45 | 09/22/16 01:00 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 09/22/16 01:00 | 09/22/16 01:30 | [12 empty] | FLUSHED CEMENT LINES. PRESSURE TESTED CEMENT LINES AT MIN/MAX 500PSI / 3000PSI, OK. | Productive |  |  |  | No
z | z | z |  | 09/22/16 01:30 | 09/22/16 02:30 | [12 empty] | PUMPED 40 BBL WATER @ 5BPM. FLY MIXED & PUMPED 15.8 PPG CEMENT SLURRY @ 5BPM. OBSERVED MUD WATER CONTAMINATION AFTER 10 BBL OF CEMENT. OBSERVED CONTAMINATED CEMENT AFTER 60 BBL & NEAT CEMENT AFTER 85 BBL (RETURN CEMENT WT. 15.8 PPG) . TOTAL 93 BBL CEMENT WAS PUMPED. CHECKED RETURNS, FLOATS HOLD. STING OUT STINGER AND FLUSHED LINES WITH 1.5 BBL OF MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 09/22/16 02:30 | 09/22/16 03:15 | [12 empty] | WOC, MEANWHILE R/D CEMENT LINES. POOH & L/D 2 X 5" DP PUP JOINTS & 1 X 5" HWDP. RACK BACK 1 X 5" HWDP STAND. |  |  |  |  | No
z | z | z |  | 09/22/16 03:15 | 09/22/16 09:00 | [12 empty] | WOC. MEANWHILE WINDOW CUT 42" STOVE PIPE. |  |  |  |  | No
z | z | z |  | 09/22/16 09:00 | 09/22/16 14:00 | [12 empty] | CUT & L/D 42" STOVE PIPE & 30" CONDUCTOR PIPE. FINAL CUT 30" CONDUCTOR. |  |  |  |  | Yes
z | z | z |  | 09/22/16 14:00 | 09/23/16 00:00 | [12 empty] | WELDED 29 1/2" FLANGE. N/U MUD CROSS & DIVERTER. H/U VENT LINE & N/U FLOW RISER. |  |  |  |  | No
z | z | z |  | 09/23/16 00:00 | 09/23/16 02:00 | [12 empty] | FUNCTION TESTED DIVERTER. OBSERVED DIVERTER ELEMENT NOT CLOSING. ATTEMPTED MANY TIMES BUT NO SUCCESS. |  |  |  |  | No
z | z | z |  | 09/23/16 02:00 | 09/23/16 06:00 | [12 empty] | WAIT ON EQUIPMENT MEANWHILE M/U 4 x 5" HWDP STANDS IN MOUSE HOLE. |  |  |  |  | No
z | z | z |  | 09/23/16 00:00 | 09/23/16 02:00 | [12 empty] | FUNCTION TESTED DIVERTER. OBSERVED DIVERTER ELEMENT NOT CLOSING. ATTEMTED MANY TIMES BUT NO SUCCESS. |  |  |  |  | No
z | z | z |  | 09/23/16 02:00 | 09/23/16 11:30 | [12 empty] | WAIT ON EQUIPMENT (WOE), MEANWHILE M/U & R/B 4 x 5" HWDP STDS, 7 X 5" DP STDS & 1 X 8" DC STD IN MOUSE HOLE. |  |  |  |  | No
z | z | z |  | 09/23/16 11:30 | 09/23/16 12:30 | [12 empty] | M/U 26" NEW TC BIT, BIT SUB & SHOCK SUB. TAGGED AT 38M. |  |  |  |  | No
z | z | z |  | 09/23/16 12:30 | 09/23/16 17:30 | [12 empty] | DRILLED CEMENT & FLOAT SHOE. | Productive |  |  |  | No
z | z | z | 26 | 09/23/16 17:30 | 09/24/16 00:00 |  |  | 41 | 46 | [8 empty] | COMMENCED DRILLING & DRILLED 26" HOLE FROM 41M TO 46M WITH CONTROLLED PARAMETERS. | Productive |  |  |  | No
z | z | z | 26 | 09/24/16 00:00 | 09/24/16 04:30 |  |  | 46 | 52 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 46M TO 52M. | Productive |  |  |  | No
z | z | z |  | 09/24/16 04:30 | 09/24/16 05:30 | [12 empty] | POOH TO SURFACE & ADDED ST. STAB IN THE STRING. |  |  |  |  | No
z | z | z |  | 09/24/16 05:30 | 09/24/16 06:00 | [12 empty] | RIH WHILE REAMING THE HOLE IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 26 | 09/24/16 00:00 | 09/24/16 04:30 |  |  | 46 | 52 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 46M TO 52M WITH CONTROLLED PARAMETERS. | Productive |  |  |  | No
z | z | z |  | 09/24/16 04:30 | 09/24/16 05:30 | [12 empty] | POOH TO SURFACE & ADDED ST. STAB IN THE STRING. |  |  |  |  | No
z | z | z |  | 09/24/16 05:30 | 09/24/16 08:15 | [12 empty] | RIH WHILE REAMING THE HOLE. | Productive |  |  |  | No
z | z | z | 26 | 09/24/16 08:15 | 09/24/16 21:15 |  |  | 52 | 64 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 52M TO 64M WITH CONTROLLED PARAMETERS. | Productive |  |  |  | No
z | z | z |  | 09/24/16 21:15 | 09/24/16 21:30 | [12 empty] | POOH FROM 64M TO 16M. |  |  |  |  | No
z | z | z |  | 09/24/16 21:30 | 09/24/16 22:00 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 09/24/16 22:00 | 09/24/16 22:45 | [12 empty] | ADDED SECOND ST. STAB & 2 X 9" DCS IN THE STRING. |  |  |  |  | Yes
z | z | z |  | 09/24/16 22:45 | 09/24/16 23:00 | [12 empty] | CONDUCTED TOTCO SURVEY, RECORDED ZERO DEG DEVIATION @ 54M. | Productive |  |  |  | No
z | z | z |  | 09/24/16 23:00 | 09/24/16 23:15 | [12 empty] | RIH WHILE REAMING THE HOLE. | Productive |  |  |  | No
z | z | z |  | 09/24/16 23:15 | 09/25/16 00:00 |  |  | 64 | 65 | [8 empty] | RESUMED DRILLING FROM 64M TO 65M WITH CONTROLLED PARAMETERS & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 09/25/16 00:00 | 09/25/16 06:00 |  |  | 65 | 70 | [8 empty] | CONTINUED DRILLING FROM 65M TO 70M WITH CONTROLLED PARAMETERS & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 26 | 09/25/16 00:00 | 09/25/16 00:00 |  |  | 65 | 86 | [8 empty] | DRILLED 26" HOLE FROM 65M TO 86M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 09/25/16 00:00 | 09/25/16 06:00 |  |  | 86 | 91 | [8 empty] | CONTINUED DRILLING FROM 86M TO 91M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 26 | 09/26/16 00:00 | 09/26/16 12:00 |  |  | 86 | 93 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 86M TO 93M. | Productive |  |  |  | No
z | z | z |  | 09/26/16 12:00 | 09/26/16 12:30 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 09/26/16 12:30 | 09/26/16 14:30 | [12 empty] | POOH TO SURFACE (L/D BIT, SHOCK SUB & 2 X 26" ST. STAB). |  |  |  |  | No
z | z | z |  | 09/26/16 14:30 | 09/26/16 16:00 | [12 empty] | N/D 29 1/2" RIG DIVERTER ASSY & FLOW RISER. |  |  |  |  | No
z | z | z |  | 09/26/16 16:00 | 09/26/16 19:00 | [12 empty] | N/U 29 1/2" RENTAL DIVERTER ASSY & FLOW RISER. |  |  |  |  | No
z | z | z |  | 09/26/16 19:00 | 09/26/16 22:30 | [12 empty] | ATTEMPTED FUNCTION TEST OF DIVERTER MANY TIMES, BUT NO SUCCESS. OBSERVED LEAKAGE OF HYDRAULIC OIL ACROSS PISTON SEALS. MODIFIED RETURN HYDRAULIC HOSE WITH VALVE. DIVERTER ELEMENT CLOSED BY BLEEDING TWICE THROUGH RETURN HOSE. DIVERTER ELEMENT OPENED BY DRAINING HYDRAULIC OIL. (MODIFIED FUNCTION TEST FOUND OK). | Non Productive |  |  |  | No
z | z | z |  | 09/26/16 22:30 | 09/27/16 00:00 | [12 empty] | M/U 26" RR TC BIT & RIH DOWN TO 37M. |  |  |  |  | Yes
z | z | z |  | 09/27/16 00:00 | 09/27/16 00:30 | [12 empty] | CONTINUED RIH FROM 37M TO BOTTOM @ 93M. |  |  |  |  | No
z | z | z |  | 09/27/16 00:30 | 09/27/16 06:00 |  |  | 93 | 100 | [8 empty] | RESUMED DRILLING FROM 93M TO 100M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 09/27/16 00:00 | 09/27/16 00:30 | [12 empty] | CONTINUED RIH FROM 37M TO BOTTOM @ 93M. |  |  |  |  | No
z | z | z |  | 09/27/16 00:30 | 09/27/16 09:45 |  |  | 93 | 104 | [8 empty] | RESUMED DRILLING FROM 93M TO 104M. | Productive |  |  |  | No
z | z | z |  | 09/27/16 09:45 | 09/27/16 10:30 | [12 empty] | OBSERVED PROBLEM IN TDS. RECTIFIED THE SAME. |  |  |  |  | No
z | z | z |  | 09/27/16 10:30 | 09/27/16 20:45 |  |  | 104 | 121 | [8 empty] | RESUMED DRILLING FROM 104M TO 121M. | Productive |  |  |  | No
z | z | z |  | 09/27/16 20:45 | 09/27/16 21:00 | [12 empty] | CIRCULATED FOR BOTTOM UP. | Productive |  |  |  | No
z | z | z |  | 09/27/16 21:00 | 09/27/16 22:00 | [12 empty] | ADDED 8" HMD JAR AND 8" DC IN STRING. |  |  |  |  | No
z | z | z |  | 09/27/16 22:00 | 09/27/16 22:15 | [12 empty] | CONDUCTED TOTCO SURVEY. FOUND MISRUN. | Productive |  |  |  | Yes
z | z | z |  | 09/27/16 22:15 | 09/27/16 22:30 | [12 empty] | CONDUCTED TOTCO SURVEY AGAIN, RECORDED ZERO DEG DEVIATION AT 115M. | Productive |  |  |  | No
z | z | z |  | 09/27/16 22:30 | 09/28/16 00:00 |  |  | 121 | 123 | [8 empty] | RESUMED DRILLING FROM 121M TO 123M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 09/28/16 00:00 | 09/28/16 06:00 |  |  | 123 | 131 | [8 empty] | CONTINUED DRILLING FROM 123M TO 131M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 09/28/16 00:00 | 09/28/16 17:00 |  |  | 123 | 149 | [8 empty] | CONTINUED DRILLING FROM 123M TO 149M. | Productive |  |  |  | No
z | z | z |  | 09/28/16 17:00 | 09/28/16 19:00 | [12 empty] | OBSERVED LEAKAGE IN HIGH PRESSURE HYDRAULIC PIPE OF TDS. REPLACED THE SAME. MEANWHILE CIRCULATED. | Productive |  |  |  | No
z | z | z |  | 09/28/16 19:00 | 09/29/16 00:00 |  |  | 149 | 154 | [8 empty] | RESUMED DRILLING FROM 149M TO 154M. | Productive |  |  |  | No
z | z | z |  | 09/29/16 00:00 | 09/29/16 06:00 |  |  | 154 | 160 | [8 empty] | CONTINUED DRILLING FROM 154M TO 160M. | Productive |  |  |  | No
z | z | z |  | 09/29/16 00:00 | 09/29/16 15:45 |  |  | 154 | 171 | [8 empty] | CONTINUED DRILLING FROM 154M TO 171M. | Productive |  |  |  | No
z | z | z |  | 09/29/16 15:45 | 09/29/16 16:15 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 09/29/16 16:15 | 09/29/16 16:30 | [12 empty] | DROPPED TOTCO. |  |  |  |  | No
z | z | z |  | 09/29/16 16:30 | 09/29/16 18:30 | [12 empty] | POOH FROM 171M TO SURFACE. L/D BIT. (RECORDED 0.25 DEG DEVIATION AT 169M) |  |  |  |  | No
z | z | z |  | 09/29/16 18:30 | 09/29/16 20:15 | [12 empty] | M/U NEW 26" TC BIT AND RIH WITH SAME BHA DOWN TO 171M. |  |  |  |  | No
z | z | z |  | 09/29/16 20:15 | 09/30/16 00:00 |  |  | 171 | 185 | [8 empty] | RESUMED DRILLING FROM 171M TO 185M. | Productive |  |  |  | No
z | z | z |  | 09/30/16 00:00 | 09/30/16 06:00 |  |  | 185 | 210 | [8 empty] | CONTINUED DRILLING FROM 185M TO 210M & IS IN PROGRESS. REAMED ONCE AT CONNECTION. | Productive |  |  |  | No
z | z | z | 26 | 09/30/16 00:00 | 09/30/16 23:00 |  |  | 185 | 304 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 185M TO 304M. REAMED ONCE AT EACH CONNECTION. | Productive |  |  |  | No
z | z | z |  | 09/30/16 23:00 | 09/30/16 23:30 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 09/30/16 23:30 | 09/30/16 23:45 | [12 empty] | CONDUCTED TOTCO SURVEY. RECORDED 1 DEG DEVIATION AT 294M. | Productive |  |  |  | No
z | z | z |  | 09/30/16 23:45 | 10/01/16 00:00 |  |  | 304 | 305 | [8 empty] | RESUMED DRILLING FROM 304M TO 305M. | Productive |  |  |  | No
z | z | z | 26 | 10/01/16 00:00 | 10/01/16 05:45 |  |  | 305 | 330 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 305M TO 330M. | Productive |  |  |  | No
z | z | z |  | 10/01/16 05:45 | 10/01/16 06:00 | [12 empty] | CIRCULATION TILL SHAKERS CLEAN PRIOR WIPER TRIP IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 26 | 10/01/16 00:00 | 10/01/16 05:45 |  |  | 305 | 330 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 305M TO 330M. | Productive |  |  |  | No
z | z | z |  | 10/01/16 05:45 | 10/01/16 07:15 | [12 empty] | CIRCULATION TILL SHAKERS CLEAN PRIOR WIPER TRIP. | Productive |  |  |  | No
z | z | z |  | 10/01/16 07:15 | 10/01/16 07:45 | [12 empty] | POOH FROM 330M TO TOP OF BHA AT 247M. |  |  |  |  | No
z | z | z |  | 10/01/16 07:45 | 10/01/16 10:45 | [12 empty] | POOH FROM 247M TO 141M. OBSERVED TIGHT SPOTS AT 240M, 232M, 195M & 142M. CLEARED WITH BACK REAMING. | Productive |  |  |  | No
z | z | z |  | 10/01/16 10:45 | 10/01/16 12:45 | [12 empty] | POOH FROM 141M TO SURFACE. BIT & ST. STABS COMPLETELY BALLED UP. CLEANED THE SAME. | Non Productive |  |  |  | No
z | z | z |  | 10/01/16 12:45 | 10/01/16 14:45 | [12 empty] | RIH FROM SURFACE TO TOP OF BHA AT 247M. |  |  |  |  | No
z | z | z |  | 10/01/16 14:45 | 10/01/16 15:15 | [12 empty] | RIH FROM 247M TO 330M. WASHED DOWN LAST STAND. |  |  |  |  | Yes
z | z | z |  | 10/01/16 15:15 | 10/01/16 17:00 | [12 empty] | CIRCULATED MEANWHILE PREPARED KCL POLYMER MUD. | Productive |  |  |  | No
z | z | z |  | 10/01/16 17:00 | 10/01/16 18:00 | [12 empty] | PUMPED 25 BBL WATER AND DISPLACED SPUD MUD WITH 7% KCL POLYMER MUD OF 1.13 SG. CIRCULATED TILL HOMOGENIZED MUD. | Productive |  |  |  | No
z | z | z |  | 10/01/16 18:00 | 10/02/16 00:00 |  |  | 330 | 352 | [8 empty] | RESUMED DRILLING FROM 330M TO 352M. | Productive |  |  |  | No
z | z | z | 26 | 10/02/16 00:00 | 10/02/16 06:00 |  |  | 352 | 369 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 352M TO 369M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 26 | 10/02/16 00:00 | 10/02/16 14:30 |  |  | 352 | 401 | [8 empty] | CONTINUED DRILLING 26" HOLE FROM 352M TO 401M (SECTION TD). | Productive |  |  |  | No
z | z | z |  | 10/02/16 14:30 | 10/02/16 16:30 | [12 empty] | CIRCULATION TILL SHAKERS CLEAN PRIOR POOH. |  |  |  |  | No
z | z | z |  | 10/02/16 16:30 | 10/02/16 17:30 | [12 empty] | POOH FROM 401M TO TOP OF BHA AT 247M. |  |  |  |  | No
z | z | z |  | 10/02/16 17:30 | 10/02/16 20:15 | [12 empty] | POOH FROM 247M TO SURFACE. L/D JAR, 1X11" DC & SHOCK SUB. (HOLE CONDITION GOOD). |  |  |  |  | No
z | z | z |  | 10/02/16 20:15 | 10/02/16 22:45 | [12 empty] | RIH 3RR1 BIT, 9 5/8" NMDC WITH BHA DOWN TO 243M. |  |  |  |  | No
z | z | z |  | 10/02/16 22:45 | 10/02/16 23:45 | [12 empty] | RIH FROM 243M TO 401M. WASHED DOWN LAST STAND. |  |  |  |  | No
z | z | z |  | 10/02/16 23:45 | 10/03/16 00:00 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN IS IN PROGRESS. | Productive |  |  |  | Yes
z | z | z |  | 10/03/16 00:00 | 10/03/16 01:15 | [12 empty] | CONTINUED CIRCULATION TILL SHAKERS CLEAN. |  |  |  |  | No
z | z | z |  | 10/03/16 01:15 | 10/03/16 02:00 | [12 empty] | SPOTTED 150 BBL OF HI VIS PILL AT BOTTOM. DROPPED EMS TOOL. |  |  |  |  | No
z | z | z |  | 10/03/16 02:00 | 10/03/16 03:00 | [12 empty] | POOH FROM 401M TO TOP OF BHA AT 243M. |  |  |  |  | No
z | z | z |  | 10/03/16 03:00 | 10/03/16 05:30 | [12 empty] | POOH FROM 243M TO SURFACE. L/D JAR, NMDC & ST.STAB. (HOLE CONDITION GOOD). RETRIEVED EMS TOOL. |  |  |  |  | No
z | z | z |  | 10/03/16 05:30 | 10/03/16 06:00 | [12 empty] | R/U WFD TRS EQUIPMENT IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/03/16 00:00 | 10/03/16 01:15 | [12 empty] | CONTINUED CIRCULATION TILL SHAKERS CLEAN. |  |  |  |  | No
z | z | z |  | 10/03/16 01:15 | 10/03/16 02:00 | [12 empty] | SPOTTED 150 BBL OF HI-VIS PILL AT BOTTOM. DROPPED EMS TOOL. |  |  |  |  | No
z | z | z |  | 10/03/16 02:00 | 10/03/16 03:00 | [12 empty] | POOH FROM 401M TO TOP OF BHA AT 243M. |  |  |  |  | No
z | z | z |  | 10/03/16 03:00 | 10/03/16 05:30 | [12 empty] | POOH FROM 243M TO SURFACE. L/D JAR, NMDC & ST.STAB. (HOLE CONDITION GOOD). RETRIEVED EMS TOOL. |  |  |  |  | No
z | z | z |  | 10/03/16 05:30 | 10/03/16 06:30 | [12 empty] | R/U WFD TRS EQUIPMENT. CHANGED TDS LINKS. |  |  |  |  | No
z | z | z |  | 10/03/16 06:30 | 10/03/16 07:00 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 10/03/16 07:00 | 10/03/16 15:00 | [12 empty] | P/U & M/U 20" CSG SHOE TRACK (JTS ALREADY THREADED WITH FLOAT SHOE AND FLOAT COLLAR). RIH 20" CSG TO BOTTOM. M/U CIRCULATING HEAD & CONVERTED AUTOFILL FLOATS TO NRV BY APPLYING 550PSI PRESSURE. WASHED DOWN LAST CSG JOINT. | Productive |  |  |  | Yes
z | z | z |  | 10/03/16 15:00 | 10/03/16 17:00 | [12 empty] | CIRCULATION TO CONDITION MUD. |  |  |  |  | No
z | z | z |  | 10/03/16 17:00 | 10/03/16 20:30 | [12 empty] | RIH STINGER ON 5" DPS. STAB IN STINGER WITH 15 KLBS. |  |  |  |  | No
z | z | z |  | 10/03/16 20:30 | 10/03/16 21:30 | [12 empty] | R/U CEMENTING LINES AND CIRCULATING HEAD. | Productive |  |  |  | No
z | z | z |  | 10/03/16 21:30 | 10/03/16 23:30 | [12 empty] | CIRCULATION TO CONDITION MUD. STINGER SEALS - OK. MEANWHILE PREPARED MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 10/03/16 23:30 | 10/04/16 00:00 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 10/04/16 00:00 | 10/04/16 00:15 | [12 empty] | FLUSHED CEMENT LINES AND PRESSURE TESTED AT 3000 PSI - OK. | Productive |  |  |  | No
z | z | z |  | 10/04/16 00:15 | 10/04/16 03:15 | [12 empty] | PUMPED 100 BBL SPACER OF 11.5 PPG WITH RIG PUMP. SWITCHED TO CEMENTING UNIT & PUMPED 504 BBL FLY MIXED LEAD SLURRY OF 13.5 PPG FOLLOWED BY 197 BBL FLY MIXED TAIL SLURRY OF 15.8 PPG. DISPLACED CEMENT WITH 21 BBL MIX FLUID. NO BACK FLOW OBSERVERD, FLOATS HOLD. STING OUT AND FLUSHED LINES WITH 2 BBL OF MIX FLUID. WHILE PUMPING RECEIVED 100 BBL SPACER, 92 BBL CONTAMINATION & 78 BBL NEAT CEMENT AT SURFACE (TOTAL 270 BBL VOLUME DUMPED). | Productive |  |  |  | No
z | z | z |  | 10/04/16 03:15 | 10/04/16 05:30 | [12 empty] | POOH STINGER STRING TO SURFACE. |  |  |  |  | No
z | z | z |  | 10/04/16 05:30 | 10/04/16 06:00 | [12 empty] | WAIT ON CEMENT (WOC). |  |  |  |  | No
z | z | z |  | 10/04/16 00:00 | 10/04/16 00:15 | [12 empty] | FLUSHED CEMENT LINES AND PRESSURE TESTED AT 3000 PSI - OK. | Productive |  |  |  | No
z | z | z |  | 10/04/16 00:15 | 10/04/16 03:15 | [12 empty] | PUMPED 100 BBL SPACER OF 11.5 PPG WITH RIG PUMP. SWITCHED TO CEMENTING UNIT & PUMPED 504 BBL FLY MIXED LEAD SLURRY OF 13.5 PPG FOLLOWED BY 197 BBL FLY MIXED TAIL SLURRY OF 15.8 PPG. DISPLACED CEMENT WITH 21 BBL MIX FLUID. NO BACK FLOW OBSERVERD, FLOATS HOLD. STING OUT AND FLUSHED LINES WITH 2 BBL OF MIX FLUID. WHILE PUMPING RECEIVED 100 BBL SPACER, 92 BBL CONTAMINATION & 78 BBL NEAT CEMENT AT SURFACE (TOTAL 270 BBL VOLUME DUMPED). | Productive |  |  |  | No
z | z | z |  | 10/04/16 03:15 | 10/04/16 05:30 | [12 empty] | POOH STINGER STRING TO SURFACE. |  |  |  |  | No
z | z | z |  | 10/04/16 05:30 | 10/04/16 13:00 | [12 empty] | WAIT ON CEMENT (WOC). MEANWHILE MADE ARRANGEMENTS FOR N/D DIVERTER ASSY. |  |  |  |  | No
z | z | z |  | 10/04/16 13:00 | 10/04/16 14:30 | [12 empty] | CUT 30" CONDUCTOR & 20" CASING. |  |  |  |  | No
z | z | z |  | 10/04/16 14:30 | 10/04/16 15:30 | [12 empty] | N/D DIVERTER ASSY & FLOW RISER. |  |  |  |  | No
z | z | z |  | 10/04/16 15:30 | 10/04/16 17:00 | [12 empty] | FINAL CUT 20" CASING. |  |  |  |  | Yes
z | z | z |  | 10/04/16 17:00 | 10/04/16 21:30 | [12 empty] | WELDED 21-1/4"-5K CASING HEAD HOUSING (CHH). |  |  |  |  | No
z | z | z |  | 10/04/16 21:30 | 10/05/16 00:00 | [12 empty] | WAIT ON COOLING OF WELLHEAD WELDING. |  |  |  |  | No
z | z | z |  | 10/05/16 00:00 | 10/05/16 04:00 | [12 empty] | WAIT ON COOLING OF WELLHEAD WELDING. |  |  |  |  | No
z | z | z |  | 10/05/16 04:00 | 10/05/16 04:30 | [12 empty] | PRESSURE TESTED CHH WELD AT 325 PSI - OK. | Productive |  |  |  | No
z | z | z |  | 10/05/16 04:30 | 10/05/16 06:00 | [12 empty] | N/U BOP IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/05/16 00:00 | 10/05/16 04:00 | [12 empty] | WAIT ON COOLING OF WELLHEAD WELDING. |  |  |  |  | No
z | z | z |  | 10/05/16 04:00 | 10/05/16 04:30 | [12 empty] | PRESSURE TESTED CHH WELD AT 325 PSI - OK. | Productive |  |  |  | No
z | z | z |  | 10/05/16 04:30 | 10/05/16 09:00 | [12 empty] | N/U BOP & FLOW RISER. |  |  |  |  | No
z | z | z |  | 10/05/16 09:00 | 10/05/16 12:00 | [12 empty] | M/U TEST PLUG ASSY AND P/T SPACER SPOOL/MUD CROSS FLANGES, CHOKE & KILL LINES HCRS/MANUAL VALVES, LOWER & UPPER IBOP, SAFETY VALVE, STANDPIPE MANIFOLD AT 300 PSI LOW & 2000 PSI HIGH. P/T CHOKE MANIFOLD AT 5000 PSI. |  |  |  |  | No
z | z | z |  | 10/05/16 12:00 | 10/05/16 12:30 | [12 empty] | M/U COMBINATION TOOL & INSTALLED WEAR BUSHING. |  |  |  |  | No
z | z | z |  | 10/05/16 12:30 | 10/05/16 14:15 | [12 empty] | L/D 2 X 11" DC, 3 X 9" DC & 26" ST. STAB. |  |  |  |  | No
z | z | z |  | 10/05/16 14:15 | 10/05/16 20:00 | [12 empty] | P/U & M/U NEW 17-1/2" PDC BIT, 9-5/8" MUD MOTOR & MWD. SHALLOW TESTED MOTOR & MWD TOOLS. RESUMED RIH DOWN TO 194M. |  |  |  |  | Yes
z | z | z |  | 10/05/16 20:00 | 10/05/16 21:15 | [12 empty] | CONTINUED RIH ON 5" DP FROM 194M TO 370M. WASHED DOWN LAST STAND AND TAGGED FLOAT COLLAR AT 386M. |  |  |  |  | No
z | z | z |  | 10/05/16 21:15 | 10/06/16 00:00 |  |  | 194 | 392 | [8 empty] | DRILLED FLOAT COLLAR AT 386M & SHOE TRACK CEMENT DOWN TO 392M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/06/16 00:00 | 10/06/16 03:30 |  |  |  | 392 | [8 empty] | CONTINUED DRILLING CEMENT AND FLOAT SHOE & 2 METERS INTO FORMATION. | Productive |  |  |  | No
z | z | z |  | 10/06/16 03:30 | 10/06/16 04:00 | [12 empty] | CIRCULATED FOR BOTTOM UP. | Productive |  |  |  | No
z | z | z |  | 10/06/16 04:00 | 10/06/16 05:45 | [12 empty] | PUMPED 50 BBL BAROLIFT HI-VIS PILL & DISPLACED KCL POLYMER MUD WITH HYDRO GUARD MUD OF 1.15 SG & HOMOGENISED. | Productive |  |  |  | No
z | z | z |  | 10/06/16 05:45 | 10/06/16 06:00 | [12 empty] | R/U CEMENT UNIT FOR FIT IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/06/16 00:00 | 10/06/16 01:30 |  |  |  | 396 | [8 empty] | CONTINUED DRILLING CEMENT DOWN TO 396M. | Productive |  |  |  | No
z | z | z |  | 10/06/16 01:30 | 10/06/16 01:45 | [12 empty] | P/T 20" CSG WITH RIG PUMP AT 1000 PSI - OK. | Productive |  |  |  | No
z | z | z |  | 10/06/16 01:45 | 10/06/16 03:30 |  |  |  | 396 | [8 empty] | RESUMED DRILLING CEMENT AND FLOAT SHOE & 2 METERS INTO FORMATION. | Productive |  |  |  | No
z | z | z |  | 10/06/16 03:30 | 10/06/16 04:00 | [12 empty] | CIRCULATED FOR BOTTOM UP. | Productive |  |  |  | No
z | z | z |  | 10/06/16 04:00 | 10/06/16 05:45 | [12 empty] | PUMPED 50 BBL BAROLIFT HI-VIS PILL & DISPLACED KCL POLYMER MUD WITH HYDRO GUARD MUD OF 1.15 SG & HOMOGENISED. | Productive |  |  |  | No
z | z | z |  | 10/06/16 05:45 | 10/06/16 06:00 | [12 empty] | R/U CEMENT UNIT FOR FIT. |  |  |  |  | No
z | z | z |  | 10/06/16 06:00 | 10/06/16 06:15 | [12 empty] | P/T CEMENT LINES AT 2000 PSI. |  |  |  |  | Yes
z | z | z |  | 10/06/16 06:15 | 10/06/16 06:45 | [12 empty] | CONDUCTED FIT AT 200 PSI SURFACE PRESSURE WITH 1.15 SG MUD (EMW = 1.5 SG). |  |  |  |  | No
z | z | z | 85.5 | 10/06/16 06:45 | 10/07/16 00:00 |  |  | 403 | 537 | [8 empty] | RESUMED DRILLING 17 1/2" HOLE FROM 403 M TO 537M. WASHED UP & DOWN AT EACH CONNECTION AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/07/16 00:00 | 10/07/16 01:00 |  |  | 537 | 540 | [8 empty] | CONTINUED DRILLING FROM 537M TO 540M. WASHED UP & DOWN AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/07/16 01:00 | 10/07/16 01:45 | [12 empty] | CIRCULATED OUT 30 BBL HI-VIS PILL. FLOW CHECKED FOR 10 MIN - OK. | Productive |  |  |  | No
z | z | z |  | 10/07/16 01:45 | 10/07/16 02:45 | [12 empty] | CONDUCTED WIPER TRIP FROM 540M TO 397M INSIDE 20" CSG SHOE. OBSERVED 10-15 KLBS OVERPULL, PUMPED OUT FROM 518M TO 482M. RIH FROM 397M TO BOTTOM. WASHED DOWN LAST STAND. HOLE CONDITION GOOD. | Productive |  |  |  | No
z | z | z |  | 10/07/16 02:45 | 10/07/16 03:30 |  |  | 540 | 547 | [8 empty] | RESUMED DRILLING FROM 540M TO 547M. | Productive |  |  |  | No
z | z | z |  | 10/07/16 03:30 | 10/07/16 06:00 | [12 empty] | OBSERVED 5% GASES. PUMP PRESSURE DECREASED 100 PSI. SHUT IN THE WELL. RECORDED 3 BBL PIT GAIN AND 60 PSI CSG PRESSURE. STARTED CIRCULATION THROUGH POORBOY DEGASER. MAX 10% GASES RECORDED. MAX CUT WEIGHT IS 1.13 SG DURING CIRCULATION. INCREASING MW 1.17 SG IS IN PROGRESS, WHILE CIRCULATING THROUGH POORBOY DEGASER. | Productive |  |  |  | No
z | z | z |  | 10/07/16 00:00 | 10/07/16 01:00 |  |  | 537 | 540 | [8 empty] | CONTINUED DRILLING FROM 537M TO 540M. WASHED UP & DOWN AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/07/16 01:00 | 10/07/16 01:45 | [12 empty] | CIRCULATED OUT 30 BBL HI-VIS PILL. FLOW CHECKED FOR 10 MIN - OK. | Productive |  |  |  | No
z | z | z |  | 10/07/16 01:45 | 10/07/16 02:45 | [12 empty] | CONDUCTED WIPER TRIP FROM 540M TO 397M INSIDE 20" CSG SHOE. OBSERVED 10-15 KLBS OVERPULL, PUMPED OUT FROM 518M TO 482M. RIH FROM 397M TO BOTTOM. WASHED DOWN LAST STAND. HOLE CONDITION GOOD. | Productive |  |  |  | No
z | z | z |  | 10/07/16 02:45 | 10/07/16 03:30 |  |  | 540 | 547 | [8 empty] | RESUMED DRILLING FROM 540M TO 547M. | Productive |  |  |  | No
z | z | z |  | 10/07/16 03:30 | 10/07/16 08:00 | [12 empty] | OBSERVED WELL FLOWING. SHUT IN THE WELL, RECORDED SICP = 60 PSI ; SIDPP = 0 PSI, STARTED CIRCULATION THROUGH POORBOY DEGASSER. MAX 18% GASES RECORDED. MAX CUT WEIGHT IS 1.13 SG DURING CIRCULATION. INCREASED MW 1.20 SG, WHILE CIRCULATING THROUGH POORBOY DEGASSER & THEN DIRECT CIRCULATED TO HOMOGENISE MUD. | Productive |  |  |  | No
z | z | z |  | 10/07/16 08:00 | 10/07/16 10:00 | [12 empty] | FLOW CHECKED, OBSERVED WELL FLOWING. SHUT IN THE WELL. RECORDED SICP = 70 PSI ; SIDPP = 0 PSI. MEANWHILE INCREASED MW TO 1.25 SG. |  |  |  |  | No
z | z | z |  | 10/07/16 10:00 | 10/07/16 14:00 | [12 empty] | CIRCULATED THROUGH POORBOY DEGASSER & THEN DIRECT CIRCULATED TO HOMOGENISE THE MUD (MWIN = 1.25 SG ; MWOUT = 1.25 SG). FLOW CHECKED, WELL STATIC. | Productive |  |  |  | Yes
z | z | z |  | 10/07/16 14:00 | 10/07/16 22:30 |  |  | 547 | 598 | [8 empty] | RESUMED DRILLING FROM 547M TO 598M. WASHED UP & DOWN AT CONNECTIONS & TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/07/16 22:30 | 10/07/16 23:45 | [12 empty] | PUMPED 50 BBL BAROLIFT HI-VIS PILL & CIRCULATED OUT. CONTINUED CIRCULATION TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 10/07/16 23:45 | 10/08/16 00:00 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/08/16 00:00 | 10/08/16 00:45 | [12 empty] | POOH FROM 598M TO 396M INSIDE 20"CSG SHOE. OBSERVED TIGHT SPOTS AT 540M, 508M, 482M, 471M, 440M & 422M. (CLEARED THE SAME WITH RECIPROCATION & WASHED UP FROM 498M TO 486M & 422M TO 408M. OBSERVED MAX OVERPULL 15-20 KLBS) |  |  |  |  | No
z | z | z |  | 10/08/16 00:45 | 10/08/16 01:00 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/08/16 01:00 | 10/08/16 02:00 | [12 empty] | RESUMED POOH FROM 396M TO 194M AT THE TOP OF BHA. |  |  |  |  | No
z | z | z |  | 10/08/16 02:00 | 10/08/16 02:15 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/08/16 02:15 | 10/08/16 04:30 | [12 empty] | POOH FROM 194M TO SURFACE. L/D 1 X 5" HWDP STD (FOR INSPECTION), JAR, ST. STAB & BIT. | Non Productive |  |  |  | No
z | z | z |  | 10/08/16 04:30 | 10/08/16 06:00 | [12 empty] | ADJUSTED MOTOR BEND AT 1.5 DEG. P/U & M/U NEW 17 1/2" TC BIT, 14 3/4" ST. STAB & RIH TO 21M. INSTALLING MWD TOOL IN HOC IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/08/16 00:00 | 10/08/16 00:45 | [12 empty] | POOH FROM 598M TO 396M INSIDE 20"CSG SHOE. OBSERVED TIGHT SPOTS AT 540M, 508M, 482M, 471M, 440M & 422M. (CLEARED THE SAME WITH RECIPROCATION & WASHED UP FROM 498M TO 486M & 422M TO 408M. OBSERVED MAX OVERPULL 15-20 KLBS) |  |  |  |  | No
z | z | z |  | 10/08/16 00:45 | 10/08/16 01:00 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/08/16 01:00 | 10/08/16 02:00 | [12 empty] | RESUMED POOH FROM 396M TO 194M AT THE TOP OF BHA. |  |  |  |  | No
z | z | z |  | 10/08/16 02:00 | 10/08/16 02:15 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/08/16 02:15 | 10/08/16 04:30 | [12 empty] | POOH FROM 194M TO SURFACE. L/D 1 X 5" HWDP STD (FOR INSPECTION), JAR, ST. STAB & BIT. | Non Productive |  |  |  | No
z | z | z |  | 10/08/16 04:30 | 10/08/16 08:15 | [12 empty] | ADJUSTED MOTOR BEND AT 1.5 DEG. P/U & M/U NEW 17 1/2" TC BIT, 14 3/4" ST. STAB & RIH TO 21M. SHALLOW TESTED MUD MOTOR & MWD TOOL. RESUMED RIH FROM 21M TO 193M AT THE TOP OF BHA. |  |  |  |  | No
z | z | z |  | 10/08/16 08:15 | 10/08/16 10:00 | [12 empty] | RIH FROM 193M TO 598M. WASHED DOWN LAST STAND. |  |  |  |  | Yes
z | z | z |  | 10/08/16 10:00 | 10/08/16 11:00 | [12 empty] | CIRCULATED FOR BOTTOM UP. RECORDED 5% GASES. | Productive |  |  |  | No
z | z | z |  | 10/08/16 11:00 | 10/08/16 12:30 |  |  | 598 | 602 | [8 empty] | RESUMED DRILLING FROM 598M TO 602M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/08/16 12:30 | 10/08/16 13:45 |  |  | 602 | 604 | [8 empty] | DRILLED FROM 602M TO 604M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/08/16 13:45 | 10/08/16 14:00 | [12 empty] | FLOW CHECKED, OBSERVED WELL FLOWING (15 BBL PIT GAIN). |  |  |  |  | No
z | z | z |  | 10/08/16 14:00 | 10/08/16 15:30 | [12 empty] | SHUT IN THE WELL, RECORDED SICP = 30 PSI ; SIDPP = 0 PSI. CIRCULATED THROUGH POOR BOY DEGASSER. RECORDED MAX 20% GASES. (OPENED WELL & OBSERVED - WELL STATIC). | Productive |  |  |  | No
z | z | z |  | 10/08/16 15:30 | 10/08/16 16:00 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 10/08/16 16:00 | 10/08/16 17:30 |  |  | 604 | 607 | [8 empty] | RESUMED DRILLING FROM 604M TO 607M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/08/16 17:30 | 10/09/16 00:00 |  |  | 607 | 626 | [8 empty] | DRILLED FROM 607M TO 626M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 00:00 | 10/09/16 00:30 | [12 empty] | WASHED UP & DOWN AND RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/09/16 00:30 | 10/09/16 02:00 |  |  | 626 | 630 | [8 empty] | CONTINUED DRILLING FROM 626M TO 630M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 02:00 | 10/09/16 06:00 |  |  | 630 | 636 | [8 empty] | DRILLED FROM 630M TO 636M IN SLIDE MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/09/16 00:00 | 10/09/16 00:30 | [12 empty] | WASHED UP & DOWN AND RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/09/16 00:30 | 10/09/16 02:00 |  |  | 626 | 630 | [8 empty] | CONTINUED DRILLING FROM 626M TO 630M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 02:00 | 10/09/16 06:45 |  |  | 630 | 637 | [8 empty] | DRILLED FROM 630M TO 637M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 06:45 | 10/09/16 09:45 |  |  | 637 | 647 | [8 empty] | DRILLED FROM 637M TO 647M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 09:45 | 10/09/16 12:00 |  |  | 647 | 652 | [8 empty] | DRILLED FROM 647M TO 652M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 12:00 | 10/09/16 14:00 |  |  | 652 | 659 | [8 empty] | DRILLED FROM 652M TO 659M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/09/16 14:00 | 10/09/16 18:00 |  |  | 659 | 666 | [8 empty] | DRILLED FROM 659M TO 666M IN SLIDE MODE. | Productive |  |  |  | Yes
z | z | z |  | 10/09/16 18:00 | 10/09/16 21:45 |  |  | 666 | 675 | [8 empty] | DRILLED FROM 666M TO 675M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/09/16 21:45 | 10/10/16 00:00 |  |  | 675 | 678 | [8 empty] | DRILLED FROM 675M TO 678M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 00:00 | 10/10/16 03:15 |  |  | 678 | 682 | [8 empty] | DRILLED FROM 678M TO 682M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 03:15 | 10/10/16 06:00 |  |  | 682 | 688 | [8 empty] | DRILLED FROM 682M TO 688M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/10/16 00:00 | 10/10/16 03:15 |  |  | 678 | 682 | [8 empty] | DRILLED FROM 678M TO 682M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 03:15 | 10/10/16 06:30 |  |  | 682 | 689 | [8 empty] | DRILLED FROM 682M TO 689M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/10/16 06:30 | 10/10/16 11:30 |  |  | 689 | 696 | [8 empty] | DRILLED FROM 689M TO 696M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 11:30 | 10/10/16 16:00 |  |  | 696 | 704 | [8 empty] | DRILLED FROM 696M TO 704M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 16:00 | 10/10/16 20:30 |  |  | 704 | 710 | [8 empty] | DRILLED FROM 704M TO 710M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/10/16 20:30 | 10/11/16 00:00 |  |  | 710 | 717 | [8 empty] | DRILLED FROM 710M TO 717M IN ROTARY MODE. RECODED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/11/16 00:00 | 10/11/16 03:15 |  |  | 717 | 721 | [8 empty] | DRILLED FROM 717M TO 721M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/11/16 03:15 | 10/11/16 06:00 |  |  | 721 | 732 | [8 empty] | DRILLED HOEL FROM 721M TO 732M IN ROTARY MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z | 85.5 | 10/11/16 00:00 | 10/11/16 03:15 |  |  | 717 | 721 | [8 empty] | DRILLED 17 1/2" HOLE FROM 717M TO 721M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/11/16 03:15 | 10/11/16 08:45 |  |  | 721 | 740 | [8 empty] | DRILLED FROM 721M TO 740M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/11/16 08:45 | 10/11/16 09:45 | [12 empty] | CIRCULATED BOTTOM UP FOR SAMPLE. | Productive |  |  |  | No
z | z | z |  | 10/11/16 09:45 | 10/11/16 11:45 |  |  | 740 | 744 | [8 empty] | RESUMED DRILLING FROM 740M TO 744M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/11/16 11:45 | 10/11/16 13:00 | [12 empty] | PUMPED 30 BBL HI-VIS & CIRCULATED TILL SHAKERS CLEAN PRIOR POOH. FLOW CHECK FOR 10 MIN - OK. | Productive |  |  |  | No
z | z | z |  | 10/11/16 13:00 | 10/11/16 15:15 | [12 empty] | POOH FROM 744M TO 400M INSIDE CSG SHOE. OBSERVED TIGHT SPOT AT 650M, 623M, 612M. CLEARED THE SAME WITH PUMP OUT. BACK REAMED FROM 568M TO 400M. | Productive |  |  |  | No
z | z | z |  | 10/11/16 15:15 | 10/11/16 15:30 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | Yes
z | z | z |  | 10/11/16 15:30 | 10/11/16 16:45 |  |  | 400 | 193 | [8 empty] | POOH FROM 400M TO 193M AT TOP OF BHA. (CONDUCTED KICK DRILL) | Productive |  |  |  | No
z | z | z |  | 10/11/16 16:45 | 10/11/16 20:15 | [12 empty] | POOH FROM 193M TO SURFACE. L/D 2X5" HWDP SINGLE, 4X8" DC, JAR (FOR INSPECTION), RETRIEVED MWD TOOLS, 17 1/2" BIT & 9 1/2" MUD MOTOR. | Non Productive |  |  |  | No
z | z | z |  | 10/11/16 20:15 | 10/11/16 23:15 | [12 empty] | P/U & M/U NEW 17 1/2" TC BIT, 9 1/2" MOTOR. SET 1.5 DEG BEND. INSTALLED MWD TOOLS IN HOC & RIH DOWN TO 21M. SHALLOW TESTED MOTOR & MWD TOOLS - OK. |  |  |  |  | No
z | z | z |  | 10/11/16 23:15 | 10/12/16 00:00 | [12 empty] | RESUMED RIH FROM 21M TO 105M. P/U NEW JAR & 4X8" DC FROM CATWALK SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 10/12/16 00:00 | 10/12/16 00:30 | [12 empty] | CONTINUED RIH FROM 105M TO 194M AT TOP OF BHA. |  |  |  |  | No
z | z | z |  | 10/12/16 00:30 | 10/12/16 03:00 | [12 empty] | RIH FROM 194M TO 744M. WASHED DOWN LAST STAND. HOLE CONDITION GOOD. |  |  |  |  | No
z | z | z |  | 10/12/16 03:00 | 10/12/16 04:00 |  |  | 744 | 745 | [8 empty] | BROKE IN THE BIT AND RESUME DRILLING FROM 744M TO 745M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/12/16 04:00 | 10/12/16 06:00 |  |  | 745 | 748 | [8 empty] | DRILLED FROM 745M TO 748M IN SLIDE MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/12/16 00:00 | 10/12/16 00:30 | [12 empty] | CONTINUED RIH FROM 105M TO 194M AT TOP OF BHA. |  |  |  |  | No
z | z | z |  | 10/12/16 00:30 | 10/12/16 03:00 | [12 empty] | RIH FROM 194M TO 744M. WASHED DOWN LAST STAND. |  |  |  |  | No
z | z | z |  | 10/12/16 03:00 | 10/12/16 04:00 |  |  | 744 | 745 | [8 empty] | BROKE IN THE BIT AND RESUME DRILLING FROM 744M TO 745M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/12/16 04:00 | 10/12/16 09:00 |  |  | 745 | 753 | [8 empty] | DRILLED FROM 745M TO 753M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/12/16 09:00 | 10/12/16 11:30 |  |  | 753 | 760 | [8 empty] | DRILLED FROM 753M TO 760M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/12/16 11:30 | 10/12/16 14:00 |  |  | 760 | 768 | [8 empty] | DRILLED FROM 760M TO 768M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/12/16 14:00 | 10/13/16 00:00 |  |  | 768 | 791 | [8 empty] | DRILLED FROM 768M TO 791M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | Yes
z | z | z |  | 10/13/16 00:00 | 10/13/16 03:00 |  |  | 791 | 796 | [8 empty] | DRILLED FROM 791M TO 796M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 03:00 | 10/13/16 05:00 |  |  | 796 | 799 | [8 empty] | DRILLED FROM 796M TO 799M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 05:00 | 10/13/16 05:30 | [12 empty] | REAMED/BACK REAMED TWICE AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/13/16 05:30 | 10/13/16 06:00 |  |  | 799 | 800 | [8 empty] | RESUMED DRILLING FROM 799M TO 800M IN ROTARY MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/13/16 00:00 | 10/13/16 03:00 |  |  | 791 | 796 | [8 empty] | DRILLED FROM 791M TO 796M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 03:00 | 10/13/16 05:00 |  |  | 796 | 799 | [8 empty] | DRILLED FROM 796M TO 799M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 05:00 | 10/13/16 05:30 | [12 empty] | REAMED/BACK REAMED TWICE AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/13/16 05:30 | 10/13/16 08:00 |  |  | 799 | 804 | [8 empty] | RESUMED DRILLING FROM 799M TO 804M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 08:00 | 10/13/16 11:30 |  |  | 804 | 809 | [8 empty] | DRILLED FROM 804M TO 809M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 11:30 | 10/13/16 15:00 |  |  | 809 | 817 | [8 empty] | DRILLED FROM 809M TO 817M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 15:00 | 10/13/16 18:30 |  |  | 817 | 822 | [8 empty] | DRILLED FROM 817M TO 822M IN SLIDE MODE. | Productive |  |  |  | Yes
z | z | z |  | 10/13/16 18:30 | 10/13/16 22:30 |  |  | 822 | 828 | [8 empty] | DRILLED FROM 822M TO 828M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/13/16 22:30 | 10/13/16 23:00 | [12 empty] | WASHED UP / REAMED DOWN TWICE AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/13/16 23:00 | 10/14/16 00:00 |  |  | 828 | 830 | [8 empty] | DRILLED FROM 828M TO 830M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 00:00 | 10/14/16 00:45 |  |  | 830 | 832 | [8 empty] | CONTINUED DRILLING FROM 830M TO 832M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 00:45 | 10/14/16 05:15 |  |  | 832 | 837.5 | [8 empty] | DRILLED FROM 832M TO 837.5M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 05:15 | 10/14/16 06:00 |  |  | 837.5 | 839 | [8 empty] | DRILLED FROM 837.5M TO 839M IN ROTARY MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/14/16 00:00 | 10/14/16 00:45 |  |  | 830 | 832 | [8 empty] | CONTINUED DRILLING FROM 830M TO 832M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 00:45 | 10/14/16 05:15 |  |  | 832 | 837.5 | [8 empty] | DRILLED FROM 832M TO 837.5M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 05:15 | 10/14/16 18:30 |  |  | 837.5 | 865 | [8 empty] | DRILLED FROM 837.5M TO 865M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/14/16 18:30 | 10/14/16 21:30 |  |  | 865 | 869 | [8 empty] | DRILLED FROM 865M TO 869M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/14/16 21:30 | 10/15/16 00:00 |  |  | 869 | 874 | [8 empty] | DRILLED FROM 869M TO 874M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/15/16 00:00 | 10/15/16 06:00 |  |  | 874 | 886 | [8 empty] | CONTINUED DRILLING FROM 874M TO 886M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/15/16 00:00 | 10/15/16 08:15 |  |  | 874 | 890 | [8 empty] | DRILLED FROM 874M TO 890M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/15/16 08:15 | 10/15/16 12:00 |  |  | 890 | 894 | [8 empty] | DRILLED FROM 890M TO 894M IN SLIDE MODE | Productive |  |  |  | No
z | z | z |  | 10/15/16 12:00 | 10/15/16 15:30 |  |  | 894 | 900 | [8 empty] | DRILLED FROM 894M TO 900M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/15/16 15:30 | 10/15/16 16:30 | [12 empty] | CIRCULATED TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 10/15/16 16:30 | 10/15/16 16:45 | [12 empty] | FLOW CHECKED PRIOR POOH, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/15/16 16:45 | 10/15/16 19:45 | [12 empty] | POOH FROM 900M TO 194M AT THE TOP OF BHA. FLOW CHECKED INSIDE CSG SHOE & AT TOP OF BHA FOR 10 MIN EACH, OK. |  |  |  |  | No
z | z | z |  | 10/15/16 19:45 | 10/15/16 21:15 | [12 empty] | POOH FROM 194M TO SURFACE. L/D 17 1/2" TC BIT. |  |  |  |  | Yes
z | z | z |  | 10/15/16 21:15 | 10/16/16 00:00 | [12 empty] | P/U & M/U NEW 17 1/2" TC BIT WITH SAME MOTOR (1.5 DEG BEND) & HOC (TOOLS INSIDE) & RIH DOWN TO 49M. SHALLOW TESTED MOTOR & MWD TOOLS, OK. RESUMED RIH WITH SAME BHA DOWN TO 193M. P/U 3 X 5" HWDP SINGLE BY SINGLE FROM CATWALK. |  |  |  |  | No
z | z | z |  | 10/16/16 00:00 | 10/16/16 01:00 | [12 empty] | CONTINUED RIH FROM 193M TO 435M. |  |  |  |  | No
z | z | z |  | 10/16/16 01:00 | 10/16/16 02:15 | [12 empty] | OBSERVED COMPRESSION. WASHED DOWN FROM 435M TO 568M. |  |  |  |  | No
z | z | z |  | 10/16/16 02:15 | 10/16/16 03:45 | [12 empty] | RESUMED RIH FROM 568M TO 873M. |  |  |  |  | No
z | z | z |  | 10/16/16 03:45 | 10/16/16 04:15 | [12 empty] | REAMED DOWN LAST STAND DOWN TO BOTTOM AT 900M. | Productive |  |  |  | No
z | z | z |  | 10/16/16 04:15 | 10/16/16 06:00 |  |  | 900 | 904 | [8 empty] | BREAK IN BIT & RESUMED DRILLING FROM 900M TO 904M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/16/16 00:00 | 10/16/16 01:00 | [12 empty] | CONTINUED RIH FROM 193M TO 435M. |  |  |  |  | No
z | z | z |  | 10/16/16 01:00 | 10/16/16 02:15 | [12 empty] | OBSERVED COMPRESSION. WASHED DOWN FROM 435M TO 568M. |  |  |  |  | No
z | z | z |  | 10/16/16 02:15 | 10/16/16 03:45 | [12 empty] | RESUMED RIH FROM 568M TO 873M. |  |  |  |  | No
z | z | z |  | 10/16/16 03:45 | 10/16/16 04:15 | [12 empty] | REAMED DOWN LAST STAND DOWN TO BOTTOM AT 900M. | Productive |  |  |  | No
z | z | z |  | 10/16/16 04:15 | 10/16/16 12:00 |  |  | 900 | 921 | [8 empty] | BREAK IN BIT & RESUMED DRILLING FROM 900M TO 921M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/16/16 12:00 | 10/16/16 13:00 |  |  | 921 | 923 | [8 empty] | DRILLED FROM 921M TO 923M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/16/16 13:00 | 10/16/16 19:30 |  |  | 923 | 941 | [8 empty] | DRILLED FROM 923M TO 941M IN ROTARY MODE. | Productive |  |  |  | Yes
z | z | z |  | 10/16/16 19:30 | 10/16/16 20:00 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 10/16/16 20:00 | 10/16/16 22:30 |  |  | 941 | 949 | [8 empty] | DRILLED FROM 941M TO 949M IN ROTARY MODE. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/16/16 22:30 | 10/17/16 00:00 |  |  | 949 | 951 | [8 empty] | DRILLED FROM 949M TO 951M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 00:00 | 10/17/16 00:30 |  |  | 951 | 952 | [8 empty] | CONTINUED DRILLING FROM 951M TO 952M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 00:30 | 10/17/16 06:00 |  |  | 952 | 971 | [8 empty] | DRILLED FROM 952M TO 971M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 00:00 | 10/17/16 00:30 |  |  | 951 | 952 | [8 empty] | CONTINUED DRILLING FROM 951M TO 952M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 00:30 | 10/17/16 06:30 |  |  | 952 | 973 | [8 empty] | DRILLED FROM 952M TO 973M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 06:30 | 10/17/16 07:45 | [12 empty] | REAMED / BACK REAMED TWICE AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/17/16 07:45 | 10/17/16 09:45 |  |  | 973 | 978 | [8 empty] | RESUMED DRILLING FROM 973M TO 978M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 09:45 | 10/17/16 11:30 |  |  | 978 | 981.5 | [8 empty] | DRILLED FROM 978M TO 981.5M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 11:30 | 10/17/16 17:45 |  |  | 981.5 | 1002 | [8 empty] | DRILLED FROM 981.5M TO 1002M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 17:45 | 10/17/16 19:00 | [12 empty] | REAMED / BACK REAMED TWICE AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | Yes
z | z | z |  | 10/17/16 19:00 | 10/17/16 21:15 |  |  | 1002 | 1008 | [8 empty] | RESUMED DRILLING FROM 1002M TO 1008M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 21:15 | 10/17/16 23:00 |  |  | 1008 | 1011 | [8 empty] | DRILLED FORM 1008M TO 1011M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z |  | 10/17/16 23:00 | 10/18/16 00:00 |  |  | 1011 | 1015 | [8 empty] | DRILLED FROM 1011M TO 1015M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 00:00 | 10/18/16 01:00 | [12 empty] | CONTINUED FROM 1015M TO 1017.5M IN ROTARY MODE. |  |  |  |  | No
z | z | z |  | 10/18/16 01:00 | 10/18/16 01:30 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 10/18/16 01:30 | 10/18/16 02:45 | [12 empty] | OBSERVED LEAKAGE IN GOOSE NECK HAMMER UNION. RECTIFIED THE SAME AND PRESSURE TESTED. | Productive |  |  |  | No
z | z | z |  | 10/18/16 02:45 | 10/18/16 06:00 |  |  | 1017.5 | 1024 | [8 empty] | RESUMED DRILLING FROM 1017.5M TO 1024M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 00:00 | 10/18/16 01:00 |  |  | 1015 | 1017.5 | [8 empty] | CONTINUED DRILLING FROM 1015M TO 1017.5M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 01:00 | 10/18/16 01:30 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 10/18/16 01:30 | 10/18/16 02:45 | [12 empty] | OBSERVED LEAKAGE IN GOOSE NECK HAMMER UNION. RECTIFIED THE SAME AND PRESSURE TESTED. | Productive |  |  |  | No
z | z | z |  | 10/18/16 02:45 | 10/18/16 08:45 |  |  | 1017.5 | 1031 | [8 empty] | RESUMED DRILLING FROM 1017.5M TO 1031M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 08:45 | 10/18/16 09:45 | [12 empty] | REAMED / BACK REAMED TWICE AT CONNECTION. REOCORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/18/16 09:45 | 10/18/16 12:15 |  |  | 1031 | 1037 | [8 empty] | RESUMED DRILLING FROM 1031M TO 1037M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 12:15 | 10/18/16 13:45 |  |  | 1037 | 1040 | [8 empty] | DRILLED FROM 1037M TO 1040M IN SLIDE MODE | Productive |  |  |  | Yes
z | z | z |  | 10/18/16 13:45 | 10/18/16 17:30 |  |  | 1040 | 1050 | [8 empty] | DRILLED FROM 1040M TO 1050M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/18/16 17:30 | 10/18/16 19:00 | [12 empty] | PUMPED HI-VIS AND CIRCULATED TILL SHAKERS CLEAN PRIOR TO WIPER TRIP. | Productive |  |  |  | No
z | z | z |  | 10/18/16 19:00 | 10/18/16 19:15 | [12 empty] | FLOW CHECKED, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/18/16 19:15 | 10/18/16 22:30 | [12 empty] | POOH FROM 1050M TO 1023M. BACK REAMED FROM 1023M TO 886M. | Productive |  |  |  | No
z | z | z |  | 10/18/16 22:30 | 10/18/16 23:00 | [12 empty] | REAMED / WASHED DOWN FROM 886M TO 945M. | Productive |  |  |  | No
z | z | z |  | 10/18/16 23:00 | 10/18/16 23:30 | [12 empty] | RIH FROM 945M TO 1039M. |  |  |  |  | No
z | z | z |  | 10/18/16 23:30 | 10/19/16 00:00 | [12 empty] | OBSERVED COMPRESSION. HARD REAMED FROM 1039M TO 1043M. | Productive |  |  |  | No
z | z | z |  | 10/19/16 00:00 | 10/19/16 01:00 | [12 empty] | CONTINUED HARD REAMING FROM 1043M TO 1050M. MEANWHILE INRCEASED MUD WEIGHT FROM 1.27 SG TO 1.32 SG. | Productive |  |  |  | No
z | z | z |  | 10/19/16 01:00 | 10/19/16 06:00 |  |  | 1050 | 1057 | [8 empty] | RESUMED DRILLILNG FROM 1050M TO 1057M IN ROTARY MODE & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/19/16 00:00 | 10/19/16 01:00 | [12 empty] | CONTINUED HARD REAMING FROM 1043M TO 1050M. MEANWHILE INRCEASED MUD WEIGHT FROM 1.27 SG TO 1.32 SG. | Productive |  |  |  | No
z | z | z |  | 10/19/16 01:00 | 10/19/16 23:30 |  |  | 1050 | 1075 | [8 empty] | RESUMED DRILLILNG FROM 1050M TO 1075M IN ROTARY MODE. REAMED / BACK REAMED TWICE AT CONNECTION. REOCORDED MWD SURVEY. INCREASED MUD WEIGHT TO 1.35 DURING DRILLING. CHECKED CONDITION OF HOLE FOUND HOLE TIGHT. | Productive |  |  |  | No
z | z | z |  | 10/19/16 23:30 | 10/20/16 00:00 | [12 empty] | CIRCULATED MEANWHILE INRCEASED MUD WEIGHT TO 1.40 SG IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/20/16 00:00 | 10/20/16 01:30 | [12 empty] | CONTINUED CIRCULATED TO CONDITION MUD MEANWHILE INRCEASED MUD WEIGHT TO 1.40 SG. | Productive |  |  |  | No
z | z | z |  | 10/20/16 01:30 | 10/20/16 01:45 | [12 empty] | FLOW CHECKED PRIOR POOH, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/20/16 01:45 | 10/20/16 03:30 | [12 empty] | POOH OBSERVED OVERPULL OF 5- 7 TONS, BACK REAMED FROM 1075M TO 1002M. | Productive |  |  |  | No
z | z | z |  | 10/20/16 03:30 | 10/20/16 04:30 | [12 empty] | POOH ON ELEVATOR FROM 1002M TO 886M. OBSERVED OVERPULL OF 3-5 TONS. |  |  |  |  | No
z | z | z |  | 10/20/16 04:30 | 10/20/16 06:00 | [12 empty] | PUMPED OUT FROM 886M TO 806M & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/20/16 00:00 | 10/20/16 01:30 | [12 empty] | CONTINUED CIRCULATED TO CONDITION MUD MEANWHILE INRCEASED MUD WEIGHT TO 1.40 SG. | Productive |  |  |  | No
z | z | z |  | 10/20/16 01:30 | 10/20/16 01:45 | [12 empty] | FLOW CHECKED PRIOR POOH, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/20/16 01:45 | 10/20/16 03:30 | [12 empty] | POOH OBSERVED OVERPULL OF 5- 7 TONS, BACK REAMED FROM 1075M TO 1002M. | Productive |  |  |  | No
z | z | z |  | 10/20/16 03:30 | 10/20/16 04:30 | [12 empty] | POOH ON ELEVATOR FROM 1002M TO 886M. OBSERVED OVERPULL OF 3-5 TONS. |  |  |  |  | No
z | z | z |  | 10/20/16 04:30 | 10/20/16 08:00 | [12 empty] | PUMPED OUT FROM 886M TO 684M. | Productive |  |  |  | No
z | z | z |  | 10/20/16 08:00 | 10/20/16 10:00 | [12 empty] | POOH ON ELEVATOR FROM 684M TO 193M. |  |  |  |  | No
z | z | z |  | 10/20/16 10:00 | 10/20/16 10:15 | [12 empty] | FLOW CHECKED INSIDE CASING SHOE, WELL STATIC. |  |  |  |  | Yes
z | z | z |  | 10/20/16 10:15 | 10/20/16 15:00 |  |  |  | 193 | [8 empty] | POOH FROM 193M TO SURFACE. L/D 17 1/2" TC BIT, DRILLING JAR AND MUD MOTOR. | Productive |  |  |  | No
z | z | z |  | 10/20/16 15:00 | 10/20/16 18:30 | [12 empty] | P/U & M/U NEW 17 1/2" PDC BIT WITH NEW MOTOR (1.5 DEG BEND) & HOC (TOOLS INSIDE) & RIH. SHALLOW TESTED MOTOR & MWD TOOLS, OK. RESUMED RIH WITH BHA DOWN TO 194M. P/U 2 x 6", 3 x 9" DC & 6 X 5" HWDP SINGLE BY SINGLE FROM CATWALK. DRIFFTED AND CLEANED EVERY SINGLE P/U FROM CATWALK. |  |  |  |  | No
z | z | z |  | 10/20/16 18:30 | 10/20/16 19:00 | [12 empty] | CONTINUE RIH 5" DP STANDS DOWN TO 396M. |  |  |  |  | No
z | z | z |  | 10/20/16 19:00 | 10/20/16 19:30 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 10/20/16 19:30 | 10/20/16 20:30 | [12 empty] | F/UP STRING OBSERVED HIGH SPP, TRIED TO RELEASE THE PRESSURE WITH DIFFERENT PARAMETERS NO SUCCESS. DECIDED TO POOH. |  |  |  |  | No
z | z | z |  | 10/20/16 20:30 | 10/20/16 21:00 | [12 empty] | POOH TO 193M. |  |  |  |  | No
z | z | z |  | 10/20/16 21:00 | 10/20/16 23:30 | [12 empty] | CONTINUE POOH BHA FROM 193M TO SURFACE. OBSERVED STRING STAB PARTIALLY BALLEED UP, BIT AND SLEEVE STAB 75% BALLED-UP. CHECKED BIT NOZZLES FOUND 4 NOZZLES PLUGGED WITH RUST AND SCALE CLEAN THE SAME. WAHSED MOTOR AND MWD WITH WATWER. | Non Productive |  |  |  | No
z | z | z |  | 10/20/16 23:30 | 10/21/16 00:00 | [12 empty] | M/U 17 1/2" PDC BIT WITH MOTOR FOR RIH. |  |  |  |  | No
z | z | z |  | 10/21/16 00:00 | 10/21/16 02:45 | [12 empty] | M/U 17 1/2" PDC BIT WITH MOTOR (1.5 DEG BEND) & HOC (TOOLS INSIDE) & RIH. SHALLOW TESTED MOTOR & MWD TOOLS, OK. RESUMED RIH WITH BHA DOWN TO 194M. BREAK CIRCULATION AT BHA. | Non Productive |  |  |  | No
z | z | z |  | 10/21/16 02:45 | 10/21/16 03:30 | [12 empty] | CONTINUE RIH DOWN TO 396M WHILE FILLING UP STRING AFTER EVERY 10 STANDS. |  |  |  |  | No
z | z | z |  | 10/21/16 03:30 | 10/21/16 04:00 | [12 empty] | RIH DOWN TO 441M. OBSERVED OBSTRUCTION. |  |  |  |  | No
z | z | z |  | 10/21/16 04:00 | 10/21/16 05:30 | [12 empty] | OBSERVED COMPRESSION OF 5 - 10 TONS, REAMED FROM 441M TO 598M. | Productive |  |  |  | No
z | z | z |  | 10/21/16 05:30 | 10/21/16 06:00 | [12 empty] | RIH FROM 598M TO 685M, RIH IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/21/16 00:00 | 10/21/16 02:45 | [12 empty] | M/U 17 1/2" PDC BIT WITH MOTOR (1.5 DEG BEND) & HOC (TOOLS INSIDE) & RIH. SHALLOW TESTED MOTOR & MWD TOOLS, OK. RESUMED RIH WITH BHA DOWN TO 194M. BREAK CIRCULATION AT BHA. | Non Productive |  |  |  | No
z | z | z |  | 10/21/16 02:45 | 10/21/16 03:30 | [12 empty] | CONTINUE RIH DOWN TO 396M WHILE FILLING UP STRING AFTER EVERY 10 STANDS. |  |  |  |  | No
z | z | z |  | 10/21/16 03:30 | 10/21/16 04:00 | [12 empty] | RIH DOWN TO 441M. OBSERVED OBSTRUCTION. |  |  |  |  | No
z | z | z |  | 10/21/16 04:00 | 10/21/16 05:30 | [12 empty] | OBSERVED COMPRESSION OF 5 - 10 TONS, REAMED FROM 441M TO 598M. | Productive |  |  |  | No
z | z | z |  | 10/21/16 05:30 | 10/21/16 07:45 | [12 empty] | RIH FROM 598M TO 1027M. |  |  |  |  | No
z | z | z |  | 10/21/16 07:45 | 10/21/16 15:45 | [12 empty] | HARD REAMED FROM 1027M TO 1075M. | Productive |  |  |  | No
z | z | z | 85.5 | 10/21/16 15:45 | 10/21/16 20:00 |  |  | 1075 | 1077.5 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1075M TO 1077.5M IN ROTARY MODE. TRIED DIFFERENT PARAMETERS TO INCREASE ROP NO SUCCESS. | Productive |  |  |  | Yes
z | z | z |  | 10/21/16 20:00 | 10/21/16 20:15 | [12 empty] | PUMPED DETERGENT PILL TO CLEAR THE SUSPECTED BALLED UP BIT. | Productive |  |  |  | No
z | z | z | 85.5 | 10/21/16 20:15 | 10/21/16 22:45 |  |  | 1077.5 | 1078.5 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1077.5M TO 1078.5M IN ROTARY MODE. TRIED DIFFERENT PARAMETERS TO INCREASE ROP NO SUCCESS. | Productive |  |  |  | No
z | z | z |  | 10/21/16 22:45 | 10/21/16 23:00 | [12 empty] | PUMPED DETERGENT PILL TO CLEAR THE SUSPECTED BALLED UP BIT. | Productive |  |  |  | No
z | z | z | 85.5 | 10/21/16 23:00 | 10/22/16 00:00 |  |  | 1078.5 | 1079 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1078.5M TO 1079M. TRIED DIFFERENT PARAMETERS TO INCREASE ROP NO SUCCESS. DECIDED TO POOH. | Productive |  |  |  | No
z | z | z |  | 10/22/16 00:00 | 10/22/16 01:15 | [12 empty] | STARTED POOH PUMPED OUT FROM 1079M TO 1031M. | Productive |  |  |  | No
z | z | z |  | 10/22/16 01:15 | 10/22/16 06:00 | [12 empty] | CONTINUE POOH TO 49M, WHILE POOH FLOW CHECKED AT BHA AND INSIDE CASING SHOE. |  |  |  |  | No
z | z | z |  | 10/22/16 00:00 | 10/22/16 01:15 | [12 empty] | STARTED POOH PUMPED OUT FROM 1079M TO 1031M. | Productive |  |  |  | No
z | z | z |  | 10/22/16 01:15 | 10/22/16 05:00 | [12 empty] | CONTINUE POOH TO 194M, WHILE POOH FLOW CHECKED INSIDE CASING SHOE. |  |  |  |  | No
z | z | z |  | 10/22/16 05:00 | 10/22/16 07:00 | [12 empty] | FLOW CHECKED AT BHA, CONTINUE POOH TO SURFACE. |  |  |  |  | No
z | z | z |  | 10/22/16 07:00 | 10/22/16 08:00 | [12 empty] | L/D BIT FOUND BIT AND SLEEVE STAB BALLED-UP, P/U AND M/U RR PDC BIT. | Non Productive |  |  |  | No
z | z | z |  | 10/22/16 08:00 | 10/22/16 09:30 | [12 empty] | RIH FROM SURFACE TO 194M. FUNCTION TESTED MOTOR AT SURFACE. |  |  |  |  | No
z | z | z |  | 10/22/16 09:30 | 10/22/16 14:00 | [12 empty] | CONTINUE RIH FROM 194M TO 1031M. |  |  |  |  | No
z | z | z |  | 10/22/16 14:00 | 10/22/16 15:30 | [12 empty] | WHILE RIH OBSERVED COMPRESSION. REAMED AND WASHED DOWN FROM 1031M TO 1079M. | Productive |  |  |  | Yes
z | z | z | 85.5 | 10/22/16 15:30 | 10/22/16 18:00 |  |  | 1079 | 1089 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1079M TO 1089M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/22/16 18:00 | 10/22/16 19:15 | [12 empty] | REAMED TWICE AT CONNECTION AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/22/16 19:15 | 10/22/16 19:45 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z | 85.5 | 10/22/16 19:45 | 10/22/16 21:15 |  |  | 1089 | 1094 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1089M TO 1094M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/22/16 21:15 | 10/22/16 23:15 |  |  | 1094 | 1099 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1094M TO 1099M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/22/16 23:15 | 10/23/16 00:00 |  |  | 1099 | 1108 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1099M TO 1108M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 00:00 | 10/23/16 01:45 |  |  | 1108 | 1113 | [8 empty] | CONTINUE DRILLING 17 1/2" HOLE FROM 1108M TO 1113M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 01:45 | 10/23/16 04:00 |  |  | 1113 | 1116 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1113M TO 1116M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 04:00 | 10/23/16 06:00 |  |  | 1116 | 1123 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1116M TO 1123M IN ROTARY MODE. CONDUCTED MWD SURVEY ON CONNECTION. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 00:00 | 10/23/16 01:45 |  |  | 1108 | 1113 | [8 empty] | CONTINUE DRILLING 17 1/2" HOLE FROM 1108M TO 1113M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 01:45 | 10/23/16 04:00 |  |  | 1113 | 1116 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1113M TO 1116M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 04:00 | 10/23/16 06:00 |  |  | 1116 | 1123 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1116M TO 1123M IN ROTARY MODE. CONDUCTED MWD SURVEY ON CONNECTION. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 06:00 | 10/23/16 07:45 |  |  | 1123 | 1127 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1123M TO 1127M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 07:45 | 10/23/16 12:15 |  |  | 1127 | 1153 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1127M TO 1153M IN ROTARY MODE. CONDUCTED MWD SURVEYS. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 12:15 | 10/23/16 13:45 |  |  | 1153 | 1156 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1153M TO 1156M IN SLIDE MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 13:45 | 10/23/16 16:30 |  |  | 1156 | 1176 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1156M TO 1176M IN ROTARY MODE. | Productive |  |  |  | Yes
z | z | z |  | 10/23/16 16:30 | 10/23/16 17:30 | [12 empty] | REAMED TWICE AT CONNECTION AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 17:30 | 10/23/16 21:45 |  |  | 1176 | 1205 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1176M TO 1205M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z |  | 10/23/16 21:45 | 10/23/16 22:30 | [12 empty] | REAMED TWICE AT CONNECTION AND TOOK MWD SURVEY. | Productive |  |  |  | No
z | z | z | 85.5 | 10/23/16 22:30 | 10/24/16 00:00 |  |  | 1205 | 1219 | [8 empty] | DRILLED 17 1/2" HOLE FROM 1205M TO 1219M IN ROTARY MODE. | Productive |  |  |  | No
z | z | z | 85.5 | 10/24/16 00:00 | 10/24/16 00:30 |  |  | 1219 | 1222 | [8 empty] | CONTINUE DRILLING 17 1/2" HOLE FROM 1219M TO 1222M IN ROTARY MODE (SECTION TD). | Productive |  |  |  | No
z | z | z |  | 10/24/16 00:30 | 10/24/16 03:30 | [12 empty] | PUMPED HI-VIS AND CIRCULATED MUD TILL SHAKER CLEAN. FLOW CHECKED FOUND WELL STATIC. | Productive |  |  |  | No
z | z | z |  | 10/24/16 03:30 | 10/24/16 06:00 | [12 empty] | POOH FROM 1222M TO 598M. |  |  |  |  | No
z | z | z | 85.5 | 10/24/16 00:00 | 10/24/16 00:30 |  |  | 1219 | 1222 | [8 empty] | CONTINUE DRILLING 17 1/2" HOLE FROM 1219M TO 1222M IN ROTARY MODE (SECTION TD). | Productive |  |  |  | No
z | z | z |  | 10/24/16 00:30 | 10/24/16 03:30 | [12 empty] | PUMPED HI-VIS AND CIRCULATED MUD TILL SHAKER CLEAN. FLOW CHECKED FOUND WELL STATIC. | Productive |  |  |  | No
z | z | z |  | 10/24/16 03:30 | 10/24/16 07:00 | [12 empty] | POOH FROM 1222M TO 396M (CASING SHOE). |  |  |  |  | No
z | z | z |  | 10/24/16 07:00 | 10/24/16 10:00 | [12 empty] | RIH FROM 396M TO 1155M. |  |  |  |  | No
z | z | z |  | 10/24/16 10:00 | 10/24/16 11:30 | [12 empty] | OBSERVED COMPRESSION AT 1120 M STARTED CIRCULATION AND CLEAR TIGHT SPOT DOWN TO BOTTOM. CIRCULATED AND HARD REAMED DOWN TO BOTTOM. | Productive |  |  |  | No
z | z | z |  | 10/24/16 11:30 | 10/24/16 14:15 | [12 empty] | PUMPED HI-VIS AND CIRCULATED TO CLEAN HOLE. PUMED AND CIRCULATED OUT TRACER. (DURING CIRCULATION INCREASED MUD WEIGHT TO 1.54 SG.) | Productive |  |  |  | No
z | z | z |  | 10/24/16 14:15 | 10/24/16 21:00 | [12 empty] | POOH FROM BOTTOM TO 194M WHILE POOH FLOW CHECKED AT CASING SHOE. |  |  |  |  | Yes
z | z | z |  | 10/24/16 21:00 | 10/24/16 22:45 | [12 empty] | CONTINUE POOH FROM 194M TO SURFACE. B/U BIT AND R/B MUD MOTOR WITH HOC. |  |  |  |  | No
z | z | z |  | 10/24/16 22:45 | 10/25/16 00:00 | [12 empty] | INSTALLED WEATHERFORD WIRELINE EQUIPMENT WITH SHOOTING NIPPLE AND PRESSURE TEST WIRELINE BOP @ 300 PSI OK. | Productive |  |  |  | No
z | z | z |  | 10/25/16 00:00 | 10/25/16 00:30 | [12 empty] | CONTINUE R/U WIRELINE TOOLS FOR LOGGING. |  |  |  |  | No
z | z | z |  | 10/25/16 00:30 | 10/25/16 04:00 | [12 empty] | PROBLEM IN WIRELINE LOGGING WINCH. RECTIFY THE PROBLEM |  |  |  |  | No
z | z | z |  | 10/25/16 04:00 | 10/25/16 06:00 | [12 empty] | CONDUCT WIRLINE LOGGING 1ST RUN (HRLA-HBC-GR-CALI-SP) & IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/25/16 00:00 | 10/25/16 00:30 | [12 empty] | CONTINUED R/U WIRELINE TOOLS FOR LOGGING. |  |  |  |  | No
z | z | z |  | 10/25/16 00:30 | 10/25/16 04:00 | [12 empty] | OBSERVED PROBLEM IN WIRELINE LOGGING WINCH. RECTIFIED THE PROBLEM |  |  |  |  | No
z | z | z |  | 10/25/16 04:00 | 10/25/16 14:45 | [12 empty] | CONDUCTED WIRLINE LOGGING 1ST RUN (HRLA-HBC-GR-CALI-SP) & 2ND RUN (SPED-CNT-SGR-CALI). |  |  |  |  | No
z | z | z |  | 10/25/16 14:45 | 10/25/16 15:30 | [12 empty] | L/D WEATHERFORD WIRELINE TOOLS AND EQUIPMENT. |  |  |  |  | No
z | z | z |  | 10/25/16 15:30 | 10/25/16 17:00 | [12 empty] | B/U MUD MOTOR SET BEND TO ZERO AND L/D WITH HOC. |  |  |  |  | No
z | z | z |  | 10/25/16 17:00 | 10/25/16 19:45 | [12 empty] | RIH WITH RR BIT AND NEW BHA DOWN TO 178M. BREAK CIRCULATED AT BHA. | Productive |  |  |  | No
z | z | z |  | 10/25/16 19:45 | 10/25/16 22:15 | [12 empty] | CONTINUED RIH TILL 456M. |  |  |  |  | Yes
z | z | z |  | 10/25/16 22:15 | 10/25/16 22:45 | [12 empty] | OBSERVED COMPRESSION WASHED AND REAMED DOWN FROM 456M TO 524M. | Productive |  |  |  | No
z | z | z |  | 10/25/16 22:45 | 10/25/16 23:00 | [12 empty] | CONTINUED RIH FROM 524M TO 670M. |  |  |  |  | No
z | z | z |  | 10/25/16 23:00 | 10/25/16 23:30 | [12 empty] | WASHED DOWN FROM 670M TO 756M. |  |  |  |  | No
z | z | z |  | 10/25/16 23:30 | 10/26/16 00:00 | [12 empty] | CONTINUED RIH FROM 756M TO 958M. |  |  |  |  | No
z | z | z |  | 10/26/16 00:00 | 10/26/16 00:30 | [12 empty] | CONTINUED RIH FROM 958M TO 1016M. |  |  |  |  | No
z | z | z |  | 10/26/16 00:30 | 10/26/16 06:00 | [12 empty] | REAMED AND WASHED DOWN FROM 1016M TO 1193M. (HARD REAMED FROM 1103M TO 1193M) | Productive |  |  |  | No
z | z | z |  | 10/26/16 00:00 | 10/26/16 00:30 | [12 empty] | CONTINUED RIH FROM 958M TO 1016M. |  |  |  |  | No
z | z | z |  | 10/26/16 00:30 | 10/26/16 10:30 | [12 empty] | REAMED AND WASHED DOWN FROM 1016M TO 1202M. (HARD REAMED FROM 1103M TO 1202M). | Productive |  |  |  | No
z | z | z |  | 10/26/16 10:30 | 10/26/16 11:30 | [12 empty] | OBSERVED STRING GOT STUCK @ 1202M (NO ROTATION) WORKED ON STRING TO RELEASE WITH MXIMUM 50TON OVERPULL. APPLIED JARRING UPWARD STRING GOT RELEASED. | Non Productive |  |  |  | No
z | z | z |  | 10/26/16 11:30 | 10/26/16 12:00 | [12 empty] | PUMPED OUT OF HOLE TO 1100M. | Productive |  |  |  | No
z | z | z |  | 10/26/16 12:00 | 10/26/16 14:30 | [12 empty] | INCREASED MUD WEIGHT TO 1.60 SG. CIRCULATED AND HOMOGENIZED MUD. | Productive |  |  |  | No
z | z | z |  | 10/26/16 14:30 | 10/27/16 00:00 | [12 empty] | REAMED AND WASHED DOWN FROM 1100M TO 1154M (HARD REAMING, TRIED TO INCREASE WOB OBSERVE STRING GOT STALLED). | Productive |  |  |  | No
z | z | z |  | 10/27/16 00:00 | 10/27/16 06:00 | [12 empty] | CONTINUED HARD REAMAING FROM 1154M TO 1178M. MEANWHILE INCREASED MUD WEIGHT TO 1.61 SG. | Productive |  |  |  | No
z | z | z |  | 10/27/16 00:00 | 10/27/16 14:45 | [12 empty] | CONTINUED HARD REAMING FROM 1154M TO 1195M. MEANWHILE INCREASED MUD WEIGHT TO 1.62 SG. BACK REAMED FROM 1195M TO 1188M. | Productive |  |  |  | No
z | z | z |  | 10/27/16 14:45 | 10/27/16 15:45 | [12 empty] | OBSERVED STRING GOT STUCK @ 1188M (NO ROTATION) WORKED ON STRING TO RELEASE WITH MAXIMUM 50TON OVERPULL. APPLIED JARRING UPWARD STRING GOT RELEASED. | Non Productive |  |  |  | No
z | z | z |  | 10/27/16 15:45 | 10/27/16 16:30 | [12 empty] | PUMPED OUT OF HOLE TO 1165M. | Productive |  |  |  | No
z | z | z |  | 10/27/16 16:30 | 10/27/16 17:30 | [12 empty] | REAMED AND WASHED DOWN FROM 1165M TO 1180M. | Productive |  |  |  | No
z | z | z |  | 10/27/16 17:30 | 10/28/16 00:00 | [12 empty] | INCREASED MUD WEIGHT TO 1.68 SG. CIRCULATED AND HOMOGENIZED MUD. | Productive |  |  |  | No
z | z | z |  | 10/28/16 00:00 | 10/28/16 06:00 | [12 empty] | REAMING FROM 1180M TO 1193M. | Productive |  |  |  | No
z | z | z |  | 10/28/16 00:00 | 10/28/16 12:30 | [12 empty] | CONTINUED REAMING FROM 1180M TO 1206M. BACK REAMED FROM 1206M TO 1204M. | Productive |  |  |  | No
z | z | z |  | 10/28/16 12:30 | 10/28/16 13:00 | [12 empty] | OBSERVED STRING GOT STUCK @ 1204M WORKED ON STRING AND RELEASED STRING. PUMPED TO 1190M. | Productive |  |  |  | No
z | z | z |  | 10/28/16 13:00 | 10/28/16 17:30 | [12 empty] | REAMED AND WASHED DOWN FROM 1190M TO 1222M. REAMED AND CIRCULATED AT BOTTOM. | Productive |  |  |  | No
z | z | z |  | 10/28/16 17:30 | 10/28/16 19:45 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 10/28/16 19:45 | 10/28/16 22:15 | [12 empty] | POOH TO 380M ON ELEVATORS. |  |  |  |  | No
z | z | z |  | 10/28/16 22:15 | 10/28/16 22:30 | [12 empty] | FLOW CHECKED WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/28/16 22:30 | 10/29/16 00:00 |  |  |  | 380 | [8 empty] | CUT AND SLIP DRILL LINE. | Productive |  |  |  | Yes
z | z | z |  | 10/29/16 00:00 | 10/29/16 04:00 | [12 empty] | RIH FROM 380M TO 1222M WASHED DOWN LAST STAND. |  |  |  |  | No
z | z | z |  | 10/29/16 04:00 | 10/29/16 06:00 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS , CIRCULATING TO CLEAN SHAKERS. | Productive |  |  |  | No
z | z | z |  | 10/29/16 00:00 | 10/29/16 04:00 | [12 empty] | RIH FROM 380M TO 1222M WASHED DOWN LAST STAND. |  |  |  |  | No
z | z | z |  | 10/29/16 04:00 | 10/29/16 08:15 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS , CIRCULATING TO CLEAN SHAKERS. SPOTTED 300 BBL/1.7 SG. LUBRA BEADS PILL AT BOTTOM. | Productive |  |  |  | No
z | z | z |  | 10/29/16 08:15 | 10/29/16 11:30 | [12 empty] | POOH FROM BOTTOM TO 178M. |  |  |  |  | No
z | z | z |  | 10/29/16 11:30 | 10/29/16 12:45 | [12 empty] | POOH FROM 178M TO SURFACE. |  |  |  |  | No
z | z | z |  | 10/29/16 12:45 | 10/29/16 14:00 | [12 empty] | L/D BHA AND BIT. |  |  |  |  | No
z | z | z |  | 10/29/16 14:00 | 10/29/16 14:30 | [12 empty] | RETRIEVED WEAR BUSHING. |  |  |  |  | No
z | z | z |  | 10/29/16 14:30 | 10/29/16 16:30 | [12 empty] | RIG UP WEATHERFORD CASING RUNNING GEARS. |  |  |  |  | Yes
z | z | z |  | 10/29/16 16:30 | 10/29/16 21:00 | [12 empty] | HELD PJSM P/U 1ST JOINT OF 13 3/8" CASING WITH SHOE AND RIH CASING FROM SURFACE TO 384M. |  |  |  |  | No
z | z | z |  | 10/29/16 21:00 | 10/29/16 22:30 | [12 empty] | P/U AND INSTALLED WEATHERFORD SPIDER SLIPS. CONVERTED DIFFERENTIAL FILL UP INTO NRV BY APPLYING 400 PSI CIRCULATING PRESSURE. | Productive |  |  |  | No
z | z | z |  | 10/29/16 22:30 | 10/30/16 00:00 | [12 empty] | CONTINUED RIH 13 3/8" CASING FROM 384M TO 479M. |  |  |  |  | No
z | z | z |  | 10/30/16 00:00 | 10/30/16 06:00 | [12 empty] | CONTINUED RIH 13 3/8" CASING FROM 479M TO 881M. |  |  |  |  | No
z | z | z |  | 10/30/16 00:00 | 10/30/16 10:30 | [12 empty] | CONTINUED RIH 13 3/8" CASING FROM 479M TO 1192M. |  |  |  |  | No
z | z | z |  | 10/30/16 10:30 | 10/30/16 11:30 | [12 empty] | INSTALLED CIRCULATION HEAD, WASHED DOWN LAST TWO CASING JOINTS DOWN TO 1219.5M. |  |  |  |  | No
z | z | z |  | 10/30/16 11:30 | 10/30/16 14:00 | [12 empty] | CIRCULATED TO CONDITION MUD PRIOR CEMENT JOB. MEANWHILE PREPARED MIX FLUIDS. L/D CASING RUNNING GEARS. | Productive |  |  |  | No
z | z | z |  | 10/30/16 14:00 | 10/30/16 14:30 | [12 empty] | R/U HALLIBURTON CEMENTING LINES AND CEMENTING HEAD PRELOADED WITH TOP AND BOTTOM PLUGS. |  |  |  |  | No
z | z | z |  | 10/30/16 14:30 | 10/30/16 15:00 | [12 empty] | PRESSURE TESTED HALLIBURTON CEMENT LINES, FOUND CHOKED. RECTIFIED THE PROBLEM AND AGAIN PRESSURE TESTED @ 3500 PSI FOUND OK. | Productive |  |  |  | No
z | z | z |  | 10/30/16 15:00 | 10/30/16 15:15 | [12 empty] | CONDUCTED PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 10/30/16 15:15 | 10/30/16 18:30 | [12 empty] | PUMPED 100 BBL OF 1.74 SG SPACER FROM RIG PUMP @ 7 BPM. DROPPED BOTTOM PLUG. SWITCHED BACK TO CEMENT UNIT, FLY MIXED & PUMPED 628 BBL OF 1.8 SG CEMENT SLURRY FOLLOWED BY 104 BBL OF 1.9 SG FLY MIXED SLURRY @ 5 BPM. DROPPED TOP PLUG. | Productive |  |  |  | Yes
z | z | z |  | 10/30/16 18:30 | 10/30/16 19:30 | [12 empty] | DISPLACED CEMENT SLURRY WITH 583 BBL MUD @ 10 BPM THRU RIG PUMPS, OBSERVED TOP PLUG BUMPED AND PRESSURE INCREASED TO 1500 PSI. BLED OFF PRESSURE, OBSERVED NO BACK FLOW. NO LOSS DURING CEMENT JOB. RECEIVED 50 BBL SPACER CONTAMINATED WITH CEMNT AT SURFACE. | Productive |  |  |  | No
z | z | z |  | 10/30/16 19:30 | 10/30/16 21:00 | [12 empty] | RIG DOWN CIRCULATING HEAD AND HALLIBURTON CEMENT LINES. | Productive |  |  |  | No
z | z | z |  | 10/30/16 21:00 | 10/30/16 23:00 | [12 empty] | LIFTED & HANGED OFF BOP STACK. SET 13 3/8" CASING SLIPS. |  |  |  |  | No
z | z | z |  | 10/30/16 23:00 | 10/31/16 00:00 | [12 empty] | WOC. ROUGH CUT 13 3/8" CASING JOINT, N/D FLOW LINE. |  |  |  |  | No
z | z | z |  | 10/31/16 00:00 | 10/31/16 03:30 | [12 empty] | WOC. MEANWHILE N/D BOP STACK. FINAL CUT 13 3/8" CASING WITH COLD CUTTER. |  |  |  |  | No
z | z | z |  | 10/31/16 03:30 | 10/31/16 06:00 | [12 empty] | WOC. INSTALLATION OF CASING HEAD SPOOL IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 10/31/16 00:00 | 10/31/16 03:30 | [12 empty] | WOC. MEANWHILE N/D BOP STACK. FINAL CUT 13 3/8" CASING WITH COLD CUTTER. |  |  |  |  | No
z | z | z |  | 10/31/16 03:30 | 10/31/16 09:00 | [12 empty] | WOC. N/U CASING HEAD SPOOL. DURING N/U CASING HEAD SPOOL REST ON SECONDARY SEALS MADE SEVERAL ATTEMPTS AND SET CHS AFTER APPLYING WEIGHT. |  |  |  |  | No
z | z | z |  | 10/31/16 09:00 | 10/31/16 11:00 | [12 empty] | TRIED TO PRESSURE TESTED CHS FOUND PRESSURE DROP @ 100 PSI/10MIN, TIGHTENED THE SCREWS OF SPOOL AND ENERGIZED SECONDARY SEALS, AFTER SEVERAL ATTEMPTS PRESSURE TESTED CHS @ 2000 PSI OK. | Productive |  |  |  | No
z | z | z |  | 10/31/16 11:00 | 10/31/16 18:00 | [12 empty] | N/U BOP STACK, MAKEUP FLOW LINE AND BELL NIPPLE. |  |  |  |  | No
z | z | z |  | 10/31/16 18:00 | 10/31/16 21:30 | [12 empty] | P/U, M/U TEST PLUG ASSY AND P/T LOWER & UPPER PIPE RAMS, LOWER & UPPER IBOP AND BLIND RAM WITH MUD CROSS FLANGES, HCRS/MANUAL VALVES, SAFETY VALVE, AT 300 PSI LOW & 6500 PSI HIGH. P/T ANNULAR, STANDPIPE MANIFOLD CHOKE MANIFOLD AT 300 PSI LOW & 3500 PSI HIGH. |  |  |  |  | No
z | z | z |  | 10/31/16 21:30 | 10/31/16 22:00 | [12 empty] | INSTALLED WEAR BUSHING. POOH AND L/D TEST PLUG ASSEMBLY. |  |  |  |  | No
z | z | z |  | 10/31/16 22:00 | 10/31/16 22:30 | [12 empty] | SERVICED TDS. |  |  |  |  | Yes
z | z | z |  | 10/31/16 22:30 | 11/01/16 00:00 | [12 empty] | B/U AND L/D 3 x 9" DC SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 11/01/16 00:00 | 11/01/16 01:00 | [12 empty] | B/U AND L/D 4 x 8" DC AND 6 x 5" HWDP SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 11/01/16 01:00 | 11/01/16 05:00 |  |  |  | 171 | [8 empty] | P/U, M/U 12 1/4" TRICONE BIT WITH BIT SUB AND RIH DOWN TO 171M. WHILE RIH P/U 7 x 8" DC, 1 x DRILLING JAR AND 6 x 5" HWDP FROM CATWALK. | Productive |  |  |  | No
z | z | z |  | 11/01/16 05:00 | 11/01/16 06:00 | [12 empty] | CONTINUE RIH DOWN TO 287M, WHILE P/U 5" S GRADE DP FROM CAT WALK SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 11/01/16 00:00 | 11/01/16 01:00 | [12 empty] | B/U AND L/D 4 x 8" DC AND 6 x 5" HWDP SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 11/01/16 01:00 | 11/01/16 05:00 |  |  |  | 171 | [8 empty] | P/U, M/U 12 1/4" TRICONE BIT WITH BIT SUB AND RIH DOWN TO 171M. WHILE RIH P/U 7 x 8" DC, 1 x DRILLING JAR AND 6 x 5" HWDP FROM CATWALK. | Productive |  |  |  | No
z | z | z |  | 11/01/16 05:00 | 11/01/16 08:00 | [12 empty] | CONTINUED RIH DOWN TO 519M, WHILE RIH P/U 5" S-135 DP FROM CAT WALK SINGLE BY SINGLE. |  |  |  |  | No
z | z | z |  | 11/01/16 08:00 | 11/01/16 09:00 | [12 empty] | WORKED ON POWER TONG HYDRAULIC HOSE. RECTIFIED THE PROBLEM, FUNCTION TESTED FOUND OK. |  |  |  |  | No
z | z | z |  | 11/01/16 09:00 | 11/01/16 11:15 | [12 empty] | CHANGED SAVER SUB AND WASH PIPE OF TDS. |  |  |  |  | No
z | z | z |  | 11/01/16 11:15 | 11/01/16 15:00 | [12 empty] | CONTINUED RIH DOWN TO 1157M, WHILE RIH P/U 5" S-135 DP FROM CAT WALK SINGLE BY SINGLE (TOTAL 84 JOINTS WERE PICKED UP). |  |  |  |  | No
z | z | z |  | 11/01/16 15:00 | 11/01/16 15:30 | [12 empty] | OBSERVED 2 TON COMPRESSION, STARTED WASHED DOWN FROM 1157M TO 1193M. |  |  |  |  | Yes
z | z | z |  | 11/01/16 15:30 | 11/01/16 19:45 |  |  | 1193 | 1214 | [8 empty] | TAGGED CEMENT / PLUG AT 1193M, DRILLED CEMENT AND FLOAT COLLAR FROM 1193M TO 1214M. (DRILLED CEMENT WITH 3-5 TON WOB). | Productive |  |  |  | No
z | z | z |  | 11/01/16 19:45 | 11/01/16 20:00 | [12 empty] | PRESSURE TESTED CASING @ 1500 PSI FOR 10 MINUTES OK. | Productive |  |  |  | No
z | z | z |  | 11/01/16 20:00 | 11/01/16 23:00 |  |  |  | 1220 | [8 empty] | CONTINUED DRILLING CEMENT AND FLOAT SHOE DOWN TO 1220M | Productive |  |  |  | No
z | z | z |  | 11/01/16 23:00 | 11/02/16 00:00 | [12 empty] | OBSERVED MUD FLOWING FROM CASING HEAD SPOOL WING VALVE (20" x 13 3/8" ANNULUS). STOPPED PUMPING, POOH 4 STANDS. | Productive |  |  |  | No
z | z | z |  | 11/02/16 00:00 | 11/02/16 01:30 | [12 empty] | FILLED HOLE FROM TRIP TANK, MONITORED FLOW FROM THE WING VALVE (RECEIVED 1.45 SG. CEMENT CONTAMINATION). CLOSED THE VALVE. |  |  |  |  | No
z | z | z |  | 11/02/16 01:30 | 11/02/16 01:45 | [12 empty] | RIH 4 STANDS DOWN TO 1220M. |  |  |  |  | No
z | z | z |  | 11/02/16 01:45 | 11/02/16 02:30 |  |  |  | 1222 | [8 empty] | CONTINUED DRILLING CEMENT DOWN TO 1222M | Productive |  |  |  | No
z | z | z |  | 11/02/16 02:30 | 11/02/16 03:45 | [12 empty] | CIRCULATED TO CLEAN SHAKERS. | Productive |  |  |  | No
z | z | z |  | 11/02/16 03:45 | 11/02/16 06:00 | [12 empty] | POOH FROM 1222M TO 374M. |  |  |  |  | No
z | z | z |  | 11/02/16 00:00 | 11/02/16 01:30 | [12 empty] | FILLED HOLE FROM TRIP TANK, MONITORED FLOW FROM THE WING VALVE (RECEIVED 1.45 SG. CEMENT CONTAMINATION). CLOSED THE VALVE. |  |  |  |  | No
z | z | z |  | 11/02/16 01:30 | 11/02/16 01:45 | [12 empty] | RIH 4 STANDS DOWN TO 1220M. |  |  |  |  | No
z | z | z |  | 11/02/16 01:45 | 11/02/16 02:30 |  |  |  | 1222 | [8 empty] | CONTINUED DRILLING CEMENT DOWN TO 1222M. | Productive |  |  |  | No
z | z | z |  | 11/02/16 02:30 | 11/02/16 03:45 | [12 empty] | CIRCULATED TO CLEAN SHAKERS. | Productive |  |  |  | No
z | z | z |  | 11/02/16 03:45 | 11/02/16 06:45 | [12 empty] | POOH FROM 1222M TO 171M. FLOW CHECKED AT BHA. |  |  |  |  | No
z | z | z |  | 11/02/16 06:45 | 11/02/16 08:30 | [12 empty] | CONTINUED POOH FROM 171M TO SURFACE. |  |  |  |  | No
z | z | z |  | 11/02/16 08:30 | 11/02/16 10:45 | [12 empty] | MONITORED FLOW FROM THE WING VALVE (RECEIVED 1.45 SG. CEMENT CONTAMINATION). |  |  |  |  | Yes
z | z | z |  | 11/02/16 10:45 | 11/02/16 14:15 | [12 empty] | RIH WITH 5" OEDP DOWN TO 1220M. |  |  |  |  | No
z | z | z |  | 11/02/16 14:15 | 11/03/16 00:00 | [12 empty] | STARTED CIRCULATION AT SLOW RATE AND CHECKED RETURNS. (OBSERVED IN/OUT MUD WEIGHT EQUAL AFTER PUMPING 140 BBL OF MUD). | Productive |  |  |  | No
z | z | z |  | 11/03/16 00:00 | 11/03/16 00:30 | [12 empty] | CIRCULATED TO CONDITION MUD. STOPPED CIRCULATION. | Productive |  |  |  | No
z | z | z |  | 11/03/16 00:30 | 11/03/16 06:00 | [12 empty] | OBSERVED THE WELL (FOUND STATIC) MEANWHILE CIRCULATED AND RECIPROCATED STRING INTERMITTENTLY. | Productive |  |  |  | No
z | z | z |  | 11/03/16 00:00 | 11/03/16 00:30 | [12 empty] | CIRCULATED TO CONDITION MUD. STOPPED CIRCULATION. | Productive |  |  |  | No
z | z | z |  | 11/03/16 00:30 | 11/03/16 12:00 | [12 empty] | CONTINUED OBSERVING THE WELL (FOUND STATIC) MEANWHILE CIRCULATED AND RECIPROCATED STRING INTERMITTENTLY. | Productive |  |  |  | No
z | z | z |  | 11/03/16 12:00 | 11/03/16 12:15 | [12 empty] | RUN TRACER FOR VOLUME ESTIMATION. (CHANNEL VOLUME IS ABOUT 75BBL) |  |  |  |  | No
z | z | z |  | 11/03/16 12:15 | 11/04/16 00:00 | [12 empty] | CONTINUED OBSERVING THE WELL (FOUND STATIC) MEANWHILE CIRCULATED AND RECIPROCATED STRING INTERMITTENTLY. | Productive |  |  |  | No
z | z | z |  | 11/04/16 00:00 | 11/04/16 06:00 | [12 empty] | CONTINUED OBSERVING THE WELL (FOUND STATIC) MEANWHILE CIRCULATED AND RECIPROCATED STRING INTERMITTENTLY. | Productive |  |  |  | No
z | z | z |  | 11/04/16 00:00 | 11/04/16 11:00 | [12 empty] | CONTINUED OBSERVING THE WELL (FOUND STATIC) MEANWHILE CIRCULATED AND RECIPROCATED STRING INTERMITTENTLY. | Productive |  |  |  | No
z | z | z |  | 11/04/16 11:00 | 11/04/16 13:30 | [12 empty] | RUN TRACER FOR VOLUME ESTIMATION. (CHANNEL VOLUME IS ABOUT 72BBL). |  |  |  |  | No
z | z | z |  | 11/04/16 13:30 | 11/04/16 16:15 | [12 empty] | POOH FROM 1220M TO SURFACE. |  |  |  |  | No
z | z | z |  | 11/04/16 16:15 | 11/04/16 21:45 | [12 empty] | P/U, M/U WEATHERFORD CEMENT RETAINER WITH SETTING TOOL AND RIH ON 5" DP DOWN TO 1188.75M. DROPPED BALL FOR THE SETTING OF PACKER. |  |  |  |  | No
z | z | z |  | 11/04/16 21:45 | 11/04/16 22:15 | [12 empty] | HELD PJSM TO SET PACKER. |  |  |  |  | No
z | z | z |  | 11/04/16 22:15 | 11/04/16 23:00 | [12 empty] | PRESSURE TESTED HALLIBURTON CEMENTING LINES @ 5000 PSI OK. | Productive |  |  |  | No
z | z | z |  | 11/04/16 23:00 | 11/05/16 00:00 | [12 empty] | PUMPED FROM CEMENT UNIT TO CHASE THE BALL CONFIRMED BALL SETTING BY INCREASE IN PRESSURE. SET CEMENT RETAINER PACKER BY INCREASING THE PRESSURE, RELEASED TOOL BY INCREASING THE PRESSURE @ 3500 PSI. CONFIRM RETAINER SETTING BY TAGGING WITH SETTING TOOL. PERFORMED CEMENT RETAINER INTEGRITY TEST THROGH ANNULUS @ 500 PSI PRESSURE. | Productive |  |  |  | Yes
z | z | z |  | 11/05/16 00:00 | 11/05/16 04:00 | [12 empty] | POOH FROM 1188M TO SURFACE. |  |  |  |  | No
z | z | z |  | 11/05/16 04:00 | 11/05/16 04:45 | [12 empty] | B/U & L/D WEATHERFORD RETAINER SETTING ASSEBLY. |  |  |  |  | No
z | z | z |  | 11/05/16 04:45 | 11/05/16 05:45 | [12 empty] | P/U, M/U WEATHERFORD STINGER WITH SETTING TOOL. |  |  |  |  | No
z | z | z |  | 11/05/16 05:45 | 11/05/16 06:00 | [12 empty] | RIH ON 5" DP DOWN TO 31M FOR SQUEEZE CEMENTING JOB. |  |  |  |  | No
z | z | z |  | 11/05/16 00:00 | 11/05/16 04:00 | [12 empty] | POOH FROM 1188M TO SURFACE. |  |  |  |  | No
z | z | z |  | 11/05/16 04:00 | 11/05/16 04:45 | [12 empty] | B/U & L/D WEATHERFORD RETAINER SETTING ASSEMBLY. |  |  |  |  | No
z | z | z |  | 11/05/16 04:45 | 11/05/16 06:00 | [12 empty] | P/U, M/U WEATHERFORD STINGER WITH SETTING TOOL & RIH DOWN TO 31M FOR SQUEEZE CEMENTING JOB. . |  |  |  |  | No
z | z | z |  | 11/05/16 06:00 | 11/05/16 06:30 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 11/05/16 06:30 | 11/05/16 10:00 | [12 empty] | CONTINUE RIH WITH CEMENT STINGER ASSEMBLY DOWN TO 1188M. |  |  |  |  | No
z | z | z |  | 11/05/16 10:00 | 11/05/16 11:00 | [12 empty] | STABBED IN STINGER IN CEMENT RETAINER WITH CIRCULATION AT 150 PSI. PRESSURE TESTED ANNULUS TO CHECK SEAL INTEGRITY. OK. | Productive |  |  |  | No
z | z | z |  | 11/05/16 11:00 | 11/05/16 14:30 | [12 empty] | CIRCULATED TO CONDITION MUD. MEANWHILE PREPARED MIX FLUID FOR THE CEMENT SLURRY. | Productive |  |  |  | Yes
z | z | z |  | 11/05/16 14:30 | 11/05/16 15:00 | [12 empty] | PRESSURE TESTED HALLIBURTON CEMENTING LINES @ 3500 PSI OK. | Productive |  |  |  | No
z | z | z |  | 11/05/16 15:00 | 11/05/16 16:00 | [12 empty] | CIRCULATED TO CONDITION MUD. MEANWHILE PREPARED BATCH MIXED CEMENT SLURRY. | Productive |  |  |  | No
z | z | z |  | 11/05/16 16:00 | 11/05/16 18:00 | [12 empty] | PUMPED 80 BBL OF 14.5PPG SPACER FROM RIG PUMPS, FOLLOWED BY 80 BBL OF 15.8 PPG FLY MIXED LEAD SLURRY AND 100 BBL OF 15.8 PPG BATCHED MIXED TAIL SLURRIES. DISPLACED CEMENT SLURRY BY PUMPING 10 BBL SPACER FROM RIG PUMP AND 57 BBL OF MUD FROM CEMENT UNIT (UNDER DISPLACED 2 BARREL). RECEIVED 50BBL OF NEAT CEMENT AT SURFACE. | Productive |  |  |  | No
z | z | z |  | 11/05/16 18:00 | 11/05/16 18:30 | [12 empty] | POOH FROM 1188M TO 1102M. |  |  |  |  | No
z | z | z |  | 11/05/16 18:30 | 11/05/16 20:00 | [12 empty] | REVERSE CIRCULATED 1.5 (STRING CAPACITY) RECEIVED 50BBL CONTAMINATION BY REVERSE CIRCULATION. DIRECT CIRCULATED TO CLEAN HOLE. | Productive |  |  |  | No
z | z | z |  | 11/05/16 20:00 | 11/05/16 23:30 | [12 empty] | POOH FROM 1102M TO SURFACE. L/D STINGER ASSEMBLY. |  |  |  |  | No
z | z | z |  | 11/05/16 23:30 | 11/06/16 00:00 | [12 empty] | P/U, M/U 9RR1 BIT FOR THE COC. |  |  |  |  | No
z | z | z |  | 11/06/16 00:00 | 11/06/16 01:30 | [12 empty] | RIH WITH 9RR1 BIT DOWN TO 171M. |  |  |  |  | No
z | z | z |  | 11/06/16 01:30 | 11/06/16 04:45 | [12 empty] | CONTINUED RIH DOWN TO 1000M. |  |  |  |  | No
z | z | z |  | 11/06/16 04:45 | 11/06/16 06:00 | [12 empty] | WOC. |  |  |  |  | No
z | z | z |  | 11/06/16 00:00 | 11/06/16 01:30 | [12 empty] | RIH WITH 9RR1 BIT DOWN TO 171M. |  |  |  |  | No
z | z | z |  | 11/06/16 01:30 | 11/06/16 04:45 | [12 empty] | CONTINUE RIH DOWN TO 1000M. |  |  |  |  | No
z | z | z |  | 11/06/16 04:45 | 11/06/16 17:45 | [12 empty] | WOC. |  |  |  |  | No
z | z | z |  | 11/06/16 17:45 | 11/06/16 18:45 | [12 empty] | RESUMED RIH FROM 1000M TO 1188M. |  |  |  |  | No
z | z | z |  | 11/06/16 18:45 | 11/07/16 00:00 |  |  | 1188 | 1202 | [8 empty] | TAGGED CEMENT AND RETAINER @ 1188M. STARTED DRILLING RETAINER AND CEMENT FROM 1188M TO 1202M. (AFTER DRILLING RETAINER, RIH FREE FROM 1190M TO 1200M WITH CIRCULATION). | Productive |  |  |  | No
z | z | z |  | 11/07/16 00:00 | 11/07/16 05:00 |  |  | 1200 | 1212 | [8 empty] | CONTINUE DRILLING CEMENT AND PIECES OF RETAINER FROM 1200M TO 1212M (WOB 6-8 TONS RPM 60-80) | Productive |  |  |  | No
z | z | z |  | 11/07/16 05:00 | 11/07/16 05:15 | [12 empty] | PRESSURE TESTED CASING @ 700 PSI OK. | Productive |  |  |  | No
z | z | z |  | 11/07/16 05:15 | 11/07/16 06:00 |  |  | 1212 | 1216 | [8 empty] | CONTINUE DRILLING CEMENT FROM 1212M TO 1216M | Productive |  |  |  | No
z | z | z |  | 11/07/16 00:00 | 11/07/16 05:00 |  |  | 1200 | 1212 | [8 empty] | CONTINUED DRILLING CEMENT AND PIECES OF RETAINER FROM 1200M TO 1212M (WOB 6-8 TONS RPM 60-80). | Productive |  |  |  | No
z | z | z |  | 11/07/16 05:00 | 11/07/16 05:15 | [12 empty] | PRESSURE TESTED CASING @ 700 PSI OK. | Productive |  |  |  | No
z | z | z |  | 11/07/16 05:15 | 11/07/16 06:30 |  |  | 1212 | 1222 | [8 empty] | CONTINUED DRILLING CEMENT FROM 1212M TO 1222M. | Productive |  |  |  | No
z | z | z | 30.25 | 11/07/16 06:30 | 11/07/16 10:30 |  |  | 1222 | 1225 | [8 empty] | DRILLED 12 1/4" HOLE FROM 1222M TO 1225M.. | Productive |  |  |  | No
z | z | z |  | 11/07/16 10:30 | 11/07/16 12:00 | [12 empty] | PUMPED 60 BBL HI-VIS AND CIRCULATED OUT. | Productive |  |  |  | No
z | z | z |  | 11/07/16 12:00 | 11/07/16 14:30 | [12 empty] | R/U CEMENT LINES. PERFORMED FIT FOUND SURFACE LEAKAGE REPAIRED AND CONDUCTED FIT @ 2 SG. EMW. | Non Productive |  |  |  | No
z | z | z |  | 11/07/16 14:30 | 11/07/16 15:00 | [12 empty] | B/U AND R/D CEMENT UNIT LINES. |  |  |  |  | Yes
z | z | z | 30.25 | 11/07/16 15:00 | 11/07/16 17:30 |  |  | 1225 | 1226.5 | [8 empty] | DRILLED 12 1/4" HOLE FROM 1225M TO 1226.5M. | Productive |  |  |  | No
z | z | z |  | 11/07/16 17:30 | 11/07/16 19:00 | [12 empty] | CIRCULATED AT BOTTOM TO CLEAN HOLE. | Productive |  |  |  | No
z | z | z |  | 11/07/16 19:00 | 11/07/16 22:30 | [12 empty] | POOH FROM 1226M TO 171M (BHA). WHILE POOH RIH AND FLUSHED TWO STANDS OF 5" HWDP. |  |  |  |  | No
z | z | z |  | 11/07/16 22:30 | 11/08/16 00:00 | [12 empty] | CONTINUED POOH FROM 171M TO 60M. |  |  |  |  | No
z | z | z |  | 11/08/16 00:00 | 11/08/16 01:30 | [12 empty] | CONTINUED POOH FROM 60M TO SURFACE. B/U AND L/D TRICONE BIT. |  |  |  |  | No
z | z | z |  | 11/08/16 01:30 | 11/08/16 06:00 | [12 empty] | P/U & M/U NEW PDC BIT WITH RSS ASSEBLY (GEO-PILOT) AND MWD. PROGRAMMED RSS. |  |  |  |  | No
z | z | z |  | 11/08/16 00:00 | 11/08/16 01:30 | [12 empty] | CONTINUED POOH FROM 60M TO SURFACE. B/U AND L/D TRICONE BIT. |  |  |  |  | No
z | z | z |  | 11/08/16 01:30 | 11/08/16 07:00 | [12 empty] | P/U & M/U NEW PDC BIT WITH RSS ASSEBLY AND MWD. PROGRAMMED RSS. FUNCTION TESTED MWD. |  |  |  |  | No
z | z | z |  | 11/08/16 07:00 | 11/08/16 08:00 | [12 empty] | RIH DOWN TO 218M. |  |  |  |  | No
z | z | z |  | 11/08/16 08:00 | 11/08/16 16:30 | [12 empty] | CONTINUED RIH FROM 218M TO 1226M. WHILE RIH PROGRAMMED DIRECTIONAL TOOLS. |  |  |  |  | No
z | z | z | 30.25 | 11/08/16 16:30 | 11/08/16 20:00 |  |  | 1226 | 1229 | [8 empty] | DRILLED 12 1/4" HOLE FROM 1226M TO 1229M. OBSERVED BIT HELD AT SEVERAL POINTS AND OCCASIONAL ROTARTY STALLED. | Productive |  |  |  | No
z | z | z |  | 11/08/16 20:00 | 11/08/16 22:45 |  |  | 1226 | 1229 | [8 empty] | CLEARED DRILLED FORMATION WITH BACK REAMING. MEANWHILE INCREASED MUD WEIGHT TO 1.65 SG. | Productive |  |  |  | No
z | z | z | 30.25 | 11/08/16 22:45 | 11/09/16 00:00 |  |  | 1229 | 1231 | [8 empty] | DRILLED 12 1/4" HOLE FROM 1229M TO 1231M. INCREASED MUD WEIGHT TO 1.68 SG. | Productive |  |  |  | Yes
z | z | z | 30.25 | 11/09/16 00:00 | 11/09/16 06:00 |  |  | 1231 | 1247 | [8 empty] | CONTINUED DRILLING 12 1/4" HOLE FROM 1231M TO 1247M. CLEARED DRILLED STAND WITH BACK REAMING. | Productive |  |  |  | No
z | z | z | 30.25 | 11/09/16 00:00 | 11/09/16 06:30 |  |  | 1231 | 1249 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1231M TO 1249M. | Productive |  |  |  | No
z | z | z |  | 11/09/16 06:30 | 11/09/16 11:30 |  |  | 1231 | 1249 | [8 empty] | CLEARED DRILLED STAND WITH BACK REAMING. OBSERVED TIGHT SPOTS CLEARED WITH REAMING. INCREASED MUD WEIGHT TO 1.72 SG. | Productive |  |  |  | No
z | z | z | 30.25 | 11/09/16 11:30 | 11/09/16 17:00 |  |  | 1249 | 1307 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1249M TO 1307M. | Productive |  |  |  | No
z | z | z |  | 11/09/16 17:00 | 11/09/16 18:00 | [12 empty] | WORKED ON MUD PUMPS. | Productive |  |  |  | No
z | z | z | 30.25 | 11/09/16 18:00 | 11/10/16 00:00 |  |  | 1307 | 1344 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1307M TO 1344M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z | 30.25 | 11/10/16 00:00 | 11/10/16 06:00 |  |  | 1344 | 1374 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1344M TO 1374M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z | 30.25 | 11/10/16 00:00 | 11/10/16 08:45 |  |  | 1344 | 1403 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1344M TO 1403M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z |  | 11/10/16 08:45 | 11/10/16 10:15 | [12 empty] | PUMPED HI-VIS AND CIRCULATED OUT. | Productive |  |  |  | No
z | z | z |  | 11/10/16 10:15 | 11/10/16 13:30 | [12 empty] | POOH FROM 1403M TO 1201M. WHILE POOH PUMPED OUT FROM 1374M TO 1201M. | Productive |  |  |  | No
z | z | z |  | 11/10/16 13:30 | 11/10/16 14:30 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z |  | 11/10/16 14:30 | 11/10/16 15:45 | [12 empty] | RIH DOWN TO 1403M. |  |  |  |  | No
z | z | z | 30.25 | 11/10/16 15:45 | 11/11/16 00:00 |  |  | 1403 | 1477 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1403M TO 1477M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z | 30.25 | 11/11/16 00:00 | 11/11/16 06:00 |  |  | 1477 | 1519 | [8 empty] | CONTINUED DRILLING OF 12 1/4" HOLE FROM 1477M TO 1519M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z | 30.25 | 11/11/16 00:00 | 11/11/16 13:15 |  |  | 1477 | 1570 | [8 empty] | CONTINUED DRILLING 12 1/4" HOLE FROM 1477M TO 1570M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z |  | 11/11/16 13:15 | 11/11/16 13:45 | [12 empty] | SERVICED TDS. |  |  |  |  | No
z | z | z | 30.25 | 11/11/16 13:45 | 11/11/16 22:30 |  |  | 1570 | 1616 | [8 empty] | CONTINUED DRILLING 12 1/4" HOLE FROM 1570M TO 1616M. (REAMED AND CLEARED DRILLED STAND. RECORDED MWD SURVEY AT CONNECTION). | Productive |  |  |  | No
z | z | z |  | 11/11/16 22:30 | 11/11/16 23:30 | [12 empty] | CIRCULATED BOTTOM UP FOR SAMPLE. | Productive |  |  |  | No
z | z | z | 30.25 | 11/11/16 23:30 | 11/12/16 00:00 |  |  | 1616 | 1617 | [8 empty] | PUMPED HI-VIS CONTINUED DRILLING OF 12 1/4" HOLE FROM 1616M TO 1617M. | Productive |  |  |  | No
z | z | z |  | 11/12/16 00:00 | 11/12/16 01:00 | [12 empty] | CIRCULATED BOTTOM UP FOR SAMPLE. DECLARED SECTION TD. | Productive |  |  |  | No
z | z | z |  | 11/12/16 01:00 | 11/12/16 02:45 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS. CONTINUE CIRCULATION TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 11/12/16 02:45 | 11/12/16 06:00 | [12 empty] | POOH FROM 1617M TO 1466M. PUMPED OUT OF HOLE FROM 1617M TO 1548M. BACK REAMED FROM 1548M TO 1466M. | Productive |  |  |  | No
z | z | z |  | 11/12/16 00:00 | 11/12/16 01:00 | [12 empty] | CIRCULATED BOTTOM UP FOR SAMPLE. DECLARED SECTION TD. | Productive |  |  |  | No
z | z | z |  | 11/12/16 01:00 | 11/12/16 02:45 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS. CONTINUE CIRCULATION TILL SHAKERS CLEAN. | Productive |  |  |  | No
z | z | z |  | 11/12/16 02:45 | 11/12/16 07:00 | [12 empty] | POOH FROM 1617M TO 1461M. PUMPED OUT OF HOLE FROM 1617M TO 1548M. BACK REAMED FROM 1548M TO 1461M. | Productive |  |  |  | No
z | z | z |  | 11/12/16 07:00 | 11/12/16 08:30 | [12 empty] | FOUND LEAKAGE IN ROTARY HOSE. REPLACED SAME AND PRESSURE TESTED OK. | Productive |  |  |  | No
z | z | z |  | 11/12/16 08:30 | 11/12/16 17:00 | [12 empty] | BACK REAMED FROM 1461M TO 1220M (CASING SHOE). FLOW CHECKED OK. | Productive |  |  |  | No
z | z | z |  | 11/12/16 17:00 | 11/12/16 18:30 | [12 empty] | STARTED RIH DOWN TO 1606M. |  |  |  |  | No
z | z | z |  | 11/12/16 18:30 | 11/12/16 19:30 | [12 empty] | OBSERVED OBSTRUCTION. REAMED AND WASHED DOWN TO 1617M. | Productive |  |  |  | Yes
z | z | z |  | 11/12/16 19:30 | 11/12/16 22:30 | [12 empty] | CIRCULATED AND INCREASED MUD WEIGHT TO 1.75 SG. RUN TRACER AND CIRCULATED FOUND HOLE GAUGE. | Productive |  |  |  | No
z | z | z |  | 11/12/16 22:30 | 11/13/16 00:00 | [12 empty] | PUMPED & CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/13/16 00:00 | 11/13/16 00:30 | [12 empty] | CONTINUE PUMPED & CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/13/16 00:30 | 11/13/16 03:45 | [12 empty] | POOH FROM 1617M TO 1201M. FLOW CHECKED OK. (CLEARED TIGHT SPOT WITH CIRCULATION 1524-1520 & 1233-1230) |  |  |  |  | No
z | z | z |  | 11/13/16 03:45 | 11/13/16 05:30 | [12 empty] | RIH FROM 1201M TO BOTTOM. WASHED LAST STAND. |  |  |  |  | No
z | z | z |  | 11/13/16 05:30 | 11/13/16 06:00 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/13/16 00:00 | 11/13/16 00:30 | [12 empty] | CONTINUE PUMPED & CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/13/16 00:30 | 11/13/16 03:45 | [12 empty] | POOH FROM 1617M TO 1201M. FLOW CHECKED OK. (CLEARED TIGHT SPOT WITH CIRCULATION 1524-1520 & 1233-1230) |  |  |  |  | No
z | z | z |  | 11/13/16 03:45 | 11/13/16 05:30 | [12 empty] | RIH FROM 1201M TO BOTTOM. WASHED LAST STAND. |  |  |  |  | No
z | z | z |  | 11/13/16 05:30 | 11/13/16 07:00 | [12 empty] | PUMPED AND CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/13/16 07:00 | 11/13/16 09:00 | [12 empty] | PUMPED AND SPOTTED 200 BBL 1.77 SG LUBRA BEADS PILL AT BOTTOM. | Productive |  |  |  | No
z | z | z |  | 11/13/16 09:00 | 11/13/16 15:00 | [12 empty] | POOH TO 218M. WHILE POOH OBSERVED OBSTRUCTION/OVERPULL IN CSG AT 1143M, CLEARED WITH CIRCULATION AND ROTATION. |  |  |  |  | No
z | z | z |  | 11/13/16 15:00 | 11/13/16 20:00 | [12 empty] | STARTED POOH BHA FROM 218M TO SURFACE.DOWN LOAD PROGRAM, L/D BHA, MWD TOOLS, RSS AND BIT. |  |  |  |  | Yes
z | z | z |  | 11/13/16 20:00 | 11/13/16 20:30 | [12 empty] | RETERIEVED WEAR BUSHING. |  |  |  |  | No
z | z | z |  | 11/13/16 20:30 | 11/13/16 22:00 | [12 empty] | R/U OVER DRIVE CASING RUNNING EQUIPMENT. |  |  |  |  | No
z | z | z |  | 11/13/16 22:00 | 11/14/16 00:00 | [12 empty] | INSTALLATION OF 9 5/8" CASING RAMS. |  |  |  |  | No
z | z | z |  | 11/14/16 00:00 | 11/14/16 01:00 | [12 empty] | CONTINUE INSTALLATION OF 9 5/8" CASING RAMS AND TESTED BONNET SEALS OK. |  |  |  |  | No
z | z | z |  | 11/14/16 01:00 | 11/14/16 02:00 | [12 empty] | CHANGED SAVER SUB AND L/D ELEVATOR LINKS. |  |  |  |  | No
z | z | z |  | 11/14/16 02:00 | 11/14/16 04:15 | [12 empty] | R/U OVER DRIVE CASING RUNNING EQUIPMENT. INSTALLED OVERDRIVE SYSTEM. |  |  |  |  | No
z | z | z |  | 11/14/16 04:15 | 11/14/16 04:30 | [12 empty] | HELD PJSM AND ASSIGNED JOBS TO PROFESSIONALS. |  |  |  |  | No
z | z | z |  | 11/14/16 04:30 | 11/14/16 06:00 | [12 empty] | P/U 1ST JOINT OF 9 5/8" CASING WITH SHOE AND RIH CASING FROM SURFACE TO 29M. |  |  |  |  | No
z | z | z |  | 11/14/16 00:00 | 11/14/16 01:00 | [12 empty] | CONTINUE INSTALLATION OF 9 5/8" CASING RAMS AND TESTED BONNET SEALS OK. |  |  |  |  | No
z | z | z |  | 11/14/16 01:00 | 11/14/16 02:00 | [12 empty] | CHANGED SAVER SUB AND L/D ELEVATOR LINKS. |  |  |  |  | No
z | z | z |  | 11/14/16 02:00 | 11/14/16 04:15 | [12 empty] | R/U OVER DRIVE CASING RUNNING EQUIPMENT. INSTALLED OVERDRIVE SYSTEM. |  |  |  |  | No
z | z | z |  | 11/14/16 04:15 | 11/14/16 04:30 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 11/14/16 04:30 | 11/14/16 16:45 | [12 empty] | P/U 1ST JOINT OF 9 5/8" CASING WITH SHOE AND RIH CASING FROM SURFACE TO 1215M INSIDE 13 3/8" CSG SHOE. |  |  |  |  | No
z | z | z |  | 11/14/16 16:45 | 11/14/16 17:00 | [12 empty] | BROKE CIRCULATION. |  |  |  |  | No
z | z | z |  | 11/14/16 17:00 | 11/14/16 20:00 | [12 empty] | RESUMED RIH 9 5/8" CSG FROM 1215M TO 1576M. |  |  |  |  | Yes
z | z | z |  | 11/14/16 20:00 | 11/14/16 21:00 | [12 empty] | WASHED DOWN LAST 3 CSG JTS & P/JOINT DOWN TO 1616M. |  |  |  |  | No
z | z | z |  | 11/14/16 21:00 | 11/15/16 00:00 | [12 empty] | CIRCULATION TO CONDITION MUD MEANWHILE PREPARED SPACER AND MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 11/15/16 00:00 | 11/15/16 01:30 | [12 empty] | CONTINUED CIRCULATION TO CONDITION MUD MEANWHILE PREPARED SPACER AND MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 11/15/16 01:30 | 11/15/16 02:15 | [12 empty] | R/U CEMENT HEAD AND CEMENT LINES. |  |  |  |  | No
z | z | z |  | 11/15/16 02:15 | 11/15/16 02:30 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 11/15/16 02:30 | 11/15/16 02:45 | [12 empty] | FLUSHED CEMENT LINES AND PRESSURE TESTED LINES AT 500 PSI LOW & 3500 PSI HIGH, OK. | Productive |  |  |  | No
z | z | z |  | 11/15/16 02:45 | 11/15/16 06:00 | [12 empty] | PUMPED 200 BBL 15 YP MUD FOLLOWED BY 100 BBL SPACER OF 15.5 PPG WITH RIG PUMP. DROPPED BOTTOM PLUG & SWITCHED TO THE CEMENT UNIT. PUMPED 311 BBL FLY MIXED LEAD SLURRY OF 16.2 PPG @ 5BPM FOLLOWED BY 80 BBL BATCH MIXED TAIL SLURRY OF 17 PPG @ 5BPM. DROPPED TOP PLUG & PUMPED 5 BBL MIX FLUID TO FLUSH CEMENT LINES. SWITCHED TO RIG PUMP & CEMENT DISPLACEMENT IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 11/15/16 00:00 | 11/15/16 01:30 | [12 empty] | CONTINUED CIRCULATION TO CONDITION MUD MEANWHILE PREPARED SPACER AND MIX FLUID. | Productive |  |  |  | No
z | z | z |  | 11/15/16 01:30 | 11/15/16 02:15 | [12 empty] | R/U CEMENT HEAD AND CEMENT LINES. |  |  |  |  | No
z | z | z |  | 11/15/16 02:15 | 11/15/16 02:30 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 11/15/16 02:30 | 11/15/16 02:45 | [12 empty] | FLUSHED CEMENT LINES AND PRESSURE TESTED LINES AT 500 PSI LOW & 3500 PSI HIGH, OK. | Productive |  |  |  | No
z | z | z |  | 11/15/16 02:45 | 11/15/16 06:45 | [12 empty] | PUMPED 200 BBL 15 YP MUD FOLLOWED BY 100 BBL SPACER OF 15.5 PPG WITH RIG PUMP. DROPPED BOTTOM PLUG & SWITCHED TO THE CEMENT UNIT. PUMPED 311 BBL FLY MIXED LEAD SLURRY OF 16.2 PPG @ 5BPM FOLLOWED BY 80 BBL BATCH MIXED TAIL SLURRY OF 17 PPG @ 5BPM. DROPPED TOP PLUG & PUMPED 5 BBL MIX FLUID TO FLUSH CEMENT LINES. SWITCHED TO RIG PUMP & DISPLACED CEMENT WITH MUD OF 1.75 SG. RECEIVED 42 BBL NEAT CEMENT AT SURFACE. DUMPED 100 BBL SPACER AND 52 BBL CONTAMINATION. PLUG BUMPED & HELD PRESSURE AT 1600 PSI. BLED OFF PRESSURE, OBSERVED NO BACK FLOW. | Productive |  |  |  | No
z | z | z |  | 11/15/16 06:45 | 11/15/16 09:15 | [12 empty] | LIFTED BOP & SET 9 5/8" CSG SLIPS. ROUGH CUT 9 5/8" CSG. |  |  |  |  | No
z | z | z |  | 11/15/16 09:15 | 11/15/16 10:00 | [12 empty] | N/D BOP STACK. |  |  |  |  | Yes
z | z | z |  | 11/15/16 10:00 | 11/15/16 14:00 | [12 empty] | FINAL CUT 9 5/8" CSG MEANWHILE R/D WEATHERFORD OVERDRIVE SYSTEM. |  |  |  |  | No
z | z | z |  | 11/15/16 14:00 | 11/15/16 18:00 | [12 empty] | INSTALLED TUBING HEAD SPOOL (THS). |  |  |  |  | No
z | z | z |  | 11/15/16 18:00 | 11/15/16 19:30 | [12 empty] | ENERGIZED & P/T P SEALS OF THS AT 2800 PSI, OK. PRESSURE TESTED THS/ADAPTER FLANGE CONNECTION AT 2800 PSI, OK. | Productive |  |  |  | No
z | z | z |  | 11/15/16 19:30 | 11/16/16 00:00 | [12 empty] | N/U 13 5/8" 10K BOP STACK. |  |  |  |  | No
z | z | z |  | 11/16/16 00:00 | 11/16/16 03:30 | [12 empty] | M/U TEST PLUG ASSY AND P/T IBOP, FULL OPENING SAFETY VALVE, UPPER & LOWER PIPE RAMS, BLIND RAMS, STANDPIPE MANIFOLD, CHOKE & KILL LINE MANUAL & HCR VALVES, CHOKE MANIFOLD MASTER VALVE AT 500 PSI LOW & 4000 PSI HIGH. P/T ANNULAR AT 500 PSI LOW & 3000 PSI HIGH. L/D TEST PLUG ASSY. |  |  |  |  | No
z | z | z |  | 11/16/16 03:30 | 11/16/16 04:00 | [12 empty] | M/U COMBINATION TOOL ASSY & INSTALLED WEAR BUSHING. |  |  |  |  | No
z | z | z |  | 11/16/16 04:00 | 11/16/16 06:00 | [12 empty] | P/U & M/U NEW 8 1/2" TRICONE BIT WITH 9 5/8" CSG SCRAPPER AND RIH DOWN TO 81M. WHILE RIH P/U 5 X 6 1/2" DCS, HMD JAR & 3 X 5" HWDP FROM CATWALK. |  |  |  |  | No
z | z | z |  | 11/16/16 00:00 | 11/16/16 03:30 | [12 empty] | M/U TEST PLUG ASSY AND P/T IBOP, FULL OPENING SAFETY VALVE, UPPER & LOWER PIPE RAMS, BLIND RAMS, STANDPIPE MANIFOLD, CHOKE & KILL LINE MANUAL & HCR VALVES, CHOKE MANIFOLD MASTER VALVE AT 500 PSI LOW & 4000 PSI HIGH. P/T ANNULAR AT 500 PSI LOW & 3000 PSI HIGH. L/D TEST PLUG ASSY. |  |  |  |  | No
z | z | z |  | 11/16/16 03:30 | 11/16/16 04:00 | [12 empty] | M/U COMBINATION TOOL ASSY & INSTALLED WEAR BUSHING. |  |  |  |  | No
z | z | z |  | 11/16/16 04:00 | 11/16/16 06:30 | [12 empty] | P/U & M/U NEW 8 1/2" TRICONE BIT WITH 9 5/8" CSG SCRAPPER AND RIH DOWN TO 109M. WHILE RIH P/U 5 X 6 1/2" DCS, HMD JAR & 6 X 5" HWDP FROM CATWALK. FLUSHED THE STRING BY RESUMING CIRCULATION. |  |  |  |  | No
z | z | z |  | 11/16/16 06:30 | 11/16/16 11:30 | [12 empty] | RIH SCRAPPER ASSY FROM 109M TO 1556M. WASHED DOWN LAST STAND AND TAGGED TOP PLUG AT 1585M. |  |  |  |  | No
z | z | z |  | 11/16/16 11:30 | 11/16/16 12:45 | [12 empty] | CIRCULATED ONE CYCLE MEANWHILE RECIPROCATED THE STRING. | Productive |  |  |  | No
z | z | z |  | 11/16/16 12:45 | 11/16/16 16:00 | [12 empty] | POOH SCRAPPER ASSY TO 109M AT THE TOP OF BHA. |  |  |  |  | No
z | z | z |  | 11/16/16 16:00 | 11/16/16 17:00 | [12 empty] | RIH WITH 6 X 5" HWDP (NEW) DOWN TO 170M AND FLUSHED THE STRING. |  |  |  |  | Yes
z | z | z |  | 11/16/16 17:00 | 11/16/16 18:00 | [12 empty] | POOH FROM 170M TO SURFACE. L/D 8 1/2" TC BIT, 9 5/8" CSG SCRAPPER & HMD JAR. |  |  |  |  | No
z | z | z |  | 11/16/16 18:00 | 11/16/16 18:15 | [12 empty] | HELD PRE JOB SAFETY MEETING. | Productive |  |  |  | No
z | z | z |  | 11/16/16 18:15 | 11/16/16 19:00 | [12 empty] | R/U WFD WIRELINE GEARS. |  |  |  |  | No
z | z | z |  | 11/16/16 19:00 | 11/16/16 22:00 | [12 empty] | CONDUCTED WIRELINE LOG (CBL-VDL-CCL-GR). |  |  |  |  | No
z | z | z |  | 11/16/16 22:00 | 11/16/16 22:30 | [12 empty] | R/D WFD WIRELINE GEARS. |  |  |  |  | No
z | z | z |  | 11/16/16 22:30 | 11/16/16 23:30 | [12 empty] | RIH SAME 8 1/2" TC BIT WITH SLIM ROTARY BHA DOWN TO 117M. |  |  |  |  | No
z | z | z |  | 11/16/16 23:30 | 11/17/16 00:00 | [12 empty] | CONTINUED RIH 8 1/2" TC BIT WITH SLIM BHA FROM 117M TO 290M. |  |  |  |  | No
z | z | z |  | 11/17/16 00:00 | 11/17/16 03:00 | [12 empty] | CONTINUED RIH 8 1/2" TC BIT WITH SLIM BHA FROM 290M TO 1585M. |  |  |  |  | No
z | z | z |  | 11/17/16 03:00 | 11/17/16 06:00 |  |  | 290 | 1585 | [8 empty] | DRILLED TOP PLUG, BOTTOM PLUG, FLOAT COLLAR & SHOE TRACK CEMENT DOWN TO 1593 & IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 11/17/16 00:00 | 11/17/16 03:00 | [12 empty] | CONTINUED RIH 8 1/2" TC BIT WITH SLIM BHA FROM 290M TO 1585M. |  |  |  |  | No
z | z | z |  | 11/17/16 03:00 | 11/17/16 10:00 |  |  | 290 | 1613 | [8 empty] | DRILLED TOP PLUG, BOTTOM PLUG, FLOAT COLLAR & SHOE TRACK CEMENT DOWN TO 1613M. | Productive |  |  |  | No
z | z | z |  | 11/17/16 10:00 | 11/17/16 11:00 | [12 empty] | CIRCULATED OUT HI-VIS. | Productive |  |  |  | No
z | z | z |  | 11/17/16 11:00 | 11/17/16 12:15 | [12 empty] | DISPLACED HOLE VOLUME WITH KCL POLYMER NON DAMAGING MUD OF 1.07SG. |  |  |  |  | No
z | z | z |  | 11/17/16 12:15 | 11/17/16 13:45 | [12 empty] | CIRCULATED TO HOMOGENIZE THE MUD (CLEANED SAND TRAP & DITCHES). | Productive |  |  |  | No
z | z | z |  | 11/17/16 13:45 | 11/17/16 14:30 | [12 empty] | H/U CEMENT LINES & P/T LINES AT 4000 PSI. PRESSURE TESTED CASING AT 3500 PSI, OK. | Productive |  |  |  | No
z | z | z |  | 11/17/16 14:30 | 11/17/16 15:00 |  |  |  | 1613 | [8 empty] | CONDUCTED H2S DRILL. | Productive |  |  |  | Yes
z | z | z |  | 11/17/16 15:00 | 11/17/16 19:00 |  |  |  | 1617 | [8 empty] | RESUMED DRILLING CEMENT & FLOAT SHOE DOWN TO 1617M. | Productive |  |  |  | No
z | z | z | 40.5 | 11/17/16 19:00 | 11/17/16 20:15 |  |  | 1617 | 1618 | [8 empty] | DRILLED 8 1/2" HOLE FROM 1617M TO 1618M. | Productive |  |  |  | No
z | z | z |  | 11/17/16 20:15 | 11/17/16 21:30 | [12 empty] | CIRCULATED TO HOMOGENIZE THE MUD. | Productive |  |  |  | No
z | z | z |  | 11/17/16 21:30 | 11/17/16 22:00 | [12 empty] | R/U CEMENT LINES & P/T LINES AT 2000 PSI. |  |  |  |  | No
z | z | z |  | 11/17/16 22:00 | 11/17/16 22:30 | [12 empty] | CONDUCTED FIT / SHOE BOND TEST WITH 1.07SG MUD WT. @ 940 PSI SURFACE PRESSURE (EMW = 1.50 SG). |  |  |  |  | No
z | z | z |  | 11/17/16 22:30 | 11/17/16 22:45 | [12 empty] | FLOW CHECKED, WELL STATIC. MEANWHILE R/D CEMENT LINES. |  |  |  |  | No
z | z | z |  | 11/17/16 22:45 | 11/18/16 00:00 | [12 empty] | POOH FROM 1618M TO 1274M. |  |  |  |  | No
z | z | z |  | 11/18/16 00:00 | 11/18/16 02:00 | [12 empty] | CONTINUED POOH FROM 1274M TO 290M. |  |  |  |  | No
z | z | z |  | 11/18/16 02:00 | 11/18/16 02:30 |  |  | 1274 | 290 | [8 empty] | CONDUCTED H2S DRILL. | Productive |  |  |  | No
z | z | z |  | 11/18/16 02:30 | 11/18/16 03:00 | [12 empty] | CONTINUED POOH FROM 290M TO 149M. |  |  |  |  | No
z | z | z |  | 11/18/16 03:00 | 11/18/16 03:30 |  |  | 290 | 149 | [8 empty] | SLIPPED 24' FT DRILL LINE. | Productive |  |  |  | No
z | z | z |  | 11/18/16 03:30 | 11/18/16 04:30 | [12 empty] | POOH FROM 149M TO SURFACE. L/D BIT & JAR. |  |  |  |  | No
z | z | z |  | 11/18/16 04:30 | 11/18/16 06:00 | [12 empty] | P/U & M/U NEW 8 1/2" PDC BIT WITH RSS ASSY & IS IN PROGRESS. |  |  |  |  | No
z | z | z |  | 11/18/16 00:00 | 11/18/16 02:00 | [12 empty] | CONTINUED POOH FROM 1274M TO 290M. |  |  |  |  | No
z | z | z |  | 11/18/16 02:00 | 11/18/16 02:30 |  |  | 1274 | 290 | [8 empty] | CONDUCTED H2S DRILL. | Productive |  |  |  | No
z | z | z |  | 11/18/16 02:30 | 11/18/16 03:00 | [12 empty] | CONTINUED POOH FROM 290M TO 149M. |  |  |  |  | No
z | z | z |  | 11/18/16 03:00 | 11/18/16 03:30 |  |  | 290 | 149 | [8 empty] | SLIPPED 24' FT DRILL LINE. | Productive |  |  |  | No
z | z | z |  | 11/18/16 03:30 | 11/18/16 04:30 | [12 empty] | POOH FROM 149M TO SURFACE. L/D BIT & JAR. |  |  |  |  | No
z | z | z |  | 11/18/16 04:30 | 11/18/16 08:45 | [12 empty] | P/U & M/U NEW 8 1/2" PDC BIT WITH RSS ASSY & DOWNLOADED PROGRAM IN MWD TOOLS. |  |  |  |  | No
z | z | z |  | 11/18/16 08:45 | 11/18/16 09:30 | [12 empty] | FUNCTION TESTED RSS TOOLS (400 GPM ; 550 PSI). |  |  |  |  | Yes
z | z | z |  | 11/18/16 09:30 | 11/18/16 10:30 | [12 empty] | M/U PBL SUB & FUNCTION TESTED BY ACTIVATING (40 PSI) & DEACTIVATING (3000 PSI) THE TOOL. RETREIVED THE BALLS. |  |  |  |  | No
z | z | z |  | 11/18/16 10:30 | 11/18/16 11:15 | [12 empty] | RIH FROM 20M TO 221M (TOP OF BHA). PLACED 1ST CORROSION RING IN 1ST HWDP STAND. |  |  |  |  | No
z | z | z |  | 11/18/16 11:15 | 11/18/16 15:00 | [12 empty] | RIH FROM 221M TO 1552M. |  |  |  |  | No
z | z | z |  | 11/18/16 15:00 | 11/18/16 18:00 | [12 empty] | RIH FROM 1552M TO 1618M WIPING FOR GAMMA CALLIBRATION. PLACED 2ND CORROSION RING IN 48TH DP STAND. |  |  |  |  | No
z | z | z | 40.5 | 11/18/16 18:00 | 11/18/16 21:30 |  |  | 1618 | 1639 | [8 empty] | BROKE IN BIT AND RESUMED DRILLING 8 1/2" HOLE FROM 1618M TO 1639M. MAX RECORDED GAS 17%. @ 1639M. | Productive |  |  |  | No
z | z | z |  | 11/18/16 21:30 | 11/18/16 22:45 | [12 empty] | REAMED TWICE AND PUMPED HI-VIS AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 11/18/16 22:45 | 11/19/16 00:00 |  |  | 1639 | 1650 | [8 empty] | RESUMED DRILLING FROM 1639M TO 1650M. | Productive |  |  |  | No
z | z | z | 40.5 | 11/19/16 00:00 | 11/19/16 06:00 |  |  | 1650 | 1685 | [8 empty] | CONTINUED DRILLING 8 1/2" HOLE FROM 1650M TO 1685M & IS IN PROGRESS. REAMED & PUMPED HI-VIS AT CONNECTION. RECORDED MWD SURVEY. | Productive |  |  |  | No
z | z | z |  | 10/19/16 00:00 | 10/19/16 01:00 | [12 empty] | CONTINUED HARD REAMING FROM 1043M TO 1050M. MEANWHILE INRCEASED MUD WEIGHT FROM 1.27 SG TO 1.32 SG. | Productive |  |  |  | No
z | z | z |  | 10/19/16 01:00 | 10/19/16 23:30 |  |  | 1050 | 1075 | [8 empty] | RESUMED DRILLILNG FROM 1050M TO 1075M IN ROTARY MODE. REAMED / BACK REAMED TWICE AT CONNECTION. REOCORDED MWD SURVEY. INCREASED MUD WEIGHT TO 1.35 DURING DRILLING. CHECKED CONDITION OF HOLE FOUND HOLE TIGHT. | Productive |  |  |  | No
z | z | z |  | 10/19/16 23:30 | 10/20/16 00:00 | [12 empty] | CIRCULATED MEANWHILE INRCEASED MUD WEIGHT TO 1.40 SG IS IN PROGRESS. | Productive |  |  |  | No
z | z | z |  | 10/20/16 00:00 | 10/20/16 01:30 | [12 empty] | CONTINUED CIRCULATED TO CONDITION MUD MEANWHILE INRCEASED MUD WEIGHT TO 1.40 SG. | Productive |  |  |  | No
z | z | z |  | 10/20/16 01:30 | 10/20/16 01:45 | [12 empty] | FLOW CHECKED PRIOR POOH, WELL STATIC. |  |  |  |  | No
z | z | z |  | 10/20/16 01:45 | 10/20/16 03:30 | [12 empty] | POOH OBSERVED OVERPULL OF 5- 7 TONS, BACK REAMED FROM 1075M TO 1002M. | Productive |  |  |  | No
z | z | z |  | 10/20/16 03:30 | 10/20/16 04:30 | [12 empty] | POOH ON ELEVATOR FROM 1002M TO 886M. OBSERVED OVERPULL OF 3-5 TONS. |  |  |  |  | No
z | z | z |  | 10/20/16 04:30 | 10/20/16 06:00 | [12 empty] | PUMPED OUT FROM 886M TO 806M & IS IN PROGRESS. | Productive |  |  |  | No